## DG 13_Base Case IDC_orig sch
Working of base case IDC considering original schedule
Particulars | UoM | Actual | Allowable | Installment | Drawl Date | Drawl % | Drawl | Date | Days | No of days till COD | Rate of Interest | IDC
Scheduled CoD (considering 55 months construction period) | Date | 2023-07-31
Actual COD | Date | 2025-02-22 |  | 0 | 2018-12-31 |  |  | 2023-07-31 | 1 | 1673 | 9.65% | 0
Capital cost |  |  |  | 1 | 2019-01-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1672 | 9.773% | 33.0097
Plant & Mc | Rs. Crore | 4148.9883 | 4148.9883 | 2 | 2019-02-01 | 1.818% | 73.7315 | 2023-07-31 | 28 | 1641 | 9.773% | 32.3977
Unrecovered Fuel | Rs. Crore | 203.1286 | 203.1286 | 3 | 2019-03-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1613 | 9.773% | 31.8449
Overheads | Rs. Crore | 338.2321 | 298.3019 | 4 | 2019-04-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 1582 | 9.788% | 31.2794
Undischarged Liabilities | Rs. Crore |  | -493.6176 | 5 | 2019-05-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1552 | 9.788% | 30.6862
Hard Cost | Rs. Crore | 4690.349 | 4156.8012 | 6 | 2019-06-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 1521 | 9.788% | 30.0733
IDC | Rs. Crore | 1122.0283 | 912.2386 | 7 | 2019-07-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1491 | 9.812% | 29.5539
Total Cost | Rs. Crore | 5812.3773 | 5069.0398 | 8 | 2019-08-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1460 | 9.812% | 28.9395
Construction Period (normative considering extension of 13 months | Months |  | 55 | 9 | 2019-09-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 1429 | 9.812% | 28.325
Drawl of installment as per methodology adopted by Hon'ble MERC (in previous Orders) in equallly spread for the schedule completion period | % |  | 1.818% | 10 | 2019-10-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1399 | 9.837% | 27.7985
Actual Construction Period | Months |  | 72 | 11 | 2019-11-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 1368 | 9.837% | 27.1825
Drawl of installment as per actual schedule | % |  | 1.389% | 12 | 2019-12-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1338 | 9.837% | 26.5864
|  |  |  | 13 | 2020-01-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1307 | 9.765% | 25.7814
Means of finance |  |  |  | 14 | 2020-02-01 | 1.818% | 73.7315 | 2023-07-31 | 29 | 1276 | 9.765% | 25.1699
Debt | % |  | 80% | 15 | 2020-03-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1247 | 9.765% | 24.5978
Equity | % |  | 20% | 16 | 2020-04-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 1216 | 9.74% | 23.9242
|  |  |  | 17 | 2020-05-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1186 | 9.74% | 23.3339
Working of allowable overheads |  |  |  | 18 | 2020-06-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 1155 | 9.74% | 22.724
Actual overheads | Rs.Crore |  | 338.2321 | 19 | 2020-07-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1125 | 9.802% | 22.275
Actual construction period | Months |  | 72 | 20 | 2020-08-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1094 | 9.802% | 21.6612
Scheduled construction period incl 13 months extn | Months |  | 55 | 21 | 2020-09-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 1063 | 9.802% | 21.0474
Excess overhead - proportionate to delay | % |  | 79.8604 | 22 | 2020-10-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 1033 | 9.644% | 20.1244
50% of excess overheads | % |  | 39.9302 | 23 | 2020-11-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 1002 | 9.644% | 19.5205
Net overhead allowable |  |  | 298.3019 | 24 | 2020-12-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 972 | 9.644% | 18.936
|  |  |  | 25 | 2021-01-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 941 | 9.447% | 17.9571
|  |  |  | 26 | 2021-02-01 | 1.818% | 73.7315 | 2023-07-31 | 28 | 910 | 9.447% | 17.3656
|  |  |  | 27 | 2021-03-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 882 | 9.447% | 16.8312
|  |  |  | 28 | 2021-04-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 851 | 9.682% | 16.6439
|  |  |  | 29 | 2021-05-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 821 | 9.682% | 16.0571
|  |  |  | 30 | 2021-06-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 790 | 9.682% | 15.4508
|  |  |  | 31 | 2021-07-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 760 | 9.457% | 14.5183
|  |  |  | 32 | 2021-08-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 729 | 9.457% | 13.9261
|  |  |  | 33 | 2021-09-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 698 | 9.457% | 13.334
|  |  |  | 34 | 2021-10-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 668 | 9.388% | 12.6676
|  |  |  | 35 | 2021-11-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 637 | 9.388% | 12.0798
|  |  |  | 36 | 2021-12-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 607 | 9.388% | 11.5109
|  |  |  | 37 | 2022-01-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 576 | 9.326% | 10.8509
|  |  |  | 38 | 2022-02-01 | 1.818% | 73.7315 | 2023-07-31 | 28 | 545 | 9.326% | 10.2669
|  |  |  | 39 | 2022-03-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 517 | 9.326% | 9.7395
|  |  |  | 40 | 2022-04-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 486 | 9.209% | 9.0412
|  |  |  | 41 | 2022-05-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 456 | 9.209% | 8.4831
|  |  |  | 42 | 2022-06-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 425 | 9.209% | 7.9064
|  |  |  | 43 | 2022-07-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 395 | 9.184% | 7.3282
|  |  |  | 44 | 2022-08-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 364 | 9.184% | 6.7531
|  |  |  | 45 | 2022-09-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 333 | 9.184% | 6.178
|  |  |  | 46 | 2022-10-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 303 | 9.129% | 5.5878
|  |  |  | 47 | 2022-11-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 272 | 9.129% | 5.0161
|  |  |  | 48 | 2022-12-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 242 | 9.129% | 4.4629
|  |  |  | 49 | 2023-01-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 211 | 9.042% | 3.8541
|  |  |  | 50 | 2023-02-01 | 1.818% | 73.7315 | 2023-07-31 | 28 | 180 | 9.042% | 3.2878
|  |  |  | 51 | 2023-03-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 152 | 9.042% | 2.7764
|  |  |  | 52 | 2023-04-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 121 | 9.16% | 2.239
|  |  |  | 53 | 2023-05-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 91 | 9.16% | 1.6839
|  |  |  | 54 | 2023-06-01 | 1.818% | 73.7315 | 2023-07-31 | 30 | 60 | 9.16% | 1.1102
|  |  |  | 55 | 2023-07-01 | 1.818% | 73.7315 | 2023-07-31 | 31 | 30 | 9.203% | 0.55773
[5 empty] | Total |  | 4055.2318 |  | 1674 |  |  | 912.2386
Formulas:
Drawl Date = EOMONTH([Drawl Date, row above],0)+1

## Qtr wise wtd avg rate
|  | FY 18-19 |  | FY 19-20 |  |  |  | FY 20-21 |  |  |  | FY 21-22 |  |  |  | FY 22-23 |  |  |  | FY 23-24 |  |  |  | FY 24-25
| Rate | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
13399 | Main Loan | 9.65% | 9.773% | 9.788% | 9.812% | 9.837% | 9.765% | 9.74% | 9.802% | 9.644% | 9.447% | 9.682% | 9.457% | 9.388% | 9.326% | 9.209% | 9.184% | 9.129% | 9.042% | 9.138% | 9.18% | 9.19% | 9.201% | 9.202% | 9.202% | 9.204% | 9.23%
18246-A1 | Addnl Loan | FY 24-25 Q1: 9.18%; FY 24-25 Q2: 9.185%; FY 24-25 Q3: 9.254%; FY 24-25 Q4: 9.402%
15090-FGD | FGD Loan | FY 23-24 Q1: 10.42%; FY 23-24 Q2: 10.55%; FY 23-24 Q3: 10.94%; FY 23-24 Q4: 10.99%; FY 24-25 Q1: 10.27%; FY 24-25 Q2: 10%; FY 24-25 Q3: 10%; FY 24-25 Q4: 10.03%
| Short term loan | FY 23-24 Q3: 8.25%; FY 23-24 Q4: 8.3%; FY 24-25 Q1: 8.945%; FY 24-25 Q2: 8.984%; FY 24-25 Q3: 9.03%; FY 24-25 Q4: 9.13%
Loan Amount
| Main Loan | 118.423 | 233.8397 | 264.1877 | 338.1778 | 466.79 | 631.916 | 771.1292 | 924.5538 | 1149.4426 | 1441.6652 | 1547.4509 | 1731.8812 | 2140.914 | 2408.244 | 2518.0177 | 2946.1815 | 3071.7772 | 3233.8956 | 3306.6135 | 3392.5796 | 3428.15 | 3353.6368 | 3296.0774 | 3238.1599 | 3179.9894 | 3121.8189
| Addnl Loan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.1947 | 120.8597 | 225.878 | 654.1215
| FGD Loan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.9421 | 59.3917 | 100.4091 | 212.2628 | 252.7992 | 252.7992 | 248.5859 | 245.777
| Short term loan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.3681 | 77.5059 | 135.808 | 195.9258 | 257.2956 | 280.46
| Wtd Avg rate | 9.65% | 9.773% | 9.788% | 9.812% | 9.837% | 9.765% | 9.74% | 9.802% | 9.644% | 9.447% | 9.682% | 9.457% | 9.388% | 9.326% | 9.209% | 9.184% | 9.129% | 9.042% | 9.16% | 9.203% | 9.235% | 9.286% | 9.264% | 9.243% | 9.246% | 9.295%
|  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Note on B6: HP: for repayment of loan
Note on B12: HP: for repayment of loan