## F14.3
Maharashtra State Power Generation Company Ltd.
Capital Cost Approval Petition Formats - Bhusawal Unit 6
Form 14.3 - Break-up of Capital Cost
(Rs. Crore)
Sr. No. | Break Down | Break up of Capital Cost | [6 empty] | Variation | Reasons for Variation
|  | Ordering Cost |  |  |  | As on COD of Unit 6
|  | Contractors | Foreign Currency Component (Specify Currency) | Domestic Component | Total Cost | Foreign Currency Component (Specify Currency) | Domestic Component | Total Cost
|  |  | (a) | (b) | (c) = (a) + (b) | (d) | (e) | (f) = (d) + (e) | (g) = (f) - (c)
1 | Cost of Land & Site Development | Own Land |  |  |  |  | 31.7258 | 31.7258
2 | Plant & Equipment (BTG) | M/s BHEL |  | 3040.9178 | 3040.9178 |  | 3325.6218 | 3325.6218 | 284.7039 | Balance amount of capitalisation is submitted under additional capitalistaion post COD under form 14.7
3 | Taxes |  |  | 573.2834 | 573.2834 |  |  | 0 | -573.2834
4 | Initial spares | M/s BHEL |  | 143.9898 | 143.9898 |  | 96.1135 | 96.1135 | -47.8763
5 | Construction & Pre- Commissioning Expenses | M/s BHEL |  | 234.25 | 234.25 |  | 89.9733 | 89.9733 | -144.2767
6 | Unbilled infirm power | [5 empty] | 203.1286 | 203.1286 | 203.1286
7 | Other Works | M/s BHEL |  | 514.82 | 514.82 |  | 63.8463 | 63.8463 | -450.9737
8 | PV | M/s BHEL |  | 751.64 | 751.64 |  | 527.8933 | 527.8933 | -223.7467
9 | CSR |  |  | 25 | 25 |  | 4.5812 | 4.5812 | -20.4188
10 | Overheads |  |  | 321.57 | 321.57 |  | 338.2363 | 338.2363 | 16.6663
11 | Consultancy | [5 empty] | 9.2318 | 9.2318 | 9.2318
12 | Capital cost Excluding IDC & FC |  |  | 5605.4711 | 5605.4711 | 0 | 4690.3519 | 4690.3519 | -946.845
13 | IDC and FC |  |  | 745.52 | 745.52 |  | 1122.0283 | 1122.0283 | 376.5083
14
15 | Capital cost including IDC & FC |  |  | 6350.9911 | 6350.9911 |  | 5812.3802 | 5812.3802 | -570.3366

## F14.4
MAHAGENCO
Capital Cost Approval Petition Formats - Generation
Form 14.4 : Break up of Construction / Supply / Services / Package
| Sr. No. | Name / No. of Construction / Supply / Service Package | Scope of works (in line with head of cost break-ups as applicable) | Whether awarded through ICB/DCB/Departmentally | No. of bids recd. | Date of Award | Date of Start of Work | Scheduled date of completion of work | Actual date of completion of work | Value of Award in Rs. Crore | Firm or with Escalation in prices | Total incl. Price Variation | Actual expenditure till the completion or upto COD whichever is earlier (Rs. Crore) | 10000000
| 1 | 1 x 660 MW Bhusawal Project Unit 6 | BTG + BOP + FGD + SCR | ICB | 4 | 17.01.2018 | 31.12.2018 | 30.06.2022 | 21.02.2025 | 3758.1911 | Esclation in prices upto 20 % | 4509.8293 | 3421.7353
527.8933
| 2 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of personal steel bed and other items required for temporary chummery at 1x660 MW Bhusawal Project, Deepnagar (PO NO - 4500139820) | DCB | 3 | 2025-01-22 | 2025-01-22 | 2025-02-21 | 2025-01-27 | 0.02032 | Firm | 0.02032 | 0.02032
| 3 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of drivers for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500137624) | DCB | 3 | 2024-11-05 | 2024-11-01 | 2025-11-01 | 2025-10-31 | 0.16775 | PV on labour component payble at actual | 0.16775 | 0.028663
| 4 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Procurement of lubrication oil through rate contract at 1x660 MW, BTPS at risk & cost of M/s. BHEL. (PO NO - 4500137233) | - | 1 | 2024-09-30 | 2024-09-30 |  | 2024-12-21 | 0.22705 | Firm | 0.22705 | 0.22114
| 5 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Procurement of lubrication oil through rate contract at 1x660 MW, BTPS at risk & cost of M/s. BHEL. (PO NO - 4500137237) | - | 1 | 2024-09-30 | 2024-09-30 |  | 2024-12-02 | 0.006198 | Firm | 0.006198 | 0.006198
| 6 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of Control Cable for provision of Generator protection Trip on operation of Tee-Differential proteacttion of 400 KV GT bay at 1x660 MW Bhusawal Project (PO NO - 4500135615) | DCB | 3 | 2024-09-24 | 2024-09-24 | 2024-11-08 | 2024-10-25 | 0.038197 | Firm | 0.038197 | 0.040106
| 7 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of computer operators for day-to-day office works at 1x660MW Bhusawal Project (PO NO - 4500136722) | DCB | 3 | 2024-09-24 | 2024-10-01 | 2025-03-30 | 2025-03-10 | 0.24377 | PV on labour component payble at actual | 0.24377 | 0.18568
| 8 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply , erection and commissioning of high masts in 2x500 MW and 1x660 MW railway siding yard at deepnagar bhusawal (PO NO - 4500135481) | DCB | 3 | 2024-09-09 | 2024-09-09 | 2024-11-08 | 2024-11-05 | 0.36893 | Firm | 0.36893 | 0.23453
| 9 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work Contract for providing skilled manpower in Coal Handling Plant for monitoring the site activities & unskilled assistant for Fire Fighting works at 1X660 MW at 1X660 MW Bhusawal Project. (PO NO - 4500136301) | DCB | 3 | 2024-09-05 | 2024-09-09 | 2025-03-08 | 2025-12-24 | 0.035177 | Firm | 0.035177 | 0.021926
| 10 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Work contract for Boiler balance structure welding works at 1x660MW Bhusawal Project. (PO NO - 4500136467) | DCB | 3 | 2024-08-24 | 2024-08-30 | 2024-10-14 | 2024-09-27 | 0.038822 | Firm | 0.038822 | 0.038822
| 11 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Deployment of MSSC (MSF) for security services at 1x660 MW Bhusawal Project (PO NO - 4500135502) | - | 1 | 2024-07-29 | 2024-08-01 | 2024-10-30 | 2025-01-31 | 1.2659 | Firm | 1.2659 | 1.2363
| 12 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing Safety Assistants / Safety Sergeants to assist safety works at 1X660 MW Bhusawal Project (PO NO - 4500135358) | DCB | 3 | 2024-07-12 | 2024-08-01 | 2025-01-28 | 2024-10-31 | 0.035011 | Firm | 0.035011 | 0.023527
| 13 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicles (TATA Sumo/NEO/Scorpio/Bolero) along with drivers for MSF staff at 1X660 MW Bhusawal Project through tenderization (PO NO - 4500135327) | DCB | 3 | 2024-07-12 | 2024-07-31 | 2025-03-28 | 2025-03-27 | 0.06828 | Firm | 0.06828 | 0.055264
| 14 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of photography and video shooting at 1x660 MW Bhusawal Project through tenderization (PO NO - 4500134876) | DCB | 3 | 2024-07-12 | 2024-07-19 | 2025-07-19 | 2025-02-02 | 0.023501 | Firm | 0.023501 | 0.0067383
| 15 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Plotter printer original cartridges Canon Ink tank PFI-8120 through GeM portal (PO NO - 4500135027) | DCB | 3 | 2024-07-05 | 2024-07-05 | 2024-06-29 | 2024-06-17 | 0.01225 | Firm | 0.01225 | 0.01225
| 16 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of providing and fixing aluminum partitions on as-and-when required basis at 1x660MW Bhusawal Project (PO NO - 4500135062) | DCB | 3 | 2024-07-05 | 2024-07-05 |  |  | 0.01756 | Firm | 0.01756 | 0.0082424
| 17 | 1x660 MW Bhusawal Project - Other misc Expenditure | hiring consultancy services for analysis of boiler thermal expansion and temperature variation after spiral water wall restoration work at 1x660MW Bhusawal Project (PO NO - 4500135080) | - | 1 | 2024-07-02 | 2024-07-02 |  |  | 0.033099 | Firm | 0.033099 | 0.033099
| 18 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement tailored made apron for engineers and covers for chairs at 1x660MW Bhusawal Project office (PO NO - 4500134547) | DCB | 3 | 2024-06-24 | 2024-06-24 | 2024-07-24 | 2024-12-25 | 0.024338 | Firm | 0.024338 | 0.0231
| 19 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement and installation of MW indicators and frequency displays for Plant Control Room (PCR) along with supply of measuring instruments for 1x660 MW Bhusawal Project (PO NO - 4500134270) | DCB | 3 | 2024-06-10 | 2024-06-10 | 2024-08-09 | 2024-11-18 | 0.065379 | Firm | 0.065379 | 0.065379
| 20 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring consultancy services to analyse deformation observed in spiral water walls of supercritical boiler at 1x660 MW Bhusawal project & for reviewing repair & rectification action plan submitted by M/s. BHEL. (PO NO - 4500133333) | - | 1 | 2024-04-27 | 2024-04-27 |  |  | 0.033099 | Firm | 0.033099 | 0.033099
| 21 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Industrial safety helmet at 1 x 660 MW Bhusawal Project, Deepnagar through GeM portal (PO NO - 4500134188) | DCB | 3 | 2024-05-30 | 2024-05-30 |  | 2024-07-19 | 0.0083798 | Firm | 0.0083798 | 0.0083799
| 22 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Providing skilled manpower in Coal Handling Plant for monitoring the site activities & unskilled assistant for Fire Fighting works at 1X660 MW Bhusawal Project by placing limited enquiry. (PO NO - 4500133886) | DCB | 3 | 2024-05-21 | 2024-05-27 | 2024-11-23 | 2024-08-31 | 0.035348 | Firm | 0.035348 | 0.035348
| 23 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Computer and network spares through GeM portal (PO NO - 4500133590) | DCB | 3 | 2024-05-11 | 2024-05-11 |  | 2024-05-14 | 0.096219 | Firm | 0.096219 | 0.096219
| 24 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for hiring of vehicle along with driver for Security staff on round-o-clock at 1x660 MWBhusawal Project (PO NO - 4500133712) | DCB | 3 | 2024-05-04 | 2024-05-02 | 2024-12-28 | 2024-12-27 | 0.0594 | Firm | 0.0594 | 0.06237
| 25 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of unskilled labours for day-to-day office work at 1x660 MW Bhusawal Project. (PO NO - 4500133236) | DCB | 3 | 2024-04-29 | 2024-04-01 | 2024-09-28 | 2024-09-30 | 0.36481 | PV on labour component payble at actual | 0.36481 | 0.36225
| 26 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for Hiring services of M/s. CPRI, Nagpur for boiler tube samples metallurgical analysis at 1x660 MW project Bhusawal (PO NO - 4500133345) | - | 1 | 2024-04-29 | 2024-04-01 |  | 2024-04-29 | 0.031617 | Firm | 0.031617 | 0.031617
| 27 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero or equivalent ) along with driver for project staff at 1x660MW Bhusawal Project (PO NO - 4500133256) | DCB | 3 | 2024-04-29 | 2024-05-15 | 2024-11-11 | 2024-12-09 | 0.028602 | Firm | 0.028602 | 0.030032
| 28 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicle (TATA Indica/Vista/Bolt, or equivalent) along with driver for Superintending Engineers (Project) at 1x660 MW Bhusawal Project (PO NO - 4500133237) | DCB | 3 | 2024-04-29 | 2024-05-10 | 2025-05-10 | 2025-05-31 | 0.1679 | Firm | 0.1679 | 0.079792
| 29 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply and installation of Large Format Display (65 Inches/164 CM) for conference hall at Central Control Room (CCR) at 1x660 MW project office through GeM portal (PO NO - 4500132783) | DCB | 3 | 2024-04-23 | 2024-04-23 |  | 2024-05-14 | 0.016133 | Firm | 0.016133 | 0.016133
| 30 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiiring services of VNIT, Nagpur for boiler tube samples analysis viz. Tensile Testing, Hardness Testing, Microscopy - Optical+ Sem, With Sample Cutting, machining & Specimen Preparation at 1x660 MW Bhusawal Project. (PO NO - 4500132778) | - | 1 | 2024-04-10 | 2020-04-05 |  | 2020-04-05 | 0.0354 | Firm | 0.0354 | 0.00354
| 31 | 1x660 MW Bhusawal Project - Other misc Expenditure | Works of Design, Supply, Installation and Commissioning of IT system for establishing DSM (Deviation Settlement Mechanism) database connectivity at 1x660 MW project Unit-6 through GeM portal (PO NO - 4500132402) | DCB | 3 | 2024-04-02 | 2024-04-02 |  | 2024-04-17 | 0.07847 | Firm | 0.07847 | 0.07847
| 32 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for supplying air coolers on hire basis at 1x660 MW Bhusawal Project (PO NO - 4500132568) | DCB | 3 | 2024-04-02 | 2024-04-04 | 2024-08-02 | 2024-08-03 | 0.029736 | Firm | 0.029736 | 0.029736
| 33 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing assistance for parking management services at 1X660 MW Bhusawal Project site (PO NO - 4500132257) | DCB | 3 | 2024-04-02 | 2024-04-02 | 2024-09-29 | 2024-10-28 | 0.042331 | Firm | 0.042331 | 0.042331
| 34 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Deployment of MSSC (MSF) for security services at 1x660 MW Bhusawal Project (PO NO - 4500131919) | - | 1 | 2024-03-22 | 2024-04-01 | 2024-06-30 | 2024-07-31 | 0.84394 | Firm | 0.84394 | 0.80989
| 35 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of Spares for Bull dozer type BD 155, Bhusawal. (PO NO - 4500130644) | - | 1 | 2024-01-23 | 2024-01-23 |  | 2024-04-17 | 0.16385 | Firm | 0.16385 | 0.16579
| 36 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply of tarpaulin for covering coal in stockyard during monsoon’, at 1 X 660 MW Project Bhusawal (PO NO - 4500130906) | DCB | 3 | 2024-01-17 | 2024-01-17 |  | 2024-03-27 | 0.18635 | Firm | 0.18635 | 0.18568
| 37 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract for operation and maintenance of 33/11 KV Substation and cable laying at 1x660MWBhusawal Project (PO NO - 4500130577) | DCB | 3 | 2024-01-12 | 2024-01-12 | 2025-01-11 | 2025-03-27 | 0.22942 | Firm | 0.22942 | 0.18329
| 38 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for hiring of vehicle (TATA Indica/Vista/Bolt) along with driver for Dy. CE (P) at 1x660 MW Bhusawal Project (PO NO - 4500130839) | DCB | 3 | 2024-01-10 | 2024-01-11 | 2025-01-10 | 2025-03-13 | 0.070452 | Firm | 0.070452 | 0.066923
| 39 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of computer operators for day-to-day office works at 1x660MW Bhusawal Project through tenderization (PO NO - 4500130858) | DCB | 3 | 2024-01-08 | 2024-01-08 | 2025-01-07 | 2024-09-30 | 0.49082 | PV on labour component payble at actual | 0.49082 | 0.4703
| 40 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply, Erection and commissioning of Boom Barrier Gate at 1 X 660 MW Bhusawal Project (PO NO - 4500130833) | DCB | 3 | 2024-01-08 | 2024-01-08 | 2024-03-08 | 2024-01-31 | 0.15057 | Firm | 0.15057 | 0.14278
| 41 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement Night vision binocular for Security Staff at 1x660MW Bhusawal Project office (PO NO - 4500130273) | DCB | 3 | 2024-01-03 | 2024-01-03 | 2024-02-02 | 2024-02-02 | 0.017464 | Firm | 0.017464 | 7.4e-05
| 42 | 1x660 MW Bhusawal Project - Other misc Expenditure | Design, modification of existing 210 MW ADPL lines to making space for routing of 1 X 660 MW ADPL under existing railway culvert for 1 x 600 MW Bhusawal Project (PO NO - 4500130522) | DCB | 3 | 2023-12-22 | 2023-12-16 | 2024-01-30 | 2024-01-25 | 0.41768 | Firm | 0.41768 | 0.41597
| 43 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicle (TATA Indica/Vista/Bolt) along with driver for Higher officers at 1x660 MW Bhusawal Project (PO NO - 4500130322) | DCB | 3 | 2023-12-14 | 2023-12-15 | 2024-12-14 | 2025-03-05 | 0.15056 | Firm | 0.15056 | 0.14956
| 44 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero/Neo or equivalent vehicle ) along with driver for security staff at 1x660MW Bhusawal Project (PO NO - 4500130261) | DCB | 3 | 2023-12-05 | 2023-12-05 | 2024-06-02 | 2024-04-06 | 0.029513 | Firm | 0.029513 | 0.030988
| 45 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Providing temporary police protection at 1x660 MW Bhusawal Project (PO NO - 4500130186) | - | 1 | 2023-12-02 | 2023-11-29 |  | 2025-02-12 | 0.17077 | Firm | 0.17077 | 0.15199
| 46 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Work contract for BCW pump (mandatory spares) inspection, replacement of damaged heat barrier pipe and demonstration of procedure for preservation of pump at 1x660 MW Bhusawal Project at risk and cost of M/s BHEL. (PO NO - 4500130143) | - | 1 | 2023-12-01 | 2023-12-13 | 2024-04-11 | 2023-12-15 | 0.032804 | Firm | 0.032804 | 0.020768
| 47 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for deployment of MSSC (MSF) for security services at 1x660 MW Bhusawal Project (PO NO - 4500129666) | - | 1 | 2023-11-30 | 2023-12-01 | 2024-02-29 | 2024-03-31 | 0.84394 | Firm | 0.84394 | 0.82959
| 48 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | works of providing customized furniture in the Central Control Room (CCR) comprising of Conference Room, Shift In-Charge cabin and PCR In-Charge sitting arrangements (PO NO - 4500130078) | DCB | 3 | 2023-11-30 | 2023-12-22 | 2024-02-05 | 2024-02-05 | 0.2655 | Firm | 0.2655 | 0.2655
| 49 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Transportation of 2.0 Lakh Ton coal from BTPS (O&M) to 1x660MW Bhusawal Project site (PO NO - 4500130031) | DCB | 3 | 2023-11-30 | 2024-12-08 |  | 2025-01-15 | 0.60699 | Firm | 0.60699 | 0.28475
| 50 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Transportation of 2.0 Lakh Ton coal from BTPS (O&M) to 1x660MW Bhusawal Project site (PO NO - 4500130005) | DCB | 3 | 2023-11-30 | 2023-12-26 |  | 2025-01-15 | 0.60699 | Firm | 0.60699 | 0.38824
| 51 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of HP printer original cartridges through GeM portal (PO NO - 4500130052) | DCB | 3 | 2023-11-28 | 2023-11-28 |  | 2023-12-07 | 0.01215 | Firm | 0.01215 | 0.01215
| 52 | 1x660 MW Bhusawal Project - Other misc Expenditure | Design, manufacturing, supply & installation of upright panel and allied related components at 1x660 MW Bhusawal Project (PO NO - 4500129999) | DCB | 3 | 2023-11-24 | 2023-11-24 | 2024-02-22 | 2024-02-07 | 2.0746 | Firm | 2.0746 | 2.0746
| 53 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicle vehicles for VIP on as-and-when required basis at 1x660 MW Bhusawal Project (PO NO - 4500129502) | DCB | 3 | 2023-11-06 | 2023-10-07 | 2024-10-06 | 2024-04-27 | 0.023973 | Firm | 0.023973 | 0.024754
| 54 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicle vehicles for VIP on as-and-when required basis at 1x660 MW Bhusawal Project (PO NO - 4500129500) | DCB | 3 | 2023-11-06 | 2023-11-06 | 2024-11-05 | 2024-03-16 | 0.023973 | Firm | 0.023973 | 0.024675
| 55 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract of "Maintenance works of Split Air Conditioners such as Breakdown Maintenance, Preventive Maintenance, Servicing, Repairing etc." at 1x660MW Project (PO NO - 4500129404) | DCB | 3 | 2023-11-03 | 2023-11-03 | 2024-11-02 | 2024-04-26 | 0.027027 | Firm | 0.027027 | 0.025452
| 56 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply installation, testing, calibration and commissioning of APEX 150 ABT ENERGY METER for 1x660 MW Project Bhusawal (PO NO - 4500125804) | DCB | 3 | 2023-05-04 | 2023-05-04 |  | 2023-05-12 | 0.01947 | Firm | 0.01947 | 0.01947
| 57 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for hiring of expert services of CPRI for work of material hardness test a site for 1 x 660 MW Bhusawal Project (PO NO - 4500123604) | - | 1 | 2023-02-01 | 2022-11-15 |  | 2023-03-03 | 0.03599 | Firm | 0.03599 | 0.027376
| 58 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero or equivalent ) along with driver for project staff at 1x660MW Bhusawal Project (PO NO - 4500129645) | DCB | 3 | 2023-11-03 | 2023-11-04 | 2024-05-02 | 2024-05-14 | 0.028602 | Firm | 0.028602 | 0.030032
| 59 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract for safety audit as per IS 14489:1998 of 1x660MW bhusawal Project site (PO NO - 4500128246) | - | 1 | 2023-09-04 | 2023-10-31 |  | 2023-11-02 | 0.032686 | Firm | 0.032686 | 0.032686
| 60 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply, erection & commissioning of high masts at 1x660 MW Project site Bhusawal (PO NO - 4500127828) | DCB | 3 | 2023-08-28 | 2024-02-27 | 2024-04-12 | 2024-04-06 | 0.27211 | Firm | 0.27211 | 0.27186
| 61 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Providing temporary police protection at 1x660 MW Bhusawal Project (PO NO - 4500128242) | - | 1 | 2023-08-23 | 2023-08-18 |  | 2023-09-14 | 0.20506 | Firm | 0.20506 | 0.056507
| 62 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of drivers for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500128111) | DCB | 3 | 2023-08-17 | 2023-08-20 | 2024-08-19 | 2024-08-10 | 0.19201 | PV on labour component payble at actual | 0.19201 | 0.16698
| 63 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicles (TATA Sumo/NEO/ Scorpio/Bolero) along with drivers for MSF staff at 1X660 MW Bhusawal Project through tenderization (PO NO - 4500126489) | DCB | 3 | 2023-07-29 | 2023-08-01 | 2024-07-31 | 2024-07-30 | 0.098915 | Firm | 0.098915 | 0.10386
| 64 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Providing assistance for day to day maintenance of electrical installations at project office, staff quarter and other miscellaneous electrical works at 1 X 660 MW Project ,Bhusawal (PO NO - 4500127085) | DCB | 3 | 2023-06-28 | 2023-07-18 | 2024-07-17 | 2024-08-31 | 0.08151 | Firm | 0.08151 | 0.078121
| 65 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero/Neo or equivalent vehicle ) along with driver for security staff at 1x660MW Bhusawal Project (PO NO - 4500126982) | DCB | 3 | 2023-06-20 | 2023-06-20 | 2023-12-17 | 2023-10-22 | 0.029513 | Firm | 0.029513 | 0.030988
| 66 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Providing temporary police protection at 1x660 MW Bhusawal Project (PO NO - 4500126933) | - | 1 | 2023-06-16 | 2023-07-06 |  | 2023-08-18 | 0.028335 | Firm | 0.028335 | 0.02795
| 67 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of unskilled labours for day-to-day office work at 1x660 MW Bhusawal Project (PO NO - 4500126430) | DCB | 3 | 2023-06-07 | 2023-06-07 | 2024-06-06 | 2024-03-31 | 0.57017 | PV on labour component payble at actual | 0.57017 | 0.58069
| 68 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work contract for providing services of computer operator for day-to-day officeworks at 1x660MWBhusawal Project through tenderization (PO NO - 4500126751) | DCB | 3 | 2023-06-07 | 2023-06-01 | 2024-05-31 | 2024-01-06 | 0.41491 | PV on labour component payble at actual | 0.41491 | 0.41421
| 69 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Providing temporary police protection at 1x660 MW Bhusawal Project (PO NO - 4500126767) | - | 1 | 2023-06-06 | 2023-06-03 |  | 2023-06-10 | 0.041047 | Firm | 0.041047 | 0.041047
| 70 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing assistance for parking management services at 1X660 MW Bhusawal Project site (PO NO - 4500126438) | DCB | 3 | 2023-05-31 | 2023-06-01 | 2023-11-28 | 2023-11-30 | 0.032833 | Firm | 0.032833 | 0.032833
| 71 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for providing skilled assistants for C&I works at 1x660 MW Bhusawal Project (PO NO - 4500125834) | DCB | 3 | 2023-05-10 | 2023-06-06 | 2024-03-02 | 2023-11-30 | 0.028428 | Firm | 0.028428 | 0.028428
| 72 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Approval for procurement of ink cartridge for SHARP MX-printer through GeM portal (PO NO - 4500125866) | DCB | 3 | 2023-05-04 | 2023-05-04 |  | 2023-06-08 | 0.00895 | Firm | 0.00895 | 0.00895
| 73 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work for Environmental Parameters Monitoring at 1x660MW, Bhusawal Project (PO NO - 4500125665) | DCB | 3 | 2023-04-28 | 2023-06-01 | 2023-09-29 | 2025-03-31 | 0.265 | Firm | 0.265 | 0.1379
| 74 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for providing skilled assistants for Chemical division (Chemist) works at 1X660 MW Bhusawal Project (PO NO - 4500125634) | DCB | 3 | 2023-04-27 | 2023-06-01 | 2024-02-26 | 2023-09-30 | 0.029204 | Firm | 0.029204 | 0.016175
| 75 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of plastic chair through GeM portal. (PO NO - 4500125640) | DCB | 3 | 2023-04-21 | 2023-04-21 |  | 2023-04-18 | 0.0081 | Firm | 0.0081 | 0.0081
| 76 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for Desert coolers on hire basisat 1x660 MW Bhusawal Project- office (PO NO - 4500124359) | DCB | 3 | 2023-03-24 | 2023-04-01 | 2023-07-30 | 2023-07-31 | 0.034692 | Firm | 0.034692 | 0.034692
| 77 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of ruled registers at 1x660 MW project through GeM portal (PO NO - 4500124194) | DCB | 3 | 2023-03-21 | 2023-03-21 |  | 2023-04-04 | 0.0039601 | Firm | 0.0039601 | 0.0039601
| 78 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Box files at 1x660 MW project through GeM portal (PO NO - 4500124237) | DCB | 3 | 2023-03-21 | 2023-03-21 |  | 2023-04-13 | 0.0032249 | Firm | 0.0032249 | 0.0032249
| 79 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero) along with driver for project staff at 1x660MW Bhusawal Project (PO NO - 4500124036) | DCB | 3 | 2023-03-02 | 2023-03-03 | 2023-08-30 | 2023-10-31 | 0.02862 | Firm | 0.02862 | 0.030051
| 80 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of electrical consumables at 1x660MW Bhusawal Project (PO NO - 4500124023) | DCB | 3 | 2023-03-02 | 2023-03-02 | 2023-04-01 | 2023-04-06 | 0.02448 | Firm | 0.02448 | 0.02448
| 81 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero/Neo or equivalent vehicle ) along with driver for security staff at 1x660MW Bhusawal Project (PO NO - 4500123847) | DCB | 3 | 2023-02-14 | 2023-02-15 | 2023-08-14 | 2023-06-19 | 0.029513 | Firm | 0.029513 | 0.030988
| 82 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of various LT power cables at of 1x660 MW Bhusawal Project (PO NO - 4500123607) | DCB | 3 | 2023-02-06 | 2023-02-06 | 2023-03-23 | 2023-07-28 | 0.16886 | Firm | 0.16886 | 0.17584
| 83 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract Evaluation of castable and pourable refractory through VNIT Nagpur (PO NO - 4500123542) | - | 1 | 2023-01-30 | 2023-01-30 |  | 2023-01-20 | 0.00826 | Firm | 0.00826 | 0.00826
| 84 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of IPR (Jyoti make RE-300 Relay), Terminal Blocks, MCB (16Amps) and C-Channel for Bhusawal Projects 1x660MW (PO NO - 4500123393) | DCB | 3 | 2023-01-24 | 2023-01-24 | 2023-02-23 | 2023-01-25 | 0.013591 | Firm | 0.013591 | 0.013591
| 85 | 1x660 MW Bhusawal Project - Other misc Expenditure | Contract for Weld joint preparations for hardness testing at 1X660 MW Bhusawal Project (PO NO - 4500123397) | DCB | 3 | 2023-01-20 | 2023-03-01 | 2024-02-29 | 2023-03-04 | 0.032474 | Firm | 0.032474 | 0.032311
| 86 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of ABT meter (as per MSEDCL specification) for Station Transformer 6B (PO NO - 4500123358) | DCB | 3 | 2023-01-19 | 2023-01-19 | 2023-02-18 | 2023-01-16 | 0.01947 | Firm | 0.01947 | 0.01947
| 87 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Work contract for providing services of unskilled labours for day-to-day housekeeping and other work at 1x660 MW Bhusawal Project site office as and when required basis at the risk and cost of M/s. BHEL (PO NO - 4500123240) | DCB | 3 | 2023-01-11 | 2023-02-01 | 2023-07-31 | 2024-06-30 | 0.050659 | Firm | 0.050659 | 0.04871
| 88 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of hiring of vehicle (TATA Indica/Vista/Bolt, or equivalent) along with driver for Superintending Engineers (Project) at 1x660 MW Bhusawal Project through tenderization (PO NO - 4500123306) | DCB | 3 | 2023-01-11 | 2023-02-26 | 2024-02-26 | 2024-05-09 | 0.16057 | Firm | 0.16057 | 0.1438
| 89 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of fogging of chemicals to contain the spread of flies, insects, mosquitos etc. in and around 1x660 MW Project Office complex area (PO NO - 4500123299) | DCB | 3 | 2023-01-09 | 2023-01-10 | 2023-07-09 | 2023-07-09 | 0.012295 | Firm | 0.012295 | 0.012295
| 90 | 1x660 MW Bhusawal Project - Other misc_Paras FGD Expenditure | Providing supply, Erection, Testing & Commissioning LT panel along with Electrical accessories, items etc. for Paras Wet Limestone FGD projects (PO NO - 4500123225) | DCB | 3 | 2023-01-02 | 2023-01-02 |  | 2023-01-18 | 0.03514 | Firm | 0.03514 | 0.03514
| 91 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicle (TATA Indica/Vista/Bolt) along with driver for Dy. C.E. (Project) and Higher officers & services of hiring of vehicles for VIP on as-and-when required basis at 1x660 MW Bhusawal Project (PO NO - 4500123157) | DCB | 3 | 2022-12-23 | 2022-12-09 | 2023-12-09 | 2023-11-28 | 0.1435 | Firm | 0.1435 | 0.15061
| 92 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicles for VIP on as-and-when required basis at 1x660 MW Bhusawal Project (PO NO - 4500123164) | DCB | 3 | 2022-12-23 | 2022-07-29 | 2023-07-29 | 2023-07-05 | 0.023975 | Firm | 0.023975 | 0.026329
| 93 | 1x660 MW Bhusawal Project - Other misc_Paras FGD Expenditure | Contract for various electrical works associated with installation of electrical equipments for provision of construction power supply at Paras TPS FGD Project (PO NO - 4500123214) | DCB | 3 | 2022-12-23 | 2022-12-23 | 2023-06-21 | 2023-03-03 | 0.034336 | Firm | 0.034336 | 0.034336
| 94 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of photography and video shooting at 1x660 MW Bhusawal Project (PO NO - 4500122909) | DCB | 3 | 2022-12-06 | 2022-12-07 | 2023-12-07 | 2023-04-30 | 0.044098 | Firm | 0.044098 | 0.040989
| 95 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Electrical consumables at 1x660MW Project, Bhusawal (PO NO - 4500122483) | DCB | 3 | 2022-12-02 | 2022-12-02 |  | 2023-01-03 | 0.029881 | Firm | 0.029881 | 0.029881
| 96 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Deployment of MSSC (MSF) for security services at 1x660 MW Bhusawal Project (PO NO - 4500122808) | - | 1 | 2022-11-29 | 2023-01-01 | 2024-01-01 | 2023-11-30 | 2.0999 | Firm | 2.0999 | 1.8707
| 97 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | procurement of A4 size paper rim through GeM portal (PO NO - 4500122764) | DCB | 3 | 2022-11-29 | 2022-11-29 |  | 2022-11-29 | 0.019477 | Firm | 0.019477 | 0.019478
| 98 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for supply, erection & commissioning of open well submersible pumps at Fulgaon water supply station (PO NO - 4500122727) | DCB | 3 | 2022-11-25 | 2022-11-29 | 2023-05-28 | 2022-12-03 | 0.028462 | Firm | 0.028462 | 0.028462
| 99 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of safety shoes, Rain suits & gum boots for the employees working at the office of C.E (Project), 1 x 660 MW Bhusawal Project, Deepnagar (PO NO - 4500122554) | DCB | 3 | 2022-11-17 | 2022-11-17 | 2022-12-17 | 2023-07-14 | 0.033128 | Firm | 0.033128 | 0.033128
| 100 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of dismantling, erection & commissioning of street light poles at project office premises & various locations (PO NO - 4500121916) | DCB | 3 | 2022-11-17 | 2022-11-17 | 2023-05-16 | 2022-12-31 | 0.030152 | Firm | 0.030152 | 0.030152
| 101 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract of Maintenance works of Split Air Conditioners such as Breakdown Maintenance, Preventive Maintenance, Servicing, Repairing etc. at 1x660MW Project (PO NO - 4500121589) | DCB | 3 | 2022-10-21 | 2022-10-01 | 2023-10-01 | 2023-04-30 | 0.032975 | Firm | 0.032975 | 0.032975
| 102 | 1x660 MW Bhusawal Project - Other misc Expenditure | shifting of 11KV Over head Line of Bhusawal rural emanating from 132/11Kv Deepnagar EHV S/s at Railway Siding Area (for Railway Over Bridge) of Bhusawal Projects 1x660MW (PO NO - 4500121734) | DCB | 3 | 2022-10-18 | 2022-10-18 | 2022-11-17 | 2022-12-29 | 0.049062 | Firm | 0.049062 | 0.049062
| 103 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract for deploying skilled Electrical assistance for commissioning activities at 1X660 MW Bhusawal Project (PO NO - 4500121508) | DCB | 3 | 2022-10-10 | 2022-11-01 | 2023-11-01 | 2023-08-09 | 0.034223 | Firm | 0.034223 | 0.033351
| 104 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero/Neo or equivalent vehicle) along with driver for security staff at 1x660MW Bhusawal Project (PO NO - 4500121609) | DCB | 3 | 2022-10-08 | 2022-10-12 | 2023-04-10 | 2023-02-12 | 0.029513 | Firm | 0.029513 | 0.03074
| 105 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract for Conducting RLA study of existing River Water Pump House at Bhusawal TPS (PO NO - 4500121428) | - | 1 | 2022-10-07 | 2022-10-07 |  |  | 0.1121 | Firm | 0.1121 | 0.1121
| 106 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of drivers for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500121203) | DCB | 3 | 2022-09-16 | 2022-08-10 | 2023-08-10 | 2023-08-20 | 0.16601 | PV on labour component payble at actual | 0.16601 | 0.17192
| 107 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work Contract for operating scanner cum photocopy (xerox) machine at 1X660 MW Bhusawal Project office (PO NO - 4500120393) | DCB | 3 | 2022-08-08 | 2022-08-01 | 2023-08-01 | 2023-07-31 | 0.031874 | Firm | 0.031874 | 0.031874
| 108 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of computer operator for day-to-day officeworks at 1x660MW Bhusawal Project (PO NO - 4500120597) | DCB | 3 | 2022-08-08 | 2022-08-18 | 2023-08-18 | 2023-05-31 | 0.39226 | PV on labour component payble at actual | 0.39226 | 0.41178
| 109 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Laptop and Computer spares, networking devices through GeM portal (PO NO - 4500120623) | DCB | 3 | 2022-08-08 | 2022-08-08 |  | 2022-07-05 | 0.15674 | Firm | 0.15674 | 0.092911
| 110 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicles (TATA Sumo/ Scorpio/Bolero) along with drivers for MSF staff at 1X660 MW Bhusawal Project through tenderization (PO NO - 4500120398) | DCB | 3 | 2022-08-05 | 2022-08-01 | 2023-08-01 | 2023-07-31 | 0.089827 | Firm | 0.089827 | 0.094318
| 111 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract for operation & Maintenance of 33/11 KV Substation and cable laying at Bhusawal Project (PO NO - 4500120424) | DCB | 3 | 2022-08-05 | 2022-09-01 | 2023-09-01 | 2024-01-11 | 0.23039 | Firm | 0.23039 | 0.20496
| 112 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero) along with driver for project staff at 1x660MW Bhusawal Project (PO NO - 4500120131) | DCB | 3 | 2022-07-29 | 2022-07-07 | 2023-01-03 | 2023-02-08 | 0.028422 | Firm | 0.028422 | 0.029346
| 113 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of unskilled labours for day-to-day office work at 1x660 MW Bhusawal Project (PO NO - 4500120130) | DCB | 3 | 2022-07-26 | 2022-06-27 | 2023-06-27 | 2023-06-06 | 0.46771 | PV on labour component payble at actual | 0.46771 | 0.49074
| 114 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | work of cutting of grass, bushes, shrubs, small trees, trimming of trees, removing dead trees and cleaning of area 1x660MW Bhusawal Project site at the risk & cost of M/s. BHEL (PO NO - 4500119861) | DCB | 3 | 2022-06-22 | 2022-11-22 | 2023-05-21 | 2023-04-04 | 0.021169 | Firm | 0.021169 | 0.021169
| 115 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for hiring of expert services of CPRI for work of material hardness test a site for 1 x 660 MW Bhusawal Project (PO NO - 4500119851) | - | 1 | 2022-06-14 | 2022-07-04 |  | 2022-07-05 | 0.013688 | Firm | 0.013688 | 0.013688
| 116 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Works contract for Providing assistance for day to day maintenance of electrical installations at project office, staff quarter and other miscellaneous electrical works at 1 X 660 MW Project , Bhusawal (PO NO - 4500119227) | DCB | 3 | 2022-05-12 | 2022-06-01 | 2023-06-01 | 2023-06-30 | 0.067277 | Firm | 0.067277 | 0.065122
| 117 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of plain and printed registers, log books at 1x660MW Bhusawal Project office (PO NO - 4500119221) | DCB | 3 | 2022-05-09 | 2022-05-09 | 2022-06-08 | 2022-06-28 | 0.019771 | Firm | 0.019771 | 0.019771
| 118 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of upgradation of conference hall PA system at 1x660 MW Bhusawal Project Office (PO NO - 4500119157) | DCB | 3 | 2022-04-28 | 2022-04-28 | 2022-10-25 | 2022-05-30 | 0.025196 | Firm | 0.025196 | 0.025196
| 119 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing parking management services at 1X660 MW Bhusawal Project site (PO NO - 4500119126) | DCB | 3 | 2022-04-26 | 2022-04-20 | 2023-04-20 | 2022-12-31 | 0.061455 | PV on labour component payble at actual | 0.061455 | 0.048937
| 120 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of stationary items at 1x660MW Bhusawal Project office (PO NO - 4500119038) | DCB | 3 | 2022-04-26 | 2022-04-26 | 2022-05-26 | 2022-06-04 | 0.021683 | Firm | 0.021683 | 0.021683
| 121 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Provision of Air coolers on hire basis at 1 X 660 MW Project , Bhusawal (PO NO - 4500118464) | DCB | 3 | 2022-04-05 | 2022-04-01 | 2022-07-30 | 2022-07-31 | 0.034692 | Firm | 0.034692 | 0.034692
| 122 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing round the clock services of medical attendant on ambulance at 1x660 MW Bhusawal Project (PO NO - 4500118387) | DCB | 3 | 2022-03-28 | 2022-06-07 | 2023-06-07 | 2023-02-27 | 0.069156 | Firm | 0.069156 | 0.069156
| 123 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work of sourcing Raw Water through abandoned pump house at 210MW BTPS (PO NO - 4500118252) | DCB | 3 | 2022-03-22 | 2022-03-22 | 2022-06-20 | 2022-06-30 | 0.37654 | Firm | 0.37654 | 0.37654
| 124 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Box files at 1x660 MW project through GeM portal (PO NO - 4500117971) | DCB | 3 | 2022-03-16 | 2022-03-16 |  | 2022-04-05 | 0.0029996 | Firm | 0.0029996 | 0.0029996
| 125 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of spring files at 1x660 MW project through GeM portal (PO NO - 4500117978) | DCB | 3 | 2022-03-16 | 2022-03-16 |  | 2022-03-30 | 0.002799 | Firm | 0.002799 | 0.002798
| 126 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of plastic chairs at 1x660 MW project through GeM portal (PO NO - 4500118058) | DCB | 3 | 2022-03-15 | 2022-03-15 |  | 2022-03-04 | 0.00394 | Firm | 0.00394 | 0.00394
| 127 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply and installation of electrically operated safety siren (Hooter) at 1X660 MW Bhusawal Project (PO NO - 4500117789) | DCB | 3 | 2022-02-28 | 2022-02-28 | 2022-03-30 | 2022-05-18 | 0.012487 | Firm | 0.012487 | 0.012487
| 128 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of various storage furniture items at 1x660 MW Bhusawal Project through GeM (PO NO - 4500117844) | DCB | 3 | 2022-02-18 | 2022-02-18 |  | 2022-03-30 | 0.081219 | Firm | 0.081219 | 0.0012024
| 129 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work Contract for maintenance and providing catering services at Tapi Guest House (old guest house near Tapi river) at BTPS Deepnagar (PO NO - 4500117249) | DCB | 3 | 2022-01-11 | 2022-01-01 | 2023-01-01 | 2022-10-31 | 0.20846 | PV on labour component payble at actual | 0.20846 | 0.12939
| 130 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for construction of shed at 1X660 MW Bhusawal Project office. (PO NO - 4500117199) | DCB | 3 | 2022-01-10 | 2022-07-01 | 2023-07-01 | 2022-07-11 | 0.022555 | Firm | 0.022555 | 0.022555
| 131 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of providing and fixing aluminum partition at various sections of 1x660 MW Project Office on as and when required basis. (PO NO - 4500117190) | DCB | 3 | 2022-01-10 | 2022-01-10 |  |  | 0.021502 | Firm | 0.021502 | 0.021502
| 132 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of engaging MSSC (MSF) security agency at 1x660 MW Bhusawal Project (PO NO - 4500117043) | - | 1 | 2021-12-27 | 2022-01-26 | 2023-01-26 | 2022-12-31 | 1.9249 | Firm | 1.9249 | 1.924
| 133 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicle (TATA Indica/Vista/Bolt) along with driver for Project higher officials & services of hiring of vehicles on as-and-when required basis at 1x660 MW Bhusawal Project (PO NO - 4500117186) | DCB | 3 | 2021-12-25 | 2022-01-01 | 2023-01-01 | 2022-12-08 | 0.08294 | Firm | 0.08294 | 0.091243
| 134 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work Contract for hiring of Ambulance (TATA winger/407/ Equivalent) along with driver on round-o-clock basis at 1x660 MW Bhusawal Project (PO NO - 4500116822) | DCB | 3 | 2021-12-23 | 2022-01-01 | 2023-01-01 | 2022-12-31 | 0.1 | Firm | 0.1 | 0.097674
| 135 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of Reusable N-95 face masks and liquid sanitizer for staff working at 1X660 MW Project office (PO NO - 4500116830) | DCB | 3 | 2021-12-15 | 2021-12-15 | 2022-01-14 | 2022-01-17 | 0.020272 | Firm | 0.020272 | 0.018129
| 136 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of fogging of chemicals to contain the spread of flies, insects, mosquitos etc. in and around 1x660 MW Project Office complex area (PO NO - 4500116869) | DCB | 3 | 2021-12-14 | 2021-12-14 | 2022-01-13 | 2022-07-14 | 0.012295 | Firm | 0.012295 | 0.012295
| 137 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of original cartridges for Sharp make photocopier machine through GeM portal (PO NO - 4500116903) | DCB | 3 | 2021-12-06 | 2021-12-06 |  | 2022-01-07 | 0.004445 | Firm | 0.004445 | 0.004445
| 138 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of various printer original cartridges through GeM portal (PO NO - 4500116758) | DCB | 3 | 2021-11-25 | 2021-11-25 |  | 2021-11-18 | 0.022924 | Firm | 0.022924 | 0.022924
| 139 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work contract for providing services of computer operator for day-to-day office works at 1x660MW Bhusawal Project (PO NO - 4500116717) | DCB | 3 | 2021-11-18 | 2021-12-01 | 2022-12-01 | 2022-08-13 | 0.30931 | PV on labour component payble at actual | 0.30931 | 0.32466
| 140 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Electrical consumables at 1x660MW Project, Bhusawal (PO NO - 4500116287) | DCB | 3 | 2021-10-11 | 2021-10-11 | 2021-11-25 | 2022-01-05 | 0.015113 | Firm | 0.015113 | 0.015113
| 141 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract of "Maintenance works of Split Air Conditioners such as Breakdown Maintenance, Preventive Maintenance, Servicing, Repairing etc." at 1x660MW Project office (PO NO - 4500116142) | DCB | 3 | 2021-09-16 | 2021-09-01 | 2022-09-01 | 2022-05-31 | 0.039718 | Firm | 0.039718 | 0.039718
| 142 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of PC, Printers & Laptops etc (Printer) (PO NO - 4500116149) | DCB | 3 | 2021-09-14 | 2021-09-14 |  | 2021-10-04 | 0.0094 | Firm | 0.0094 | -2e-09
| 143 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of PC, Printers & Laptops etc (Desktop PC) (PO NO - 4500116109) | DCB | 3 | 2021-09-06 | 2021-09-06 |  | 2022-01-14 | 0.0492 | Firm | 0.0492 | -4e-09
| 144 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Electrical consumables at 1x660MW Project, Bhusawal (PO NO - 4500115940) | DCB | 3 | 2021-08-27 | 2021-08-27 | 2021-10-11 | 2021-11-18 | 0.016342 | Firm | 0.016342 | 0.016342
| 145 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Electrical consumables at 1x660MW Project, Bhusawal (PO NO - 4500115958) | DCB | 3 | 2021-08-27 | 2021-08-27 | 2021-10-11 | 2021-10-13 | 0.014424 | Firm | 0.014424 | 0.01115
| 146 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Electrical consumables at 1x660MW Project, Bhusawal (PO NO - 4500115934) | DCB | 3 | 2021-08-27 | 2021-08-27 | 2021-10-11 | 2022-04-21 | 0.010574 | Firm | 0.010574 | 0.010574
| 147 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for hiring of vehicle along with driver for Security staff on round-o-clock at 1x660 MW Bhusawal Project - approval for processing new work contract reg (PO NO - 4500115805) | DCB | 3 | 2021-08-25 | 2021-09-19 | 2022-09-19 | 2022-10-06 | 0.082092 | Firm | 0.082092 | 0.090448
| 148 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of submersible sewage/mud pumps at 1X660 MW Bhusawal Project (PO NO - 4500115871) | DCB | 3 | 2021-08-25 | 2021-08-25 | 2021-10-24 | 2021-10-07 | 0.05082 | Firm | 0.05082 | 4.6e-08
| 149 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of submersible sewage/mud pumps at 1X660 MW Bhusawal Project (PO NO - 4500115872) | DCB | 3 | 2021-08-25 | 2021-08-25 | 2021-10-24 | 2021-12-17 | 0.031978 | Firm | 0.031978 | 0.0012334
| 150 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work of shifting of 11KV Double Pole Structure & XLPE cable (Supply, Erection, Installation of 11KV Two Pole Structures, Cable laying, Re-routing) at Railway Siding Area of Bhusawal Project 1x660MW (PO NO - 4500115925) | DCB | 3 | 2021-08-25 | 2021-08-25 | 2021-10-24 | 2022-01-19 | 0.36482 | Firm | 0.36482 | 0.36477
| 151 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicle (TATA Indica/Vista/Bolt) along with driver for Superintending Engineers (Project) at 1x660 MW Bhusawal Project (PO NO - 4500115807) | DCB | 3 | 2021-08-17 | 2021-11-01 | 2022-11-01 | 2023-02-06 | 0.12968 | Firm | 0.12968 | 0.13617
| 152 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for providing & fixing of cushion to various chairs at 1X660 MW Bhusawal Project (PO NO - 4500115607) | DCB | 3 | 2021-08-06 | 2021-08-06 | 2021-09-05 | 2021-08-28 | 0.012782 | Firm | 0.012782 | 0.012782
| 153 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for operating plotter machine and scanner cum photocopy (xerox) machine at 1X660 MW Bhusawal Project office (PO NO - 4500115558) | DCB | 3 | 2021-08-02 | 2021-08-01 | 2022-08-01 | 2022-07-31 | 0.02999 | Firm | 0.02999 | 0.029895
| 154 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of drivers for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500115528) | DCB | 3 | 2021-07-23 | 2021-08-01 | 2022-08-01 | 2022-08-08 | 0.14135 | PV on labour component payble at actual | 0.14135 | 0.14638
| 155 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of computer keyboard and mouse (combo) set through GeM portal (PO NO - 4500115530) | DCB | 3 | 2021-07-23 | 2021-07-23 |  | 2021-07-17 | 0.00262 | Firm | 0.00262 | 0.00262
| 156 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract for providing Safety Assistants / Safety Sergeants to assist safety works at 1X660 MW Bhusawal Project. (PO NO - 4500115292) | DCB | 3 | 2021-07-12 | 2021-08-01 | 2022-08-01 | 2022-10-18 | 0.19429 | PV on labour component payble at actual | 0.19429 | 0.14946
| 157 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicles (TATA Sumo/ Scorpio/Bolero) along with drivers for MSF staff at 1X660 MW Bhusawal Project (PO NO - 4500115444) | DCB | 3 | 2021-07-12 | 2021-07-14 | 2022-07-14 | 2022-07-31 | 0.081701 | Firm | 0.081701 | 0.090017
| 158 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of printer cartridges & ink bottles through GeM portal. (Cartridges) (PO NO - 4500115226) | DCB | 3 | 2021-07-07 | 2021-07-07 |  | 2021-07-19 | 0.0061832 | Firm | 0.0061832 | 0.0061832
| 159 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing & fixing of 3D LED light name board at 1X660 MW Bhusawal Project main gate (PO NO - 4500115300) | DCB | 3 | 2021-07-06 | 2021-09-07 | 2021-10-07 | 2021-09-13 | 0.022892 | Firm | 0.022892 | 0.022892
| 160 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of various security items through GeM portal (HHMD) (PO NO - 4500115170) | DCB | 3 | 2021-06-29 | 2021-06-29 |  | 2021-06-21 | 0.00098 | Firm | 0.00098 | 0.00098
| 161 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of various security items through GeM portal (Search light torch) (PO NO - 4500115171) | DCB | 3 | 2021-06-29 | 2021-06-29 |  | 2021-07-01 | 0.00105 | Firm | 0.00105 | 0.00105
| 162 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for operation and maintenance of 33KV/11KV substation and cable laying at 1x660MW Project, Bhusawal. (PO NO - 4500114413) | DCB | 3 | 2021-06-28 | 2021-06-28 | 2022-06-28 | 2022-08-31 | 0.19948 | PV on labour component payble at actual | 0.19948 | 0.1969
| 163 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of unskilled labours for day-to-day office work at 1x660 MW Bhusawal Project (PO NO - 4500115035) | DCB | 3 | 2021-06-28 | 2021-06-05 | 2022-06-05 | 2022-06-26 | 0.36437 | PV on labour component payble at actual | 0.36437 | 0.38232
| 164 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of 33/11 KV substation transformer control panel spares at 1x660MW Project, Bhusawal (PO NO - 4500114646) | DCB | 3 | 2021-05-12 | 2021-05-12 |  | 2021-07-16 | 0.052186 | Firm | 0.052186 | 0.052186
| 165 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of erection and commissioning of street light system at super D, Type II building area, Tapi guest house and project office premises (PO NO - 4500114590) | DCB | 3 | 2021-05-07 | 2021-06-07 |  | 2021-06-21 | 0.023672 | Firm | 0.023672 | 0.023672
| 166 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Wwork contract for providing cleaning services at security gate of 1X660 MW Bhusawal Project (PO NO - 4500114622) | DCB | 3 | 2021-04-30 | 2021-06-01 | 2022-02-26 | 2022-03-31 | 0.020609 | Firm | 0.020609 | 0.020433
| 167 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of various security items through GeM portal (Trolley Mirror) (PO NO - 4500114631) | DCB | 3 | 2021-04-30 | 2021-04-30 |  | 2021-05-03 | 0.00097 | Firm | 0.00097 | 0.00097
| 168 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing parking management services at 1X660 MW Bhusawal Project site (PO NO - 4500114521) | DCB | 3 | 2021-04-30 | 2021-06-01 | 2021-11-28 | 2021-09-30 | 0.034246 | PV on labour component payble at actual | 0.034246 | 0.034728
| 169 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply & installation of 55 nos. of End Point Security Anti-Virus Software with validity of 3 years through Government e-Marketplace (GeM) portal at 1x660MW Bhusawal Project (PO NO - 4500114520) | DCB | 3 | 2021-04-26 | 2021-04-26 |  | 2021-04-30 | 0.017847 | Firm | 0.017847 | 0.017847
| 170 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | works contract for day to day maintenance of electrical installations at project office, staff quarters and other miscellaneous electrical works at 1x660MW Project, Bhusawal (PO NO - 4500114538) | DCB | 3 | 2021-04-24 | 2021-04-25 | 2022-04-25 | 2022-05-31 | 0.066233 | PV on labour component payble at actual | 0.066233 | 0.064756
| 171 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work contract for Provision of Air Coolers on hire basis at 1x660 MW Bhusawal Project (PO NO - 4500113774) | DCB | 3 | 2021-03-26 | 2021-03-26 | 2021-07-24 | 2021-07-24 | 0.034692 | Firm | 0.034692 | 0.034692
| 172 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply ,Erection and commissioning of High Masts at Project Site (PO NO - 4500113326) | DCB | 3 | 2021-03-19 | 2021-03-19 | 2021-05-03 | 2022-01-12 | 0.20112 | Firm | 0.20112 | 0.20112
| 173 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of computer operator for day-to-day office works at 1x660MW Bhusawal Project (PO NO - 4500113522) | DCB | 3 | 2021-03-18 | 2021-03-19 | 2022-03-19 | 2021-11-30 | 0.26242 | PV on labour component payble at actual | 0.26242 | 0.26521
| 174 | 1x660 MW Bhusawal Project - Other misc Expenditure | Contract for carrying out Safety Audit as per IS 14489 : 1998in 1X660 MW Bhusawal Project (PO NO - 4500113485) | - | 1 | 2021-03-15 | 2021-06-30 |  | 2021-07-02 | 0.032214 | Firm | 0.032214 | 0.032214
| 175 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for providing Safety Assistants / Safety Sergeants to assist Safety work at 1X660 MW Bhusawal Project (PO NO - 4500113502) | DCB | 3 | 2021-03-13 | 2021-03-15 | 2021-07-13 | 2021-06-29 | 0.020862 | Firm | 0.020862 | 0.020862
| 176 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of CCTV items for 1X660 MW MSPGCL project material entry gate through GeM portal (MONITOR / DISPLAY) (PO NO - 4500113025) | DCB | 3 | 2021-03-04 | 2021-03-04 |  | 2021-02-16 | 0.00198 | Firm | 0.00198 | 9.9e-06
| 177 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of various safety related equipments at 1x660MW Bhusawal Project office (PO NO - 4500113258) | DCB | 3 | 2021-03-01 | 2021-03-01 | 2021-03-31 | 2021-03-26 | 0.018499 | Firm | 0.018499 | 0.018499
| 178 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply, Installation & Testing of 42U capacity server cum network rack alongwith all ancillary system components for 1x660MW Bhusawal Project (PO NO - 4500113043) | DCB | 3 | 2021-03-01 | 2021-03-01 |  | 2021-03-03 | 0.00775 | Firm | 0.00775 | 3.88e-05
| 179 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of photography and video shooting at 1x660 MW Bhusawal Project (PO NO - 4500112899) | DCB | 3 | 2021-02-05 | 2021-02-12 | 2022-02-12 | 2022-09-29 | 0.037371 | Firm | 0.037371 | 0.037272
| 180 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply, Installation & Testing of 42U capacity server cum network rack alongwith all ancillary system components for 1x660MW Bhusawal Project (PO NO - 4500112893) | DCB | 3 | 2021-02-04 | 2021-02-04 |  | 2021-02-17 | 0.0033929 | Firm | 0.0033929 | 0.0033929
| 181 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Line Interactive Uninterruptible Power Source (UPS) and Canon TM-5300 Ink Tank PFI-8120 cartridge for plotter at 1x660 MW MSPGCL Project (PO NO - 4500112775) | DCB | 3 | 2021-01-19 | 2021-01-19 | 2021-02-18 | 2021-02-03 | 0.0217 | Firm | 0.0217 | 0.023319
| 182 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Wwork of providing and fixing aluminum partition at various sections of 1x660 MW Project Office (PO NO - 4500112785) | DCB | 3 | 2021-01-08 | 2021-01-11 | 2022-01-11 | 2021-01-25 | 0.012602 | Firm | 0.012602 | 0.013233
| 183 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for servicing & maintenance of foot operated wash basins installed at 1X660 MW Bhusawal Project (PO NO - 4500112560) | DCB | 3 | 2021-01-08 | 2021-01-11 | 2022-01-11 | 2022-01-07 | 0.02124 | Firm | 0.02124 | 0.02124
| 184 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of engaging MSSC (MSF) security agency at 1x660MW Bhusawal Project. (PO NO - 4500112688) | - | 1 | 2020-12-28 | 2021-01-01 | 2022-01-01 | 2022-01-31 | 2.0999 | Firm | 2.0999 | 2.0921
| 185 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of plotter paper roll of various sizes through GeM portal (A0) (PO NO - 4500112403) | DCB | 3 | 2020-12-08 | 2020-12-08 |  | 2020-12-03 | 0.000924 | Firm | 0.000924 | 0.000924
| 186 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of plotter paper roll of various sizes through GeM portal (A1) (PO NO - 4500112404) | DCB | 3 | 2020-12-08 | 2020-12-08 |  | 2020-12-18 | 0.00123 | Firm | 0.00123 | 0.00123
| 187 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of engaging MSSC (MSF) security agency at 1x660MW Bhusawal Project. (PO NO - 4500112257) | - | 1 | 2020-11-19 | 2020-12-01 | 2020-12-31 | 2020-12-31 | 0.17499 | Firm | 0.17499 | 0.16563
| 188 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement and installation of biometric (Face recognition) attendance machine at project office (PO NO - 4500111987) | DCB | 3 | 2020-10-28 | 2020-10-28 |  | 2020-11-21 | 0.0016596 | Firm | 0.0016596 | 3.3199e-05
| 189 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Large Format display at 1X660 MW Project Bhusawal - (164 CM) (PO NO - 4500111824) | DCB | 3 | 2020-10-26 | 2020-10-26 |  | 2020-10-28 | 0.0098408 | Firm | 0.0098408 | 0.0098408
| 190 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of LED Street light fixtures at 1x660MW Project, Bhusawal (PO NO - 4500111842) | DCB | 3 | 2020-10-19 | 2020-10-19 | 2020-12-03 | 2021-02-03 | 0.022136 | Firm | 0.022136 | 0.022136
| 191 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of Reusable N-95 face masks and other healthcare accessories for staff working at 1X660 MW Project office (PO NO - 4500111745) | DCB | 3 | 2020-10-08 | 2020-10-08 | 2020-11-07 | 2020-10-15 | 0.030565 | Firm | 0.030565 | 0.030565
| 192 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply, installation, testing and commissioning of DC system (battery bank with charger) for 33/11KV substation supplying construction power supply at 1X660 MW Project Bhusawal. (PO NO - 4500111658) | DCB | 3 | 2020-10-07 | 2020-10-07 | 2020-12-06 | 2021-03-31 | 0.098301 | Firm | 0.098301 | 0.096543
| 193 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of safety shoes, Rain suits & gum boots for the employees working at the office of C.E (Project), 1 x 660 MW Bhusawal Project, Deepnagar (PO NO - 4500111657) | DCB | 3 | 2020-10-01 | 2020-10-01 | 2020-10-31 | 2020-10-30 | 0.022339 | Firm | 0.022339 | 0.022339
| 194 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of 33/11KV construction power supply substation spares and electrical consumables at 1x660MW Bhusawal project (PO NO - 4500111609) | DCB | 3 | 2020-10-01 | 2020-10-01 | 2020-11-15 | 2021-09-25 | 0.034796 | Firm | 0.034796 | 0.034783
| 195 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement and installation of server at project office (PO NO - 4500111515) | DCB | 3 | 2020-09-29 | 2020-09-29 |  | 2020-11-21 | 0.0755 | Firm | 0.0755 | 0.0011324
| 196 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of potential and current transformers of various ratings at 1x660MW Project, Bhusawal (PO NO - 4500111458) | DCB | 3 | 2020-09-25 | 2020-09-25 |  | 2020-12-24 | 0.048834 | Firm | 0.048834 | 0.048834
| 197 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of fabrications of security barricades and material storages racks at 1x660 MW Bhusawal project office (PO NO - 4500111206) | DCB | 3 | 2020-09-14 | 2020-10-03 | 2021-04-01 | 2021-01-02 | 0.024298 | Firm | 0.024298 | 0.024298
| 198 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of security helmet through GeM portal (PO NO - 4500111052) | DCB | 3 | 2020-09-09 | 2020-09-09 |  | 2020-11-23 | 0.0029 | Firm | 0.0029 | 0.0029
| 199 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for hiring of Ambulance (TATA winger/407) along with driver on round-o-clock basis at 1x660 MW Bhusawal Project. (PO NO - 4500108800) | DCB | 3 | 2020-09-08 | 2020-09-08 | 2021-09-08 | 2021-03-26 | 0.041139 | Firm | 0.041139 | 0.043196
| 200 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of reflective tape for security through GeM portal (PO NO - 4500111055) | DCB | 3 | 2020-08-25 | 2020-08-25 |  | 2020-08-24 | 0.0013125 | Firm | 0.0013125 | 0.0013125
| 201 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply & Installation of Porta Cabin at 1x660MW Bhusawal Project (PO NO - 4500110940) | DCB | 3 | 2020-08-13 | 2020-08-13 | 2020-09-07 | 2020-10-31 | 0.1442 | Firm | 0.1442 | 0.003062
| 202 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | procurement & installation of Automatic hand sanitizer machine & Hands free hand washing points at 1X660 MW Bhusawal Project office complex & site (PO NO - 4500110954) | DCB | 3 | 2020-08-13 | 2020-08-13 | 2020-09-12 | 2020-09-02 | 0.026728 | Firm | 0.026728 | 0.026728
| 203 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for hiring of vehicle along with driver for Security staff on round-o-clock at 1x660 MW Bhusawal Project (PO NO - 4500110926) | DCB | 3 | 2020-08-06 | 2020-08-06 | 2021-08-06 | 2021-09-18 | 0.078183 | Firm | 0.078183 | 0.078183
| 204 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for construction of anti chamber at CE cabin at 1x660 MW Bhusawal project office (PO NO - 4500110875) | DCB | 3 | 2020-08-06 | 2020-08-07 | 2020-09-06 | 2020-09-05 | 0.023411 | Firm | 0.023411 | 0.023411
| 205 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement projectoor screen at 1X660 MW Project Bhusawal (PO NO - 4500110803) | DCB | 3 | 2020-07-27 | 2020-07-27 |  | 2020-09-07 | 0.0026006 | Firm | 0.0026006 | 0.0026006
| 206 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of various stationary items (PO NO - 4500110734) | DCB | 3 | 2020-07-22 | 2020-07-22 | 2020-08-21 | 2020-07-23 | 0.010968 | Firm | 0.010968 | 0.010968
| 207 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of street light poles at 1x660MW Bhusawal project. (PO NO - 4500110537) | DCB | 3 | 2020-07-17 | 2020-07-17 | 2020-08-31 | 2020-09-02 | 0.025712 | Firm | 0.025712 | 0.025712
| 208 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of drivers for day to day office work at 1x660 MW Bhusawal Project. (PO NO - 4500110534) | DCB | 3 | 2020-07-09 | 2020-08-01 | 2021-08-01 | 2021-07-31 | 0.10749 | Firm | 0.10749 | 0.10739
| 209 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply of LT, DC and control cables for 1X660 MW Project Bhusawal. (PO NO - 4500110503) | DCB | 3 | 2020-07-08 | 2020-07-08 |  | 2020-09-02 | 0.099913 | Firm | 0.099913 | 0.099318
| 210 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of providing and fixing mosquito grills to office windows at 1x660MW Bhusawal Project office area (PO NO - 4500110449) | DCB | 3 | 2020-06-26 | 2020-07-02 | 2020-12-29 | 2020-07-28 | 0.020034 | Firm | 0.020034 | 0.020034
| 211 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of hiring of vehicles (TATA Sumo/ Scorpio/Bolero) along with drivers for MSF staff at 1X660 MW Bhusawal Project (PO NO - 4500110432) | DCB | 3 | 2020-06-22 | 2020-06-27 | 2021-06-27 | 2021-07-13 | 0.078183 | Firm | 0.078183 | 0.080968
| 212 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of instant water heaters (Geysers) for renovated project quarters at Bhusawal Project (PO NO - 4500110440) | DCB | 3 | 2020-06-19 | 2020-06-19 | 2020-07-19 | 2020-07-17 | 0.022939 | Firm | 0.022939 | 0.022939
| 213 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of various sanitizing items at 1X660 MW Project office (PO NO - 4500110422) | DCB | 3 | 2020-06-19 | 2020-06-19 | 2020-07-19 | 2020-07-06 | 0.022356 | Firm | 0.022356 | 0.022356
| 214 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply and works of alternate cable laying for 11KV construction power supply (PO NO - 4500110346) | DCB | 3 | 2020-06-17 | 2020-06-17 | 2020-08-01 | 2022-08-07 | 0.31434 | Firm | 0.31434 | 0.31434
| 215 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of computer tables through GeM portal (PO NO - 4500110348) | DCB | 3 | 2020-06-15 | 2020-06-15 |  | 2020-06-22 | 0.00675 | Firm | 0.00675 | 0.00675
| 216 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work Contract for maintenance and providing catering services at Tapi Guest House (old guest house near Tapi river) at BTPS Deepnagar (PO NO - 4500110367) | DCB | 3 | 2020-06-12 | 2020-06-12 | 2021-06-12 | 2021-06-11 | 0.2031 | Firm | 0.2031 | 0.2031
| 217 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of unskilled labours for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500110328) | DCB | 3 | 2020-06-11 | 2020-05-20 | 2021-05-20 | 2021-06-04 | 0.33668 | Firm | 0.33668 | 0.33668
| 218 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for operating newly procured plotter machine and scanner cum photocopy (xerox) machine at 1X660 MW Bhusawal Project office. (PO NO - 4500110252) | DCB | 3 | 2020-06-08 | 2020-07-03 | 2021-07-03 | 2021-07-09 | 0.029067 | Firm | 0.029067 | 0.029067
| 219 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for providing Safety Assistants / Safety Sergeants to assist Safety work at 1X660 MW Bhusawal Project (PO NO - 4500110275) | DCB | 3 | 2020-06-08 | 2020-08-17 | 2021-02-13 | 2021-02-17 | 0.029218 | Firm | 0.029218 | 0.029218
| 220 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of revolving chairs through GeM portal (PO NO - 4500110261) | DCB | 3 | 2020-06-05 | 2020-06-05 |  | 2020-06-12 | 0.033037 | Firm | 0.033037 | 0.02178
| 221 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of A4 paper RIM through GeM (PO NO - 4500110244) | DCB | 3 | 2020-05-29 | 2020-05-29 |  | 2020-06-05 | 0.0071201 | Firm | 0.0071201 | 0.0071201
| 222 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of various printer cartridges at 1X660 MW Project Bhusawal (PO NO - 4500110250) | DCB | 3 | 2020-05-29 | 2020-05-29 |  | 2020-06-20 | 0.011884 | Firm | 0.011884 | 0.011884
| 223 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for spraying of disinfectant for maintaining sanitation at 1X660 MW Bhusawal Project office complex. (PO NO - 4500110206) | DCB | 3 | 2020-05-29 | 2020-05-15 | 2020-11-11 | 2020-11-12 | 0.013982 | Firm | 0.013982 | 0.013982
| 224 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Works contract for day to day maintenance of electrical installations at project office, staff quarters and other miscellaneous electrical works in the project premises. (PO NO - 4500109822) | DCB | 3 | 2020-05-29 | 2020-04-24 | 2021-04-24 | 2021-04-21 | 0.050332 | Firm | 0.050332 | 0.050332
| 225 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of hiring of vehicle (TATA Indica/Vista/Bolt) along with driver for Dy. C.E. (Project) & services of hiring of vehicles on as-and-when required basis at 1x660 MW Bhusawal Project (PO NO - 4500109440) | DCB | 3 | 2020-04-22 | 2020-06-24 | 2021-06-24 | 2021-12-29 | 0.075848 | Firm | 0.075848 | 0.082306
| 226 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for supplying air coolers on hire basis at 1x660 MW Bhusawal Project. (PO NO - 4500109438) | DCB | 3 | 2020-04-07 | 2020-04-15 | 2020-08-13 | 2020-07-31 | 0.029736 | Firm | 0.029736 | 0.026196
| 227 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract for operation & maintenance of 33/11KV substation and cable laying at Bhusawal Project (PO NO - 4500109794) | DCB | 3 | 2020-04-07 | 2020-04-07 | 2021-04-07 | 2021-06-27 | 0.16051 | Firm | 0.16051 | 0.16051
| 228 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicles (Mahindra TUV 300) along with driver at 1X660 MW Bhusawal Project. (PO NO - 4500109070) | DCB | 3 | 2020-03-20 | 2021-01-08 | 2022-01-08 | 2023-06-30 | 0.12648 | Firm | 0.12648 | 0.12368
| 229 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work of dismentling, shifting and re-erection of 11KV two pole structure with underground cable in front of 2x500MW Factory gate. (PO NO - 4500108990) | DCB | 3 | 2020-03-20 | 2020-06-23 | 2020-12-20 | 2020-07-25 | 0.019914 | Firm | 0.019914 | 0.019914
| 230 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement & installation of UTM device (Sophos XG-135) with three years license for the O/o Chief Engineer (Project), 1X660 MW Project Bhusawal through GeM portal (PO NO - 4500109193) | DCB | 3 | 2020-03-20 | 2020-03-20 |  | 2020-06-13 | 0.02495 | Firm | 0.02495 | 0.02495
| 231 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for maintenance of 1.5T & 2T split air conditioners installed at project office. (PO NO - 4500109131) | DCB | 3 | 2020-03-18 | 2020-04-01 | 2021-04-01 | 2021-03-17 | 0.029606 | Firm | 0.029606 | 0.029606
| 232 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing parking management services at 1x660 MW Bhusawal project office (PO NO - 4500108775) | DCB | 3 | 2020-03-12 | 2020-07-08 | 2021-01-04 | 2021-01-08 | 0.031614 | Firm | 0.031614 | 0.031614
| 233 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for hiring of vehicles along with driver for Superintending Engineer (Project) at 1x660 MW Bhusawal Project. (PO NO - 4500108617) | DCB | 3 | 2020-03-09 | 2020-04-01 | 2021-04-01 | 2021-10-31 | 0.11944 | Firm | 0.11944 | 0.12642
| 234 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of A4 paper rims at 1x660 MW Bhusawal project office through GeM portal (PO NO - 4500109060) | DCB | 3 | 2020-03-04 | 2020-03-04 |  | 2020-02-17 | 0.0016594 | Firm | 0.0016594 | 0.0016594
| 235 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of New large format Inkjet (colour) plotter for the office of Cheif Engineer at 1x660 MW Bhusawal project office through GeM portal (PO NO - 4500108511) | DCB | 3 | 2020-02-13 | 2020-02-13 |  | 2020-02-17 | 0.016391 | Firm | 0.016391 | 0.016391
| 236 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for cutting of grass, bushes, shrubs, small trees, trimming of trees and removing dead trees at 1x660 MW Bhusawal project office (PO NO - 4500108487) | DCB | 3 | 2020-02-11 | 2020-02-20 | 2020-08-18 | 2020-08-08 | 0.019405 | Firm | 0.019405 | 0.019405
| 237 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Industrial Safety Helmet for the office of Cheif Engineer at 1x660 MW Bhusawal project office through GeM portal (PO NO - 4500108532) | DCB | 3 | 2020-02-07 | 2020-02-07 |  | 2020-02-05 | 0.0021299 | Firm | 0.0021299 | 0.0021299
| 238 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of new scanner cum photocopy machine at project office through GeM portal (PO NO - 4500108454) | DCB | 3 | 2020-02-06 | 2020-02-06 |  | 2020-06-18 | 0.015849 | Firm | 0.015849 | 0.015849
| 239 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Projector at project office through GeM portal (PO NO - 4500108456) | DCB | 3 | 2020-02-06 | 2020-02-06 |  | 2020-01-24 | 0.008945 | Firm | 0.008945 | 0.008945
| 240 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work of electrification of 03 Nos. of D-type buildings (18 quarters) and 04 Nos. of E-type buildings (24 quarters) alongwith providing & fitting of electrical items, fixtures etc. at BTPS colony (PO NO - 4500108470) | DCB | 3 | 2020-02-06 | 2020-02-06 | 2020-03-22 | 2020-07-24 | 0.22371 | Firm | 0.22371 | 0.20215
| 241 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply & Installation of air conditioners & appliances with accessories for project transit quarter. (PO NO - 4500106506) | DCB | 3 | 2019-09-25 | 2019-09-25 | 2019-10-25 | 2019-10-24 | 0.036354 | Firm | 0.036354 | 0.036354
| 242 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of engaging MSSC (MSF) security agency at 1x660 MW Bhusawal Project. (PO NO - 4500106329) | - | 1 | 2019-08-20 | 2019-11-20 | 2020-11-19 | 2020-11-30 | 2.3605 | Firm | 2.3605 | 2.3039
| 243 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicle along with driver for Security staff for round the clock at 1x660 MW Bhusawal Project through tenderization (PO NO - 4500105522) | DCB | 3 | 2019-06-29 | 2019-07-01 | 2020-06-30 | 2020-08-06 | 0.11667 | Firm | 0.11667 | 0.11705
| 244 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of A3 & A4 paper rim through GeM portal (PO NO - 4500117065) | DCB | 3 |  | 2021-12-17 |  | 2021-12-16 | 0.0095286 | Firm | 0.0095286 | 0.0094938
| 245 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for hiring of Ambulance (TATA winger/407) along with driver on round-o-clock basis at 1x660 MW Bhusawal Project. (PO NO - 4500117072) | DCB | 3 |  | 2021-01-01 |  | 2021-11-01 | 0.049738 | Firm | 0.049738 | 0.06248
| 246 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Poly Carbonate Shield(MHA) at project office through GeM portal (PO NO - 4500108416) | DCB | 3 |  | 2020-01-30 |  | 2020-02-03 | 0.003363 | Firm | 0.003363 | 0.003363
| 247 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of poly carbonate lathi at project office through GeM portal (PO NO - 4500108406) | DCB | 3 |  | 2020-01-30 |  | 2020-01-22 | 0.00090001 | Firm | 0.00090001 | 0.00090001
| 248 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of computer operators for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500108386) | DCB | 3 |  | 2020-01-27 | 2021-01-26 | 2021-04-15 | 0.13886 | Firm | 0.13886 | 0.13728
| 249 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of computer operators for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500108385) | DCB | 3 |  | 2020-01-27 | 2021-01-26 | 2025-03-18 | 0.13886 | Firm | 0.13886 | 0.13886
| 250 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing aluminum partition at 1x660 MW Bhusawal project office (PO NO - 4500108304) | DCB | 3 |  | 2020-02-05 | 2020-08-03 | 2020-02-25 | 0.034657 | Firm | 0.034657 | 0.034657
| 251 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of various transformer protection relays for 33/11KV substation at x1660MW Bhusawal Project. (PO NO - 4500108214) | DCB | 3 |  | 2020-01-07 | 2020-02-21 | 2020-02-20 | 0.023211 | Firm | 0.023211 | 0.023211
| 252 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for hiring of vehicle along with driver for MSSC (MSF) staff for round the clock at 1x660 MW Bhusawal Project (PO NO - 4500107936) | DCB | 3 |  | 2019-12-04 | 2020-06-01 | 2020-06-30 | 0.044264 | Firm | 0.044264 | 0.044125
| 253 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of color printer through GeM portal at 1X660 MW Project (PO NO - 4500107871) | DCB | 3 |  | 2019-12-16 |  | 2019-12-10 | 0.0006814 | Firm | 0.0006814 | 0.0006814
| 254 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Desktop computers for 1x660MW Bhusawal Project office. (PO NO - 4500107618) | DCB | 3 |  | 2019-11-25 |  | 2019-12-22 | 0.1372 | Firm | 0.1372 | 0.1372
| 255 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of multifunction printers for Project Office through GeM portal. (PO NO - 4500107569) | DCB | 3 |  | 2019-11-25 |  | 2019-12-05 | 0.014786 | Firm | 0.014786 | 0.014786
| 256 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for providing services of computer operators for day to day office work at 1x660 MW Bhusawal Project. (PO NO - 4500107567) | DCB | 3 |  | 2019-11-11 | 2020-03-10 | 2020-01-25 | 0.026158 | Firm | 0.026158 | 0.026158
| 257 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Laptops for Project Office through GeM portal (PO NO - 4500107527) | DCB | 3 |  | 2019-11-25 |  | 2019-12-07 | 0.01276 | Firm | 0.01276 | 0.01276
| 258 | 1x660 MW Bhusawal Project - Other misc Expenditure | PROCUREMENT OF ESSENTIAL SPARES REQUIRED FOR 33KV & 11KV ABB MAKE VCBs AT 33/11KV SUBSTATION. (PO NO - 4500107483) | DCB | 3 |  |  |  | 2019-12-05 | 0.021771 | Firm | 0.021771 | 0.021771
| 259 | 1x660 MW Bhusawal Project - Other misc Expenditure | WORK CONTRACT FOR REPAIRING/OVERHAULING OF 33KV & 11KV ABB MAKE VCBs AT 33/11KV SUBSTATION (PO NO - 4500107426) | DCB | 3 |  | 2019-11-20 | 2019-12-05 | 2020-02-18 | 0.025458 | Firm | 0.025458 | 0.025458
| 260 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of ceiling fans for various newly renovated NE-type & D-type quarters at BTPS colony. (PO NO - 4500107263) | DCB | 3 |  |  |  | 2019-11-05 | 0.029648 | Firm | 0.029648 | 0.029648
| 261 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for point wiring at 1x660MW Bhusawal Project on as & when requird basis. (PO NO - 4500107261) | DCB | 3 |  | 2019-11-01 | 2019-12-01 | 2019-12-21 | 0.030071 | Firm | 0.030071 | 0.030071
| 262 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for day to day electrical installations at project office, staff quarters & other electrical works at Bhusawal Project Premises. (PO NO - 4500106937) | DCB | 3 |  | 2019-09-25 | 2020-03-25 | 2020-04-23 | 0.029739 | Firm | 0.029739 | 0.029739
| 263 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of All-in-one computers for senior officers at Bhusawal Project office through GeM. (PO NO - 4500106287) | DCB | 3 |  | 2019-08-22 | 2019-09-21 | 2019-10-03 | 0.011873 | Firm | 0.011873 | 0.011873
| 264 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for miscellaneous electrical works during renovation & modification of cabins of senior officers at Bhusawal Project (PO NO - 4500106196) | DCB | 3 |  | 2019-08-26 | 2019-09-25 | 2019-09-21 | 0.018754 | Firm | 0.018754 | 0.018754
| 265 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of 5 KV Insulation Tester for day to day maintenance of the electrical installations for Bhusawal Project. (PO NO - 4500106160) | DCB | 3 |  | 2019-08-26 | 2019-09-25 | 2019-09-04 | 0.029075 | Firm | 0.029075 | 0.029075
| 266 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Chairs for Office of Dy. Chief Engineer(project) 1x660 MW Bhusawal Project Office. (PO NO - 4500105965) | DCB | 3 |  | 2019-08-08 | 2019-09-07 | 2019-08-26 | 0.022007 | Firm | 0.022007 | 0.022007
| 267 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of providing, making and fixing of Glazed partition, partition framing, door modification and reception sitting arrangement at 1X660 MW, Bhusawal Project (PO NO - 4500105963) | DCB | 3 |  | 2019-09-04 | 2019-10-04 | 2019-09-14 | 0.034894 | Firm | 0.034894 | 0.034894
| 268 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of providing, making and fixing of Conference sitting arrangement, Removal of old partition, partition framing, Highlighter and back paneling light arrangement of C.E. cabin at 1X660 MW, Bhusawal Project. (PO NO - 4500105955) | DCB | 3 |  | 2019-08-08 | 2019-09-07 | 2019-08-26 | 0.034766 | Firm | 0.034766 | 0.034766
| 269 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for hiring of vehicle along with driver for Superintending Engineer (Project) at 1x660 MW Bhusawal Project (PO NO - 4500105402) | DCB | 3 |  | 2019-06-01 | 2020-05-31 | 2020-03-31 | 0.06135 | Firm | 0.06135 | 0.060935
| 270 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Desktop Computers for project office (through GeM portal : 6 nos) (PO NO - 4500105252) | DCB | 3 |  | 2019-05-20 | 2019-06-19 | 2019-05-31 | 0.02988 | Firm | 0.02988 | 0.02988
| 271 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement & installation of water heaters & AC's with accessories for project Transit quarter BM-23 (PO NO - 4500104831) | DCB | 3 |  | 2019-05-09 | 2019-05-24 | 2019-05-10 | 0.027292 | Firm | 0.027292 | 0.027292
| 272 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for providing services of driver for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500104781) | DCB | 3 |  | 2019-05-07 | 2020-05-06 | 2020-05-31 | 0.09708 | Firm | 0.09708 | 0.0973
| 273 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of computer operator for day to day office work at 1x660 MW Bhusawal Project through tenderization (PO NO - 4500104780) | DCB | 3 |  | 2019-04-27 | 2019-10-24 | 2019-10-12 | 0.12999 | Firm | 0.12999 | 0.13649
| 274 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of providing establishment & interconnection of LAN Network at 1x660MW project office. (PO NO - 4500104751) | DCB | 3 |  | 2019-05-02 | 2019-06-01 | 2019-05-20 | 0.035282 | Firm | 0.035282 | 0.034928
| 275 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of unskilled & semi-skilled labours for day to day office work at 1x660 MW Bhusawal Project through tenderization (PO NO - 4500104750) | DCB | 3 |  | 2019-04-22 | 2020-04-21 | 2020-05-08 | 0.28559 | Firm | 0.28559 | 0.298
| 276 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of 06Nos. All-In-One printer required for Office of Dy. Chief Engineer (Proj.) through GeM (PO NO - 4500104741) | DCB | 3 |  |  |  | 2019-05-07 | 0.008595 | Firm | 0.008595 | 0.008595
| 277 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of home appliances for project transit quarter (PO NO - 4500104724) | DCB | 3 |  |  |  | 2019-05-02 | 0.025801 | Firm | 0.025801 | 0.025801
| 278 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for maintenance and providing catering services at old guest house (near Tapi river), BTPS Deepnagar through tenderization. (PO NO - 4500104530) | DCB | 3 |  | 2019-04-20 | 2020-04-19 | 2020-04-21 | 0.20001 | Firm | 0.20001 | 0.20001
| 279 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for hiring of vehicles for project staff along with driver & fuel for 1x660 MW Bhusawal Project office through tenderization (PO NO - 4500104383) | DCB | 3 |  | 2019-04-11 | 2020-04-10 | 2020-02-29 | 0.077089 | Firm | 0.077089 | 0.077025
| 280 | 1x660 MW Bhusawal Project - MCE Expenditure | Payment of MCE Insurance Premium to M/s. BHEL - New Delhi (PO NO - 4500103519) | - | 1 |  | 2018-12-14 |  | 2022-05-13 | 0.94711 | Firm | 0.94711 | 0
| 281 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of maintenance & repair of 1.5/2 T AC & water cooler with RO at 1x660 MW Bhusawal Project office. (PO NO - 4500103365) | DCB | 3 |  | 2019-04-09 |  | 2019-06-09 | 0.023557 | Firm | 0.023557 | 0.023557
| 282 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of general electrical items for routine maintenance work of project office & quarters. (PO NO - 4500103333) | DCB | 3 |  |  |  | 2019-04-19 | 0.032465 | Firm | 0.032465 | 0.032465
| 283 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of Air coolers during summer season for 1x660 MW Bhusawal Project (PO NO - 4500103194) | DCB | 3 |  |  |  |  | 0.0264 | Firm | 0.0264 | 0.0264
| 284 | 1x660 MW Bhusawal Project - MCE Expenditure | Payment of MCE Insurance Premium to M/s. BHEL - New Delhi (PO NO - 4500103166) | - | 1 |  |  |  |  | 1.5451 | Firm | 1.5451 | 0
| 285 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of networking materials required for establishment of LAN at 1x660 MW Bhusawal Project (PO NO - 4500103087) | DCB | 3 |  |  |  |  | 0.031882 | Firm | 0.031882 | 0.031882
| 286 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of LED slim panel fixtures for project offices at 1x660MW project building (PO NO - 4500103085) | DCB | 3 |  |  |  |  | 0.03203 | Firm | 0.03203 | 0.03203
| 287 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | various carpentry works along-with required materials at project transit quarter in BTPS Colony and providing and fixing one way glass partition for Dy. CE cabin, Deepnagar (PO NO - 4500102864) | DCB | 3 |  |  |  |  | 0.012142 | Firm | 0.012142 | 0.012142
| 288 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work of 33/11 KV Substation operation & 11 KV line maintenance contract (PO NO - 4500102832) | DCB | 3 |  |  |  |  | 0.13297 | Firm | 0.13297 | 0.13297
| 289 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work contract for providing services of skilled attendant as caretaker for project transit quarters at 1x660 MW Bhusawal Project (PO NO - 4500102755) | DCB | 3 |  |  |  |  | 0.031008 | Firm | 0.031008 | 0.022521
| 290 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | works by engaging agency for providing services of skilled manpower as computer operator for assisting day to day office works (PO NO - 4500102583) | DCB | 3 |  |  |  |  | 0.033748 | Firm | 0.033748 | 0.033664
| 291 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | works by engaging agency for providing services of unskilled manpower for assisting day to day office works (PO NO - 4500102484) | DCB | 3 |  |  |  |  | 0.033793 | Firm | 0.033793 | 0.033793
| 292 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of of Executive Revolving Chairs for Office of Chief Engineer (project) 1x660 MW Bhusawal Project Office (PO NO - 4500102270) | DCB | 3 |  |  |  |  | 0.014361 | Firm | 0.014361 | 0.014361
| 293 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of providing & fixing of flooring PVC carpets, vertical blends, windows curtains, sofa cushioning and covering etc. at 1x660 MW Bhusawal Project Office. (PO NO - 4500102253) | DCB | 3 |  |  |  |  | 0.15128 | Firm | 0.15128 | 0.15128
| 294 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of providing, making and fixing of round office table, Side lappy runner unit, Sofa two Seater, Central table, Fancy sofa cornice, Door modification etc.at project officecabin for 1X660 MW, Bhusawal Project (PO NO - 4500102205) | DCB | 3 |  |  |  |  | 0.032135 | Firm | 0.032135 | 0.032135
| 295 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of providing, making and fixing of Back Paneling, Table Cushioning, Displays, Vertical Blinds, CPC carpet at Project Office Cabin for 1X660 MW, Bhusawal Project (PO NO - 4500102200) | DCB | 3 |  |  |  |  | 0.032411 | Firm | 0.032411 | 0.032411
| 296 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work of providing, fixing and constructing watchman tower structure as per IB recommendation for security guards for safety & security of project premises as per scope of work at1x660MW Bhusawal Project Site. (PO NO - 4500102125) | DCB | 3 |  |  |  |  | 0.20081 | Firm | 0.20081 | 0.20081
| 297 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of printing of Identity cards of MSPGCL employees posted at the office of C.E (Project), 1 x 660 MW Bhusawal Project, Deepnagar (PO NO - 4500102124) | DCB | 3 |  |  |  |  | 0.00435 | Firm | 0.00435 | 0.001557
| 298 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for day to day electrical installations at project office, staff quarters & other electrical works at Bhusawal Project Premises. (PO NO - 4500102119) | DCB | 3 |  |  |  |  | 0.027831 | Firm | 0.027831 | 0.027831
| 299 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract for applying Anti-fire coating for HT/LT cables at substation & batching plant supply cabin. (PO NO - 4500101829) | DCB | 3 |  |  |  |  | 0.020375 | Firm | 0.020375 | 0.021674
| 300 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | procurement of Tailored apron, Napkin, Towel and Chaircover for engineers of1x660 MW Bhusawal Project Office (PO NO - 4500101816) | DCB | 3 |  |  |  |  | 0.012206 | Firm | 0.012206 | 0.012206
| 301 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for electrical wiring for various aitional points at residensial quarter for CE (P) (PO NO - 4500101701) | DCB | 3 |  |  |  |  | 0.0098931 | Firm | 0.0098931 | 0.0098931
| 302 | 1x660 MW Bhusawal Project - Other misc Expenditure | Extension of 11 KV construction supply from 33/11 KV substation to 1x660 MW site (PO NO - 4500101522) | DCB | 3 |  |  |  |  | 0.27404 | Firm | 0.27404 | 0.27404
| 303 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | providing & fixing of concrete & steel benches for 1x660 MW Bhusawal Project Office (PO NO - 4500101362) | DCB | 3 |  |  |  |  | 0.013668 | Firm | 0.013668 | 0.016128
| 304 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | works by engaging agency for providing services of skilled manpower (drivers) for office vehicles. (PO NO - 4500101347) | DCB | 3 |  |  |  |  | 0.026934 | Firm | 0.026934 | 0.026708
| 305 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | works by engaging agency for providing services of unskilled manpower for assisting day to day office works (PO NO - 4500101306) | DCB | 3 |  |  |  |  | 0.028066 | Firm | 0.028066 | 0.033117
| 306 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | works by engaging agency for providing services of skilled manpower as computer operator for assisting day to day office works. (PO NO - 4500101305) | DCB | 3 |  |  |  |  | 0.027808 | Firm | 0.027808 | 0.032733
| 307 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of 33 KV, 3 core, 300 sq.mm XLPE cable for standby source supply to 33/11 KV substation (PO NO - 4500100763) | DCB | 3 |  |  |  |  | 0.021672 | Firm | 0.021672 | 0.021672
| 308 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply and erection of safety statue indicating importance of safety at 1x660 MW Bhusawal Project (PO NO - 4500100577) | DCB | 3 |  |  |  |  | 0.02301 | Firm | 0.02301 | 0.02301
| 309 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for overhauling of ceiling fans & replacement of spare parts (PO NO - 4500099989) | DCB | 3 |  |  |  |  | 0.01893 | Firm | 0.01893 | 0.022337
| 310 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of upgradation of existing 4 nos. of 1.5 T ACs at bhusawal project office. (PO NO - 4500099277) | DCB | 3 |  |  |  |  | 0.023458 | Firm | 0.023458 | 0.023458
| 311 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for cleaning, screening & refilling of metal stones and painting of transformers at 33/11 KV substation near 2x500 MW Gate (PO NO - 4500099274) | DCB | 3 |  |  |  |  | 0.021559 | Firm | 0.021559 | 0.021559
| 312 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Painting of internal walls of Panel room at Substation along with metering cabins,battery room & structure foundations. (PO NO - 4500099272) | DCB | 3 |  |  |  |  | 0.022186 | Firm | 0.022186 | 0.022186
| 313 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of 240 W LED flood lamps for project office premises. (PO NO - 4500099184) | DCB | 3 |  |  |  |  | 0.021712 | Firm | 0.021712 | 0.021712
| 314 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of energy efficient LED fixtures for 33/11 KV substation & street lighting of project premises. (PO NO - 4500099183) | DCB | 3 |  |  |  |  | 0.022684 | Firm | 0.022684 | 0.02153
| 315 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of up gradation of existing office PCs (Desktop Computers) for 1x660 MW Bhusawal Project Office. (PO NO - 4500099079) | DCB | 3 |  |  |  |  | 0.019975 | Firm | 0.019975 | 0.023571
| 316 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | awarding maintenance work of trees (600 Nos.) planted during “Van Mahotsav 2018”. (PO NO - 4500099065) | DCB | 3 |  |  |  |  | 0.0198 | Firm | 0.0198 | 0.023364
| 317 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Erection & commissioning of mini high mast pole along with LED flood lights. (PO NO - 4500098722) | DCB | 3 |  |  |  |  | 0.016526 | Firm | 0.016526 | 0.016526
| 318 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of fabrication and erection of canopy for parking (PO NO - 4500098626) | DCB | 3 |  |  |  |  | 0.022922 | Firm | 0.022922 | 0.022922
| 319 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Expert consultation for SAP (PO NO - 4500098625) | - | 1 |  |  |  |  | 0.0118 | Firm | 0.0118 | 0.01
| 320 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Services of Photography and video shooting of various events & Project Milestone Activities (PO NO - 4500098624) | DCB | 3 |  |  |  |  | 0.02173 | Firm | 0.02173 | 0.02173
| 321 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of removing of grass, bushes, shrubs, small trees, trimming of trees and removing dead trees around the 1x660 MW Bhusawal Project Office. (PO NO - 4500098622) | DCB | 3 |  |  |  |  | 0.02325 | Firm | 0.02325 | 0.023246
| 322 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of Vehicles (PO NO - 4500098274) | DCB | 3 |  |  |  |  | 0.031326 | Firm | 0.031326 | 0.027151
| 323 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of Vehicles (PO NO - 4500098273) | DCB | 3 |  |  |  |  | 0.03089 | Firm | 0.03089 | 0.028693
| 324 | 1x660 MW Bhusawal Project - Other misc Expenditure | Painting of structures of Substation along with metering cabin,Gate & fencing (PO NO - 4500098116) | DCB | 3 |  |  |  |  | 0.023579 | Firm | 0.023579 | 0.023579
| 325 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply of 11 KV, XLPE cable for construction supply from 33/11 KV substation to 1x660 MW site (PO NO - 4500098050) | DCB | 3 |  |  |  |  | 0.20911 | Firm | 0.20911 | 0.21025
| 326 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract for modification of 11 KV supply line to project & BHEL office (PO NO - 4500097797) | DCB | 3 |  |  |  |  | 0.020809 | Firm | 0.020809 | 0.020809
| 327 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply of material for 11 kv line modification for improving stability of supply at project office (PO NO - 4500097649) | DCB | 3 |  |  |  |  | 0.012836 | Firm | 0.012836 | 0.012836
| 328 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | procurement of safety shoes, Rain suit & gum boots (PO NO - 4500097456) | DCB | 3 |  |  |  |  | 0.019005 | Firm | 0.019005 | 0.019005
| 329 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of routine electrical maintenance of project office. (PO NO - 4500097190) | DCB | 3 |  |  |  |  | 0.023323 | Firm | 0.023323 | 0.023323
| 330 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of fabrication and erection of sliding entrance main gate at 1x660 MW Bhusawal Project Office. (PO NO - 4500097157) | DCB | 3 |  |  |  |  | 0.023305 | Firm | 0.023305 | 0.023305
| 331 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work contract for tree plantation at 1 x 600 MW project site (PO NO - 4500097155) | DCB | 3 |  |  |  |  | 0.022897 | Firm | 0.022897 | 0.022897
| 332 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of providing Mobile Toilet/ Urinal Van at 1x660 MW Bhusawal Project Site. (PO NO - 4500096811) | DCB | 3 |  |  |  |  | 0.023103 | Firm | 0.023103 | 0.023103
| 333 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Annual work contract for providing services of unskilled labours for extra miscellaneous office works at 1x660 MW Bhusawal Project. (On As & When basis) (PO NO - 4500096733) | DCB | 3 |  |  |  |  | 0.021976 | Firm | 0.021976 | 0.021976
| 334 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of repairs & painting of Quarter -Block 19 at BM building aollted for Dy.CE (Project), Bhusawal (PO NO - 4500096664) | DCB | 3 |  |  |  |  | 0.021726 | Firm | 0.021726 | 0.021726
| 335 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Repair & maintenance of samsung make 2T AC at project office & upgradation of existing 2T AC into energy saver split AC (PO NO - 4500096663) | DCB | 3 |  |  |  |  | 0.023562 | Firm | 0.023562 | 0.023562
| 336 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of Renovation (Furniture) of Dy.CE (Project) Cabin by providing Cupboard and Office table for 1X660 MW, Bhusawal Project. (PO NO - 4500096650) | DCB | 3 |  |  |  |  | 0.016821 | Firm | 0.016821 | 0.016821
| 337 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of Energy efficient LED Flood light & tube lights for project office & premises. (PO NO - 4500096524) | DCB | 3 |  |  |  |  | 0.023287 | Firm | 0.023287 | 0.023287
| 338 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work contract for arranging various kinds of tree saplings and pots to celebrate National Tree Plantation Day: 01 July 2018 at 1 x 660 MW Bhusawal Project office, Deepnagar. (PO NO - 4500096510) | DCB | 3 |  |  |  |  | 0.021417 | Firm | 0.021417 | 0.021417
| 339 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of painting of parking stand shed & supporting structure at 1x660 Bhusawal project office. (PO NO - 4500096504) | DCB | 3 |  |  |  |  | 0.021122 | Firm | 0.021122 | 0.021122
| 340 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of printing of security related various identity cards and daily report book for the office of Dy. C.E (Project), 1 x 660 MW Bhusawal Project, Deepnagar. (PO NO - 4500096503) | DCB | 3 |  |  |  |  | 0.01239 | Firm | 0.01239 | 0.01239
| 341 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of RSJ pole for erection of 33KV line. (PO NO - 4500096347) | DCB | 3 |  |  |  |  | 0.017098 | Firm | 0.017098 | 0.017388
| 342 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Stationary & general items for day to day use for O/o Dy.CE,Bhusawal project (PO NO - 4500096201) | DCB | 3 |  |  |  |  | 0.00084429 | Firm | 0.00084429 | 0.00084429
| 343 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicle along with driver for Dy. Chief Engineer, 1 x 660 MW Bhusawal Project (FOR 2 MONTHS) (PO NO - 4500096094) | DCB | 3 |  |  |  |  | 0.010524 | Firm | 0.010524 | 0.0099415
| 344 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Stationary & general items for day to day use for O/o Dy.CE,Bhusawal project (PO NO - 4500095891) | DCB | 3 |  |  |  |  | 0.0084998 | Firm | 0.0084998 | 0.0084998
| 345 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work contract for providing services of unskilled labours for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500095850) | DCB | 3 |  |  |  |  | 0.057092 | Firm | 0.057092 | 0.059901
| 346 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | providing services of drivers for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500095702) | DCB | 3 |  |  |  |  | 0.032608 | Firm | 0.032608 | 0.026688
| 347 | 1x660 MW Bhusawal Project - Other misc Expenditure | Servicing & maintenance of 33/11 KV substation near 2x500MW gate. (PO NO - 4500095665) | DCB | 3 |  |  |  |  | 0.023146 | Firm | 0.023146 | 0.023146
| 348 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of computer operation for day to day office work at 1x660 MW Bhusawal Project (PO NO - 4500095439) | DCB | 3 |  |  |  |  | 0.12949 | Firm | 0.12949 | 0.13578
| 349 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply of End termination kit for 3 core, 300 sqmm XLPE cable & insulators for diversion of 33 KV line (PO NO - 4500095068) | DCB | 3 |  |  |  |  | 0.03057 | Firm | 0.03057 | 0.03057
| 350 | 1x660 MW Bhusawal Project - Other misc Expenditure | Erection & commissioning and diversion of 33 KV O/H supply lines to 33/11 KV substation (PO NO - 4500094993) | DCB | 3 |  |  |  |  | 0.019095 | Firm | 0.019095 | 0.019095
| 351 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of providing & fixing of windows curtains, wooden flooring PVC carpet & roll blinds at 1x660 MW Bhusawal Project Office. (PO NO - 4500094977) | DCB | 3 |  |  |  |  | 0.023543 | Firm | 0.023543 | 0.023543
| 352 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of 01 Nos. computer along with printer required for Office of Dy. Chief Engineer (Proj.). (PO NO - 4500093956) | DCB | 3 |  |  |  |  | 0.010313 | Firm | 0.010313 | 0.0005244
| 353 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of supply & commissioning of earthing pits at 1x660 MW Bhusawal Project foundation stone laying area. (PO NO - 4500093519) | DCB | 3 |  |  |  |  | 0.01981 | Firm | 0.01981 | 0.023376
| 354 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Repairs & maintenance of Samsung make 2T # Air conditioners at 1x660 MW Project office and up gradation of existing water cooler 60 lit (PO NO - 4500093505) | DCB | 3 |  |  |  |  | 0.019919 | Firm | 0.019919 | 0.023505
| 355 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work contract for providing services of unskilled labours for day to day office work (PO NO - 4500093492) | DCB | 3 |  |  |  |  | 0.014898 | Firm | 0.014898 | 0.01758
| 356 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for providing services of drivers for day to day office work (PO NO - 4500093477) | DCB | 3 |  |  |  |  | 0.007072 | Firm | 0.007072 | 0.008345
| 357 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | work of painting of project office roof (inner side) along the corridor and supporting structure, walls & window grills at 1x660 MW Bhusawal Project Office. (PO NO - 4500093433) | DCB | 3 |  |  |  |  | 0.018548 | Firm | 0.018548 | 0.021887
| 358 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of providing CCTV & related IT services for security system for 1x660 MW Bhusawal Project foundation stone laying program. (PO NO - 4500093184) | DCB | 3 |  |  |  |  | 0.02301 | Firm | 0.02301 | 0.02301
| 359 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of removing of bushes, shrubs, small trees, trimming of trees and cleaning of the drains and area around the 1x660 MW Bhusawal Project Office. (PO NO - 4500093026) | DCB | 3 |  |  |  |  | 0.019546 | Firm | 0.019546 | 0.015906
| 360 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Erection of chianlin fencing around 500KVA Transformer near 500MW/660MW wall compound (PO NO - 4500092866) | DCB | 3 |  |  |  |  | 0.008794 | Firm | 0.008794 | 0.010377
| 361 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for day to day electrical complaints of Project office & other electrical works in the Bhusawal Project premises. (PO NO - 4500092863) | DCB | 3 |  |  |  |  | 0.019845 | Firm | 0.019845 | 0.023417
| 362 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work Contract for providing skilled assistance for operating day to day computers in Account, Technical & GAD section (PO NO - 4500092573) | DCB | 3 |  |  |  |  | 0.017706 | Firm | 0.017706 | 0.020893
| 363 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Supply of air coolers on hire basis for 1x660 MW Bhusawal Project (PO NO - 4500092433) | DCB | 3 |  |  |  |  | 0.019974 | Firm | 0.019974 | 0.023569
| 364 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicle AC (Swift Dzire) along with driver for 1 x 660 MW Bhusawal Project office. (PO NO - 4500092241) | DCB | 3 |  |  |  |  | 0.01795 | Firm | 0.01795 | 0.014607
| 365 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Providing unskilled manpower in Coal Handling Plant for removal of tarpaulin covered on stacked coal at 1X660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500140879) | - | 1 | 2025-02-14 |  |  |  | 0.0052546 | Firm | 0.0052546 | 0.0052546
| 366 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of license free walkie-talkie sets at 1x660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500140024) | - | 1 | 2025-01-28 |  |  |  | 0.011328 | Firm | 0.011328 | 0.011328
| 367 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of printing of logbooks for commissioning activities at 1x660 MW project on confirmatory basis (PO NO - 4500138830) | - | 1 | 2025-01-22 |  |  |  | 0.0080909 | Firm | 0.0080909 | 0.0080909
| 368 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of repairing of 20 Mtr. high mast tower near NDCT at 1x660 MW Bhusawal Project on confirmatory basis (PO NO - 4500139234) | - | 1 | 2025-01-22 |  |  |  | 0.0037406 | Firm | 0.0037406 | 0.0037406
| 369 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Network Rack for mounting of DSM equipment’s at 1 x 660 MW project on confirmatory basis (PO NO - 4500138090) | - | 1 | 2025-01-15 |  |  |  | 0.0051413 | Firm | 0.0051413 | 0.0051413
| 370 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work of stacking loading transportation of resins and water filtration sand at project site on confirmatory basis (PO NO - 4500138212) | - | 1 | 2024-12-04 |  |  |  | 0.0087733 | Firm | 0.0087733 | 0.0087733
| 371 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work of stacking loading transportation of resins and water filtration sand at project site on confirmatory basis (PO NO - 4500138211) | - | 1 | 2024-12-04 |  |  |  | 0.00885 | Firm | 0.00885 | 0.00885
| 372 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of repairing of 150KVA, 11KV/415V distribution transformer for water fitration plant at Fulgaon Kathora on confirmatory basis. (PO NO - 4500136845) | - | 1 | 2024-11-28 |  |  |  | 0.021211 | Firm | 0.021211 | 0.021211
| 373 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of 3 Phase Electronic energy meter & ring type current transformers on confirmatory basis. (PO NO - 4500136535) | - | 1 | 2024-09-10 |  |  |  | 0.0031624 | Firm | 0.0031624 | 0.0031624
| 374 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Work of hiring tractor with diesel and driver for shifting of insulation material stacked in project sheds at the risk and cost of M/s BHEL by placing confirmatory order. (PO NO - 4500136492) | - | 1 | 2024-09-04 |  |  |  | 0.0045312 | Firm | 0.0045312 | 0.0045312
| 375 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for dismantling, loading, transportation, unloading and assembly of storage racks from Storage shed at Project premises to storage shed at Major Stores ‘A’ premises on confirmatory basis (PO NO - 4500136322) | - | 1 | 2024-08-24 |  |  |  | 0.010856 | Firm | 0.010856 | 0.010856
| 376 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for refreshment arrangements at Purna Guest House in view of visit of Hon’ble Member, TPMG, CEA, Hon’ble Director (Projects), MSPGCL and Higher officials & top management of MSPGCL at 1x660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500135820) | - | 1 | 2024-08-08 |  |  |  | 0.0049061 | Firm | 0.0049061 | 0.0048986
| 377 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for dismantling, loading, transportation, unloading and assembly of storage racks from Storage shed at Project premises to storage shed at Major Stores ‘A’ premises on confirmatory basis (PO NO - 4500135098) | - | 1 | 2024-07-05 |  |  |  | 0.005664 | Firm | 0.005664 | 0.005664
| 378 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of log books and permit books for commissioning staff at 1X660 MW Bhusawal Project on confirmatory basis (PO NO - 4500134361) | - | 1 | 2024-06-14 |  |  |  | 0.0045666 | Firm | 0.0045666 | 0.0045666
| 379 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for replacement of compressor of split air conditioner (2.0 Ton capacity) through Confirmatory order (PO NO - 4500134118) | - | 1 | 2024-05-30 |  |  |  | 0.0018461 | Firm | 0.0018461 | 0.0018461
| 380 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero/Neo or equivalent vehicle) along with driver for security staff at 1x660MW Bhusawal Project through Confirmatory order (PO NO - 4500134103) | - | 1 | 2024-05-30 |  |  |  | 0.0049581 | Firm | 0.0049581 | 0.005206
| 381 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | hiring services of M/s. TCR Engineering Services Pvt. Ltd., Navi Mumbai for boiler tube samples analysis viz, Tensile testing, hardness testing, micrstructure analysis with sample cutting machining & specimen preparation at 1x660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500132862) | - | 1 | 2024-04-29 |  |  |  | 0.0048144 | Firm | 0.0048144 | 0.0048144
| 382 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Prior approval for the Work contract for operating scanner cum photocopy (Xerox), Plotter machine at 1X660 MW Bhusawal Project office on confirmatory basis (PO NO - 4500132278) | - | 1 | 2024-04-15 |  |  |  | 0.0053972 | Firm | 0.0053972 | 0.0053972
| 383 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of license free walkie-talkie sets for AHP package at 1x660 MW Bhusawal Project by placing confirmatory order. (PO NO - 4500131756) | - | 1 | 2024-03-22 |  |  |  | 0.0058528 | Firm | 0.0058528 | 0.0058528
| 384 | 1x660 MW Bhusawal Project - Other misc_BHEL R&C Expenditure | Work order for providing consultants & expert services for renewal of PESO CCOE license for storgae of fuel oil (HFO & LDO) at 1x660 MW Bhusawal Project at the risk & cost of M/s. BHEL by placing confirmatory order. (PO NO - 4500131991) | - | 1 | 2024-03-22 |  |  |  | 0.0055342 | Firm | 0.0055342 | 0.0055342
| 385 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work of Loading, Unloading & transportation of removed non-operational pipeline from Ash Bund to TPS at 1X660MW BSL project by placing confirmatory order (PO NO - 4500130622) | - | 1 | 2024-03-20 |  |  |  | 0.017807 | Firm | 0.017807 | 0.017807
| 386 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero or equivalent ) along with driver for project staff at 1x660MW Bhusawal Project on confirmatory basis (PO NO - 4500131717) | - | 1 | 2024-03-07 |  |  |  | 0.0038136 | Firm | 0.0038136 | 0.0040043
| 387 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of refreshment arrangements at Purna Guest House in view of visit of Hon’ble CMD, MSPGCL and Higher officials & top management at 1x660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500131748) | - | 1 | 2024-03-07 |  |  |  | 0.00525 | Firm | 0.00525 | 0.0052435
| 388 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of refreshment arrangements at Purna Guest House in view of visit of MSPGCL Higher officials & top management at 1x660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500131754) | - | 1 | 2024-03-07 |  |  |  | 0.00504 | Firm | 0.00504 | 0.005036
| 389 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work supply and laying of OFC from 2x500 MW BTPS Server room to 1x660 MW Central Control Room (CCR) at 1x660 MW Project by placing confirmatory order (PO NO - 4500131501) | - | 1 | 2024-03-01 |  |  |  | 0.005841 | Firm | 0.005841 | 0.005841
| 390 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of license free walkie-talkie at 1x660MW Bhusawal Project through Confirmatory order (PO NO - 4500130852) | - | 1 | 2024-01-10 |  |  |  | 0.0058528 | Firm | 0.0058528 | 0.0058528
| 391 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero/Neo or equivalent vehicle) along with driver for security staff at 1x660MW Bhusawal Project through Confirmatory order (PO NO - 4500130761) | - | 1 | 2024-01-08 |  |  |  | 0.0049581 | Firm | 0.0049581 | 0.005206
| 392 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicle (TATA Indica/Vista/Bolt) along with driver for Dy. C.E. (Project) and Higher officers & services of hiring of vehicles on as-and-when required basis at 1x660 MW Bhusawal Project through Confirmatory order (PO NO - 4500130627) | - | 1 | 2024-01-03 |  |  |  | 0.0046108 | Firm | 0.0046108 | 0.0048413
| 393 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicle (TATA Indica/Vista/Bolt) along with driver for Dy. C.E. (Project) and Higher officers & services of hiring of vehicles on as-and-when required basis at 1x660 MW Bhusawal Project through Confirmatory order (PO NO - 4500130521) | - | 1 | 2023-12-27 |  |  |  | 0.0047544 | Firm | 0.0047544 | 0.0049921
| 394 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of SUV (Mahindra TUV/Bolero/Neo or equivalent vehicle) along with driver for security staff at 1x660MW Bhusawal Project through Confirmatory order (PO NO - 4500130315) | - | 1 | 2023-12-19 |  |  |  | 0.0049581 | Firm | 0.0049581 | 0.005206
| 395 | 1x660 MW Bhusawal Project - Other misc Expenditure | work of extension of intercom connection from 2x500 MW BTPS premises to 1x660 MW CCR at Project site at 1x660 MW Project by placing confirmatory order (PO NO - 4500128906) | - | 1 | 2023-10-10 |  |  |  | 0.005841 | Firm | 0.005841 | 0.005841
| 396 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of furniture items for temporary Chummery (Quarter No Super D 13/2 and Super D 15/2) For 1 x 660 MW Bhusawal Project commissioning staff by placing confirmatory order (PO NO - 4500128832) | - | 1 | 2023-10-06 |  |  |  | 0.0055342 | Firm | 0.0055342 | 0.0055342
| 397 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for refreshment arrangements at Purna Guest House in view of Hon’ble Director (Projects), MSPGCL visit at 1x660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500128838) | - | 1 | 2023-10-05 |  |  |  | 0.0025184 | Firm | 0.0025184 | 0.0025136
| 398 | 1x660 MW Bhusawal Project - Eshtablishment related_Ashtech R&C Expenditure | Work contract for replacement of OFC Cable damaged during construction work to restore Internet connection of BTPS and colony premises by placing confirmatory order at the risk and cost of M/s Ashtech Vaishnavi Engineering Pvt. Ltd - Thane (PO NO - 4500128833) | - | 1 | 2023-09-28 |  |  |  | 0.0048144 | Firm | 0.0048144 | 0.0048144
| 399 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work of hiring of vehicles for VIP on as-and-when required basis at 1x660 MW Project Office by placing confirmatory order (PO NO - 4500128648) | - | 1 | 2023-09-28 |  |  |  | 0.0049709 | Firm | 0.0049709 | 0.0052194
| 400 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | providing internet connectivity along with router and fiber cable etc. at PCR of 1 x 660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500126259) | - | 1 | 2023-06-23 |  |  |  | 0.0030798 | Firm | 0.0030798 | 0.0030798
| 401 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement and laying of optic fiber cable (OFC) for CCTV camera installed at Project site at 1x660 MW Project by placing confirmatory order. (PO NO - 4500127015) | - | 1 | 2023-06-23 |  |  |  | 0.0058882 | Firm | 0.0058882 | 0.0058882
| 402 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for VVIP dinner arrangements in view of Hon’ble CMD, MSPGCL visit at 1x660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500124664) | - | 1 | 2023-03-29 |  |  |  | 0.002625 | Firm | 0.002625 | 0.002625
| 403 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of folding tables to set up conference table in view of Hon’ble CMD, MSPGCL visit at 1x660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500124708) | - | 1 | 2023-03-29 |  |  |  | 0.00493 | Firm | 0.00493 | 0.00493
| 404 | 1x660 MW Bhusawal Project - Other misc Expenditure | Work contract for hardness testing by UCI machine at 1x660 MW Project by placing confirmatory order (PO NO - 4500124568) | - | 1 | 2023-03-28 |  |  |  | 0.005782 | Firm | 0.005782 | 0.005782
| 405 | 1x660 MW Bhusawal Project - Other misc Expenditure | Repairing, Rewinding, Lifting, Shifting of 40 HP Water pump of Fulgaon for water supply on confirmatory order basis (PO NO - 4500123261) | - | 1 | 2023-01-06 |  |  |  | 0.00413 | Firm | 0.00413 | 0.00413
| 406 | 1x660 MW Bhusawal Project - Other misc Expenditure | Works of buffing and cleaning of welded joints at various locations of boiler at 1x660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500122964) | - | 1 | 2022-12-09 |  |  |  | 0.0058516 | Firm | 0.0058516 | 0.0058516
| 407 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Providing "Sukameva" to employees of 1x660 MW Bhusawal Project, Deepnagar by placing confirmatory order (PO NO - 4500122782) | - | 1 | 2022-11-29 |  |  |  | 0.0033007 | Firm | 0.0033007 | 0.0033007
| 408 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Repairing of Submersible pump for installation at Fulgaon for water supply by placing confirmatory order (PO NO - 4500122346) | - | 1 | 2022-11-25 |  |  |  | 0.0038031 | Firm | 0.0038031 | 0.0038031
| 409 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Providing refreshment at 1x660 MW Project Office by placing confirmatory order (PO NO - 4500122637) | - | 1 | 2022-11-22 |  |  | 2022-11-11 | 0.004125 | Firm | 0.004125 | 0.004125
| 410 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for carrying out cleaning & housekeeping work at Project site in view of visit of Hon. Energy Minister at 1x660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500119601) | - | 1 | 2022-06-16 |  |  | 2022-05-13 | 0.0052835 | Firm | 0.0052835 | 0.0052835
| 411 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of safety helmets and industrial safety shoes in view of visit of Hon Energy minister at 1x660 MW Project Office by placing confirmatory order (PO NO - 4500119553) | - | 1 | 2022-06-06 |  |  | 2022-05-13 | 0.0035388 | Firm | 0.0035388 | 0.0035388
| 412 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of communication device during site visit of Hon. ED (Project)at 1x660 MW Project Office by placing confirmatory order (PO NO - 4500119649) | - | 1 | 2022-06-06 |  |  | 2021-09-27 | 0.001199 | Firm | 0.001199 | 0.001199
| 413 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Providing catering services to team of Internal Auditors at 1x660 MW Project Office by placing confirmatory order (PO NO - 4500118027) | - | 1 | 2022-03-16 | 2022-01-17 |  | 2022-02-12 | 0.0015672 | Firm | 0.0015672 | 0.0015672
| 414 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Providing catering services to team of Internal Auditors at 1x660 MW Project Office by placing confirmatory order (PO NO - 4500118095) | - | 1 | 2022-03-16 | 2022-01-18 |  | 2022-01-21 | 0.0024525 | Firm | 0.0024525 | 0.0024525
| 415 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Contract for providing and installing CCTV surveillance system at 1X660 MW Project site material entry gate through confirmatory (PO NO - 4500111196) | - | 1 | 2020-09-29 | 2020-08-06 | 2020-09-20 | 2020-08-10 | 0.002606 | Firm | 0.002606 | 0.002606
| 416 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Works of fabrication and installation of disinfectant chambers at 1 x 660 MW Bhusawal Project by placing confirmatory order (PO NO - 4500110202) | - | 1 | 2020-07-13 | 2020-04-11 | 2020-05-26 | 2020-04-13 | 0.005782 | Firm | 0.005782 | 0.005782
| 417 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Confirmatory order for transportation, loading & unloading of various electrical items from koradi to bhusawal project. (PO NO - 4500105689) | - | 1 | 2019-11-27 | 2019-04-29 | 2019-06-13 | 2019-05-01 | 0.002891 | Firm | 0.002891 | 0.002891
| 418 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Providing and fixing of various car accessories for the newly procured Dezire for CE (Project) (PO NO - 4500107991) | - | 1 |  | 2019-11-28 |  | 2019-11-28 | 0.0021931 | Firm | 0.0021931 | 0.0021931
| 419 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | CONFIRMATORY ORDER FOR CONSTRUCTION OF SAFETY GRILL FOR WATER COOLER AT BHUSAWAL PROJECT OFFICE. (PO NO - 4500107840) | - | 1 |  | 2019-11-25 | 2020-01-09 | 2019-11-27 | 0.0029323 | Firm | 0.0029323 | 0.0029323
| 420 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Confirmatory order for Repair and servicing of split Air Conditioners at various sections of 1x660MW Bhusawal Project Office. (PO NO - 4500107833) | - | 1 |  | 2019-11-25 | 2020-01-09 | 2019-11-30 | 0.0017172 | Firm | 0.0017172 | 0.0017172
| 421 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Confirmatory order for construction of portable platform for vehicles inspection at 1x660 MW project site main gate. (PO NO - 4500107832) | - | 1 |  | 2019-11-26 | 2020-01-10 | 2019-12-28 | 0.0028904 | Firm | 0.0028904 | 0.0028904
| 422 | 1x660 MW Bhusawal Project - Other misc Expenditure | Confirmatory order for modification of construction power supply cable trays structure, cable remoing & rerouting on the elavated cable trays at 400 KV switchyard. (PO NO - 4500106467) | - | 1 |  | 2019-07-23 |  | 2019-07-27 | 0.0024131 | Firm | 0.0024131 | 0.0024131
| 423 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Work contract for tree plantation at 1 x 600 MW project site through confirmatory order in emergent situation (PO NO - 4500100220) | - | 1 |  |  |  |  | 0.0028084 | Firm | 0.0028084 | 0.0028084
| 424 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | procurement of safety helmets (blue and white) in view of 660 MW Bhusawal Project Foundation Stone laying ceremony through confirmatory order after execution of work in emergent situation (PO NO - 4500096284) | - | 1 |  |  |  |  | 0.0041477 | Firm | 0.0041477 | 0.0041477
| 425 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicle AC (Swift Dzire) along with driver for 1 x 660 MW Bhusawal Project office for the period of 20.02.2018 to 17.03.2018. (PO NO - 4500092509) | - | 1 |  |  |  |  | 0.00225 | Firm | 0.00225 | 0.0023625
1 | 426 | CCC Bhusawal - ESTABLISHMENT | Providing 6 Nos skilled & 3 Nos unskilled assistance for computer cleaning work & book keeping dispatch work during vehicle division office as directed by engg. For civil const. division, deepnagar bhusawal (PO NO - 4500093464) | DCB | 3 | 02.04.2018 |  |  |  | 0.030417 | Firm | 0.030417
| 427 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC Taxi (i.e. Zest /Indigo/Swift desireequivalent) along with driver & diesel required for Dy. C.E. C.C.C. Deepnagar, Bhusawal (PO NO - 4500094493) | DCB | 3 | 27.04.2018 |  |  |  | 0.034869 | Firm | 0.034869
| 428 | CCC Bhusawal - ESTABLISHMENT | Providing Hot Weather eshtablishment for summer 2018 at civil const. circle, Deepnagar, Bhusawal (PO NO - 4500094491) | DCB | 3 | 27.04.2018 |  |  |  | 0.011233 | Firm | 0.011233
| 429 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled of unskilled assistance for division G.A.D., Account office housekeeping at new project office shed at BTPS Deepnagar, Bhusawal (PO NO - 4500094832) | DCB | 3 | 14.05.2018 |  |  |  | 0.03374 | Firm | 0.03374
| 430 | CCC Bhusawal - ESTABLISHMENT | maintainance of landscaping gardening in front of project office premises at BTPS Deepnagar, Bhusawal, Dist Jalgaon (PO NO - 4500094675) | - | 1 | 14.05.2018 |  |  |  | 0.0020636 | Firm | 0.0020636
| 431 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled of unskilled assistance for division G.A.D., Account office housekeeping at new project office shed at BTPS Deepnagar, Bhusawal (PO NO - 4500096024) | DCB | 3 | 26.06.2018 |  |  |  | 0.03374 | Firm | 0.03374
| 432 | CCC Bhusawal - CONSULTANCY | Preparation of MVAT/GST register in r/o Bhusawal civil const. circle division deepnagar, bhusawal (PO NO - 4500096025) | - | 1 | 26.06.2018 |  |  |  | 0.008496 | Firm | 0.008496
| 433 | CCC Bhusawal - ESTABLISHMENT | Providing assistance of maintainance water supply in project premises at Deepnagar, Bhusawal (PO NO - 4500096643) | DCB | 3 | 18.07.2018 |  |  |  | 0.032533 | Firm | 0.032533
| 434 | CCC Bhusawal - TENDER CANCELLED | Providing services of skilled of unskilled assistance for division G.A.D., Account office housekeeping at new project office shed at BTPS Deepnagar, Bhusawal (PO NO - 4500097921) | - | 1 | 13.08.2018 |  |  |  | 0 | Firm | 0
| 435 | CCC Bhusawal - OTHER MISC | Maintenance of miscellanious work for project staff quarters and project office at BTPS Deepnagar Bhusawal (PO NO - 4500098490) | DCB | 3 | 15.09.2018 |  |  |  | 0.035016 | Firm | 0.035016
| 436 | CCC Bhusawal - OTHER MISC | Providing services of unskilled assistance for maintainance of project chemmury BTPS colony under civil const. circle Deepnagar, Bhusawal (PO NO - 4500098486) | DCB | 3 | 17.09.2018 |  |  |  | 0.033773 | Firm | 0.033773
| 437 | CCC Bhusawal - OTHER MISC | Work of providing installation & commissioningh of verticle submerciable pump of boarwell and misc. maintainance work at civil const. cicle at BTPS Deepnagar, Bhusawal (PO NO - 4500099614) | DCB | 3 | 25.09.2018 |  |  |  | 0.023547 | Firm | 0.023547
| 438 | CCC Bhusawal - OTHER MISC | Work of water proffing for attending leakage from AC corrugated roofing sheet of project office shed at Deepnagar, Bhusawal (PO NO - 4500098485) | DCB | 3 | 25.09.2018 |  |  |  | 0.0058319 | Firm | 0.0058319
| 439 | CCC Bhusawal - ESTABLISHMENT | Renovation and reparing work of general ladies toilets & other misc work of project Dy. C.E. office at project office complex Deepnagar Bhusawal (PO NO - 4500098487) | DCB | 3 | 25.09.2018 |  |  |  | 0.022317 | Firm | 0.022317
| 440 | CCC Bhusawal - ESTABLISHMENT | Preparation of ground in view 72nd Independence Day on 15 Aug 2018 for flag hosting ceremony at project complex at Deepanagr Bhusawal (PO NO - 4500098890) | - | 1 | 26.09.2018 |  |  |  | 0.0022694 | Firm | 0.0022694
| 441 | CCC Bhusawal - ESTABLISHMENT | Hiring of vehicle for for the work mortgage deed at Bodwad in between REC PEF & MSPGCL (PO NO - 4500098891) | - | 1 | 26.09.2018 |  |  |  | 0.0018246 | Firm | 0.0018246
| 442 | CCC Bhusawal - ESTABLISHMENT | Preparing of sewage water pipeline & chamber of backside project office complex Deepnagar, Bhusawal (PO NO - 4500098489) | DCB | 3 | 29.09.2018 |  |  |  | 0.035326 | Firm | 0.035326
| 443 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled of unskilled assistance for division G.A.D., Account office housekeeping at new project office shed at BTPS Deepnagar, Bhusawal (PO NO - 4500099152) | DCB | 3 | 12.10.2018 |  |  |  | 0.035379 | Firm | 0.035379
| 444 | CCC Bhusawal - OTHER MISC | Providing drinking water source to BHEL at BTPS Deepnagar, Bhusawal (PO NO - 4500099156) | DCB | 3 | 12.10.2018 |  |  |  | 0.035215 | Firm | 0.035215
| 445 | CCC Bhusawal - OTHER MISC | Providing & fixing water meter air valve, sluice valve etc at pump house outlet canal BTPS Deepnagar Bhusawal (PO NO - 4500099148) | DCB | 3 | 12.10.2018 |  |  |  | 0.035308 | Firm | 0.035308
| 446 | CCC Bhusawal - OTHER MISC | Extension of the providing construction water supply to BHEL at BTPS Deepnagar Bhusawal (PO NO - 4500099155) | DCB | 3 | 12.10.2018 |  |  |  | 0.035322 | Firm | 0.035322
| 447 | CCC Bhusawal - OTHER MISC | Replacement of damaged fall celling at Dy. C.E. (P), Dy. C.E. (C), S.E. (C) Cabins Deepnagar, Bhusawal (PO NO - 4500099726) | DCB | 3 | 01.11.2018 |  |  |  | 0.023281 | Firm | 0.023281
| 448 | CCC Bhusawal - OTHER MISC | Workof widening of existing 1x660MW to 2x500MW connecting M/sgatefor M/S. BHEL for 1x660MW replacement unit at BTPS Deepnagar Bhusawal (PO NO - 4500099720) | DCB | 3 | 01.11.2018 |  |  |  | 0.011133 | Firm | 0.011133
| 449 | CCC Bhusawal - OTHER MISC | Work of construction of damaged security compound wall along with boundary of 1x660MW repln. Unit at BTPS Deepnagar Bhusawal (PO NO - 4500099729) | DCB | 3 | 01.11.2018 |  |  |  | 0.021996 | Firm | 0.021996
| 450 | CCC Bhusawal - ESTABLISHMENT | Work of painting of C.E. (P), Dy. C.E. (P), S.E. (P) & other cabins & renovation of toilets at BTPS Deepnagar Bhusawal (PO NO - 4500099728) | DCB | 3 | 01.11.2018 |  |  |  | 0.022474 | Firm | 0.022474
| 451 | CCC Bhusawal - OTHER MISC | Providing & Maintainance of alluminium partion work of making cabins in project office in various section at BTPS Deepnagar (PO NO - 4500099727) | DCB | 3 | 01.11.2018 |  |  |  | 0.022571 | Firm | 0.022571
| 452 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC Taxi (i.e. Zest /Indigo/Swift desireequivalent) along with driver & diesel required for Dy. C.E. C.C.C. Deepnagar, Bhusawal (PO NO - 4500099721) | DCB | 3 | 01.11.2018 |  |  |  | 0.034692 | Firm | 0.034692
| 453 | CCC Bhusawal - ESTABLISHMENT | Providing & fixing blinds curtains & carpet for Dy. C.E. cabin at other cabin civil construction circle Deepnagar Bhusawal (PO NO - 4500099997) | DCB | 3 | 13.11.2018 |  |  |  | 0.023286 | Firm | 0.023286
| 454 | CCC Bhusawal - OTHER MISC | Construction of chain-link fencing near railway siding of 2x500MW along boundary of 1x660MW replacement unit BTPS Deepnagar Bhusawal (PO NO - 4500100463) | DCB | 3 | 07.12.2018 |  |  |  | 0.12067 | Firm | 0.12067
| 455 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled of unskilled assistance for division G.A.D., Account office housekeeping at new project office shed at BTPS Deepnagar, Bhusawal (PO NO - 4500100549) | DCB | 3 | 07.12.2018 |  |  |  | 0.035379 | Firm | 0.035379
| 456 | CCC Bhusawal - OTHER MISC | Providing raw water source to project office complex at BTPS Deepnagar Bhusawal (PO NO - 4500100665) | DCB | 3 | 13.12.2018 |  |  |  | 0.035106 | Firm | 0.035106
| 457 | CCC Bhusawal - OTHER MISC | Work of cleaning of constructed darin & misc repairing work in premises of project office complex at BTPS Deepnagar (PO NO - 4500100678) | DCB | 3 | 13.12.2018 |  |  |  | 0.023513 | Firm | 0.023513
| 458 | CCC Bhusawal - OTHER MISC | Work of providing & errecting GI Chain-link fencing of 1.60 m. hight at back side of civil wing in project office complex at BTPS Deepnagar, Bhusawal (PO NO - 4500100677) | DCB | 3 | 13.12.2018 |  |  |  | 0.023287 | Firm | 0.023287
| 459 | CCC Bhusawal - OTHER MISC | Work of rerouting of drinking water supply pipe line to kapil vasti nagar Bhusawal (PO NO - 4500100666) | DCB | 3 | 13.12.2018 |  |  |  | 0.035205 | Firm | 0.035205
| 460 | CCC Bhusawal - ESTABLISHMENT | Hiring of diesel taxi car/jeep/ (Tata sumo/ Indica/bolero)along with driver & diesel required of Exect. Engg. At BTPS Deepnagar Bhusawal (PO NO - 4500100670) | DCB | 3 | 13.12.2018 |  |  |  | 0.032075 | Firm | 0.032075
| 461 | CCC Bhusawal - OTHER MISC | Providing pump operator for operating pump of pump house at outlet canal at 1x660MW at BTPS Deepnagar Bhusawal (PO NO - 4500100664) | DCB | 3 | 13.12.2018 |  |  |  | 0.035365 | Firm | 0.035365
| 462 | CCC Bhusawal - OTHER MISC | Work of cleaning and upkeeping of old (2x500MW) office record at BTPS Deepnagar Bhusawal (PO NO - 4500100944) | DCB | 3 | 26.12.2018 |  |  |  | 0.016948 | Firm | 0.016948
| 463 | CCC Bhusawal - OTHER MISC | Work of Plinth protection for E&M project office at Deepnagar, Bhusawal (PO NO - 4500100945) | DCB | 3 | 26.12.2018 |  |  |  | 0.011889 | Firm | 0.011889
| 464 | CCC Bhusawal - OTHER MISC | Repairing of general gents ladies toilets of civil construction circle at deepnagar bhusawal (PO NO - 4500100947) | DCB | 3 | 26.12.2018 |  |  |  | 0.021674 | Firm | 0.021674
| 465 | CCC Bhusawal - ESTABLISHMENT | Repairing & renovation of office of Executive Engineer (C) division I&II under civil construction circle Deepnagar Bhusawal (PO NO - 4500100946) | DCB | 3 | 26.12.2018 |  |  |  | 0.02236 | Firm | 0.02236
| 466 | CCC Bhusawal - OTHER MISC | Removing grass & cleaning the road side of old pimprisekam road in the premises of 1x660 MW project at BTPS Deepnagar, Bhusawal (PO NO - 4500100955) | DCB | 3 | 26.12.2018 |  |  |  | 0.022656 | Firm | 0.022656
| 467 | CCC Bhusawal - OTHER MISC | Work for construction of watchmen cabin for project office complex entrance gate at BTPS Deepnagar Bhusawal (PO NO - 4500100951) | DCB | 3 | 09.01.2019 |  |  |  | 0.028724 | Firm | 0.028724
| 468 | CCC Bhusawal - OTHER MISC | Work of construction of new entrance gate & watchmen cabin along with UCR compound wallfor 1x660MW (BHEL) at BTPS Deepnagar Bhusawal (PO NO - 4500102145) | DCB | 3 | 07.02.2019 |  |  |  | 0.14912 | Firm | 0.14912
| 469 | CCC Bhusawal - OTHER MISC | Providing of interlocking paving block to the side of approach road to 1x660 MW project office at Deepnagar Bhusawal (PO NO - 4500101818) | DCB | 3 | 07.02.2019 |  |  |  | 0.033299 | Firm | 0.033299
| 470 | CCC Bhusawal - OTHER MISC | Work of renovation and repairing of Executive Engineer toilet cabin of project office at BTPS Deepnagar Bhusawal (PO NO - 4500101822) | DCB | 3 | 05.03.2019 |  |  |  | 0.035086 | Firm | 0.035086
| 471 | CCC Bhusawal - OTHER MISC | Reparing of toilet and other miscllanious work at 33K.V. Submission Deepnagar at BTPS Deepnagar Bhusawal (PO NO - 4500102517) | DCB | 3 | 07.03.2019 |  |  |  | 0.023059 | Firm | 0.023059
| 472 | CCC Bhusawal - OTHER MISC | Removing grass & cleaning the road side of old pimprisekam road in the premises of 1x660 MW project at BTPS Deepnagar, Bhusawal (PO NO - 4500101821) | DCB | 3 | 07.03.2019 |  |  |  | 0.0217 | Firm | 0.0217
| 473 | CCC Bhusawal - ESTABLISHMENT | Contract for the work of Xeroxing at C.C.C. MSPGCL Bhusawal (PO NO - 4500103429) | DCB | 3 | 26.03.2019 |  |  |  | 0.00531 | Firm | 0.00531
| 474 | CCC Bhusawal - OTHER MISC | Work of water proffing to terrace for Transit Quarter No. Bm-24 at Deepnagar, Bhusawal (PO NO - 4500103425) | DCB | 3 | 26.03.2019 |  |  |  | 0.023437 | Firm | 0.023437
| 475 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled & driver, unskilled assistance for office under civil construction circle Deepnagar, Bhusawal (PO NO - 4500103254) | DCB | 3 | 26.03.2019 |  |  |  | 0.15352 | Firm | 0.15352
| 476 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled & unskilled assistance for office under civil construction circle Deepnagar, Bhusawal (PO NO - 4500103257) | DCB | 3 | 26.03.2019 |  |  |  | 0.15352 | Firm | 0.15352
| 477 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for operating computers under office of Dy. C.E. (C), in C.C.C. Deepnagar, Bhusawal (PO NO - 4500102566) | DCB | 3 | 26.03.2019 |  |  |  | 0.087531 | Firm | 0.087531
| 478 | CCC Bhusawal - ESTABLISHMENT | Repairing of area in view Republice Day on 26 jan 2019 for flag hosting ceremony at project complex deepnagar bhusawal (PO NO - 4500103418) | - | 1 | 26.03.2019 |  |  |  | 0.001806 | Firm | 0.001806
| 479 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled & unskilled assistance for office misc work under office of the Dy. Chief Engineer (C) in civil construction circle Deepnagar, Bhusawal (PO NO - 4500103406) | - | 1 | 26.03.2019 |  |  |  | 0.0028216 | Firm | 0.0028216
| 480 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for driving the departmental vehicle (as driver)office misc work under office of the Dy. Chief Engineer (C) in civil construction circle Deepnagar, Bhusawal (PO NO - 4500103405) | - | 1 | 26.03.2019 |  |  |  | 0.0011932 | Firm | 0.0011932
| 481 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for computer operator under office of the Dy. Chief Engineer (C) in civil construction circle Deepnagar, Bhusawal (PO NO - 4500103430) | - | 1 | 26.03.2019 |  |  |  | 0.003432 | Firm | 0.003432
| 482 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled & unskilled assistance for office misc work under office of the Dy. Chief Engineer (C) in civil construction circle Deepnagar, Bhusawal (PO NO - 4500103431) | - | 1 | 26.03.2019 |  |  |  | 0.0028216 | Firm | 0.0028216
| 483 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for driving the departmental vehicle (as driver)office misc work under office of the Dy. Chief Engineer (C) in civil construction circle Deepnagar, Bhusawal (PO NO - 4500103407) | - | 1 | 26.03.2019 |  |  |  | 0.001939 | Firm | 0.001939
| 484 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for computer operator under office of the Dy. Chief Engineer (C) in civil construction circle Deepnagar, Bhusawal (PO NO - 4500103402) | - | 1 | 26.03.2019 |  |  |  | 0.0017898 | Firm | 0.0017898
| 485 | CCC Bhusawal - ESTABLISHMENT | Work contract maintainance of garden in front of project office complex premises at Deepnagar bhusawal (PO NO - 4500103432) | - | 1 | 26.03.2019 |  |  |  | 0.0032826 | Firm | 0.0032826
| 486 | CCC Bhusawal - OTHER MISC | Providing assistance of maintainance water supply in project premises at Deepnagar, Bhusawal (PO NO - 4500103256) | - | 1 | 26.03.2019 |  |  |  | 0.032693 | Firm | 0.032693
| 487 | CCC Bhusawal - OTHER MISC | Work of Construction approach parking for main entry gate of 1x660 MW from NH-6, Deepnagar, Bhusawal. (PO NO - 4500105520) | DCB | 3 | 12.04.2019 |  |  |  | 0.37622 | Firm | 0.37622
| 488 | CCC Bhusawal - ESTABLISHMENT | Work of Providing, Fixing decorative tiles for entrance of office of Project complex at BTPS, Deepnagar, Bhusawal. (PO NO - 4500103427) | DCB | 3 | 12.04.2019 |  |  |  | 0.026539 | Firm | 0.026539
| 489 | CCC Bhusawal - OTHER MISC | Work of Repairing works of Projects staff quarters PA ½ & PA 2/2 at BTPS, Deepnagar, Bhusawal. (PO NO - 4500104942) | DCB | 3 | 03.05.2019 |  |  |  | 0.035224 | Firm | 0.035224
| 490 | CCC Bhusawal - ESTABLISHMENT | Work of Repairing and renovation of cabins for Dy. CIRO and security staff at BTPS, Deepnagar, Bhusawal. (PO NO - 4500104937) | DCB | 3 | 03.05.2019 |  |  |  | 0.032701 | Firm | 0.032701
| 491 | CCC Bhusawal - OTHER MISC | Work of waterproofing to terrace of transit quarter No BM -23 at BTPS, Deepnagar, Bhusawal. (PO NO - 4500104935) | DCB | 3 | 03.05.2019 |  |  |  | 0.023437 | Firm | 0.023437
| 492 | CCC Bhusawal - ESTABLISHMENT | Work of Repairing and renovation of toilet blocks in the cabins of Dy. CIRO and security staff at Project office BTPS, Deepnagar, Bhusawal. (PO NO - 4500104933) | DCB | 3 | 03.05.2019 |  |  |  | 0.013764 | Firm | 0.013764
| 493 | CCC Bhusawal - ESTABLISHMENT | Work of repairs and maintenance of aluminium doors, windows & replacement of broken glasses as and when required at various places in project office complex at BTPS, Deepnagar, Bhusawal. (PO NO - 4500103420) | DCB | 3 | 16.05.2019 |  |  |  | 0.035006 | Firm | 0.035006
| 494 | CCC Bhusawal - OTHER MISC | Work of internal painting to transit quarter No BM-23 at BTPS, Deepnagar, Bhusawal. (PO NO - 4500105207) | DCB | 3 | 16.05.2019 |  |  |  | 0.022362 | Firm | 0.022362
| 495 | CCC Bhusawal - OTHER MISC | Work of Repairing & Renovation of Super - D Type Quarters at BTPS Colony Deepnagar Bhusawal. (PO NO - 4500105542) | DCB | 3 | 07.06.2019 |  |  |  | 0.66456 | Firm | 0.66456
| 496 | CCC Bhusawal - ESTABLISHMENT | Work of Aluminum portion work for making cabins in project office complex at BTPS Deepnagar, Bhusawal. (PO NO - 4500105543) | DCB | 3 | 07.06.2019 |  |  |  | 0.046348 | Firm | 0.046348
| 497 | CCC Bhusawal - ESTABLISHMENT | Work of replacement of A.C. corrugated roofing sheets by profile roofing sheets of project office at Deepnagar Bhusawal. (PO NO - 4500105533) | DCB | 3 | 07.06.2019 |  |  |  | 0.36942 | Firm | 0.36942
| 498 | CCC Bhusawal - OTHER MISC | Work of painting of BM type Qtrs. 17, 18, 21, 22 & 34 under Civil Construction Circle, Deepnagar, Bhusawal. (PO NO - 4500106085) | DCB | 3 | 24.07.2019 |  |  |  | 0.023074 | Firm | 0.023074
| 499 | CCC Bhusawal - ESTABLISHMENT | Work of Hiring of private A/C taxi (i.e. ZEST/ Indigo CS/swift desire or equivalent) along with driver and diesel required for Dy. C.E. (C), CCC, Bhusawal. (PO NO - 4500106086) | DCB | 3 | 24.07.2019 |  |  |  | 0.034692 | Firm | 0.034692
| 500 | CCC Bhusawal - ESTABLISHMENT | Work of Providing 10 Mbps (1:1) Internet Leased Line Connectivity at Civil Construction Circle, 1x660 MW Deepngar, Bhusawal. (PO NO - 4500106257) | DCB | 3 | 03.08.2019 |  |  |  | 0.023591 | Firm | 0.023591
| 501 | CCC Bhusawal - ESTABLISHMENT | Work of Supply of one device Sophos XG 135 at BTPS Deepnagar, Bhusawal. (PO NO - 4500106081) | DCB | 3 | 03.08.2019 |  |  |  | 0.034023 | Firm | 0.034023
| 502 | CCC Bhusawal - ESTABLISHMENT | Work for construction of toilet at Div-V, CCC, Deepnagar, Bhusawal. (PO NO - 4500106449) | DCB | 3 | 19.08.2019 |  |  |  | 0.016086 | Firm | 0.016086
| 503 | CCC Bhusawal - ESTABLISHMENT | Work of Providing services of unskilled assistance for Sweeping work for Project Civil Division Offices at New Project Office Shed. BTPS Deepnagar, Bhusawal. (PO NO - 4500106393) | DCB | 3 | 19.08.2019 |  |  |  | 0.022831 | Firm | 0.022831
| 504 | CCC Bhusawal - ESTABLISHMENT | Work of Providing expertise service for carrying out the modification and renovation, interior decoration & electrification work of VIP (TAPI) Guest House at BTPS (PO NO - 4500106227) | DCB | 5 | 20.08.2019 |  |  |  | 0.02301 | Firm | 0.02301
| 505 | CCC Bhusawal - ESTABLISHMENT | Work of Providing unskilled assistance for maintenance & cleaning work of Chummery for Project staff at BTPS, Deepnagar, Bhusawal. (PO NO - 4500106333) | DCB | 4 | 20.08.2019 |  |  |  | 0.021507 | Firm | 0.021507
| 506 | CCC Bhusawal - OTHER MISC | Work of Providing services of Skilled & Unskilled labour at Transit House No. BM-23 & 24 at BTPS, Deepnagar, Bhusawal (PO NO - 4500106332) | DCB | 5 | 20.08.2019 |  |  |  | 0.022519 | Firm | 0.022519
| 507 | CCC Bhusawal - ESTABLISHMENT | Work of Work of wall paneling to cabin of the Chief Engineer (Project) at Project office complex BTPS Deepnagar, Bhusawal. (PO NO - 4500106330) | DCB | 5 | 31.08.2019 |  |  |  | 0.028733 | Firm | 0.028733
| 508 | CCC Bhusawal - ESTABLISHMENT | Work of Repairing and maintenance for split air conditioners 1x660 MW Unit at BTPS, Deepnagar, Bhusawal. (PO NO - 4500106249) | - | 1 | 03.09.2019 |  |  |  | 0.0028766 | Firm | 0.0028766
| 509 | CCC Bhusawal - OTHER MISC | Work of barricading at opening below railway bridge No. 18 in the premises of 1x660 MW Project Deepnagar, Bhusawal. (PO NO - 4500106565) | DCB | 4 | 03.09.2019 |  |  |  | 0.019337 | Firm | 0.019337
| 510 | CCC Bhusawal - ESTABLISHMENT | Work of Replacement of Damaged A.C. corrugated sheets at parking shed, at BTPS, Deepnagar, Bhusawal. (PO NO - 4500106696) | DCB | 3 | 03.09.2019 |  |  |  | 0.023122 | Firm | 0.023122
| 511 | CCC Bhusawal - ESTABLISHMENT | Work of Hiring of Diesel taxi car/ jeep (TATA Indica/ Boleor/ Sumo) alongwith Driver and Diesel required for Executive Engineer (C), CCD-I, MSPGCL, Bhusawal. (PO NO - 4500106331) | DCB | 3 | 03.09.2019 |  |  |  | 0.032075 | Firm | 0.032075
| 512 | CCC Bhusawal - ESTABLISHMENT | Work of Hiring of private diesel taxi / car (Jeep/TATA indigo/Bolero/TATA Sumo) along with driver & required diesel for EE(C), CCDn, Deepnagar, Bhusawal. (PO NO - 4500106476) | DCB | 3 | 03.09.2019 |  |  |  | 0.030869 | Firm | 0.030869
| 513 | CCC Bhusawal - ESTABLISHMENT | Work of Procurement of networing materials required for Establishment of LAN at CCC, at Deepnagar, Bhusawal. (PO NO - 4500106765) | DCB | 4 | 09.09.2019 |  |  |  | 0.02218 | Firm | 0.02218
| 514 | CCC Bhusawal - ESTABLISHMENT | Work of Repairing of scrap store shed in project office complex at BTPS, Deepnagar, Bhusawal. (PO NO - 4500106860) | DCB | 4 | 17.09.2019 |  |  |  | 0.023034 | Firm | 0.023034
| 515 | CCC Bhusawal - ESTABLISHMENT | Work of repairing of Chief Engineer (Project) Cabin & Toilet at 1x660 MW Project office, Deepnagar, Bhusawal. (PO NO - 4500106868) | DCB | 5 | 18.09.2019 |  |  |  | 0.021 | Firm | 0.021
| 516 | CCC Bhusawal - ESTABLISHMENT | Work of renovation of toilets for transit house No. BM-24 at BTPS Deepnagar, Bhusawal. (PO NO - 4500106867) | DCB | 3 | 18.09.2019 |  |  |  | 0.022018 | Firm | 0.022018
| 517 | CCC Bhusawal - ESTABLISHMENT | Work of renovation of Kitechen otta, washbasin area & toilets of Qrt no. BM-19 at BTPS, Deepnagar, Bhusawal. (PO NO - 4500106863) | DCB | 4 | 18.09.2019 |  |  |  | 0.027194 | Firm | 0.027194
| 518 | CCC Bhusawal - ESTABLISHMENT | Work of repairing of internal doors & windows of Transit quarters at BTPS Deepnagar, Bhusawal. (PO NO - 4500106866) | DCB | 3 | 18.09.2019 |  |  |  | 0.021248 | Firm | 0.021248
| 519 | CCC Bhusawal - ESTABLISHMENT | Work of interconnection & establishment of LAN network at CCC, 1x660 MW Deepnagar, Bhusawal. (PO NO - 4500106862) | DCB | 3 | 21.09.2019 |  |  |  | 0.022538 | Firm | 0.022538
| 520 | CCC Bhusawal - ESTABLISHMENT | Work of repairing & renovation of Security office at Project office, BTPS, Deepnagar, Bhusawal. (PO NO - 4500106870) | DCB | 3 | 24.09.2019 |  |  |  | 0.019397 | Firm | 0.019397
| 521 | CCC Bhusawal - OTHER MISC | Work of Providing & supplying of kitchen ware items / furniture at Project guest house (PD) at Deepnagar, Bhusawal. (PO NO - 4500107005) | DCB | 4 | 27.09.2019 |  |  |  | 0.023178 | Firm | 0.023178
| 522 | CCC Bhusawal - ESTABLISHMENT | Work of development of garden near 1x660 MW Project office complex gate at BTPS, Deepnagar, Bhusawa (PO NO - 4500107004) | DCB | 3 | 27.09.2019 |  |  |  | 0.023554 | Firm | 0.023554
| 523 | CCC Bhusawal - OTHER MISC | Work of Repairing & maintenance work of project staff guest house PD (2 No's) at BTPS, Deepnagar,Bhusawal. (PO NO - 4500107006) | DCB | 3 | 27.09.2019 |  |  |  | 0.023257 | Firm | 0.023257
| 524 | CCC Bhusawal - ESTABLISHMENT | Work of Hiring of private desile taxi car/ jeep (i.e. TATA Indica, Bolero, TATA Sumo ) along with driver and diesel requried for E.E. (C)-I, CCD, Bhusawal (PO NO - 4500107154) | - | 1 | 09.10.2019 |  |  |  | 0.0030666 | Firm | 0.0030666
| 525 | CCC Bhusawal - ESTABLISHMENT | Work of Providing hot weather establishment of for summer 2019 at Civil Construction Circle, Deepnagar, Bhusawal. (PO NO - 4500107155) | - | 1 | 09.10.2019 |  |  |  | 0.0028196 | Firm | 0.0028196
| 526 | CCC Bhusawal - ESTABLISHMENT | Work of Providing fixing & commissioning desert coolers for the office of Dy. C.E. (C), CCC, BSL & other CCDn (PO NO - 4500107156) | - | 1 | 09.10.2019 |  |  |  | 0.0028196 | Firm | 0.0028196
| 527 | CCC Bhusawal - ESTABLISHMENT | Work of Providing internal painting to CCD-III & Replacement of broken tiles of CCD-II & III at Project old office complex. (PO NO - 4500107208) | DCB | 4 | 15.10.2019 |  |  |  | 0.023403 | Firm | 0.023403
| 528 | CCC Bhusawal - OTHER MISC | Work of providing pump operator for operating pumps at pump house at outlet canal at 1x660 MW deepnagar, Bhusawal. (PO NO - 4500107085) | DCB | 3 | 15.10.2019 |  |  |  | 0.023576 | Firm | 0.023576
| 529 | CCC Bhusawal - ESTABLISHMENT | Work of extension of parking shed in front of Project office at BTPS Deepnagar, Bhusawal. (PO NO - 4500107077) | DCB | 4 | 15.10.2019 |  |  |  | 0.021601 | Firm | 0.021601
| 530 | CCC Bhusawal - ESTABLISHMENT | Work of Construction of new toilet block to Sr. Manger Cabin at 1x660 MW Project . (PO NO - 4500107084) | DCB | 3 | 15.10.2019 |  |  |  | 0.021557 | Firm | 0.021557
| 531 | CCC Bhusawal - CONSULTANCY | Work of Providing expertise service for structural audit by Non Destructive Testing of old / abandoned pump house at BTPS, Deepnagar, Bhusawal (PO NO - 4500107242) | DCB | 5 | 16.10.2019 |  |  |  | 0.022951 | Firm | 0.022951
| 532 | CCC Bhusawal - ESTABLISHMENT | Work of Plantation of saplings in 1x660 MW premises, at Deepnagar, Bhusawal (PO NO - 4500107241) | DCB | 3 | 16.10.2019 |  |  |  | 0.023357 | Firm | 0.023357
| 533 | CCC Bhusawal - OTHER MISC | Work of barricading at openings below railway bridge no 17 in the premises of 1x660 MW Project Deepnagar, Bhusawal. (PO NO - 4500107240) | DCB | 4 | 16.10.2019 |  |  |  | 0.017822 | Firm | 0.017822
| 534 | CCC Bhusawal - ESTABLISHMENT | Work of Providing Services of unskilled assistance & Skilled assistance (drivers) for departmental vehicle for office of the Civil Construction Circle, Deepnagar Bhusawal. (PO NO - 4500107272) | DCB | 3 | 22.10.2019 |  |  |  | 0.14543 | Firm | 0.14543
| 535 | CCC Bhusawal - ESTABLISHMENT | Work of Providing Services of unskilled assistance & Skilled assistance (drivers) for departmental vehicle for office of the Civil Construction Circle, Deepnagar Bhusawal. (PO NO - 4500107271) | DCB | 3 | 22.10.2019 |  |  |  | 0.14543 | Firm | 0.14543
| 536 | CCC Bhusawal - ESTABLISHMENT | Work of Providing Services of skilled assistance for computer operation & Dispatch work under office of the Dy. Chief Engineer (C) in Civil Construction Circle, Deepnagar, Bhusawal al. (PO NO - 4500107274) | DCB | 2 | 22.10.2019 |  |  |  | 0.28803 | Firm | 0.28803
| 537 | CCC Bhusawal - ESTABLISHMENT | Work of Providing fixing curtains to project civil office at Deepnagar, Bhusawal. (PO NO - 4500107463) | DCB | 5 | 05.11.2019 |  |  |  | 0.021886 | Firm | 0.021886
| 538 | CCC Bhusawal - ESTABLISHMENT | Work of Providing services of technical Assistance (Civil supervisor) for site supervision at Boiler & T.G. Of 1x660 Project Deepnagar , Bhusawa (PO NO - 4500107465) | DCB | 3 | 05.11.2019 |  |  |  | 0.022875 | Firm | 0.022875
| 539 | CCC Bhusawal - ESTABLISHMENT | Work of Providing Services of Skilled assistance for preparation of data for SAP & SRM system in the office of the Civil Construction Circle, Deepnagar Bhusawal (PO NO - 4500107462) | DCB | 3 | 05.11.2019 |  |  |  | 0.014653 | Firm | 0.014653
| 540 | CCC Bhusawal - ESTABLISHMENT | Work of painting of quarters internally under Civil Construction Circle at BTPS, Deepnagar, (PO NO - 4500107464) | DCB | 3 | 05.11.2019 |  |  |  | 0.023152 | Firm | 0.023152
| 541 | CCC Bhusawal - ESTABLISHMENT | Work of upply and installation of total value licence subscription for sophos XG 135 (3 Years) at BTPS (PO NO - 4500107659) | DCB | 4 | 19.11.2019 |  |  |  | 0.035223 | Firm | 0.035223
| 542 | CCC Bhusawal - ESTABLISHMENT | Work of Supply of Stationary in Civil Construction Circle and allied divisions MSPGCL, Bhusawal . (PO NO - 4500107700) | DCB | 4 | 22.11.2019 |  |  |  | 0.023312 | Firm | 0.023312
| 543 | CCC Bhusawal - ESTABLISHMENT | Work of Hiring of private diesel taxi / car (TUV300/Scorpio/Bolero/) along with driver & required diesel for EE(C), CCD-II, Deepnagar, Bhusawal. (PO NO - 4500107668) | DCB | 4 | 22.11.2019 |  |  |  | 0.022276 | Firm | 0.022276
| 544 | CCC Bhusawal - ESTABLISHMENT | Work of Supply of Executive office arm chair at CCC 1X660 MW Repl. Unit, at BTPS, Deepnagar Bhusawal (PO NO - 4500107669) | DCB | 3 | 22.11.2019 |  |  |  | 0.020443 | Firm | 0.020443
| 545 | CCC Bhusawal - ESTABLISHMENT | Work of Construction of ladies toilet at main entrance gate 1x660 MW Project office Deepnagar, Bhusawal. (PO NO - 4500107756) | DCB | 3 | 26.11.2019 |  |  |  | 0.021184 | Firm | 0.021184
| 546 | CCC Bhusawal - ESTABLISHMENT | Work of isolation of project office by providing fencing near canteen at BTPS Deepnagar, Bhusawal. (PO NO - 4500107666) | DCB | 4 | 26.11.2019 |  |  |  | 0.017662 | Firm | 0.017662
| 547 | CCC Bhusawal - OTHER MISC | Work of providing secondary entrance gate and approach WBM road to 660 MW Project premises at Deepnagar, Bhusawal. (PO NO - 4500107752) | DCB | 5 | 26.11.2019 |  |  |  | 0.017758 | Firm | 0.017758
| 548 | CCC Bhusawal - OTHER MISC | Work of Annual Maintenance of Project Staff Quarters. (PO NO - 4500107744) | DCB | 8 | 26.11.2019 |  |  |  | 0.11077 | Firm | 0.11077
| 549 | CCC Bhusawal - ROAD OUTSIDE BOUNDRY | Work of Pot Hole repairing of old Pimprisekam Road in the 1x660 MW Premises at BTPS, Deepnagar, Bhusawal. (PO NO - 4500107631) | DCB | 3 | 27.11.2019 |  |  |  | 0.23117 | Firm | 0.23117
| 550 | CCC Bhusawal - ESTABLISHMENT | Work of Repairing and Renovation of Four Building of New – E-Type Quarters for MSF Person (PO NO - 4500107434) | DCB | 4 | 30.11.2019 |  |  |  | 0.2474 | Firm | 0.2474
| 551 | CCC Bhusawal - OTHER MISC | Providing technical Assistance (Civil supervisor) for site supervision at CHP area 1x660 Project Deepnagar , Bhusawal (PO NO - 4500107865) | DCB | 4 | 04.12.2019 |  |  |  | 0.034313 | Firm | 0.034313
| 552 | CCC Bhusawal - ESTABLISHMENT | Supply of safety equipments at Civil Construction Circle, 1x660 MW Replacement Unit at BTPS Deepnagar Bhusawal. (PO NO - 4500107886) | DCB | 2 | 07.12.2019 |  |  |  | 0.021829 | Firm | 0.021829
| 553 | CCC Bhusawal - ESTABLISHMENT | Providing services of technical Assistance (Civil supervisor) for site supervision at ESP & Chimney Of 1x660 Project Deepnagar , Bhusawal (PO NO - 4500107892) | DCB | 4 | 07.12.2019 |  |  |  | 0.022875 | Firm | 0.022875
| 554 | CCC Bhusawal - BOUNDRY WALL | Balance work for construction of UCR masonry security compound wall with concertina coil fencing along boundry of 1x660MW project office at Deepnagar Bhusawal. (PO NO - 4500110902) | DCB | 3 | 26.12.2019 |  |  |  | 3.8365 | Firm | 3.8365
| 555 | CCC Bhusawal - CONSULTANCY | Engaging person for SAP / Accounting & SAP reconciliation work for Year 2019-2020 (PO NO - 4500108144) | - | 1 | 03.01.2020 |  |  |  | 0.0118 | Firm | 0.0118
| 556 | CCC Bhusawal - OTHER MISC | Work of rehabilitation / re-plantation of plants in proposed remote fly ash silo area of 2x500 MW premises at BTPS, Deepnagar, Bhusawal (PO NO - 4500108153) | DCB | 4 | 03.01.2020 |  |  |  | 0.023473 | Firm | 0.023473
| 557 | CCC Bhusawal - OTHER MISC | Construction of Chain-link fencing along railway siding of 2x500 MW from BR-17 to existing compound wall near BR-18 (PO NO - 4500107433) | DCB | 4 | 06.01.2020 |  |  |  | 0.23003 | Firm | 0.23003
| 558 | CCC Bhusawal - ESTABLISHMENT | Purchasing of New tyers & tubes for Departmental Vehicle (Mahindra Bolero) MH-19-AE-6942 of CCC at BTPS, Deepnagar, Bhusawal. (PO NO - 4500108208) | - | 1 | 07.01.2020 |  |  |  | 0.0025813 | Firm | 0.0025813
| 559 | CCC Bhusawal - ESTABLISHMENT | Work of construction of damaged security compound wall along boundary of 1x660 MW Replacement Unit at BTPS, Deepnagar. (As and When required) (PO NO - 4500108062) | DCB | 4 | 16.01.2020 |  |  |  | 0.023492 | Firm | 0.023492
| 560 | CCC Bhusawal - ESTABLISHMENT | Providing and Fixing of A.C. corrugated sheets to vehicle shed behind Project office at Deepnagar, Bhusawal. (PO NO - 4500108376) | DCB | 5 | 22.01.2020 |  |  |  | 0.022962 | Firm | 0.022962
| 561 | CCC Bhusawal - OTHER MISC | Work of providing & erecting GI chain link fencing of 1.60 m height to periphery of safety man statue at project office at Deepnagar Bhusawal. (PO NO - 4500108377) | DCB | 7 | 22.01.2020 |  |  |  | 0.022273 | Firm | 0.022273
| 562 | CCC Bhusawal - ESTABLISHMENT | Hiring of private diesel taxi / jeep (Tata indica/Bolero/Tata Sumo) along with driver and diesel required for Superintending Engineer , CCC, MSPGCL, Bhusawal.. (PO NO - 4500108478) | DCB | 5 | 30.01.2020 |  |  |  | 0.022941 | Firm | 0.022941
| 563 | CCC Bhusawal - ESTABLISHMENT | Hiring of private diesel taxi car/jeep (Tata indica/Bolero/Tata Sumo) along with driver and diesel required for Executive Engineer (C ),CCD-I,MSPGCL, Bhusawal. (PO NO - 4500108488) | DCB | 3 | 30.01.2020 |  |  |  | 0.022984 | Firm | 0.022984
| 564 | CCC Bhusawal - ESTABLISHMENT | Work of Decorative Granting of newly constructed gate and security cabin of 1x660 MW Project Deepnagar, Bhusawal. (PO NO - 4500108476) | DCB | 3 | 01.02.2020 |  |  |  | 0.023229 | Firm | 0.023229
| 565 | CCC Bhusawal - OTHER MISC | Work diversion of PVC agriculture water supply pipe line faling in CHP area from Bhogavati reiver (Gate no. 295) of shri. Pitamber patil land gate no. 277 in village pimprisekam, Bhusawal (PO NO - 4500108680) | DCB | 4 | 15.02.2020 |  |  |  | 0.035353 | Firm | 0.035353
| 566 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC Taxi (i.e Desire/ford/or equivalent) along with driver & diesel required for Dy. C.E. (C), Bhusawal (PO NO - 4500108702) | DCB | 3 | 18.02.2020 |  |  |  | 0.023576 | Firm | 0.023576
| 567 | CCC Bhusawal - ESTABLISHMENT | Work of annual Maintenance, servicing, cheking network administration & trouble shooting of network hardware system at 1x660 MW C.C.C., MSPGCL, Bhusawal (PO NO - 4500108696) | DCB | 2 | 18.02.2020 |  |  |  | 0.032067 | Firm | 0.032067
| 568 | CCC Bhusawal - OTHER MISC | Shifting of Railway sleepers stacked near proposed TP-Z of CHP area of 1x660MW replacement unit project site (PO NO - 4500108853) | DCB | 4 | 27.02.2020 |  |  |  | 0.02827 | Firm | 0.02827
| 569 | CCC Bhusawal - ESTABLISHMENT | Hiring of private diesel taxi car/jeep (Tata indica/Bolero/Tata Sumo) along with driver and diesel required for Executive Engineer (C ),CCD-III,MSPGCL, Bhusawal. (PO NO - 4500108919) | DCB | 4 | 28.02.2020 |  |  |  | 0.021216 | Firm | 0.021216
| 570 | CCC Bhusawal - ESTABLISHMENT | Work of maintainance of land scaping in front of project inside & outside premises at BTPS Deepnagar (PO NO - 4500109042) | DCB | 3 | 04.03.2020 |  |  |  | 0.022396 | Firm | 0.022396
| 571 | CCC Bhusawal - OTHER MISC | Providing unskilled assistance for maintainance fo cleaning work of chummery for project staff at BTPS Deepnagar, Bhusawal (PO NO - 4500109277) | DCB | 5 | 17.03.2020 |  |  |  | 0.022396 | Firm | 0.022396
| 572 | CCC Bhusawal - OTHER MISC | Work of concrete platform below watch flower (PO NO - 4500109311) | DCB | 4 | 18.03.2020 |  |  |  | 0.022208 | Firm | 0.022208
| 573 | CCC Bhusawal - ESTABLISHMENT | Interior wall painting & other painting work in the premises of project office (PO NO - 4500109309) | DCB | 4 | 18.03.2020 |  |  |  | 0.012847 | Firm | 0.012847
| 574 | CCC Bhusawal - ESTABLISHMENT | Work of annual servicing & maintainance of computers system & allied equipments etc. of civil circle & unit office Deepnagar, Bhusawal (PO NO - 4500109295) | DCB | 4 | 20.03.2020 |  |  |  | 0.022467 | Firm | 0.022467
| 575 | CCC Bhusawal - ESTABLISHMENT | Bhusawal 1x660 MW Replacement Project - Providing Services of Skilled assistance for preparation of data for SAP & SRM system in the office of the Civil Construction Circle, Deepnagar Bhusawal (PO NO - 4500110296) | DCB | 3 | 03.06.2020 |  |  |  | 0.0202 | Firm | 0.0202
| 576 | CCC Bhusawal - OTHER MISC | 1x660 MW Repacement Unit Bhusawal – Transportation of sleepers of rail tracks placed at proposed site of Wagon tippler of CHP area 1x660MW replacement unit project site (PO NO - 4500110465) | DCB | 3 | 19.06.2020 |  |  |  | 0.03084 | Firm | 0.03084
| 577 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Project - Contract for Providing pest control services in the CCC and Division offices as and when required at BTPS Deepangar (PO NO - 4500110722) | DCB | 3 | 15.07.2020 |  |  |  | 0.010747 | Firm | 0.010747
| 578 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Unit Bhusawal – Hiring of private A/C taxi (i.e. Dezire/ford or equivalent) along with driver and diesel requried for Dy. C.E.(C), C.C.C., Bhusawal (PO NO - 4500110748) | DCB | 3 | 15.07.2020 |  |  |  | 0.023576 | Firm | 0.023576
| 579 | CCC Bhusawal - ESTABLISHMENT | Bhusawal 1x660 MW Replacement Project - Work of plinth protection behind Civil and project office 1x660 MW at Depnagar, Bhusawal. (PO NO - 4500110835) | DCB | 4 | 29.07.2020 |  |  |  | 0.022786 | Firm | 0.022786
| 580 | CCC Bhusawal - ESTABLISHMENT | : 1x660 MW Replacement Unit Bhusawal – Hiring of private diesel taxi car/jeep (Tata indica/Bolero/Tata Sumo) along with driver and diesel required for Superintending Engineer (C),MSPGCL, Bhusawal. (PO NO - 4500110834) | DCB | 4 | 29.07.2020 |  |  |  | 0.022941 | Firm | 0.022941
| 581 | CCC Bhusawal - OTHER MISC | 1x660 MW Repl. Unit - Raising of peripheral UCR compound wall of Super D type building no. 13,14 & 15 at BTPS, Deepnagar, Bhusawal. (PO NO - 4500110839) | DCB | 5 | 29.07.2020 |  |  |  | 0.021839 | Firm | 0.021839
| 582 | CCC Bhusawal - OTHER MISC | 1x660 MW Repacement Unit Bhusawal – BTPS 1 x 660MW Replacement Unit - Work of Providing and fixing plywood with two side laminate to wardrobe, partitions, closets, worship place, kitchen trolley etc. and other allied works for quarter no. BM-19 at BTPS Colony, Deepnagar, Bhusawal. (PO NO - 4500110840) | DCB | 3 | 29.07.2020 |  |  |  | 0.017033 | Firm | 0.017033
| 583 | CCC Bhusawal - ESTABLISHMENT | BTPS 1x660 MW Repl. Unit - Providing of interlocking paving blocks to the front side project canteen at BTPS, Deepnagar, Bhusawal (PO NO - 4500108697) | DCB | 3 | 19.08.2020 |  |  |  | 0.022902 | Firm | 0.022902
| 584 | CCC Bhusawal - ESTABLISHMENT | BTPS 1 x 660MW Replacement Unit - Providing Semi-skilled assistance services for day to day sanitization in the Pandemic Covid-19 & providing related sanitization materials etc at Civil Construction circle New Project office shed, BTPS Deepnagar, Bhusawal (PO NO - 4500111004) | DCB | 4 | 19.08.2020 |  |  |  | 0.021995 | Firm | 0.021995
| 585 | CCC Bhusawal - OTHER MISC | BTPS 1x660 MW Replacement Unit – Miscellaneous civil works in various rooms, common toilet of Tapi rest house and work of kitchen sink pipeline with water tank to type-II building no. 4,5 & 6 at Deepnagar Bhusawal. (PO NO - 4500111011) | DCB | 3 | 19.08.2020 |  |  |  | 0.023166 | Firm | 0.023166
| 586 | CCC Bhusawal - ESTABLISHMENT | Bhusawal 1x660 MW Replacement Project - Work of dismantling existing UCR stage behind project office, removing grass and providing brick masonry to garden infront of project office building at Bhusawal (PO NO - 4500111014) | DCB | 4 | 19.08.2020 |  |  |  | 0.023326 | Firm | 0.023326
| 587 | CCC Bhusawal - OTHER MISC | BTPS 1 x 660MW Replacement Unit - Refurbishment of quarter no. BM-23 at BTPS Colony , Deepnagar, Bhusawal (PO NO - 4500111003) | DCB | 3 | 19.08.2020 |  |  |  | 0.030752 | Firm | 0.030752
| 588 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Unit Bhusawal – Work of area grading for parking area near 1x660MW replacement unit gate at Deepnagar,bhusawal (PO NO - 4500111012) | DCB | 3 | 19.08.2020 |  |  |  | 0.022771 | Firm | 0.022771
| 589 | CCC Bhusawal - ESTABLISHMENT | 1 x 660MW Replacement Unit – Providing assistance for maintaining water supply in project premises at BTPS Deepnagar Bhusawal (PO NO - 4500111015) | DCB | 3 | 20.08.2020 |  |  |  | 0.023225 | Firm | 0.023225
| 590 | CCC Bhusawal - OTHER MISC | Repairing & maintenance of raw water pump house,G.I pipeline supplying water to BHEL site near outlet canal in BTPS premises, Deepnagar. (PO NO - 4500111117) | DCB | 4 | 20.08.2020 |  |  |  | 0.019736 | Firm | 0.019736
| 591 | CCC Bhusawal - ESTABLISHMENT | Procurement of Desktop Computers 10 Nos,through GEMS Portal (PO NO - 4500111002) | DCB | 3 | 21.08.2020 |  |  |  | 0.07849 | Firm | 0.07849
| 592 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Unit – Maintenance of garden in front of Tapi Guest House at BTPS, Deepnagar, Bhusawal (PO NO - 4500111013) | DCB | 5 | 21.08.2020 |  |  |  | 0.0232 | Firm | 0.0232
| 593 | CCC Bhusawal - ESTABLISHMENT | BTPS 1 x 660MW Replacement Unit - Providing 10 Mbps (1:1) Internet Leased line connectivity at Civil Construction Circle, 1x660 MW Deepnagar, Bhusawal. (PO NO - 4500111298) | DCB | 3 | 04.09.2020 |  |  |  | 0.017693 | Firm | 0.017693
| 594 | CCC Bhusawal - OTHER MISC | BTPS 1 x 660MW Replacement Unit – Minor repairs to quarter no. BM-24 at BTPS Colony , Deepnagar, Bhusawal (PO NO - 4500111430) | DCB | 4 | 15.09.2020 |  |  |  | 0.019668 | Firm | 0.019668
| 595 | CCC Bhusawal - OTHER MISC | Bhusawal 1x660 MW Replacement Project -Work of repairing & renovation of Z. P. School (CBSE) building at BTPS Colony Deepnagar Bhusawal (PO NO - 4500111641) | DCB | 5 | 25.09.2020 |  |  |  | 0.33495 | Firm | 0.33495
| 596 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Unit Bhusawal – Hiring of private diesel taxi car/jeep (Mahindra TUV 300/Tata indica/Bolero/Tata Sumo) along with driver and diesel required for Executive Engineer (C ),CCD-I,MSPGCL, Bhusawal (PO NO - 4500111697) | DCB | 3 | 01.10.2020 |  |  |  | 0.022984 | Firm | 0.022984
| 597 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Repl. Unit - Work of internal painting to the project office on 'as and when required' basis at BTPS Deepnagar Bhusawal. (PO NO - 4500111695) | DCB | 3 | 05.10.2020 |  |  |  | 0.022509 | Firm | 0.022509
| 598 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Repacement Unit Bhusawal – Providing Services of Unskilled assistance for sweeping work for Project Civil Division offices at New Project office shed, BTPS Deepnagar, Bhusawal (PO NO - 4500111699) | DCB | 3 | 05.10.2020 |  |  |  | 0.023532 | Firm | 0.023532
| 599 | CCC Bhusawal - ESTABLISHMENT | BTPS 1x660 MW Replacement Unit – Work of providing IT Services at Civil Construction Circle Deepnagar Bhusawal (PO NO - 4500111765) | DCB | 4 | 08.10.2020 |  |  |  | 0.023069 | Firm | 0.023069
| 600 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Repacement Unit Bhusawal – Hiring of private A/C taxi (i.e. swift Dezire/Zest/or equvalent) along with driver and diesel requried for E.E.(C), C.C.D-III., Bhusawal. (PO NO - 4500111801) | DCB | 4 | 08.10.2020 |  |  |  | 0.023175 | Firm | 0.023175
| 601 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for day to day work in A/C section under office of the Dy.Chief Eng(C) Civil construction circle office on temporary basis Deepnagar,Bhusawal (PO NO - 4500111887) | - | 1 | 16.10.2020 |  |  |  | 0.0032783 | Firm | 0.0032783
| 602 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for day to day work as computer operator in A/C section and HR SCivil construction circle office on temporary basis Deepnagar,Bhusawal (PO NO - 4500111884) | - | 1 | 16.10.2020 |  |  |  | 0.0032783 | Firm | 0.0032783
| 603 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for day to day work in civil construction circle office on temporary basis Deepnagar,Bhusawal (PO NO - 4500111882) | - | 1 | 16.10.2020 |  |  |  | 0.0032783 | Firm | 0.0032783
| 604 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for day to day work in A/C section and HR SCivil construction circle office on temporary basis Deepnagar,Bhusawal (PO NO - 4500111883) | - | 1 | 16.10.2020 |  |  |  | 0.0032783 | Firm | 0.0032783
| 605 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for day to day work in A/C section and HR Civil construction circle office on temporary basis Deepnagar,Bhusawal (PO NO - 4500111885) | - | 1 | 16.10.2020 |  |  |  | 0.0032783 | Firm | 0.0032783
| 606 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for day to day work in A/C section and HR SCivil construction circle office on temporary basis Deepnagar,Bhusawal (PO NO - 4500111886) | - | 1 | 16.10.2020 |  |  |  | 0.0032783 | Firm | 0.0032783
| 607 | CCC Bhusawal - OTHER MISC | Bhusawal 1x660 MW Replacement Project - Work of kitchen sink pipeline with overhead water tank and other minor works for type-II building no. 2 & 3 at Deepnagar Bhusawal (PO NO - 4500111890) | DCB | 5 | 16.10.2020 |  |  |  | 0.022538 | Firm | 0.022538
| 608 | CCC Bhusawal - OTHER MISC | 1x660 MW Repl. Unit - Work of extension of roof sheets & misc. repairs of watch tower at 1 x 660 MW Deepnagar, Bhusawal (PO NO - 4500111889) | DCB | 3 | 22.10.2020 |  |  |  | 0.021865 | Firm | 0.021865
| 609 | CCC Bhusawal - OTHER MISC | 1x660 MW Replacement Unit – Work of pump operator for operating pumps of pump house at outlet canal at BTPS to supply raw water for on-going construction 1 x 660 MW at BTPS, Deepnagar, Bhusawal (PO NO - 4500111969) | DCB | 3 | 23.10.2020 |  |  |  | 0.023225 | Firm | 0.023225
| 610 | CCC Bhusawal - OTHER MISC | Bhusawal 1x660 MW Replacement Project -Work of area cleaning, cutting grass, tree branches and supplying, spreading, compacting murum at type II Quarters and project chummery, BTPS Colony, Deepnagar, Bhusawal (PO NO - 4500112001) | DCB | 3 | 26.10.2020 |  |  |  | 0.022788 | Firm | 0.022788
| 611 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Repacement Unit Bhusawal – Hiring of private A/C taxi (i.e. Dezire/ford/or equivalent) along with driver and diesel requried for Dy. C.E.(C), C.C.C., Bhusawal (PO NO - 4500112014) | DCB | 3 | 28.10.2020 |  |  |  | 0.023594 | Firm | 0.023594
| 612 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Repl. Unit – Construction of Flag post at 1 x 660 MW project complex and misc works at Deepnagar Bhusawal (PO NO - 4500112074) | DCB | 3 | 06.11.2020 |  |  |  | 0.012178 | Firm | 0.012178
| 613 | CCC Bhusawal - ESTABLISHMENT | BTPS T.P.S. 1 x 660MW Replacement Unit -Work of painting of quarters internally as & when required under Civil Construction Circle at BTPS, Deepnagar, Bhusawal (PO NO - 4500112073) | DCB | 3 | 06.11.2020 |  |  |  | 0.022981 | Firm | 0.022981
| 614 | CCC Bhusawal - OTHER MISC | BTPS 1x660 MW Repl. Unit - Work of dog bailing for 1 x 660 MW railway siding area at Deepnagar Bhusawal. (PO NO - 4500112101) | DCB | 4 | 12.11.2020 |  |  |  | 0.013895 | Firm | 0.013895
| 615 | CCC Bhusawal - ESTABLISHMENT | Work of construction of sunshed near watch cabin at 1x660 MW Gate at BTPS Deepnagar (PO NO - 4500112100) | DCB | 4 | 12.11.2020 |  |  |  | 0.023582 | Firm | 0.023582
| 616 | CCC Bhusawal - OTHER MISC | Checking location of 500 MW Ash water recovery underground / hidden Pipeline from 500MW Gate to Booster Pump House at TPS Bhusawal (PO NO - 4500112102) | - | 1 | 12.11.2020 |  |  |  | 0.005715 | Firm | 0.005715
| 617 | CCC Bhusawal - OTHER MISC | BTPS T.P.S. 1 x 660MW Replacement Unit -Work of painting of quarters internally as & when required under Civil Construction Circle at BTPS, Deepnagar, Bhusawal (PO NO - 4500112103) | DCB | 4 | 12.11.2020 |  |  |  | 0.021991 | Firm | 0.021991
| 618 | CCC Bhusawal - OTHER MISC | BTPS T.P.S. 1 x 660MW Replacement Unit -Providing technical assistance (Civil supervisor) for site supervision at CHP area 1x660 Project Deepnagar, Bhusawal (PO NO - 4500112158) | DCB | 3 | 20.11.2020 |  |  |  | 0.022875 | Firm | 0.022875
| 619 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Repl. Unit – Construction of parking shed near 1 x 660 MW project gate at Deepnagar Bhusawal (PO NO - 4500112160) | DCB | 4 | 20.11.2020 |  |  |  | 0.022676 | Firm | 0.022676
| 620 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Unit Bhusawal – Hiring of private diesel jeep (i.e. TUV300/Scorpio/Bolero) along with driver and diesel required for Civil Construction Division-II, Bhusawal (PO NO - 4500112163) | DCB | 3 | 20.11.2020 |  |  |  | 0.022276 | Firm | 0.022276
| 621 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Project - Providing Services of Skilled assistance for computer operation & Dispatch work under office of the Dy. Chief Engineer (C), in Civil Construction Circle, Deepnagar, Bhusawal (PO NO - 4500112346) | DCB | 3 | 24.11.2020 |  |  |  | 0.2424 | Firm | 0.2424
| 622 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Project - Providing Services of Unskilled assistance & skilled assistance (drivers for departmental vehicle & Site supervisor) for office of the Civil Construction Circle, Deepnagar, Bhusawal (PO NO - 4500112345) | DCB | 3 | 24.11.2020 |  |  |  | 0.1793 | Firm | 0.1793
| 623 | CCC Bhusawal - ESTABLISHMENT | Work of PVC Gutter drain water pipes to roof of project office at Deepnagar, Bhusawal (PO NO - 4500112309) | DCB | 4 | 24.11.2020 |  |  |  | 0.022901 | Firm | 0.022901
| 624 | CCC Bhusawal - ESTABLISHMENT | BTPS 1 x 660MW Replacement Unit - Additional work of interconnection & establishment of LAN network at Civil Construction Circle, 1x660 MW Deepnagar, Bhusawal (PO NO - 4500112161) | DCB | 3 | 24.11.2020 |  |  |  | 0.01298 | Firm | 0.01298
| 625 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Unit Bhusawal – Hiring of private A/C taxi (i.e. Dezire/ford or equivalent) along with driver and diesel requried for Dy. C.E.(C), C.C.C., Bhusawal (PO NO - 4500112334) | - | 1 | 24.11.2020 |  |  |  | 0.0029382 | Firm | 0.0029382
| 626 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Unit Bhusawal – Hiring of private A/C taxi (i.e. Dezire/ford or equivalent) along with driver and diesel requried for Dy. C.E.(C), C.C.C., Bhusawal (PO NO - 4500112335) | - | 1 | 24.11.2020 |  |  |  | 0.0021769 | Firm | 0.0021769
| 627 | CCC Bhusawal - OTHER MISC | 1x660 MW Repl. Unit – Bhusawal 1x660 MW Replacement Project -Work of providing and fixing M.S.Grill at Project Quarters, BTPS Colony, Deepnagar, Bhusawal (PO NO - 4500112356) | DCB | 3 | 25.11.2020 |  |  |  | 0.016251 | Firm | 0.016251
| 628 | CCC Bhusawal - ESTABLISHMENT | Development of garden near 1x660MW office complex entrance at BTPS,Bhusawal (PO NO - 4500112353) | DCB | 6 | 25.11.2020 |  |  |  | 0.10554 | Firm | 0.10554
| 629 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for day to day work as computer operator in A/C section in Civil construction circle office on temporary basis Deepnagar,Bhusawal (PO NO - 4500112490) | - | 1 | 07.12.2020 |  |  |  | 0.0027363 | Firm | 0.0027363
| 630 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for day to day work in civil construction circle office on temporary basis Deepnagar,Bhusawal (PO NO - 4500112487) | - | 1 | 07.12.2020 |  |  |  | 0.0025233 | Firm | 0.0025233
| 631 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for day to day work in civil construction Division - II office on temporary basis Deepnagar,Bhusawal (PO NO - 4500112486) | - | 1 | 07.12.2020 |  |  |  | 0.0027363 | Firm | 0.0027363
| 632 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for driving departmental vehicle (as driver ) in O/o Dy. CE at CCC office on temporary basis Deepnagar,Bhusawal (PO NO - 4500112488) | - | 1 | 07.12.2020 |  |  |  | 0.0027363 | Firm | 0.0027363
| 633 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for day to day work as computer operator in CCD-III office on temporary basis Deepnagar,Bhusawal (PO NO - 4500112491) | - | 1 | 07.12.2020 |  |  |  | 0.0027363 | Firm | 0.0027363
| 634 | CCC Bhusawal - ESTABLISHMENT | BTPS 1x660 MW Repl. Unit – Hiring of private taxi/jeep (i.e. TUV300/Tata indica/swift equivalent) along with driver and required fuel for E.E. (C) Admin at 1x660 MW Replacement Project at Deepnagar, Bhusawal. (PO NO - 4500112497) | DCB | 4 | 07.12.2020 |  |  |  | 0.023515 | Firm | 0.023515
| 635 | CCC Bhusawal - OTHER MISC | BTPS 1x660 MW Repl. Unit – Development of Garden cum Sitout area near 1x660MW Project New Main Gate, at BTPS, Deepnagar, Bhusawal. (PO NO - 4500112496) | DCB | 3 | 07.12.2020 |  |  |  | 0.022801 | Firm | 0.022801
| 636 | CCC Bhusawal - ESTABLISHMENT | BTPS 1x660 MW Repl. Unit – Work of renovation & maintanance of plumbing system of old projects office complex at BTPS, Deepnagar, Bhusawal.. (PO NO - 4500112530) | DCB | 3 | 10.12.2020 |  |  |  | 0.023415 | Firm | 0.023415
| 637 | CCC Bhusawal - ESTABLISHMENT | Work of repairs and maintenance of aluminum doors, windows & replacement of broken glasses on 'as and when required' basis at various places in project office complex at BTPS, Deepnagar (PO NO - 4500112565) | DCB | 3 | 14.12.2020 |  |  |  | 0.023056 | Firm | 0.023056
| 638 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Repl. Unit - Removing grass and trimming of trees obstructing to the office bldg of 1x660 MW project at BTPS, Deepnagar, Bhusawal (PO NO - 4500112564) | DCB | 4 | 14.12.2020 |  |  |  | 0.014125 | Firm | 0.014125
| 639 | CCC Bhusawal - ESTABLISHMENT | BTPS T.P.S. 1 x 660MW Replacement Unit -Providing technical assistance (Civil supervisor) for site supervision at Chimney 1x660 Project Deepnagar, Bhusawal. (PO NO - 4500112592) | DCB | 4 | 15.12.2020 |  |  |  | 0.023087 | Firm | 0.023087
| 640 | CCC Bhusawal - OTHER MISC | BTPS 1 x 660MW Replacement Unit - Work of providing isolation in left side canal at Sudgaon Pump House in order to start work of laying of 1700 NB dia. Raw water pipeline, from Sudgaon Pump House to BTPS, Deepnagar, Bhusawal (PO NO - 4500112617) | DCB | 3 | 16.12.2020 |  |  |  | 0.023395 | Firm | 0.023395
| 641 | CCC Bhusawal - OTHER MISC | BTPS 1x660 MW Repl. Unit - Providing & fixing fly proof two track sliding window at Tapi Guest House, BTPS, Deepnagar, Bhusawal (PO NO - 4500112673) | DCB | 4 | 22.12.2020 |  |  |  | 0.023117 | Firm | 0.023117
| 642 | CCC Bhusawal - ESTABLISHMENT | BTPS 1x660 MW Repl. Unit - Providing services of driver for departmental vehicle ie ambasador car no. MH-19-6375 & Bolero MH-19-6943 at civil constrcution division paras (confirmatory work for the period of dt. 01/11/2020 to dt. 23/12/2020) (PO NO - 4500112740) | - | 1 | 31.12.2020 |  |  |  | 0.0028695 | Firm | 0.0028695
| 643 | CCC Bhusawal - ESTABLISHMENT | BTPS 1x660 MW Repl. Unit - Work of Accounting & SAP reconcilation work for the year of 2020-21 (PO NO - 4500112744) | - | 1 | 31.12.2020 |  |  |  | 0.0118 | Firm | 0.0118
| 644 | CCC Bhusawal - ESTABLISHMENT | BTPS 1x660 MW Repl. Unit - Providing services of skilled assistance asa computer operator for preparation of data for SAP & SRM System in the office of the civil construciton circle, Deepnagar, Bhusawal (PO NO - 4500112879) | DCB | 5 | 13.01.2021 |  |  |  | 0.023317 | Firm | 0.023317
| 645 | CCC Bhusawal - ESTABLISHMENT | BTPS 1x660 MW Repl. Unit - Hiring of private AC Taxi (i.e. Desier/Ford/Hundai Accent/or equivalent car) along with driver and required Fuel for Superintending Engineer (C) at 1x660 MW replacement project civil construction circle at Deepnagar, Bhusawal (PO NO - 4500112881) | DCB | 3 | 13.01.2021 |  |  |  | 0.023461 | Firm | 0.023461
| 646 | CCC Bhusawal - OTHER MISC | BTPS 1x660 MW Repl. Unit - Work of providing and erecting GI Chain-link fencing of 1.60 mtr. Height to periphery of open space in front of project quarters at Deepnagar, Bhusawal (PO NO - 4500112923) | DCB | 5 | 21.01.2021 |  |  |  | 0.023016 | Firm | 0.023016
| 647 | CCC Bhusawal - ESTABLISHMENT | BTPS 1x660 MW Repl. Unit - Hiring of Private Diesel Taxi Car/Jeep (Mahindra TUV 300/TATA Indica/Bolero/TATA Sumo) along with Driver and Diesel required for Executive Engineer (C), CCD-I, MSPGCL, Deepnagar, Bhusawal (PO NO - 4500112942) | DCB | 3 | 22.01.2021 |  |  |  | 0.022276 | Firm | 0.022276
| 648 | CCC Bhusawal - OTHER MISC | Providing pump operator for operating pump house at outlet canal (PO NO - 4500112967) | DCB | 5 | 25.01.2021 |  |  |  | 0.022563 | Firm | 0.022563
| 649 | CCC Bhusawal - OTHER MISC | Providin two track mosquito jali at project quarters (PO NO - 4500112969) | DCB | 3 | 25.01.2021 |  |  |  | 0.022737 | Firm | 0.022737
| 650 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance ( Driver) for dept vehicle MH 19 AE 6943 (PO NO - 4500112947) | DCB | 4 | 27.01.2021 |  |  |  | 0.022087 | Firm | 0.022087
| 651 | CCC Bhusawal - OTHER MISC | BTPS 1x660 MW Repl. Unit – Minor repairing works for MSF qtrs at Deepnagar Bhusawal. (PO NO - 4500112954) | DCB | 3 | 27.01.2021 |  |  |  | 0.013563 | Firm | 0.013563
| 652 | CCC Bhusawal - OTHER MISC | Work of extra widening of concrete road for smooth passing of fire tender vehicle in 500MW premises. (PO NO - 4500113012) | DCB | 7 | 01.02.2021 |  |  |  | 0.020773 | Firm | 0.020773
| 653 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance ( Driver) for dept vehicle MH 40 A 8027 (PO NO - 4500113045) | DCB | 3 | 04.02.2021 |  |  |  | 0.02043 | Firm | 0.02043
| 654 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance in HR section for day to day work Civil construction circle office on temporary basis Deepnagar,Bhusawal (PO NO - 4500113141) | - | 1 | 11.02.2021 |  |  |  | 0.0026558 | Firm | 0.0026558
| 655 | CCC Bhusawal - ESTABLISHMENT | Providing housekeeping services in Chummery for project staff at bhusawal (PO NO - 4500113151) | DCB | 4 | 12.02.2021 |  |  |  | 0.022519 | Firm | 0.022519
| 656 | CCC Bhusawal - ESTABLISHMENT | 1x660 MW Replacement Unit Bhusawal – Hiring of private A/C taxi (i.e. Dezire/ford or equivalent) along with driver and diesel requried for Dy. C.E.(C), C.C.C., Bhusawal (PO NO - 4500113202) | DCB | 3 | 17.02.2021 |  |  |  | 0.023458 | Firm | 0.023458
| 657 | CCC Bhusawal - ESTABLISHMENT | Supply of Sanitization material in Covid -19 (PO NO - 4500113212) | DCB | 3 | 18.02.2021 |  |  |  | 0.01239 | Firm | 0.01239
| 658 | CCC Bhusawal - ESTABLISHMENT | Work of maintainance of landscaping near 1x660MW Premises,Bhusawal (PO NO - 4500113216) | DCB | 4 | 18.02.2021 |  |  |  | 0.022385 | Firm | 0.022385
| 659 | CCC Bhusawal - ESTABLISHMENT | Hiring of AC innova car on AS and WHEN basis along with driver and diesel required for higher officiales of Head office (PO NO - 4500113217) | DCB | 3 | 18.02.2021 |  |  |  | 0.023211 | Firm | 0.023211
| 660 | CCC Bhusawal - ESTABLISHMENT | Providing 10 MBPS (11) internet lease line conectivity at civil construction circle 1x660 MW Deepnagar. (PO NO - 4500113427) | DCB | 3 | 08.03.2021 |  |  |  | 0.017693 | Firm | 0.017693
| 661 | CCC Bhusawal - OTHER MISC | Work of cleaning grass & murum road to parking shed & constructing brink wall for sepretation of parking load at deepnagar bhusawal (PO NO - 4500113438) | DCB | 3 | 09.03.2021 |  |  |  | 0.022199 | Firm | 0.022199
| 662 | CCC Bhusawal - ESTABLISHMENT | work of supply of stationary for civil construction circle and its allied divisions, MSPGCL Bhusawal (PO NO - 4500113374) | DCB | 3 | 10.03.2021 |  |  |  | 0.0223 | Firm | 0.0223
| 663 | CCC Bhusawal - OTHER MISC | Work of day to day civil maintainance work of project staff quarters at Deepnagar, Bhusawal (PO NO - 4500113480) | DCB | 3 | 12.03.2021 |  |  |  | 0.022042 | Firm | 0.022042
| 664 | CCC Bhusawal - ESTABLISHMENT | Hiring of private diesel taxi (Car/Jeep/Mahendra TUV 300) along with driver & diesel required for Executive Engineer CCD-I MSPGCL, Deepnagar, Bhusawal Period from Dt. 11/12/2019 to Dt. 01/01/2020 (PO NO - 4500113547) | - | 1 | 15.03.2021 |  |  |  | 0.0029264 | Firm | 0.0029264
| 665 | CCC Bhusawal - OTHER MISC | Providing doors & door frams for project staff quarters as and when required at BTPS Deepnagar, Bhusawal (PO NO - 4500113634) | DCB | 4 | 18.03.2021 |  |  |  | 0.023535 | Firm | 0.023535
| 666 | CCC Bhusawal - OTHER MISC | Providing services of Technical Assistance (Civil Supervisor) for the Supervision at CHP area of 1x660 MW Project, Deepnagar, Bhusawal (PO NO - 4500114559) | DCB | 3 | 27.04.2021 |  |  |  | 0.023087 | Firm | 0.023087
| 667 | CCC Bhusawal - OTHER MISC | Providing services of Technical Assistance (Civil Supervisor) for the Supervision at CHP area of 1x660 MW Project, Deepnagar, Bhusawal (PO NO - 4500114561) | DCB | 4 | 27.04.2021 |  |  |  | 0.020065 | Firm | 0.020065
| 668 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled Assistance (Drivers) of departmenatal Vehicle MH-19 AE 6942 for office of Civil Construction Circle, Deepnagar, Bhusawal (PO NO - 4500114560) | DCB | 3 | 27.04.2021 |  |  |  | 0.022308 | Firm | 0.022308
| 669 | CCC Bhusawal - OTHER MISC | Work of diversion of drinking water supply G.I. pipe line of 1x660 MW Project, Deepnagar, Bhusawal (PO NO - 4500114570) | DCB | 3 | 27.04.2021 |  |  |  | 0.023513 | Firm | 0.023513
| 670 | CCC Bhusawal - ESTABLISHMENT | Hiring of Air Coolers During Summer Season for 1x660 MW Project Civil Construction Circle, Deepnagar, Bhusawal (PO NO - 4500114562) | DCB | 6 | 27.04.2021 |  |  |  | 0.020997 | Firm | 0.020997
| 671 | CCC Bhusawal - OTHER MISC | Work of Replacement of damaged AC Corrugated Sheet of Parking Shed No. 3 at BTPS, Deepnagar, Bhusawal (PO NO - 4500114573) | DCB | 4 | 27.04.2021 |  |  |  | 0.017507 | Firm | 0.017507
| 672 | CCC Bhusawal - OTHER MISC | Work of Providing Technical Assistance (Civil Supervisor) for site supervision at NDCT area at 1x660 MW Project, Deepnagar, Bhusawal (PO NO - 4500114581) | DCB | 3 | 29.04.2021 |  |  |  | 0.0098943 | Firm | 0.0098943
| 673 | CCC Bhusawal - OTHER MISC | Work of providing & erecting GI Chain Link Fencing of 1.6 Mtr Height to Periphery of Garden adjacent to Project Office at Deepnagar, Bhusawal (PO NO - 4500114619) | DCB | 4 | 29.04.2021 |  |  |  | 0.023487 | Firm | 0.023487
| 674 | CCC Bhusawal - OTHER MISC | Work of Closing of part partion of existing gate and repairing of damaged 1x660 MW gate at BTPS, Deepnagar, Bhusawal (PO NO - 4500114580) | DCB | 5 | 29.04.2021 |  |  |  | 0.021983 | Firm | 0.021983
| 675 | CCC Bhusawal - OTHER MISC | Work of stopping water flow in canal at sudgaon pump house in order to start work for lyaing of raw water pipeline from raw warter pump house to BTPS, Deepnagar, Bhusawal (PO NO - 4500114642) | DCB | 3 | 29.04.2021 |  |  |  | 0.023526 | Firm | 0.023526
| 676 | CCC Bhusawal - ESTABLISHMENT | Hiring of private diesel AC Car (Dezire/ford or Equivalent) along with driver and diesel required for Dy. Chief Engineer (C), C.C.C. MSPGCL, Bhusawal for the period from Dt. 28/01/2021 to Dt. 17/02/2021 (PO NO - 4500114639) | - | 1 | 29.04.2021 |  |  |  | 0.00292 | Firm | 0.00292
| 677 | CCC Bhusawal - ESTABLISHMENT | Procurement of UPB (Uninteruptable Power Supply) throuth GEMs Portal. (PO NO - 4500114882) | DCB | 3 | 20.05.2021 |  |  |  | 0.003506 | Firm | 0.003506
| 678 | CCC Bhusawal - ESTABLISHMENT | Providing services of Unskilled Assistance for day to day work on Temp Basis at CCD-I, Deepnagar. (PO NO - 4500114886) | - | 1 | 20.05.2021 |  |  |  | 0.0025233 | Firm | 0.0025233
| 679 | CCC Bhusawal - ESTABLISHMENT | Providing of fixing new 15 H.P. Pump in Canal also repair of existing pumps at outlet canal in 500 MW premises BTPS Construction Water Supply 1x660 MW Project, Deepnagar. (PO NO - 4500114897) | DCB | 3 | 20.05.2021 |  |  |  | 0.023234 | Firm | 0.023234
| 680 | CCC Bhusawal - ESTABLISHMENT | Hiring of private diesel taxi, AC Car (Dezire/Ford of equivalent) along with driver and diesel required for Dy. C.E. (C), CCC, MSPGCL, Bhusawal, Period from Dt. 16/01/2021 to Dt. 27/01/2021 (PO NO - 4500114885) | - | 1 | 21.05.2021 |  |  |  | 0.0027813 | Firm | 0.0027813
| 681 | CCC Bhusawal - OTHER MISC | Providing Technical Assistance (Civil Supervisor) for Site Supervision at W.T. area at 1x660 MW Project, Deepnagar. (PO NO - 4500115095) | DCB | 3 | 08.06.2021 |  |  |  | 0.013192 | Firm | 0.013192
| 682 | CCC Bhusawal - OTHER MISC | Work of PVC gutter of rain water pipe to foor of parking shed of project office at Deepnagar, Bhusawal (PO NO - 4500115093) | DCB | 3 | 08.06.2021 |  |  |  | 0.022964 | Firm | 0.022964
| 683 | CCC Bhusawal - OTHER MISC | Providing concrete apron to Tem. Staff Quarters at Deepnagar, Bhusawal (PO NO - 4500115092) | DCB | 3 | 08.06.2021 |  |  |  | 0.022626 | Firm | 0.022626
| 684 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private A.C. Taxi (i.e Dezire/Ford/equivalent Sedan Car) along with driver and required fuel for Superintending Engineer (C) at 1x660 MW repln. Project Site at Deepnagar. Bhusawal (PO NO - 4500114891) | DCB | 3 | 09.06.2021 |  |  |  | 0.056333 | Firm | 0.056333
| 685 | CCC Bhusawal - ESTABLISHMENT | Providing Services of Unskilled Assistance for day to day office work for project civil division No-III at mew project office shed BTPS, Deepnagar. (PO NO - 4500115153) | DCB | 4 | 11.06.2021 |  |  |  | 0.02162 | Firm | 0.02162
| 686 | CCC Bhusawal - OTHER MISC | Providing Technical Assistance (Civil Supervisor) for Site Supervision at Chimney 1x660 MW Project, Deepnagar, Bhusawal (PO NO - 4500115152) | DCB | 4 | 15.06.2021 |  |  |  | 0.023087 | Firm | 0.023087
| 687 | CCC Bhusawal - OTHER MISC | Work of Construction of security office at entrance gate of Tapi Guast House Deepnagar, Bhusawal (PO NO - 4500115145) | DCB | 4 | 15.06.2021 |  |  |  | 0.02312 | Firm | 0.02312
| 688 | CCC Bhusawal - ESTABLISHMENT | Work of Providing day to day Sanitization of Offices in Pandamic Covid-19 at office of the Dy. Chief Engineer (C), CCC, 1x660 MW Project, Deepnagar. (PO NO - 4500115218) | DCB | 4 | 18.06.2021 |  |  |  | 0.012517 | Firm | 0.012517
| 689 | CCC Bhusawal - OTHER MISC | Providing and Fixing Sanitory Pipeline and alied work Bellow E-47 Building (MSF) at Deepnagar, Bhusawal. (PO NO - 4500115216) | DCB | 3 | 18.06.2021 |  |  |  | 0.0058927 | Firm | 0.0058927
| 690 | CCC Bhusawal - OTHER MISC | Work of repairing Pat Hole of Colony Road from M/s. BHEL Office to 2x210 MW Project at BTPS, Deepnagar, Bhusawal (PO NO - 4500115217) | DCB | 4 | 18.06.2021 |  |  |  | 0.021707 | Firm | 0.021707
| 691 | CCC Bhusawal - OTHER MISC | Work of Removing grass and Laying of GI Pipeline for proposed garden adjacent to security Cabin of 1x660 MW project office at BTPS, Deepnagar. (PO NO - 4500115214) | DCB | 6 | 18.06.2021 |  |  |  | 0.0093314 | Firm | 0.0093314
| 692 | CCC Bhusawal - OTHER MISC | Work of Pot Hole Repairing of Pimprisekam Road adjacent to 1x660 MW Premises Compound wall at BTPS, Deepnagar, Bhusawal. (PO NO - 4500115213) | DCB | 3 | 18.06.2021 |  |  |  | 0.023437 | Firm | 0.023437
| 693 | CCC Bhusawal - OTHER MISC | Providing Pump Operator for Operating Pumps at Pumps HouseOutlet Canal at BTPS to Supply raw water for on going Construction at 1x660 MW , Deepnagar (PO NO - 4500115233) | DCB | 3 | 21.06.2021 |  |  |  | 0.023283 | Firm | 0.023283
| 694 | CCC Bhusawal - OTHER MISC | Work of Water Proffing Before on set of Manson to temporary Project Quarters at Deepnagar, Bhuisawal (PO NO - 4500115232) | DCB | 5 | 21.06.2021 |  |  |  | 0.022864 | Firm | 0.022864
| 695 | CCC Bhusawal - OTHER MISC | Construction of shed for MSF Quards Fouling near 1x660 MW Project Gate at Deepnagar, Bhusawal. (PO NO - 4500115234) | DCB | 3 | 21.06.2021 |  |  |  | 0.01804 | Firm | 0.01804
| 696 | CCC Bhusawal - OTHER MISC | Replacement of Damaged AC Corugated Shed of Temp staff quarters at Deepnagar, Bhusawal (PO NO - 4500115267) | DCB | 4 | 23.06.2021 |  |  |  | 0.021805 | Firm | 0.021805
| 697 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private Diesel Taxi Car Jeep (Mahindra TUV/TATA Indica/Bolero/TATA Sumo) along with driver and diesel required for Executive Engineer (C), Civil Const. Division-I MSPGCL, Bhusawal (PO NO - 4500115304) | DCB | 3 | 25.06.2021 |  |  |  | 0.022276 | Firm | 0.022276
| 698 | CCC Bhusawal - OTHER MISC | Work of removing grass and wild shrubs etc along road of pimprisekam road bhusawal (PO NO - 4500115391) | DCB | 4 | 05.07.2021 |  |  |  | 0.017995 | Firm | 0.017995
| 699 | CCC Bhusawal - OTHER MISC | Work of providing plumber with helper for attending day to day complaints of project quarters at deepnagar. (PO NO - 4500115389) | DCB | 4 | 05.07.2021 |  |  |  | 0.022347 | Firm | 0.022347
| 700 | CCC Bhusawal - ESTABLISHMENT | Providing services of office supporting staff for day to day misl. Work in office of the Dy. Chief Engineer (C), Bhusawal (PO NO - 4500115390) | DCB | 3 | 05.07.2021 |  |  |  | 0.020617 | Firm | 0.020617
| 701 | CCC Bhusawal - OTHER MISC | Construction of murum road for vehicle movement of farmers & mahagenco vihicle near existing canal in village pimprisekam. (PO NO - 4500115467) | DCB | 4 | 08.07.2021 |  |  |  | 0.023421 | Firm | 0.023421
| 702 | CCC Bhusawal - OTHER MISC | Providing and fixing guard railing near 1X660 MW project gate and labour gate on pimprisekam road at Deepnagar, Bhusawal (PO NO - 4500115465) | DCB | 4 | 08.07.2021 |  |  |  | 0.023082 | Firm | 0.023082
| 703 | CCC Bhusawal - ESTABLISHMENT | Work of removing grass along boundary wall of 1X660 MW project etc at BTPS, Deepnagar, Bhusawal (PO NO - 4500115464) | DCB | 4 | 08.07.2021 |  |  |  | 0.018899 | Firm | 0.018899
| 704 | CCC Bhusawal - ESTABLISHMENT | Work of providing & laying ceramic file flooring to security office and other (Civil & E&M) section at project office complex Deepnagar. (PO NO - 4500115507) | DCB | 3 | 14.07.2021 |  |  |  | 0.021031 | Firm | 0.021031
| 705 | CCC Bhusawal - OTHER MISC | Providing Technical assistance (Civil Supervisior) for site supervision at Transformer yard ESP control room air compressor house roads & drain & various building in BTG area at Deepnagar. (PO NO - 4500115483) | DCB | 5 | 14.07.2021 |  |  |  | 0.019789 | Firm | 0.019789
| 706 | CCC Bhusawal - ESTABLISHMENT | Work of Concreting between existing road and parking shed at project office Bhusawal (PO NO - 4500115660) | DCB | 4 | 28.07.2021 |  |  |  | 0.01511 | Firm | 0.01511
| 707 | CCC Bhusawal - OTHER MISC | Work of providing & fixing gypsum board false celing for project quarters & project office at BTPS Deepnagar (PO NO - 4500115657) | DCB | 3 | 28.07.2021 |  |  |  | 0.022479 | Firm | 0.022479
| 708 | CCC Bhusawal - OTHER MISC | Work of painting of quarters internaly as and when under Civil Construction Circle at BTPS Deepnagar (PO NO - 4500115661) | DCB | 4 | 28.07.2021 |  |  |  | 0.021629 | Firm | 0.021629
| 709 | CCC Bhusawal - OTHER MISC | Work of repairing & strenthening of RCC Chajjas of type-II project quarters Deepnagar, Bhusawal (PO NO - 4500115658) | DCB | 3 | 29.07.2021 |  |  |  | 0.021939 | Firm | 0.021939
| 710 | CCC Bhusawal - OTHER MISC | Work of providing & Installing 3.0 H.P. pump and CPVC pipe line for garden adjacent to 1X660 MW project office at BTPS Deepnagar, Bhusawal (PO NO - 4500115659) | DCB | 3 | 29.07.2021 |  |  |  | 0.022966 | Firm | 0.022966
| 711 | CCC Bhusawal - OTHER MISC | Providing assistance maintaining water supply in project office primises at BTPS, Deepnagar (PO NO - 4500115769) | DCB | 3 | 06.08.2021 |  |  |  | 0.023415 | Firm | 0.023415
| 712 | CCC Bhusawal - OTHER MISC | Confirmatory work of providing unskilled labour for dewatering of concrete drain construction of cofferdam to stop water in darin required for finding out lekages in construction water supply pipe line at BTPS Deepnagar (PO NO - 4500115826) | - | 1 | 10.08.2021 |  |  |  | 0.0033139 | Firm | 0.0033139
| 713 | CCC Bhusawal - ESTABLISHMENT | Annual maintainance servicing checking networking administration & trouble shooting of network hardware system at 1x660 MW, CCC MSPGCL, Bhusawal (PO NO - 4500115772) | DCB | 4 | 25.08.2021 |  |  |  | 0.029707 | Firm | 0.029707
| 714 | CCC Bhusawal - ESTABLISHMENT | Haring of private diesel taxi car/jeep(MahendraTUV300/TATA Indigo/Bolero/TATA Sumo) along with driver & Diesel required for Exect. Engg. (C) CCD-I Bhusawal for the period from 27/01/2020 to 31/01/2021 & 14/07/2020 to 24/07/2020 (PO NO - 4500115518) | - | 1 | 25.08.2021 |  |  |  | 0.0021948 | Firm | 0.0021948
| 715 | CCC Bhusawal - OTHER MISC | Work of driling borewell for raw water supply to 660MW project site at Deepnagar, Bhusawal (PO NO - 4500115937) | DCB | 3 | 27.08.2021 |  |  |  | 0.023444 | Firm | 0.023444
| 716 | CCC Bhusawal - OTHER MISC | Work of providing water supply, sanitary arrangment & other miscelleneous work for building no. new F-09 for MSF at BTPS, Deepnagar (PO NO - 4500115936) | DCB | 3 | 27.08.2021 |  |  |  | 0.020073 | Firm | 0.020073
| 717 | CCC Bhusawal - OTHER MISC | Providing & Supplying Clean water by 5000 Lit. tankers for construction of 1x660 MW project office at BTPS, Deepnagar (PO NO - 4500116003) | DCB | 3 | 27.08.2021 |  |  |  | 0.023194 | Firm | 0.023194
| 718 | CCC Bhusawal - ESTABLISHMENT | Renovation of Cabin of the Dy. Chief Engineer (C), C. C. Office, Deepnagar, Bhusawal (PO NO - 4500116004) | DCB | 4 | 27.08.2021 |  |  |  | 0.023423 | Firm | 0.023423
| 719 | CCC Bhusawal - OTHER MISC | Work of removing dense shrubs weeds along project office approach road of 1x660MW Project office at BTPS, Deepnagar, Bhusawal (PO NO - 4500115999) | DCB | 3 | 01.09.2021 |  |  |  | 0.022872 | Firm | 0.022872
| 720 | CCC Bhusawal - ESTABLISHMENT | Hiring Services of Skilled as Computer Typist at Account Section Civil Construction Circle office, Deepnagar, Bhusawal (PO NO - 4500116061) | DCB | 5 | 07.09.2021 |  |  |  | 0.015463 | Firm | 0.015463
| 721 | CCC Bhusawal - OTHER MISC | Work of Providing & Fixing 2HP pump in existing borewell of project office Complex at Deepnagar, Bhusawal (PO NO - 4500116055) | DCB | 4 | 07.09.2021 |  |  |  | 0.01523 | Firm | 0.01523
| 722 | CCC Bhusawal - ESTABLISHMENT | Hiring of private diesel taxi (i.e. XUV 300/TUV 300/Mahindra Scorpio/Hundai/Maruti Vista or equivalent) along with driver & required fuel for E.E. (C), admin at 1x660MW repln. Project CCC., Bhusawal (PO NO - 4500116363) | DCB | 3 | 30.09.2021 |  |  |  | 0.058595 | Firm | 0.058595
| 723 | CCC Bhusawal - ESTABLISHMENT | Work of painting of office internally as & when required under CCC, at BTPS Deepanagar, Bhusawal (PO NO - 4500116057) | DCB | 5 | 30.09.2021 |  |  |  | 0.022125 | Firm | 0.022125
| 724 | CCC Bhusawal - OTHER MISC | Work of Internal painting to quarters (2 Nos) in building No. F-9 for MSF Staff at BTPS colony Deepnagar, Bhusawal (PO NO - 4500116056) | DCB | 3 | 30.09.2021 |  |  |  | 0.020566 | Firm | 0.020566
| 725 | CCC Bhusawal - ESTABLISHMENT | Work of providi9ng of unskilled labour and Misc work at 1x660MW office at Deepanagar, Bhusawal (PO NO - 4500116062) | DCB | 4 | 30.09.2021 |  |  |  | 0.020617 | Firm | 0.020617
| 726 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance as a computer operator for preparation data for SAP & SRM syatem in the office of the civil construction circle, Deepnagar, Bhusawal (PO NO - 4500116426) | DCB | 3 | 06.10.2021 |  |  |  | 0.01804 | Firm | 0.01804
| 727 | CCC Bhusawal - OTHER MISC | Repairing and renovation of 03 Qtrs in building no. E-37 for MSF at BTPS Colony, Deepnagar, Bhusawal (PO NO - 4500116508) | DCB | 4 | 21.10.2021 |  |  |  | 0.022577 | Firm | 0.022577
| 728 | CCC Bhusawal - ESTABLISHMENT | Hiring of private diesel taxi car i.e. (XUV 300/TUV 300/Mahindra Scorpio / Hundai/Venue Maruti Vitara Brezza) along with driver and required fuel for E.E. (C), CCD-III at 1x660 Mw Repln. Project civil construction circle at Deepnagar, Bhusawal (PO NO - 4500116428) | DCB | 3 | 21.10.2021 |  |  |  | 0.058595 | Firm | 0.058595
| 729 | CCC Bhusawal - OTHER MISC | Development of garden in open space in front of temp project quarters at BTPScolony Deepnagar, Bhusawal (PO NO - 4500116756) | DCB | 4 | 18.11.2021 |  |  |  | 0.023457 | Firm | 0.023457
| 730 | CCC Bhusawal - OTHER MISC | Work of Stainless Steel Railing infront of VIP suits at Tapi Rest House Deepnagar, Bhusawal (PO NO - 4500116849) | DCB | 6 | 30.11.2021 |  |  |  | 0.022677 | Firm | 0.022677
| 731 | CCC Bhusawal - ESTABLISHMENT | Work of fixing Septi Tank of Soak Pite Minor Repairing of Toilet of Project Canteen at BTPS, Deepnagar, Bhusawal (PO NO - 4500116807) | DCB | 6 | 30.11.2021 |  |  |  | 0.015038 | Firm | 0.015038
| 732 | CCC Bhusawal - OTHER MISC | Providing and fixing kitchen trolley & misc. work for Qtr. BM-19 & BM-20 at BTPS, Deepnagar, Bhusawal (PO NO - 4500116809) | DCB | 3 | 30.11.2021 |  |  |  | 0.023599 | Firm | 0.023599
| 733 | CCC Bhusawal - OTHER MISC | Providing and fixing two track sliding mousquito jali at temp. project qtr. BTPS, Deepnagar, Bhusawal (PO NO - 4500116839) | DCB | 3 | 30.11.2021 |  |  |  | 0.023265 | Firm | 0.023265
| 734 | CCC Bhusawal - OTHER MISC | Work of removing dense grass srups weeds on as and when required basis around project qtr. Deepnagar (PO NO - 4500116848) | DCB | 4 | 30.11.2021 |  |  |  | 0.015512 | Firm | 0.015512
| 735 | CCC Bhusawal - OTHER MISC | Work of UCR Drain along Road to Project office under C.C.C. at BTPS, Deepnagar, Bhusawal (PO NO - 4500116808) | DCB | 5 | 30.11.2021 |  |  |  | 0.022635 | Firm | 0.022635
| 736 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private Diesel AC Car i.e. (Dezire/Ford or equivalent) along with driver and Diesel required for Dy. C.E. C.C.C., MSPGCL, Bhusawal from Period at (Dt. 03/06/2021 to Dt. 09/06/2021) (PO NO - 4500116914) | - | 1 | 02.12.2021 |  |  |  | 0.0029217 | Firm | 0.0029217
| 737 | CCC Bhusawal - OTHER MISC | Providing and Fixing Eco Roof Sheet over Project PA Type Quarters at BTPS Colony, Deepnagar, Bhusawal (PO NO - 4500116607) | DCB | 3 | 03.12.2021 |  |  |  | 0.034623 | Firm | 0.034623
| 738 | CCC Bhusawal - OTHER MISC | Providing and fixing two track sliding Mousquito Jali at Tapi Rest House, BTPS, Deepnagar, Bhusawal (PO NO - 4500116917) | DCB | 3 | 03.12.2021 |  |  |  | 0.021256 | Firm | 0.021256
| 739 | CCC Bhusawal - ESTABLISHMENT | Hiring of private Desiel AC Taxi (i.e. XUV 300/ TUV 300/ Mahendra scarpio/ Hundai/ Venue maruti/ Vitra Brezza) along wilth drive & required fuel for E.E.(C) CCD-I at 1X660 MW replacement project C.C.C. at Deepnagar. (PO NO - 4500116945) | DCB | 3 | 06.12.2021 |  |  |  | 0.058595 | Firm | 0.058595
| 740 | CCC Bhusawal - ESTABLISHMENT | Hiring of private Desiel AC Taxi (i.e. XUV 300/ Venue maruti/ Vitra Brezza/TUV-300/ Mahendra scarpio) along wilth drive & required fuel for E.E.(C) CCD-II at 1X660 MW replacement project C.C.C. at Deepnagar. (PO NO - 4500116946) | DCB | 4 | 06.12.2021 |  |  |  | 0.058595 | Firm | 0.058595
| 741 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance for computer operation & Dispatch work at office of the Dy.C.E. (C) CCC Deepnagar Bhusawal. (PO NO - 4500116889) | DCB | 3 | 07.12.2021 |  |  |  | 0.36103 | Firm | 0.36103
| 742 | CCC Bhusawal - OTHER MISC | Work of Water Proffing to the Terrace of VIP Suits at Tapi Rest House, Deepnagar, Bhusawal (PO NO - 4500116983) | DCB | 3 | 08.12.2021 |  |  |  | 0.021187 | Firm | 0.021187
| 743 | CCC Bhusawal - ESTABLISHMENT | Work of Repaire and Maintainace of Alluminium Doors and Partition on as when required basis at various Division / Section in Project Office Complex at BTPS, Deepnagar, Bhusawal (PO NO - 4500116918) | DCB | 4 | 08.12.2021 |  |  |  | 0.023422 | Firm | 0.023422
| 744 | CCC Bhusawal - ESTABLISHMENT | Renovation and re-painting of Circle Account and HR Section at 1x660 MW Civil Construction Circle, Office Deepnagar, Bhusawal (PO NO - 4500116938) | DCB | 4 | 08.12.2021 |  |  |  | 0.023398 | Firm | 0.023398
| 745 | CCC Bhusawal - ESTABLISHMENT | Providing unskilled assistance for monitoring of curing at 1x660 MW replacement unit Civil Construction Circle Deepnagar, Bhusawal (PO NO - 4500116942) | DCB | 3 | 08.12.2021 |  |  |  | 0.023078 | Firm | 0.023078
| 746 | CCC Bhusawal - OTHER MISC | Work of plain cement concrete behaind VIP suits of Tapi rest House, Deepnagar, Bhusawal (PO NO - 4500117069) | DCB | 4 | 16.12.2021 |  |  |  | 0.023256 | Firm | 0.023256
| 747 | CCC Bhusawal - ESTABLISHMENT | Providing 10 MBPS (1:1) Internet Leased line Connectivity at Civil Construction Circle 1x660 MW, Deepnagar, Bhusawal (PO NO - 4500116984) | DCB | 3 | 22.12.2021 |  |  |  | 0.020783 | Firm | 0.020783
| 748 | CCC Bhusawal - ESTABLISHMENT | Work of Plinth Protection to Project Canteen and Concreting below Chainlink Fencing around Canteen, at Deepnagar, Bhusawal (PO NO - 4500117201) | DCB | 4 | 29.12.2021 |  |  |  | 0.020873 | Firm | 0.020873
| 749 | CCC Bhusawal - OTHER MISC | Work of external painting to temporary project quarters at Deepnagar, Bhusawal (PO NO - 4500117202) | DCB | 4 | 29.12.2021 |  |  |  | 0.021464 | Firm | 0.021464
| 750 | CCC Bhusawal - ESTABLISHMENT | Procurement of multiflication printer for office of Dy. Chief Engineer (C), C.C.C., Deepnagar, Bhusawal (PO NO - 4500117285) | DCB | 3 | 03.01.2022 |  |  |  | 0.0208 | Firm | 0.0208
| 751 | CCC Bhusawal - OTHER MISC | Confimatory work of providing pump operator for operating pumps at pump house oulet canal at BTPS to supply raw water for ongoing constn. Of 1x660 MW Project, Deepnagar. (Period from Dt. 25/10/2021 to Dt. 15/11/2021) (PO NO - 4500117297) | - | 1 | 05.01.2022 |  |  |  | 0.0033069 | Firm | 0.0033069
| 752 | CCC Bhusawal - OTHER MISC | Confirmatory work of providing services of Technical Assistance (Civil Supervisor) for supervision at NDCT area at 1X660 MW Project Deepnagar period 01-09-21 To 27-09-21 (PO NO - 4500117363) | - | 1 | 06.01.2022 |  |  |  | 0.0029176 | Firm | 0.0029176
| 753 | CCC Bhusawal - OTHER MISC | Providing and fixing tiles to step of temp staff quarters at BTPS Deepnagar (PO NO - 4500117362) | DCB | 4 | 06.01.2022 |  |  |  | 0.022037 | Firm | 0.022037
| 754 | CCC Bhusawal - OTHER MISC | Work of cleaining undergraound drains inspection chambur removing chocks from nhani trap wash basin sink we as & when required basis along with cutting down branches of trees at project quarters at BTPS Deepnagar. (PO NO - 4500117376) | DCB | 4 | 06.01.2022 |  |  |  | 0.019604 | Firm | 0.019604
| 755 | CCC Bhusawal - ESTABLISHMENT | Providing services of unskilled assistance for Dy. Chief Engg.(C), Civil Const. Circle, Deepnagar, Bhusawal (PO NO - 4500117383) | DCB | 7 | 17.01.2022 |  |  |  | 0.12048 | Firm | 0.12048
| 756 | CCC Bhusawal - ESTABLISHMENT | Providing services of unskilled assistance for Dy. Chief Engg.(C), Civil Const. Circle, Deepnagar, Bhusawal (PO NO - 4500117386) | DCB | 7 | 17.01.2022 |  |  |  | 0.12048 | Firm | 0.12048
| 757 | CCC Bhusawal - ESTABLISHMENT | Work of hiring of Xerox Machine for day to day Xeroxing of document at C.C.C. M.S.P.G.C.L., Bhusawal (PO NO - 4500117449) | DCB | 3 | 18.01.2022 |  |  |  | 0.010478 | Firm | 0.010478
| 758 | CCC Bhusawal - OTHER MISC | Work of repairing major pot holes of colony road from BHEL office to Shaktigad Chowk at BTPS, Deepnagar, Bhusawal. (PO NO - 4500117292) | - | 1 | 18.01.2022 |  |  |  | 0.0032962 | Firm | 0.0032962
| 759 | CCC Bhusawal - ESTABLISHMENT | Supply of sanitization material for pandamic Covid-19 at Civil Constn. Circle & it allied division 1x660 MW Project, Deepnagar, Bhusawal (PO NO - 4500117472) | DCB | 4 | 18.01.2022 |  |  |  | 0.020532 | Firm | 0.020532
| 760 | CCC Bhusawal - OTHER MISC | Providing cutting down branches removing grass cleaning & misc. work at Tapi Rest House Deepnagar, Bhusawal (PO NO - 4500117497) | DCB | 4 | 18.01.2022 |  |  |  | 0.016289 | Firm | 0.016289
| 761 | CCC Bhusawal - ESTABLISHMENT | Engaging expert services for SAP reconcilation for Final Accounting work for FY-2021-22, Deepnagar, Bhusawal (PO NO - 4500117450) | DCB | 4 | 21.01.2022 |  |  |  | 0.02655 | Firm | 0.02655
| 762 | CCC Bhusawal - ESTABLISHMENT | Work of Construction of new toilet at 500MW gate for security staff at Deepnagar, Bhusawal (PO NO - 4500117612) | DCB | 5 | 05.02.2022 |  |  |  | 0.023472 | Firm | 0.023472
| 763 | CCC Bhusawal - OTHER MISC | Work of repairing/replacing sewaqge pipe line at Tapi rest house Deepnagar, Bhusawal (PO NO - 4500117611) | DCB | 4 | 05.02.2022 |  |  |  | 0.013304 | Firm | 0.013304
| 764 | CCC Bhusawal - OTHER MISC | Plantation of royal palm for tale palm and required decorative plant sapling trees in 1x660 MW at Deepnagar, Bhusawal (PO NO - 4500117609) | DCB | 4 | 05.02.2022 |  |  |  | 0.02177 | Firm | 0.02177
| 765 | CCC Bhusawal - OTHER MISC | Annual maintenance of garden near project office complex gate at Deepnagar, Bhusawal (PO NO - 4500117610) | DCB | 4 | 05.02.2022 |  |  |  | 0.021846 | Firm | 0.021846
| 766 | CCC Bhusawal - ESTABLISHMENT | Providing day to day sanitizatiuon at Cabin, Partition, Furniuture & allied toilet at C.C.C., 1X660 MW, Project, Deepnagar. (PO NO - 4500117747) | DCB | 3 | 11.02.2022 |  |  |  | 0.018776 | Firm | 0.018776
| 767 | CCC Bhusawal - OTHER MISC | Shifting of existing drinking water pipe line of peri urban Khadke water supply scheme (of MJP) near 1X660 MW railway, siding, 1X660 MW Project, Deepnagar, Bhusawal. (PO NO - 4500117622) | DCB | 3 | 11.02.2022 |  |  |  | 0.39309 | Firm | 0.39309
| 768 | CCC Bhusawal - ESTABLISHMENT | Supply of safty equipment of civil construction circle 1X660 MW Repl. Unit Deepnagar Bhusawal. (PO NO - 4500117800) | DCB | 3 | 15.02.2022 |  |  |  | 0.023302 | Firm | 0.023302
| 769 | CCC Bhusawal - ESTABLISHMENT | Xeroxing photocopying of offical documents of Civil construction Bhusawal Period 13/04/21 To 16/06/2021 (PO NO - 4500117827) | - | 1 | 17.02.2022 |  |  |  | 0.0031675 | Firm | 0.0031675
| 770 | CCC Bhusawal - OTHER MISC | Replacement of damaged files of temp staff Qtrs at BTPS Deepnagar Bhusawal. (PO NO - 4500117823) | DCB | 4 | 24.02.2022 |  |  |  | 0.023351 | Firm | 0.023351
| 771 | CCC Bhusawal - OTHER MISC | Work of minor repair and internal painting BM-24 Qtr BTPS Deepnagar. (PO NO - 4500117820) | DCB | 3 | 24.02.2022 |  |  |  | 0.016411 | Firm | 0.016411
| 772 | CCC Bhusawal - ESTABLISHMENT | Maintenance of plumbing system of old project office complex at BTPS Deepnagar Bhusawal. (PO NO - 4500117821) | DCB | 3 | 24.02.2022 |  |  |  | 0.02343 | Firm | 0.02343
| 773 | CCC Bhusawal - OTHER MISC | Work of cleaning of constructed drain & reparing works in the premises of project complex at Deepnagar, Bhusawal (PO NO - 4500117926) | - | 1 | 28.02.2022 |  |  |  | 0.0059899 | Firm | 0.0059899
| 774 | CCC Bhusawal - OTHER MISC | Providing assistance (Civil Supervisor) for site supervision at water treatment area at 1x660 MW project, Deepnagar, Bhusawal (PO NO - 4500117927) | DCB | 3 | 28.02.2022 |  |  |  | 0.020433 | Firm | 0.020433
| 775 | CCC Bhusawal - ESTABLISHMENT | Maintenace of project office complex &other misc reparing works as and when required at Deepnagar, Bhusawal (PO NO - 4500117924) | DCB | 5 | 28.02.2022 |  |  |  | 0.023414 | Firm | 0.023414
| 776 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled Assistance (Drivers) of departmenatal Vehicle MH-19 AE 6942 for office of Civil Construction Circle, Deepnagar, Bhusawal (PO NO - 4500117999) | DCB | 2 | 28.02.2022 |  |  |  | 0.03378 | Firm | 0.03378
| 777 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled Assistance (Drivers) of departmenatal Vehicle MH-40 AE 8027 for office of Civil Construction Circle, Deepnagar, Bhusawal (PO NO - 4500118000) | DCB | 3 | 28.02.2022 |  |  |  | 0.03378 | Firm | 0.03378
| 778 | CCC Bhusawal - RAILWAY SIDING | Re-routing of S&T Cables and Lacation boxes of 2X500 MW Railway Siding fouling in the route of 1X660 MW Railway Siding at Deepnagar, Bhusawal (PO NO - 4500118073) | DCB | 1 | 02.03.2022 |  |  |  | 0.68979 | Firm | 0.68979
| 779 | CCC Bhusawal - ESTABLISHMENT | Hiring of private Innova AC Car on 'as and when' required basis along with driver and diesel required for Higher Official Head Office MSPGCL, Mumbai (PO NO - 4500117982) | DCB | 3 | 03.03.2022 |  |  |  | 0.023211 | Firm | 0.023211
| 780 | CCC Bhusawal - OTHER MISC | Work of replacement of damaged tiles & misc-repairs of chummery at PD - 4/2 at BTPS Deepnagar, Bhusawal (PO NO - 4500118013) | DCB | 3 | 07.03.2022 |  |  |  | 0.023373 | Firm | 0.023373
| 781 | CCC Bhusawal - OTHER MISC | Construction of temporary road for formers along 1x660 MW railway siding at Deepnagar, Bhusawal (PO NO - 4500118108) | DCB | 3 | 08.03.2022 |  |  |  | 0.022476 | Firm | 0.022476
| 782 | CCC Bhusawal - OTHER MISC | Work of replacement of damaged tiles & misc-repairs of chummery at PD - 4/2 at BTPS Deepnagar, Bhusawal PVC Pipe Line of farmers fouling in 1X660 MW railway siding area under CCC, Deepnagar, Bhusawal (PO NO - 4500118106) | DCB | 3 | 08.03.2022 |  |  |  | 0.018496 | Firm | 0.018496
| 783 | CCC Bhusawal - OTHER MISC | Work of construction of Pipe Culvert on Railway Side Road (Rly Br. No. 15) 1X660 MW at Deepnagar, Bhusawal (PO NO - 4500118103) | DCB | 3 | 08.03.2022 |  |  |  | 0.023478 | Firm | 0.023478
| 784 | CCC Bhusawal - OTHER MISC | Work of Waterproffing of Building No - New F-09 for MSF at BTPS Deepnagar, Bhusawal (PO NO - 4500117983) | DCB | 3 | 09.03.2022 |  |  |  | 0.011669 | Firm | 0.011669
| 785 | CCC Bhusawal - OTHER MISC | Providing Pump Operator for Operating Pumps at Pumps HouseOutlet Canal at BTPS to Supply raw water for on going Construction at 1x660 MW , Deepnagar (PO NO - 4500118115) | DCB | 2 | 09.03.2022 |  |  |  | 0.078047 | Firm | 0.078047
| 786 | CCC Bhusawal - OTHER MISC | Providing housekeeping services for chummery for project staff at Deepnagar, Bhusawal (PO NO - 4500118114) | DCB | 4 | 09.03.2022 |  |  |  | 0.051088 | Firm | 0.051088
| 787 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private A.C. Taxi (i.e Amaze/Dezire/Aspire/equivalent Sedan Car) along with driver and required fuel for Superintending Engineer (C) at 1x660 MW repln. Project Site at Deepnagar. Bhusawal (PO NO - 4500118116) | DCB | 3 | 16.03.2022 |  |  |  | 0.079519 | Firm | 0.079519
| 788 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private A.C. Taxi (i.e Maruti/Ertiga/Mahindra XUV 700/Hyundai Alcazar/ MG Hector plus/ Kia cornival equivalent Sedan Car) along with driver and required fuel for Dy. C.E. (C) at 1x660 MW repln. Project Site at Deepnagar. Bhusawal (PO NO - 4500118270) | DCB | 2 | 16.03.2022 |  |  |  | 0.08359 | Firm | 0.08359
| 789 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance as a computer operator for preparation data for SAP & SRM syatem in the office of the civil construction circle, Deepnagar, Bhusawal (PO NO - 4500118440) | DCB | 3 | 25.03.2022 |  |  |  | 0.039688 | Firm | 0.039688
| 790 | CCC Bhusawal - OTHER MISC | Plumbing of Sanitary works of Tapi rest house at Deepnagar Bhusawal (PO NO - 4500118515) | DCB | 3 | 31.03.2022 |  |  |  | 0.011098 | Firm | 0.011098
| 791 | CCC Bhusawal - ESTABLISHMENT | Providing & instalation of mobile network signal booster at civil construction circle at BTPS Deepnagar. (PO NO - 4500118109) | DCB | 3 | 31.03.2022 |  |  |  | 0.022638 | Firm | 0.022638
| 792 | CCC Bhusawal - OTHER MISC | Work of diversion of agriculture pipeline in MJP water line to village khadka At 1x660 MW railway siding area under CCC, at Deepnagar, Bhusawal. (PO NO - 4500118711) | DCB | 4 | 31.03.2022 |  |  |  | 0.023479 | Firm | 0.023479
| 793 | CCC Bhusawal - OTHER MISC | Work of Brick Wall (Hedging) at entry of Tapi Rest House BTPS Deepnagar, Bhusawal (PO NO - 4500118777) | DCB | 4 | 01.04.2022 |  |  |  | 0.023578 | Firm | 0.023578
| 794 | CCC Bhusawal - OTHER MISC | Providing 300mm dia RCC for laying pipline of farmers near Railway Br. No. 15 in 1x660 MW Railway Siding area undre C.C.C., Deepnagar, Bhusawal (PO NO - 4500118789) | DCB | 4 | 01.04.2022 |  |  |  | 0.0233 | Firm | 0.0233
| 795 | CCC Bhusawal - ESTABLISHMENT | Providing & fixing of carpet & Verticle blinds at Dy. C.E., S.E., & E.E. Admin Cabin at Civil Construction circle at Deepnagar, Bhusawal (PO NO - 4500118436) | DCB | 4 | 07.04.2022 |  |  |  | 0.023109 | Firm | 0.023109
| 796 | CCC Bhusawal - OTHER MISC | Transporation of rail sleepers stocked at proposed ROB pier No. 4 (Abutment of 1x660 MW Railway siding at Deepnagar, Bhusawal (PO NO - 4500118794) | DCB | 3 | 20.04.2022 |  |  |  | 0.022659 | Firm | 0.022659
| 797 | CCC Bhusawal - OTHER MISC | Repairing of 'PA' - Type Project Quarters for Superintending Engineer (C), 1x660 MW Project at BTPS, Deepnagar, Bhusawal (PO NO - 4500118877) | DCB | 4 | 26.04.2022 |  |  |  | 0.0233 | Firm | 0.0233
| 798 | CCC Bhusawal - ESTABLISHMENT | Annual maintenance servicing checking network administration & troubles shooting of network hardware system at 1X660 MW (PO NO - 4500118871) | - | 1 | 02.05.2022 |  |  |  | 0.0031591 | Firm | 0.0031591
| 799 | CCC Bhusawal - ESTABLISHMENT | Providing 10 MBPS(1:1) inter net leased line conectivity at CCC 1X660MW Period 8/10/2021 to 7/11/2021 (PO NO - 4500118870) | - | 1 | 02.05.2022 |  |  |  | 0.0034796 | Firm | 0.0034796
| 800 | CCC Bhusawal - ESTABLISHMENT | Rejuvenation of Cabin of the S.E. (Civil) Deepnagar Bhusawal. (PO NO - 4500119269) | DCB | 5 | 02.05.2022 |  |  |  | 0.022307 | Firm | 0.022307
| 801 | CCC Bhusawal - OTHER MISC | Providing of erecting GI chainlink fencing of 1.60 m hight from 2X500 MW Gate to purna rest house gate at Deepnagar Bhusawal. (PO NO - 4500119271) | DCB | 3 | 02.05.2022 |  |  |  | 0.023515 | Firm | 0.023515
| 802 | CCC Bhusawal - ESTABLISHMENT | Prepairation of area in view of 75th Republic Day 26th Jan 2022 for Flag hoisting cerermony at project office Deepangar (PO NO - 4500119303) | - | 1 | 02.05.2022 |  |  |  | 0.020881 | Firm | 0.020881
| 803 | CCC Bhusawal - OTHER MISC | Work of construction shed for DEMD at 1X660 MW project office gate of misc work at main project gate at Deepnagar (PO NO - 4500119270) | DCB | 4 | 02.05.2022 |  |  |  | 0.021073 | Firm | 0.021073
| 804 | CCC Bhusawal - OTHER MISC | Removing dense, bushes & grass along boundary wall of 1X660 MW project at BTPS Deepangar, Bhusawal. (PO NO - 4500119267) | DCB | 4 | 02.05.2022 |  |  |  | 0.019989 | Firm | 0.019989
| 805 | CCC Bhusawal - OTHER MISC | Work of shifting of farmers pipeline at Gat No. 278 fouling in railway bridge No. 16 at 1X660 MW Railway siding area under CCC, Deepnagar, Bhusawal. (PO NO - 4500119268) | DCB | 3 | 02.05.2022 |  |  |  | 0.023428 | Firm | 0.023428
| 806 | CCC Bhusawal - OTHER MISC | Work of fabrication and erection of structural steel staircase at Tapi rest house Deepnagar, Bhusawal. (PO NO - 4500118878) | DCB | 3 | 02.05.2022 |  |  |  | 0.018537 | Firm | 0.018537
| 807 | CCC Bhusawal - ESTABLISHMENT | Providing unskilled assistance for sweeping work at Civil Construction Circle, Deepnagar (PO NO - 4500119333) | DCB | 5 | 02.05.2022 |  |  |  | 0.022545 | Firm | 0.022545
| 808 | CCC Bhusawal - OTHER MISC | Providing & fixing new 5HP pump in existing open well for water supply at 660MW gate security cabin at Deepnagar, Bhusawal. (PO NO - 4500119348) | DCB | 5 | 04.05.2022 |  |  |  | 0 | Firm | 0
| 809 | CCC Bhusawal - OTHER MISC | Work of locating & repairing of 100 mm construction water supply pipeline for 1X660 MW Project site Deepnagar. (PO NO - 4500119349) | DCB | 3 | 04.05.2022 |  |  |  | 0.017535 | Firm | 0.017535
| 810 | CCC Bhusawal - OTHER MISC | Work of water proffing and other misc work at 33/11KV Substation at BTPS Deepnagar, Bhusawal. (PO NO - 4500119328) | DCB | 4 | 04.05.2022 |  |  |  | 0.011027 | Firm | 0.011027
| 811 | CCC Bhusawal - ESTABLISHMENT | Providing & fixing of zebrablinds to doors windows along with floor carpet at all EE Divisions cabin Civil Construction Circle Deepnagar, Bhusawal. (PO NO - 4500119359) | DCB | 4 | 05.05.2022 |  |  |  | 0.023211 | Firm | 0.023211
| 812 | CCC Bhusawal - OTHER MISC | Providing & fixing RCC Covers over drain in the premises of project office complex at 1X660 MW replacement project Deepnagar, Bhusawal. (PO NO - 4500119347) | DCB | 4 | 05.05.2022 |  |  |  | 0.021497 | Firm | 0.021497
| 813 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC Taxi (i.e., Maruti Eritga / Maruti Dizire / XL6 or equivalent) along with driver & fuel for CCC at 1X660 MW replacement project CCC at Deepnagar. (PO NO - 4500119346) | DCB | 4 | 05.05.2022 |  |  |  | 0.023476 | Firm | 0.023476
| 814 | CCC Bhusawal - ESTABLISHMENT | Providing services of unskilled assistance for day to day office work for civil construction Div-III at New project office shed bhusawal. (PO NO - 4500119329) | DCB | 4 | 06.05.2022 |  |  |  | 0.022544 | Firm | 0.022544
| 815 | CCC Bhusawal - ESTABLISHMENT | Hiring services of skilled as computer typist at account section civil construction Circle, Deepnagar, Bhusawal. (PO NO - 4500119331) | DCB | 4 | 06.05.2022 |  |  |  | 0.019844 | Firm | 0.019844
| 816 | CCC Bhusawal - OTHER MISC | Repairing of approch road of railway Br. No.8B of 2X500 MW Railway Siding at Deepnagar Bhusawal (PO NO - 4500119453) | DCB | 5 | 10.05.2022 |  |  |  | 0.021893 | Firm | 0.021893
| 817 | CCC Bhusawal - OTHER MISC | Providing unskilled assistance for monitoring of curing at 1X660 MW Replacement Unit CCC, Deepnagar, Bhusawal. (PO NO - 4500119454) | DCB | 4 | 10.05.2022 |  |  |  | 0.022571 | Firm | 0.022571
| 818 | CCC Bhusawal - OTHER MISC | Providing sliding gate at 660 MW Project gate, Deepnagar, Bhusawal. (PO NO - 4500119451) | DCB | 3 | 10.05.2022 |  |  |  | 0.013246 | Firm | 0.013246
| 819 | CCC Bhusawal - OTHER MISC | Providing Technical Assistance (Civil Supervisor) for site supervision at Chimney area 1X660 MW Project, Deepnagar, Bhusawal. (PO NO - 4500119426) | DCB | 12 | 10.05.2022 |  |  |  | 0.04802 | Firm | 0.04802
| 820 | CCC Bhusawal - OTHER MISC | Work of repairing/ replacing PVC sewage pipeline at temporary project quarters at Deepnagar, Bhusawal. (PO NO - 4500119490) | DCB | 3 | 12.05.2022 |  |  |  | 0.022681 | Firm | 0.022681
| 821 | CCC Bhusawal - OTHER MISC | Providing & erecting barbed wire fencing anti-climbing arrangement around 1x660 MW project office complex, BTPS, Deepnagar, Bhusawal. (PO NO - 4500119428) | DCB | 4 | 19.05.2022 |  |  |  | 0.020554 | Firm | 0.020554
| 822 | CCC Bhusawal - ESTABLISHMENT | Hiring of Desert coolers during summer season for 1x660 MW Civil Construction Circle, and its allied Divisions/ sections, Deepnagar, Bhusawal. (PO NO - 4500119509) | DCB | 3 | 19.05.2022 |  |  |  | 0.017794 | Firm | 0.017794
| 823 | CCC Bhusawal - ESTABLISHMENT | Work of servicing & maintenance of computers & printers under Civil Construction Circle, Deepnagar, Bhusawal. (PO NO - 4500119536) | DCB | 4 | 19.05.2022 |  |  |  | 0.016541 | Firm | 0.016541
| 824 | CCC Bhusawal - OTHER MISC | Pothole repairing & surface coating of colony road Deepnagar, Bhusawal (PO NO - 4500119558) | DCB | 3 | 19.05.2022 |  |  |  | 0.69626 | Firm | 0.69626
| 825 | CCC Bhusawal - ESTABLISHMENT | Repairing of renovation of existing ladies tiolet at Civil Construction Circle BTPS Deepnagar. (PO NO - 4500119611) | DCB | 4 | 30.05.2022 |  |  |  | 0.013086 | Firm | 0.013086
| 826 | CCC Bhusawal - OTHER MISC | Providing 300 mm dia RCC pipe below 1x660 MW railway siding area for laying or farmer pipe line unde civil construction circle deepnagar. (PO NO - 4500119562) | DCB | 3 | 30.05.2022 |  |  |  | 0.0233 | Firm | 0.0233
| 827 | CCC Bhusawal - OTHER MISC | Work Providing of fixing RCC cover open drain adjucent to bulkar road up to project office road deepnagar. (PO NO - 4500119702) | DCB | 4 | 31.05.2022 |  |  |  | 0.01115 | Firm | 0.01115
| 828 | CCC Bhusawal - OTHER MISC | Diversion of underground PVC agricluture water supply pipeline falling along with route of retaining wall at bhogavati river in (GATM0295) at shri Pitamber Patil in Village Pimprisekam Bhusawal. (PO NO - 4500119689) | DCB | 3 | 31.05.2022 |  |  |  | 0.012626 | Firm | 0.012626
| 829 | CCC Bhusawal - OTHER MISC | Work of providing painting to existing chainlink fencing at project office complex Deepnagar, Bhusawal. (PO NO - 4500119687) | DCB | 3 | 31.05.2022 |  |  |  | 0.01274 | Firm | 0.01274
| 830 | CCC Bhusawal - ROAD OUTSIDE BOUNDRY | Maintenance of resurfacing of existing BT road along 1*600 MW boundary from NH-6 to Bhagvati river for village pimprisekam at Deepnagar. (PO NO - 4500119729) | DCB | 3 | 02.06.2022 |  |  |  | 0.58267 | Firm | 0.58267
| 831 | CCC Bhusawal - OTHER MISC | Work of External painting to temporary project gtrs PD-3, PD-4 and PE-5 to PE-9 at Deepnagar (PO NO - 4500119685) | DCB | 3 | 02.06.2022 |  |  |  | 0.020591 | Firm | 0.020591
| 832 | CCC Bhusawal - ESTABLISHMENT | Work of repair and maintenance of aluminium partation on as when required basis at various division/section in project office complex at BTPS Deepnagar Bhusawal. (PO NO - 4500119563) | DCB | 4 | 03.06.2022 |  |  |  | 0.022817 | Firm | 0.022817
| 833 | CCC Bhusawal - ESTABLISHMENT | Work of Internal painting to project Quters on as when required basis at Deepnagar Bhusawal. (PO NO - 4500119701) | DCB | 4 | 03.06.2022 |  |  |  | 0.022963 | Firm | 0.022963
| 834 | CCC Bhusawal - ESTABLISHMENT | Supply of 07 Nos Airconditioners 1.5 Tone capicity for cabin of Dy.C.E.(C)S.E(C) & E.E(C) at 1*660MW xplacement project Deepnagar Bhusawal. (PO NO - 4500119754) | DCB | 3 | 07.06.2022 |  |  |  | 0.02448 | Firm | 0.02448
| 835 | CCC Bhusawal - ESTABLISHMENT | Providing Servises of skilled assistsnce (oriuer) for depatmental Vehicle MH-19-6942 for office for the C.C.C. Deepnagar. (PO NO - 4500119781) | - | 1 | 07.06.2022 |  |  |  | 0.0031669 | Firm | 0.0031669
| 836 | CCC Bhusawal - OTHER MISC | Work of removing grass along chain link fencing of 2*500MW railway line for BR-17+0. Existing compund wall near BR-18 of inside peripheral of 1*660MW project site compound wall at BTPS Deepnagar. (PO NO - 4500119613) | DCB | 5 | 10.06.2022 |  |  |  | 0.01685 | Firm | 0.01685
| 837 | CCC Bhusawal - OTHER MISC | Work of plain cement concrete behind VIP suites at left side of Tapi rest house Deepnagar Bhusawal. (PO NO - 4500119819) | DCB | 5 | 13.06.2022 |  |  |  | 0.022921 | Firm | 0.022921
| 838 | CCC Bhusawal - OTHER MISC | Day to day Civil maintenance work of project staff quarters at Deepnagar, Bhusawal. (PO NO - 4500118299) | DCB | 8 | 17.06.2022 |  |  |  | 0.13517 | Firm | 0.13517
| 839 | CCC Bhusawal - OTHER MISC | Work of tree plantation along both side of pimprisekam road (PO NO - 4500120312) | DCB | 5 | 22.07.2022 |  |  |  | 0.022892 | Firm | 0.022892
| 840 | CCC Bhusawal - OTHER MISC | Work of silt removes & construction of coffer dam in 500 MW old inlet canal near abandoned pump house at BTPS Deepnagar. (PO NO - 4500120010) | DCB | 4 | 22.07.2022 |  |  |  | 0.023457 | Firm | 0.023457
| 841 | CCC Bhusawal - ESTABLISHMENT | Work of Internal & External Painting along with other misc work of project canteen at 1x660 MW Project Office, Deepnagar. (PO NO - 4500120320) | DCB | 4 | 27.07.2022 |  |  |  | 0.012893 | Firm | 0.012893
| 842 | CCC Bhusawal - ESTABLISHMENT | Annual maintenance contract of painting and related work for 26 jan, 15 aug and other required event, 1 x 660 MW CCC, Deepnagar, Bhusawal. (PO NO - 4500120612) | DCB | 5 | 08.08.2022 |  |  |  | 0.022759 | Firm | 0.022759
| 843 | CCC Bhusawal - ESTABLISHMENT | Maintenance of garden in front of temporary project quarters at, BTPS, Deepnagar,Bhusawal. (PO NO - 4500120596) | DCB | 4 | 08.08.2022 |  |  |  | 0.022971 | Firm | 0.022971
| 844 | CCC Bhusawal - OTHER MISC | Work of shifting of rail sleepers fouling in the alignment of proposed ROB embankment of 1 x 660 MW Railway siding at Deepnagar, Bhusawal. (PO NO - 4500120594) | DCB | 4 | 08.08.2022 |  |  |  | 0.023417 | Firm | 0.023417
| 845 | CCC Bhusawal - OTHER MISC | Work of removing dense shrubs, weeds & grass along Pimprisekam road (PO NO - 4500120649) | DCB | 6 | 10.08.2022 |  |  |  | 0.023146 | Firm | 0.023146
| 846 | CCC Bhusawal - OTHER MISC | Work of construction of pipe culvert on Fulgaon side patrolling road along 2x500 MW Railway siding, Deepnagar, Bhusawal. (PO NO - 4500120652) | DCB | 3 | 10.08.2022 |  |  |  | 0.023418 | Firm | 0.023418
| 847 | CCC Bhusawal - ESTABLISHMENT | Hiring of private diesel Taxi car/jeep (i.e., Mahindra TUV 300 / Tata Indica /Bolero/ Tata Sumo) along with driver & diesel for Executive Engineer (C), CCD-I, MSPGCL, Bhusawal. (PO NO - 4500120690) | DCB | 3 | 10.08.2022 |  |  |  | 0.094797 | Firm | 0.094797
| 848 | CCC Bhusawal - OTHER MISC | Work of removing dense, grass, shrubs weeds on as when required basis around project office Deepnagar Bhusawal. (PO NO - 4500120564) | DCB | 3 | 17.08.2022 |  |  |  | 0.032072 | Firm | 0.032072
| 849 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC Taxi (i.e., Swift Dezire/ ford aspire or equivalent) along with driver & disel required for E.E. (C),CCD-III, Bhusawal. (PO NO - 4500120825) | DCB | 3 | 18.08.2022 |  |  |  | 0.060302 | Firm | 0.060302
| 850 | CCC Bhusawal - OTHER MISC | Providing Technical Assistance (Civil Supervisor) for site supervision at NDCT area 1X660 MW Project, Deepnagar, Bhusawal. (PO NO - 4500120628) | DCB | 3 | 18.08.2022 |  |  |  | 0.038959 | Firm | 0.038959
| 851 | CCC Bhusawal - OTHER MISC | Providing & Fixing aluminium partitions at chemical lab building for the office purpose of 1x660 MW project Deepnagar, Bhusawal. (PO NO - 4500120866) | DCB | 4 | 19.08.2022 |  |  |  | 0.093923 | Firm | 0.093923
| 852 | CCC Bhusawal - OTHER MISC | Providing Execative office table or & revolving chair at Civil Construction Circle Division - III at Deepnagar. (PO NO - 4500120648) | - | 1 | 19.08.2022 |  |  |  | 0.0032582 | Firm | 0.0032582
| 853 | CCC Bhusawal - ESTABLISHMENT | Hiring of private A.C. Taxii.e. (Amaze/Desire/Aspire/equivalent sedan car) along with driver & required fuel for E.E.(C) CCC, Bhusawal. (PO NO - 4500120932) | DCB | 3 | 26.08.2022 |  |  |  | 0.086047 | Firm | 0.086047
| 854 | CCC Bhusawal - OTHER MISC | Providing Supervisor for site supervision at Railway siding area at 1x660 MW Project Deepnagar, Bhusawal. (PO NO - 4500120857) | DCB | 5 | 26.08.2022 |  |  |  | 0.018244 | Firm | 0.018244
| 855 | CCC Bhusawal - OTHER MISC | Work of water proffing at terrace of the type-II building no.2 at BTPS Deepnagar. (PO NO - 4500120889) | DCB | 4 | 26.08.2022 |  |  |  | 0.023481 | Firm | 0.023481
| 856 | CCC Bhusawal - OTHER MISC | Constructin of cofferdam & return to canal for construction water supply at 1x660 MW Project site Deepnagar, Bhusawal. (PO NO - 4500120887) | DCB | 5 | 26.08.2022 |  |  |  | 0.023352 | Firm | 0.023352
| 857 | CCC Bhusawal - ESTABLISHMENT | Providing assistance for maintening water supply in project office premises at BTPS Deepnagar. (PO NO - 4500120884) | DCB | 4 | 26.08.2022 |  |  |  | 0.023415 | Firm | 0.023415
| 858 | CCC Bhusawal - ESTABLISHMENT | Providing Execative chair for Execative Engineer(C) CCD-I BTPS Deepnagar. (PO NO - 4500120930) | - | 1 | 26.08.2022 |  |  |  | 0.0022418 | Firm | 0.0022418
| 859 | CCC Bhusawal - OTHER MISC | Providing brick work cheek dam & cleaining of approch sump near ashbund pump house (PO NO - 4500120886) | DCB | 5 | 02.09.2022 |  |  |  | 0.3523 | Firm | 0.3523
| 860 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC Taxi i.e (Desire/Amaze/Aspire/equivalent sedam car) along with driver of reqired fuel for E.E. (C) -Div-ll at CCC, Bhusawal. (PO NO - 4500120892) | DCB | 3 | 02.09.2022 |  |  |  | 0.082857 | Firm | 0.082857
| 861 | CCC Bhusawal - ESTABLISHMENT | Annaul maintenance, servicing cheking network administration & trouble shooting of network hardware system at 1x660MW, CCC, MSPGCL, Bhusawal. (PO NO - 4500121178) | - | 1 | 07.09.2022 |  |  |  | 0.0026722 | Firm | 0.0026722
| 862 | CCC Bhusawal - ESTABLISHMENT | Providing 10MBPS (1:1) internet leased line connectivity at civil construction circle, 1x660MW Deepnagar, Bhusawal. (PO NO - 4500121175) | - | 1 | 07.09.2022 |  |  |  | 0.0029488 | Firm | 0.0029488
| 863 | CCC Bhusawal - ESTABLISHMENT | Providing 10MBPS (1:1) internet leased line connectivity at civil construction circle, 1x660MW Deepnagar, Bhusawal. (PO NO - 4500121174) | - | 1 | 07.09.2022 |  |  |  | 0.0029488 | Firm | 0.0029488
| 864 | CCC Bhusawal - ESTABLISHMENT | Providing 10MBPS (1:1) internet leased line connectivity at civil construction circle, 1x660MW Deepnagar, Bhusawal. (PO NO - 4500121177) | - | 1 | 07.09.2022 |  |  |  | 0.0058976 | Firm | 0.0058976
| 865 | CCC Bhusawal - OTHER MISC | Work of plantation of ornamental plants & their maintenance from 500MW gate to project office road divider at Deepnagar, Bhusawal. (PO NO - 4500121164) | DCB | 4 | 07.09.2022 |  |  |  | 0.023068 | Firm | 0.023068
| 866 | CCC Bhusawal - OTHER MISC | Work of removing grass, thorny, shrubs along 1 x 660 MW Project inside boundary at BTPS, Deepnagar, Bhusawal. (PO NO - 4500121165) | DCB | 4 | 07.09.2022 |  |  |  | 0.020735 | Firm | 0.020735
| 867 | CCC Bhusawal - OTHER MISC | Work of Maintenance of kitchen trolleys on as and when required basis for project quarters at BTPS colony, Deepnagar, Bhusawal. (PO NO - 4500121181) | DCB | 3 | 07.09.2022 |  |  |  | 0.023288 | Firm | 0.023288
| 868 | CCC Bhusawal - ESTABLISHMENT | Work of internal painting to project office divisions at Deepnagar, Bhusawal. (PO NO - 4500121166) | DCB | 4 | 07.09.2022 |  |  |  | 0.023451 | Firm | 0.023451
| 869 | CCC Bhusawal - OTHER MISC | Providing services of unskilled assistance for sweeping and cleaning of wosh rooms of security cabins at 1x660 MW Project gate, near BHEL office and near project office gate at BTPS, Deepnagar, Bhusawal. (PO NO - 4500121217) | DCB | 3 | 09.09.2022 |  |  |  | 0.023332 | Firm | 0.023332
| 870 | CCC Bhusawal - OTHER MISC | Work of Construction of toilet for security cabin at secondory entance gate of 1x660 MW at BTPS, deepnagar, Bhusawal. (PO NO - 4500121269) | DCB | 4 | 13.09.2022 |  |  |  | 0.013505 | Firm | 0.013505
| 871 | CCC Bhusawal - OTHER MISC | Providing unskilled assistance for monitoring of curring at 1x660 MW Replacemant Unit CCC, Deepnagar, Bhusawal. (PO NO - 4500121282) | DCB | 4 | 14.09.2022 |  |  |  | 0.023194 | Firm | 0.023194
| 872 | CCC Bhusawal - ESTABLISHMENT | Providing Services of unskilled assistance for sweeping work at CCC, Deepnagar, Bhusawal. (PO NO - 4500121283) | DCB | 4 | 14.09.2022 |  |  |  | 0.022545 | Firm | 0.022545
| 873 | CCC Bhusawal - ESTABLISHMENT | Providing & fixing mosquito proof mesh to windows of civil division office at Deepnagar, Bhusawal. (PO NO - 4500121284) | DCB | 6 | 14.09.2022 |  |  |  | 0.016726 | Firm | 0.016726
| 874 | CCC Bhusawal - ESTABLISHMENT | Work of repairing & strengthing of RCC parapet wall of Type II Qtr's at Deepnagar, Bhusawal. (PO NO - 4500121289) | DCB | 4 | 16.09.2022 |  |  |  | 0.0227 | Firm | 0.0227
| 875 | CCC Bhusawal - ESTABLISHMENT | Providing 10 MBPS(1:1) inter net leased line conectivity at CCC 1X660MW Deepnagar, Bhusawal. (PO NO - 4500121288) | DCB | 3 | 16.09.2022 |  |  |  | 0.011795 | Firm | 0.011795
| 876 | CCC Bhusawal - OTHER MISC | Work of water proffing before onset of mansoon to temporary of Type-II project quarter at Deepnagar, Bhusawal. (PO NO - 4500121292) | DCB | 4 | 16.09.2022 |  |  |  | 0.023175 | Firm | 0.023175
| 877 | CCC Bhusawal - OTHER MISC | Providing or fixing masquito jali aluminium doors to project quarters at BTPS Deepnagar, Bhusawal. (PO NO - 4500121480) | DCB | 6 | 28.09.2022 |  |  |  | 0.019492 | Firm | 0.019492
| 878 | CCC Bhusawal - OTHER MISC | Work of repairing chain link fencing & UCR masonry & deweeding at tapi guest house deepnagar, bhusawal. (PO NO - 4500121968) | DCB | 4 | 18.10.2022 |  |  |  | 0.022928 | Firm | 0.022928
| 879 | CCC Bhusawal - OTHER MISC | Work of providing & fixing of HDPE container of 2000 liters capacity supplying water to general toilet of Civil Project Circle office at Deepnagar. (PO NO - 4500121965) | - | 4 | 18.10.2022 |  |  |  | 0.002714 | Firm | 0.002714
| 880 | CCC Bhusawal - OTHER MISC | Carring out total station survey and quantity estimation of 210 MW and 2X500 MW ash bund near village at BTPS, Bhusawal. (PO NO - 4500121967) | DCB | 3 | 18.10.2022 |  |  |  | 0.013067 | Firm | 0.013067
| 881 | CCC Bhusawal - ESTABLISHMENT | Hiring of private Ac taxi (i.e. Sedan/ SUV) along with driver and fuel for Civil Consultant at 1X660 MW Repl. Project CCC, Deepnagar, Bhusawal. (PO NO - 4500122046) | DCB | 5 | 18.10.2022 |  |  |  | 0.077359 | Firm | 0.077359
| 882 | CCC Bhusawal - ESTABLISHMENT | Hiring of private taxi along with driver & required fuel for EE (C)-II at 1x660 MW Repl. Unit Deepnagar, Bhusawal (PO NO - 4500122199) | - | 1 | 21.10.2022 |  |  |  | 0.0029453 | Firm | 0.0029453
| 883 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance (Driver) for departmental vehicle MH-40-A-8027 for office of the CCC, Deepnagar, Bhusawal. (PO NO - 4500122201) | DCB | 3 | 27.10.2022 |  |  |  | 0.041738 | Firm | 0.041738
| 884 | CCC Bhusawal - ESTABLISHMENT | Providing Technical assistance (Civil Supervisor) & Skilled assistance for AHP structure, 13 KM Ash Disposal pipeline (ADPL) & CSR work (Phase-I, 12 Village) of 1X660 MW Project, Deepnagar, Bhusawal. (PO NO - 4500122205) | DCB | 7 | 27.10.2022 |  |  |  | 0.042056 | Firm | 0.042056
| 885 | CCC Bhusawal - ESTABLISHMENT | Supply of stationary for civil construction circle division MSPGCL Bhusawal. (PO NO - 4500121434) | DCB | 4 | 03.11.2022 |  |  |  | 0.023285 | Firm | 0.023285
| 886 | CCC Bhusawal - ESTABLISHMENT | Hiring services of skilled as computer Operator at account section civil construction Circle, Deepnagar, Bhusawal. (PO NO - 4500122330) | DCB | 4 | 03.11.2022 |  |  |  | 0.020958 | Firm | 0.020958
| 887 | CCC Bhusawal - ESTABLISHMENT | Annual work contract of Video Shooting and Photography for 1x660 MW project under civil construction circle, Deepnagar, Bhusawal (PO NO - 4500122440) | DCB | 2 | 09.11.2022 |  |  |  | 0.04779 | Firm | 0.04779
| 888 | CCC Bhusawal - ESTABLISHMENT | Praparation of an estimate for fire fighting system for proposed CD and E-type residential bulding through consultant Deepnagar, Bhusawal (PO NO - 4500122461) | - | 1 | 15.11.2022 |  |  |  | 0 | Firm | 0
| 889 | CCC Bhusawal - ESTABLISHMENT | Work of clearing the clocks from underground drinage line including inspection chamber for project office and project Qtr's at BTPS Deepnagar, Bhusawal (PO NO - 4500122591) | DCB | 4 | 16.11.2022 |  |  |  | 0.02255 | Firm | 0.02255
| 890 | CCC Bhusawal - ESTABLISHMENT | Work of waterproffing to project officer's Cabin attach Toilet slab at Deepnagar, Bhusawal (PO NO - 4500122719) | DCB | 3 | 23.11.2022 |  |  |  | 0.019086 | Firm | 0.019086
| 891 | CCC Bhusawal - ESTABLISHMENT | Providing 10 MBPS (1:1) Internet Leased Line Connectivity at Civil Construction Circle 1x660 MW Deepnagar, Bhusawal (Period for Dt. 23/08/2022 to Dt. 22/09/2022) (PO NO - 4500122755) | - | 1 | 24.11.2022 |  |  |  | 0 | Firm | 0
| 892 | CCC Bhusawal - ESTABLISHMENT | Work of sevicing & maintenace of computers & printers under civil construction circle, Deepnagar, Bhusawal. (PO NO - 4500122993) | DCB | 4 | 06.12.2022 |  |  |  | 0.023444 | Firm | 0.023444
| 893 | CCC Bhusawal - OTHER MISC | Work of Supplying Clean Water by Tanker for Trees Planted along Pimprisekam road at Deepnagar, Bhusawal. (PO NO - 4500123272) | DCB | 3 | 29.12.2022 |  |  |  | 0.044168 | Firm | 0.044168
| 894 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistance (Driver) for departmental vehicle MH-19-AE-6942 for office of the CCC, Deepnagar, Bhusawal. (PO NO - 4500123260) | DCB | 4 | 29.12.2022 |  |  |  | 0.044819 | Firm | 0.044819
| 895 | CCC Bhusawal - ESTABLISHMENT | Providing services of unskilled assistance for day to day menial / petty work for Civil Construction Division No. III at new project office shed BTPS Deepnagar, Bhusawal (PO NO - 4500123303) | DCB | 5 | 05.01.2023 |  |  |  | 0.018426 | Firm | 0.018426
| 896 | CCC Bhusawal - ESTABLISHMENT | Providing Diesel Taxi (Bolero/New Mahindra TUV SUV or equivalents)along with Driver & Diesel required for CSR work at CCD-III MSPGCL, Deepnagar, Bhusawal. (PO NO - 4500123442) | DCB | 3 | 12.01.2023 |  |  |  | 0.023005 | Firm | 0.023005
| 897 | CCC Bhusawal - OTHER MISC | Providing Pump Operator for Operating Pumps at Pump House Outlet Canal at BTPS to Supply Raw Water for on poing of 1x660 MW Proj. Deepnagar, Bhusawal. (PO NO - 4500123436) | DCB | 3 | 16.01.2023 |  |  |  | 0.073819 | Firm | 0.073819
| 898 | CCC Bhusawal - ESTABLISHMENT | Providing & laying RCC Pipe on Service road near BR. No.-15 of 1x660 MW Reailway Siding at Deepnagar, Bhusawal. (PO NO - 4500123441) | DCB | 4 | 16.01.2023 |  |  |  | 0.020543 | Firm | 0.020543
| 899 | CCC Bhusawal - OTHER MISC | Work of Construction of Pipe Culvert on Railway side road near L.C. gate Pimprisekam at Deepnagar, Bhusawal. (PO NO - 4500123440) | DCB | 4 | 16.01.2023 |  |  |  | 0.023181 | Firm | 0.023181
| 900 | CCC Bhusawal - OTHER MISC | Providing Tech-Assistance (Civil Supervisor) for Supervision at CHP, FGD & Allied Structure 1x660 MW Project Deepnagar, Bhusawal. (PO NO - 4500123420) | DCB | 3 | 17.01.2023 |  |  |  | 0.085434 | Firm | 0.085434
| 901 | CCC Bhusawal - ESTABLISHMENT | Work of Soil Investigation for proposed Residential Building at 1x660 MW replacement Project, Civil Construction Circle, at Deepnagar, Bhusawal. (PO NO - 4500123492) | DCB | 6 | 17.01.2023 |  |  |  | 0.043694 | Firm | 0.043694
| 902 | CCC Bhusawal - ESTABLISHMENT | Work of Providing Office Assistance at office of the Dy. Chief Engineer (C), Civil Construction Circle, 1x660 MW, Deepnagar, Bhusawal. (PO NO - 4500123421) | DCB | 5 | 18.01.2023 |  |  |  | 0.17345 | Firm | 0.17345
| 903 | CCC Bhusawal - ESTABLISHMENT | Work of Providing Office Assistance at office of the Dy. Chief Engineer (C), Civil Construction Circle, 1x660 MW, Deepnagar, Bhusawal. (PO NO - 4500123423) | DCB | 5 | 18.01.2023 |  |  |  | 0.17345 | Firm | 0.17345
| 904 | CCC Bhusawal - ESTABLISHMENT | Work of Providing Office Assistance at office of the Dy. Chief Engineer (C), Civil Construction Circle, 1x660 MW, Deepnagar, Bhusawal. (PO NO - 4500123422) | DCB | 5 | 18.01.2023 |  |  |  | 0.17345 | Firm | 0.17345
| 905 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC Taxi (i.e. Desire, Amaze, Aspire, or equivalent Sedan Car) along with Driver & required Fuel for Superintending Engineer (C), at 1x660 MW project C. C. C. Deepnagar, Bhusawal. (PO NO - 4500123410) | DCB | 3 | 18.01.2023 |  |  |  | 0.08536 | Firm | 0.08536
| 906 | CCC Bhusawal - OTHER MISC | Providing unskilled assistance for monitoring of curing at 1X660 MW Replacement Unit CCC, Deepnagar, Bhusawal. (PO NO - 4500123609) | DCB | 3 | 25.01.2023 |  |  |  | 0.021059 | Firm | 0.021059
| 907 | CCC Bhusawal - ESTABLISHMENT | Work of providing furniture in visitor room at office of Chief Engineer (P), 1x660 MW project office. (PO NO - 4500123633) | DCB | 4 | 27.01.2023 |  |  |  | 0.023571 | Firm | 0.023571
| 908 | CCC Bhusawal - OTHER MISC | Work of removing existing Coffer Dam & Cleaning of Canal as an when required near intake Water Pump House BTPS, Deepnagar, Bhusawal. (PO NO - 4500123611) | DCB | 4 | 31.01.2023 |  |  |  | 0.022814 | Firm | 0.022814
| 909 | CCC Bhusawal - ESTABLISHMENT | Providing 15 Mbps (1:1) Internet Leased Line Connectivity at Civil Construction Circle , 1x660 MW Deepnagar, Bhusawal. (PO NO - 4500123723) | DCB | 3 | 03.02.2023 |  |  |  | 0.035386 | Firm | 0.035386
| 910 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC taxi (i.e. Amaze/Dezire/Mahindra Boloero/TUV) or equivalent along with Driver and required Fuel for Dy. CE (C) at 1x660 MW Replacement Prject, Civil Construction Circle, at Deepnagar, Bhusawal. (PO NO - 4500123709) | DCB | 3 | 03.02.2023 |  |  |  | 0.085194 | Firm | 0.085194
| 911 | CCC Bhusawal - CONSULTANCY | Engaging expert services for SAP reconcilation for final accounting wor for FY 22-23 Deepnagar, Bhusawal (PO NO - 4500123807) | DCB | 4 | 08.02.2023 |  |  |  | 0.0354 | Firm | 0.0354
| 912 | CCC Bhusawal - OTHER MISC | Work of removing grass, thorny, shrubs along 1 x 660 MW Project inside boundary at BTPS, Deepnagar, Bhusawal. (PO NO - 4500123820) | DCB | 5 | 14.02.2023 |  |  |  | 0.048148 | Firm | 0.048148
| 913 | CCC Bhusawal - OTHER MISC | Work of internal painting to project quarters of (ECP) BM, PD & PE ect BTPS Deepnagar. (PO NO - 4500123822) | DCB | 3 | 14.02.2023 |  |  |  | 0.023288 | Firm | 0.023288
| 914 | CCC Bhusawal - OTHER MISC | Work of removing grass, dense, shrubs, along canal road & Pimprisekam road (PO NO - 4500123892) | DCB | 3 | 14.02.2023 |  |  |  | 0.023451 | Firm | 0.023451
| 915 | CCC Bhusawal - ESTABLISHMENT | Work of Hiring of Xerox machine for day to day Xeroxing of Documents at CCC, MSPGCL, Bhusawal. (PO NO - 4500123923) | DCB | 3 | 17.02.2023 |  |  |  | 0.010478 | Firm | 0.010478
| 916 | CCC Bhusawal - ESTABLISHMENT | Confirmatory work of reparing damaged divider wall of road from 2X500 MW gate to bulker gate road at 1X660 MW Repln. Unit, Deepnagar, Bhusawal (PO NO - 4500124008) | - | 1 | 24.02.2023 |  |  |  | 0.0034342 | Firm | 0.0034342
| 917 | CCC Bhusawal - OTHER MISC | Work of concrete road near BHEL office gate from existing 500 MW concrete road at BTPS, Deepnagar, Bhusawal (PO NO - 4500124056) | DCB | 4 | 01.03.2023 |  |  |  | 0.03513 | Firm | 0.03513
| 918 | CCC Bhusawal - ESTABLISHMENT | Work of maintenance of landscaping in front of 1X660 MW project office premises at Deepnagar. (PO NO - 4500124038) | DCB | 4 | 03.03.2023 |  |  |  | 0.032503 | Firm | 0.032503
| 919 | CCC Bhusawal - ESTABLISHMENT | Conducting structural audit & residulel life assessment or river water pump house building near pimprisekam at BTPS, Bhusawal. (PO NO - 4500123981) | DCB | 4 | 03.03.2023 |  |  |  | 0.035047 | Firm | 0.035047
| 920 | CCC Bhusawal - ESTABLISHMENT | Providing unskilled assistance sweeping work at Civil Construction Circle, Deepnagar. (PO NO - 4500124076) | DCB | 4 | 03.03.2023 |  |  |  | 0.021059 | Firm | 0.021059
| 921 | CCC Bhusawal - ESTABLISHMENT | Annual Maintainance, Servicing. Checking, Network, Administration & trouble shooting of Network Hardware System at 1X660 MW CCC, MSPGCL, Bhusawal. (PO NO - 4500124171) | DCB | 3 | 09.03.2023 |  |  |  | 0.031827 | Firm | 0.031827
| 922 | CCC Bhusawal - ESTABLISHMENT | Work of cleaning overhead N.D.P. water tanks at 1X660 MW project office complex BTPS, Deepnagar, Bhusawal (PO NO - 4500124172) | DCB | 5 | 10.03.2023 |  |  |  | 0.017966 | Firm | 0.017966
| 923 | CCC Bhusawal - ESTABLISHMENT | Work of providing or fixing new 20 HP pump for construction water supply to 660MW project Deepnagar. (PO NO - 4500124180) | DCB | 4 | 15.03.2023 |  |  |  | 0.022906 | Firm | 0.022906
| 924 | CCC Bhusawal - OTHER MISC | Work of carrying out soil investigation for proposal construction of permant store shed within existing major store premises at BTPS Deepnagar. (PO NO - 4500124185) | DCB | 5 | 15.03.2023 |  |  |  | 0.029173 | Firm | 0.029173
| 925 | CCC Bhusawal - ESTABLISHMENT | Confirmatory work Hiring of services to carryout detailed Engineering or topographical survey for crossing of ADPL lines between OHE451/16KMS to OHE451/20 KMS between BSL & VRN rail stations. (PO NO - 4500124259) | - | 1 | 15.03.2023 |  |  |  | 0 | Firm | 0
| 926 | CCC Bhusawal - OTHER MISC | Work of replacement of old broken cement tiles of staircase in super D building No 13,14 & 15 respectively at BTPS Deepnagar. (PO NO - 4500124283) | DCB | 4 | 20.03.2023 |  |  |  | 0.023573 | Firm | 0.023573
| 927 | CCC Bhusawal - ESTABLISHMENT | Hiring of Desert coolers during summer season for 1x660 MW Civil Construction Circle, and its allied Divisions/ sections, Deepnagar, Bhusawal. (PO NO - 4500124530) | DCB | 4 | 27.03.2023 |  |  |  | 0.017794 | Firm | 0.017794
| 928 | CCC Bhusawal - ESTABLISHMENT | Supply of HP Make Computer with access Dries Laptop (HP Hevey Envy 360) Make large format Display (LED) (samsung Make) for video conferencing system at civil construction circle through Gems portal through PAC at 1x6660MW CCC office Bhusawal. (PO NO - 4500124071) | DCB | 3 | 27.03.2023 |  |  |  | 0.12201 | Firm | 0.12201
| 929 | CCC Bhusawal - RISK AND COST | Work of Repairing the existing Road crossing & drains damaged near 500 MW plant entry gate on risk & cost basis, BTPS, Deepnagar, Tal- Bhusawal. (PO NO - 4500124705) | DCB | 9 | 28.03.2023 |  |  |  | 0.036708 | Firm | 0.036708
| 930 | CCC Bhusawal - OTHER MISC | Sprinkiting of water on concret round surface and areas with dust by water tanker at 1x660 MW project Deepnagar. (PO NO - 4500124553) | DCB | 3 | 29.03.2023 |  |  |  | 0.027187 | Firm | 0.027187
| 931 | CCC Bhusawal - ESTABLISHMENT | Providing services of skilled assistants as a Computer operator for prepairation of data for SAP or SRM system in the office of CCC Deepnagar, Bhusawal (PO NO - 4500124774) | DCB | 4 | 29.03.2023 |  |  |  | 0.031436 | Firm | 0.031436
| 932 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC taxi (i.e. Swift Desire/ford Aspire or equivalent) along with driver and diesel required for E.E.(C), CCD-III, Bhusawal (PO NO - 4500124559) | DCB | 3 | 29.03.2023 |  |  |  | 0.084111 | Firm | 0.084111
| 933 | CCC Bhusawal - ESTABLISHMENT | Providing Platform, access road and approaches for additional parking area near project office at BTPS, Deepnagar, Bhusawal. (PO NO - 4500124775) | DCB | 4 | 29.03.2023 |  |  |  | 0.023312 | Firm | 0.023312
| 934 | CCC Bhusawal - ESTABLISHMENT | Confirmatory Work of repairing of damaged MTP Pipeline near 2x500 MW panel room at 1X660 MW replacement unit Deepnagar, Bhusawal. (PO NO - 4500124777) | - | 1 | 29.03.2023 |  |  |  | 0.0024605 | Firm | 0.0024605
| 935 | CCC Bhusawal - OTHER MISC | Providing Designer Cement Concrete Tiles in Garden of Tapi guest house at BTPS, Deepnagar, Bhusawal. (PO NO - 4500124793) | DCB | 4 | 29.03.2023 |  |  |  | 0.022411 | Firm | 0.022411
| 936 | CCC Bhusawal - ESTABLISHMENT | Work of external painting to 1X660 MW project office building at Deepngar, Bhusawal. (PO NO - 4500126072) | DCB | 4 | 11.05.2023 |  |  |  | 0.026961 | Firm | 0.026961
| 937 | CCC Bhusawal - OTHER MISC | Plumbing Sanitiray and miscollancous work for Type-II building No.1 at Deepngar, Bhusawal. (PO NO - 4500126105) | DCB | 4 | 12.05.2023 |  |  |  | 0.058188 | Firm | 0.058188
| 938 | CCC Bhusawal - ESTABLISHMENT | Annual maintenance servicing checking network administration or trouble shooting of network hardware system at 1X660 MW CCC Bhusawal. (PO NO - 4500126141) | - | 1 | 15.05.2023 |  |  |  | 0.0016942 | Firm | 0.0016942
| 939 | CCC Bhusawal - ESTABLISHMENT | Annual maintenance servicing checking network administration or trouble shooting of network hardware system at 1X660 MW CCC Bhusawal. (PO NO - 4500126142) | - | 1 | 15.05.2023 |  |  |  | 0.0031532 | Firm | 0.0031532
| 940 | CCC Bhusawal - ESTABLISHMENT | Providing 10 MBPS(1:1) internet leased line connectivity at CCC 1X660 MW Deepnagar. (PO NO - 4500126139) | - | 1 | 15.05.2023 |  |  |  | 0.0034796 | Firm | 0.0034796
| 941 | CCC Bhusawal - OTHER MISC | Repairing of toilet blocks in civil construction division at CCC Deepnagar, Bhusawal. (PO NO - 4500126135) | DCB | 4 | 18.05.2023 |  |  |  | 0.023424 | Firm | 0.023424
| 942 | CCC Bhusawal - ESTABLISHMENT | Work catch side drain along existing pimprisekam road from NH-6 to ROB start point at outside of 660 MW compound wall (PO NO - 4500126134) | - | 4 | 18.05.2023 |  |  |  | 0.023118 | Firm | 0.023118
| 943 | CCC Bhusawal - ESTABLISHMENT | Work of removing of dense grass shrubs weeds on as and when required basis around project office and project quarters at Deepnagar, Bhusawal. (PO NO - 4500126069) | DCB | 3 | 23.05.2023 |  |  |  | 0.037283 | Firm | 0.037283
| 944 | CCC Bhusawal - OTHER MISC | Maintenance of plantation near 1x660 MW Project gate at Deepnagar, Bhusawal (PO NO - 4500126138) | DCB | 3 | 24.05.2023 |  |  |  | 0.019836 | Firm | 0.019836
| 945 | CCC Bhusawal - OTHER MISC | Providing or fixing HDPE contaner of 2000 liters capacity supplying water to general tiolet of E & M office at Deepnagar. (PO NO - 4500126768) | - | 4 | 23.06.2023 |  |  |  | 0.0032025 | Firm | 0.0032025
| 946 | CCC Bhusawal - OTHER MISC | Work of connectivity construction of parpet wall for project quarters building at BTPS Deepnagar. (PO NO - 4500127497) | DCB | 5 | 11.07.2023 |  |  |  | 0.058809 | Firm | 0.058809
| 947 | CCC Bhusawal - OTHER MISC | Work of providing aprroach road near NH-6 box culvert crossing ADPL line at deepnagar. (PO NO - 4500127217) | - | 4 | 18.07.2023 |  |  |  | 0.0065832 | Firm | 0.0065832
| 948 | CCC Bhusawal - OTHER MISC | Providing unskilled assistance for monitoring of curing at 1x660 MW Repl. Unit,Civil Construction Circle, Deepnagar, Bhusawal. (PO NO - 4500127550) | DCB | 4 | 27.07.2023 |  |  |  | 0.021697 | Firm | 0.021697
| 949 | CCC Bhusawal - RISK & COST | Work of Providing & instualation PVC portable urinals (toilet) block at various elevation of main power house at 1x660 MW Project. (PO NO - 4500127825) | DCB | 6 | 02.08.2023 |  |  |  | 0.021467 | Firm | 0.021467
| 950 | CCC Bhusawal - ESTABLISHMENT | Hiring services of skilled as computer typists at account section civil construction Circle, Deepnagar. (PO NO - 4500127777) | DCB | 4 | 02.08.2023 |  |  |  | 0.019052 | Firm | 0.019052
| 951 | CCC Bhusawal - OTHER MISC | Confirmatory work of housekeeping at main power house transfarmer yard & surrounding area of main power block at 1x660 MW project. (PO NO - 4500127779) | - | 4 | 02.08.2023 |  |  |  | 0.0059086 | Firm | 0.0059086
| 952 | CCC Bhusawal - OTHER MISC | Work of Providing Chainlink-Fencing behind Project Staff Quarters (PD - PE) at BTPS, Deepnagar, Bhusawal (PO NO - 4500127829) | DCB | 6 | 04.08.2023 |  |  |  | 0.023385 | Firm | 0.023385
| 953 | CCC Bhusawal - OTHER MISC | Work of repairing of pipe culvert constructed across mohammad pura nallah of 2x500 MW railway siding patroling road at Deepnagar, Bhusawal. (PO NO - 4500127830) | DCB | 4 | 04.08.2023 |  |  |  | 0.0234 | Firm | 0.0234
| 954 | CCC Bhusawal - OTHER MISC | Providing supervisor for site supervision at Railway siding area of 1X660 MW project Deepnagar. (PO NO - 4500127865) | - | 4 | 18.08.2023 |  |  |  | 0.00345 | Firm | 0.00345
| 955 | CCC Bhusawal - OTHER MISC | Work of rerouting of farmers PVC water pipeline fouling in ROB approach (Towards Bhogavati river) of 1X660 MW railway siding area under CCC., Deepnagar, Bhusawal. (PO NO - 4500128119) | DCB | 5 | 23.08.2023 |  |  |  | 0.094727 | Firm | 0.094727
| 956 | CCC Bhusawal - RAILWAY SIDING WORKS | Renovation of Existing yard master service building at 2x500 MW railway siding at Deepnagar, Bhusawal. (PO NO - 4500128121) | DCB | 6 | 24.08.2023 |  |  |  | 0.24665 | Firm | 0.24665
| 957 | CCC Bhusawal - TOWNSHIP AND COLONY | Work of providing & laying sevage pipeline at back side of building no NE 41 To NE 48 & Building NE 32 To NE 40 Deepnagar. (PO NO - 4500128317) | DCB | 5 | 01.09.2023 |  |  |  | 0.22296 | Firm | 0.22296
| 958 | CCC Bhusawal - ESTABLISHMENT | Hiring of disel taxi car i.e. (Indica/Bolero/Swift Dizer) along with driver & required fuel for staff of CCD-III 1X660 MW Replacement unit Bhusawal. (PO NO - 4500128776) | DCB | 3 | 21.09.2023 |  |  |  | 0.082857 | Firm | 0.082857
| 959 | CCC Bhusawal - OTHER MISC | Work of providing GPS co ordinates, site Elevation, Location Map of chimney and project site for NOC from AAI at 1x660 MW project Deepnagar, BSL (PO NO - 4500128803) | - | 4 | 27.09.2023 |  |  |  | 0.00295 | Firm | 0.00295
| 960 | CCC Bhusawal - ESTABLISHMENT | Work of providing office assistance at office of the Dy. C.E. 1x660 MW Deepnagar, Bhusawal. (PO NO - 4500128829) | DCB | 5 | 22.09.2023 |  |  |  | 0.20447 | Firm | 0.20447
| 961 | CCC Bhusawal - ESTABLISHMENT | Hiring of private disel taxi car (i.e. sedan/suv) along with driver & fuel for civil consultant at 1x660 MW Replacement project CCC, Deepnagar. (PO NO - 4500128831) | DCB | 3 | 18.10.2023 |  |  |  | 0.094713 | Firm | 0.094713
| 962 | CCC Bhusawal - OTHER MISC | Work of NDT testing for type II Qtrs, Building No 1 along with detail report at 1x660 MW project at BTPS Deepnagar Bhusawal. (PO NO - 4500129360) | - | 4 | 19.10.2023 |  |  |  | 0.0043861 | Firm | 0.0043861
| 963 | CCC Bhusawal - ESTABLISHMENT | Annual maintenance of Garden near project office complex gate Deepnagar, Bhusawal. (PO NO - 4500129389) | DCB | 3 | 19.10.2023 |  |  |  | 0.029082 | Firm | 0.029082
| 964 | CCC Bhusawal - ESTABLISHMENT | Hiring of private disel taxi jeep (Mahundra TUV 300/Bolero/Neo) along with Driver and Disel required for CSR work & other outside work at CCD-III MSPGCL, Bhusawal. (PO NO - 4500129388) | DCB | 3 | 19.10.2023 |  |  |  | 0.068982 | Firm | 0.068982
| 965 | CCC Bhusawal - OTHER MISC | Confirmatory work of providing services of unskilled assistance for sweeping and cleaning of wash rooms of security cabins at 1x660 MW project gate, near BHEL office and near project office gate, BTPS Deepnagar, Bhusawal. (PO NO - 4500128042) | - | 4 | 23.10.2023 |  |  |  | 0.0061182 | Firm | 0.0061182
| 966 | CCC Bhusawal - ESTABLISHMENT | Confirmatory work of providing services of unskilled assistance for sweeping and cleaning of wash rooms of security cabins at 1x660 MW project gate, near BHEL office and near project office gate, BTPS Deepnagar, Bhusawal. (PO NO - 4500129773) | - | 4 | 17.11.2023 |  |  |  | 0.0063535 | Firm | 0.0063535
| 967 | CCC Bhusawal - OTHER MISC | Bhusawal 1x660 MW Replacement Project - Work of Tree Plantation in Pimprisekam Shivar along Village Roads. (PO NO - 4500130072) | DCB | 5 | 30.11.2023 |  |  |  | 0.040486 | Firm | 0.040486
| 968 | CCC Bhusawal - OTHER MISC | Providing Technical Assistance (Civil Supervisor) for site supervision at CHP, FGD and allied stucture 1x660 MW Project, Deepnagar, Bhusawal. (PO NO - 4500130132) | DCB | 3 | 01.12.2023 |  |  |  | 0.10183 | Firm | 0.10183
| 969 | CCC Bhusawal - RISK & COST | Work of Dewatering at PRDS site and diversion of unseasonal rain water runoff at construction site of 1x660 MW replacement unit, Deepnagar, BSL. (PO NO - 4500129832) | DCB | 3 | 01.12.2023 |  |  |  | 0.011508 | Firm | 0.011508
| 970 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC taxi disel taxi car i.e (Amaze/Aspire equivalent Sedan Car) along with Driver and required Fuel for S.E.(C), at 1x660 MW Proj. Repl. Unit, Deepnagar, Bhusawal. (PO NO - 4500130294) | DCB | 3 | 06.12.2023 |  |  |  | 0.095355 | Firm | 0.095355
| 971 | CCC Bhusawal - OTHER MISC | Repairing of Pot Holes of Internal Roads used for Coad Transportation from 2x500 MW to 660 MW Project at Deepnagar, Bhusawal. (PO NO - 4500130271) | DCB | 3 | 12.12.2023 |  |  |  | 0.079821 | Firm | 0.079821
| 972 | CCC Bhusawal - OTHER MISC | Work of Painting of Quarters Internally 'as and when' required under Civil Construction Circle at BTPS Deepnagar, Bhusawal (PO NO - 4500130348) | DCB | 3 | 12.12.2023 |  |  |  | 0.048925 | Firm | 0.048925
| 973 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC taxi disel taxi car i.e (Amaze/Dezir/Ford equivalent Car) along with Driver and required Fuel for Dy. C.E. (C), at 1x660 MW Proj. Repl. Unit, Deepnagar, Bhusawal. (PO NO - 4500130343) | DCB | 3 | 12.12.2023 |  |  |  | 0.095137 | Firm | 0.095137
| 974 | CCC Bhusawal - ESTABLISHMENT | Providing Services of skilled assistance (Driver) for Departmental Vehicle MH-40-A-8027 for office of the civil construction circle, Deepnagar, Bhusawal. (PO NO - 4500130487) | DCB | 3 | 18.12.2023 |  |  |  | 0.046812 | Firm | 0.046812
| 975 | CCC Bhusawal - OTHER MISC | Providing Technical Assistance (Civil Supervisor) for site supervision at NDCT area 1x660 MW Project, Deepnagar, Bhusawal. (PO NO - 4500130426) | DCB | 3 | 19.12.2023 |  |  |  | 0.044874 | Firm | 0.044874
| 976 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private AC Taxi (i.e. Amaze/Aspire/equivalent sedan car) along with Driver & required Fuel for staff of CCD-II, 1x660 MW Repln. Proj. Deepnagar, Bhusawal. (PO NO - 4500130572) | DCB | 3 | 22.12.2023 |  |  |  | 0.079506 | Firm | 0.079506
| 977 | CCC Bhusawal - OTHER MISC | Providing Supervisor for Site Supervision at Railway Siding area of 1X660 MW Project at Deepnagar, Bhusawal. (PO NO - 4500130813) | DCB | 3 | 10.01.2024 |  |  |  | 0.024056 | Firm | 0.024056
| 978 | CCC Bhusawal - RISK & COST | Providing & Fixing Aluminium Composite Panel (ACP) to Internals Wall of CCR / CER at 17.00 Mtr of Main Power House at BTPS, Deepnagar, Bhusawal. (PO NO - 4500130867) | DCB | 3 | 10.01.2024 |  |  |  | 0.14773 | Firm | 0.14773
| 979 | CCC Bhusawal - ESTABLISHMENT | Work of cleanining of tiolets of civil construction circle at its allied division deepnagar (PO NO - 4500130859) | DCB | 3 | 11.01.2024 |  |  |  | 0.018555 | Firm | 0.018555
| 980 | CCC Bhusawal - OTHER MISC | Work of providing chainlink fencing for isolation of Railway siding work for 1x660 MW Project Deepnagar. (PO NO - 4500130913) | DCB | 4 | 16.01.2024 |  |  |  | 0.20765 | Firm | 0.20765
| 981 | CCC Bhusawal - ESTABLISHMENT | Confirmatory work of providing services of unskilled assistance for sweeping and cleaning of wash rooms of security cabins at 1x660 MW project gate, near BHEL office and near project office gate, BTPS Deepnagar, Bhusawal. (PO NO - 4500130977) | - | 4 | 17.01.2024 |  |  |  | 0.0061182 | Firm | 0.0061182
| 982 | CCC Bhusawal - RISK AND COST | Bhusawal 1x660 MW Replacement Project - Work of dewatering at construction site of 1X660 MW Replacement Project, Deepnagar, Bhusawal. (PO NO - 4500130965) | DCB | 4 | 19.01.2024 |  |  |  | 0.062716 | Firm | 0.062716
| 983 | CCC Bhusawal - OTHER MISC | Repairing of rail side patrolling road (North Side) towards fulgaon upto Mohammad hallah at Deepnagar, Bhusawal. (PO NO - 4500130994) | DCB | 6 | 19.01.2024 |  |  |  | 0.022306 | Firm | 0.022306
| 984 | CCC Bhusawal - ESTABLISHMENT | Providing unskilled labour at Pump House Oulet Canel and Project Office Complex for Maintaining Water Supply at BTPS, Deepnagar, Bhusawal. (PO NO - 4500131020) | DCB | 3 | 19.01.2024 |  |  |  | 0.061776 | Firm | 0.061776
| 985 | CCC Bhusawal - OTHER MISC | Providing Plinth Protection and work to SD-14 and 15 Building under 660 MW Replacement Project, Bhusawal. (PO NO - 4500130240) | DCB | 8 | 23.01.2024 |  |  |  | 0.019143 | Firm | 0.019143
| 986 | CCC Bhusawal - RISK AND COST | Work of Providing Hydrolic Excavator and Manpower for Excavation of Dewatering Pits, Diversion of Monsoon Runoff at Construction Site of 1x660 MW Project Bhusawal. (PO NO - 4500130966) | DCB | 2 | 23.01.2024 |  |  |  | 0.06559 | Firm | 0.06559
| 987 | CCC Bhusawal - ESTABLISHMENT | Providing Skilled Services for Preparation of Data in SAP and SRM System in Office of the Dy. C.E. (C), C.C.C., Deepnagar, Bhusawal. (PO NO - 4500131169) | DCB | 3 | 30.01.2024 |  |  |  | 0.042338 | Firm | 0.042338
| 988 | CCC Bhusawal - OTHER MISC | Work of Removing Grass along Project Office Road upto Ganapati Mandir at BTPS, Deepnagar, BSL. (PO NO - 4500131140) | DCB | 3 | 31.01.2024 |  |  |  | 0.025255 | Firm | 0.025255
| 989 | CCC Bhusawal - OTHER MISC | Providing Services of Skilled Assistance for (AHP) Structure 13 km Ash Disposal Pipeline (ADPL) and CSR Works (Phase-II, 15 Villages) of 1x660 MW Project at Deepnagar, Bhusawal. (PO NO - 4500131105) | DCB | 3 | 31.01.2024 |  |  |  | 0.034607 | Firm | 0.034607
| 990 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private AC Taxi Car/Jeep (Mahindra TUV 300 / Tata Indica / Bolero / Tata Sumo) along with Driver and Diesel required for Civil Staff, of C.C.D-I, MSPGCL, Bhusawal. (PO NO - 4500131202) | DCB | 3 | 01.02.2024 |  |  |  | 0.095948 | Firm | 0.095948
| 991 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private AC Taxi (i.e. Swift/Dezire/Ford/ Aspire of equivalent car) along with Driver & required Fuel for CCD-III, 1x660 MW Repln. Proj. Deepnagar, Bhusawal. (PO NO - 4500131325) | DCB | 3 | 06.02.2024 |  |  |  | 0.08478 | Firm | 0.08478
| 992 | CCC Bhusawal - OTHER MISC | Work of providing RCC Bridge across ADP Lines in Gate No.483 at Velhala Village, Tal-Bhusawal. (PO NO - 4500131327) | DCB | 3 | 08.02.2024 |  |  |  | 0.035204 | Firm | 0.035204
| 993 | CCC Bhusawal - OTHER MISC | Work of Shifting and Rerouting of 100mm construction Water Supply Pipeline near Bunker Gate at BTPS Deepnagar. (Confirmatory Work Order) (PO NO - 4500131195) | - | 4 | 22.02.2024 |  |  |  | 0.0057197 | Firm | 0.0057197
| 994 | CCC Bhusawal - ESTABLISHMENT | Hiring of private AC taxi (i.e. XUV -300, TUV-300,/ Mahindra Scorpio/ Hundai Venue/ Maruti Vistara Brezza) along with driver & required fuel for E. E. (C), C.C.D.-I at 1x660 MW Project, Deepnagar, Bhusawal (PO NO - 4500131838) | - | 4 | 13.03.2024 |  |  |  | 0.002922 | Firm | 0.002922
| 995 | CCC Bhusawal - ESTABLISHMENT | Providing of unskilled assistance for sweeping work at C.C.C., Deepnagar, Bhusawal (Period 29/10/23 to 07/12/2023) (PO NO - 4500131815) | - | 4 | 13.03.2024 |  |  |  | 0.0033451 | Firm | 0.0033451
| 996 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private AC Taxi (i.e. Amaze/Aspire/equivalent sedan car) along with Driver & required Fuel for S. E. (C), C.C.C, 1x660 MW Repln. Proj. Deepnagar, Bhusawal. (PO NO - 4500131814) | - | 4 | 13.03.2024 |  |  |  | 0.0055801 | Firm | 0.0055801
| 997 | CCC Bhusawal - OTHER MISC | Work of supplying clean water by taker for Trees Planted along Pimprisekam Road, at 1x660 MW Project, Deepnagar, Bhusawal (PO NO - 4500132179) | DCB | 3 | 20.03.2024 |  |  |  | 0.047358 | Firm | 0.047358
| 998 | CCC Bhusawal - ESTABLISHMENT | Providing Services of skilled assistance (Driver) for Departmental Vehicle MH-19-AE-6942 for office of the civil construction circle, Deepnagar, Bhusawal. (PO NO - 4500132401) | DCB | 4 | 28.03.2024 |  |  |  | 0.057825 | Firm | 0.057825
| 999 | CCC Bhusawal - OTHER MISC | Work of Plantation of Ornamental and their maintenance from 500 MW gate of Prject office road divider at Deepanagar, Bhusawal. (PO NO - 4500132287) | DCB | 4 | 28.03.2024 |  |  |  | 0.022719 | Firm | 0.022719
| 1000 | CCC Bhusawal - OTHER MISC | Work of Housekeeping at Main Power House, Transformer Yard at 1x600 MW Project at BTPS, Deepnagar, Bhusawal,Period of Work Dtd. 17/01/2024 to 18/01/2024. (PO NO - 4500132457) | - | 4 | 24.04.2024 |  |  |  | 0.0014514 | Firm | 0.0014514
| 1001 | CCC Bhusawal - OTHER MISC | Work of External Painting for Project Quarters Type-II Building No.2 to 6 Super D Building No. 13 to 15 at Deepnagar, Bhusawal. (PO NO - 4500133449) | DCB | 4 | 25.04.2024 |  |  |  | 0.0595 | Firm | 0.0595
| 1002 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private Diesel AC taxi jeep (Mahindra TUV300/Bolero Neo/equivalent) along with driver and diesel required for CSR work at CCD-III MSPGCL, BSL. (PO NO - 4500133704) | DCB | 3 | 07.05.2024 |  |  |  | 0.073005 | Firm | 0.073005
| 1003 | CCC Bhusawal - OTHER MISC | Work of Providing Profiled Sheets to Chajja of Project Type Quarters at BTPS, Deepnagar, Bhusawl. (PO NO - 4500134003) | DCB | 3 | 24.05.2024 |  |  |  | 0.09446 | Firm | 0.09446
| 1004 | CCC Bhusawal - ESTABLISHMENT | Providing Unskilled Labour at Pump House Outlet Canal of Project Office Complex for Maintenace Water Supply at BTPS, Deepnagar, Bhusawal. (PO NO - 4500134343) | DCB | 4 | 29.05.2024 |  |  |  | 0.11542 | Firm | 0.11542
| 1005 | CCC Bhusawal - OTHER MISC | Work of Topographical Survey for Proposed Interconnection Rute of Coal Conveyor of 1x660 MW & 2x500 MW unit at BTPS, Bhusawal, Period of work Dtd. 01/11/2023 to 04/11/2023 order as per office note inward no. 00511/Dtd. 1/03/2024 (PO NO - 4500134572) | - | 4 | 06.06.2024 |  |  |  | 0.005723 | Firm | 0.005723
| 1006 | CCC Bhusawal - TOWNSHIP AND COLONY | Work of Clearing the Chocks from underground drainage line including inspection chamber for project office and project qtrs at BTPS, Deepnagar, Bhusawal. (PO NO - 4500134484) | DCB | 4 | 06.06.2024 |  |  |  | 0.027033 | Firm | 0.027033
| 1007 | CCC Bhusawal - ESTABLISHMENT | Work of Providing Office Assistants at Office of Dy. Chief Engineer (C), Civil Construction Circle, 1x660 MW Project at BTPS, Deepnagar, Bhusawal. (PO NO - 4500135035) | DCB | 3 | 25.06.2024 |  |  |  | 0.17439 | Firm | 0.17439
| 1008 | CCC Bhusawal - ESTABLISHMENT | Work of Providing Office Assistants at Office of Dy. Chief Engineer (C), Civil Construction Circle, 1x660 MW Project at BTPS, Deepnagar, Bhusawal. (PO NO - 4500135036) | DCB | 3 | 25.06.2024 |  |  |  | 0.17439 | Firm | 0.17439
| 1009 | CCC Bhusawal - ESTABLISHMENT | Work of Providing Office Assistants at Office of Dy. Chief Engineer (C), Civil Construction Circle, 1x660 MW Project at BTPS, Deepnagar, Bhusawal. (PO NO - 4500135037) | DCB | 3 | 25.06.2024 |  |  |  | 0.17439 | Firm | 0.17439
| 1010 | CCC Bhusawal - ESTABLISHMENT | Work of Painting of Flag area of Cleaning work for 26 Jan (Republic Day) at 1x660 MW C.C.C Deepnagar, Bhusawal. (PO NO - 4500131820) | - | 4 | 11.07.2024 |  |  |  | 0.0036403 | Firm | 0.0036403
| 1011 | CCC Bhusawal - ESTABLISHMENT | Work of Installation of Air Conditioner in Senior Manager (F&A) Cabin at Civil Const. Circle MSPGCL, Deepnagr, Bhusawal (PO NO - 4500135426) | - | 4 | 23.07.2024 |  |  |  | 0.0025481 | Firm | 0.0025481
| 1012 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private Diesel Taxi Car (Innova) and Dezire or Euqivalent along with Driver and Diesel / Petrol required for VVIP/VIP entertainment at CCC, MSPGCL, "as and when" required, Deepnagar, Bhusawal. (PO NO - 4500135740) | DCB | 3 | 23.07.2024 |  |  |  | 0.038497 | Firm | 0.038497
| 1013 | CCC Bhusawal - RISK AND COST | Work of Providing Unskilled Labour and Tractor for Housekeeping and Transportation of Debris from various area on Risk and Cost of M/s. BHEL such as: 1) BTG area Main Plant, House Building, Transformer Yard, Boiler area and ESP are at 660 MW, BTPS, 2) BOP area DM Plant area, PT Plant, Clearifier Pump House, STP/ETP area and AHP area at 660 MW BTPS, Deepnagar, Bhusawal. (PO NO - 4500135756) | DCB | 5 | 26.07.2024 |  |  |  | 0.099148 | Firm | 0.099148
| 1014 | CCC Bhusawal - ESTABLISHMENT | Work of Pre Mansoon Readiness - Work and repairing of drainage Chambers at 1x660MW Project Deepnagar, Bhusawal. (PO NO - 4500136227) | DCB | 3 | 13.08.2024 |  |  |  | 0.022796 | Firm | 0.022796
| 1015 | CCC Bhusawal - ESTABLISHMENT | Hiring of Private Diesel AC taxi jeep (Swift/Ford/or-equivalent) along with driver and diesel required for CCD-III BSL. (Period of Dtd.19/01/2024 to Dtd. 07/02/2024) (PO NO - 4500136245) | - | 4 | 28.08.2024 |  |  |  | 0.0042321 | Firm | 0.0042321
| 1016 | CCC Bhusawal - ESTABLISHMENT | Work of cleaning of toilet and housekeeping work at civil construction circle and its allied division bsl RFX No. 3000050124 (PO NO - 4500136763) | DCB | 4 | 12.09.2024 |  |  |  | 0.036972 | Firm | 0.036972
| 1017 | CCC Bhusawal - RISK AND COST | Work of providing furniture platform at DM Plant & SWAS lab at project site on risk & cost basis of M/s. BHEL Deepnagar, Bhusawal. (PO NO - 4500136764) | DCB | 2 | 17.09.2024 |  |  |  | 0.11287 | Firm | 0.11287
| 1018 | CCC Bhusawal - OTHER MISC | Providing and fixing chainlink fencing to temporary quarters of 1x660MW, Deepnagar, Bhusawal. (PO NO - 4500137085) | DCB | 6 | 27.09.2024 |  |  |  | 0.099708 | Firm | 0.099708
| 1019 | CCC Bhusawal - ESTABLISHMENT | Work of Servicing and Maintenance of Computer and Priters under Civil Constn Circle, Deepnagar, Bhusawal. (PO NO - 4500137412) | DCB | 3 | 04.10.2024 |  |  |  | 0.028378 | Firm | 0.028378
1 | 1020 | CCC Bhusawal - OTHER MISC | Sprinkling of water over road surface by water tanker from 500 MW unit CHP to 660 MW Project Stacler , Deepnagar, Bhusawal. (PO NO - 4500138318) | - | 4 | 11.12.2024 |  |  |  | 0.0058815 | Firm | 0.0058815
List of Works to be taken up in FY 25-26 under add cap
| 1 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Office furniture viz. Cupboard, almirah, Chairs, Tables etc. for project and O&M | [6 empty] | 0.8
| 2 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of stationary for project & O&M | [6 empty] | 0.03
| 3 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Cabin partitions, ceiling repairing/replacement etc. | [6 empty] | 0.03
| 4 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicles for SE | [6 empty] | 0.12
| 5 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicles for Dy.CE | [6 empty] | 0.12
| 6 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicles for Security | [6 empty] | 0.0944
| 7 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of TUV/Bolero/Eq. for project staff | [6 empty] | 0.14716
| 8 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of desert cooler for office and site | [6 empty] | 0.03
| 9 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Services of housekeeping | [6 empty] | 0.3
| 10 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of drivers for departmental vehicles | [6 empty] | 0.25
| 11 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Photography and video shooting | [6 empty] | 0.03
| 12 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Safety sergeants | [6 empty] | 0.06
| 13 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Services of computer operators | [6 empty] | 0.3
| 14 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Xerox machine operator | [6 empty] | 0.01
| 15 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Miscellaneous (office establishment, VIP entertainment etc.related) | [6 empty] | 0.05
| 16 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Miscellaneous / unforeseen expenditures not included in above | [6 empty] | 0.75
| 17 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of Measuring Instrument i.e. Digital Multimeter, mA loop calibrator, tool box, earth tester, tempture Gun, ultrasonic flow measurement, vernier calibration, Allen key set, thermocouple calibrator, multifunction process calibrator, 8 channel paperless recorder | [6 empty] | 0.17
| 18 | 1x660 MW Bhusawal Project - Other misc Expenditure | LED display at CHP, AHP, Main Control room etc | [6 empty] | 0.2
| 19 | 1x660 MW Bhusawal Project - Other misc Expenditure | construction power supply 33/11KV Substation O&M along with Miscellaneous Works | [6 empty] | 1
| 20 | 1x660 MW Bhusawal Project - Other misc Expenditure | Electrical Maintenance Works of Project Office & Staff Quarters | [6 empty] | 0.1
| 21 | 1x660 MW Bhusawal Project - Other misc Expenditure | Procurement of spares for construction supply sub-station | [6 empty] | 0.09
| 22 | 1x660 MW Bhusawal Project - Other misc Expenditure | Provision of High mast, illumination arrangements at Project premise, colony area etc. | [6 empty] | 0.5
| 23 | 1x660 MW Bhusawal Project - Other misc Expenditure | Misc, unforeseen expenditure | [6 empty] | 0.03
| 24 | 1x660 MW Bhusawal Project - Other misc Expenditure | Supply of required instruments during erection of turbine, Condenser and CW piping- Dial Gauges, Vernier Calipers, Micrometers, Bore Gauges, Slip Gauges, Power Jacks- (4 nos. X 100 Tonnes) | [6 empty] | 0.04
| 25 | 1x660 MW Bhusawal Project - Other misc Expenditure | T&P required for Maint | [6 empty] | 0.25
| 26 | 1x660 MW Bhusawal Project - Other misc Expenditure | misc / unforeseen | [6 empty] | 0.1
| 27 | 1x660 MW Bhusawal Project - Other misc Expenditure | misc / unforeseen works under CHP | [6 empty] | 0.5
| 28 | 1x660 MW Bhusawal Project - Other misc Expenditure | Glow sign boards fixing in project premises | [6 empty] | 0.14
| 29 | 1x660 MW Bhusawal Project - Other misc Expenditure | Safety audit | [6 empty] | 0.05
| 30 | 1x660 MW Bhusawal Project - Other misc Expenditure | Bulk and Fine Chemicals | [6 empty] | 0.03
| 31 | 1x660 MW Bhusawal Project - Other misc Expenditure | Precision Lab inst for coal & water | [6 empty] | 6
| 32 | 1x660 MW Bhusawal Project - Other misc Expenditure | Green H2 generation plant (Proposed procurement against this head is for Coal Flow Management system and Suspended Magnet) | [6 empty] | 14.61
| 33 | 1x660 MW Bhusawal Project - Other misc Expenditure | Installation of Diesel disbursing pump | [6 empty] | 1
| 34 | 1x660 MW Bhusawal Project - Other misc Expenditure | Augur Coal Sampling | [6 empty] | 1.36
| 35 | 1x660 MW Bhusawal Project - Other misc Expenditure | Establishment Related | [6 empty] | 4.58
| 36 | 1x660 MW Bhusawal Project - Other misc Expenditure | Lime Cost and amonia cost during trial operation of FGD & SCR | [6 empty] | 6
List of Works to be taken up in FY 26-27 under add cap
| 1 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Office furniture viz. Cupboard, almirah, Chairs, Tables etc. for project and O&M | [6 empty] | 0.8
| 2 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of stationary for project & O&M | [6 empty] | 0.03
| 3 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Cabin partitions, ceiling repairing/replacement etc. | [6 empty] | 0.03
| 4 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicles for SE | [6 empty] | 0.12
| 5 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicles for Dy.CE | [6 empty] | 0.12
| 6 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicles for Security | [6 empty] | 0.0944
| 7 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of TUV/Bolero/Eq. for project staff | [6 empty] | 0.14716
| 8 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of desert cooler for office and site | [6 empty] | 0.03
| 9 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Services of housekeeping | [6 empty] | 0.3
| 10 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of drivers for departmental vehicles | [6 empty] | 0.25
| 11 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Photography and video shooting | [6 empty] | 0.03
| 12 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Safety sergeants | [6 empty] | 0.06
| 13 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Services of computer operators | [6 empty] | 0.3
| 14 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Xerox machine operator | [6 empty] | 0.01
| 15 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Miscellaneous (office establishment, VIP entertainment etc.related) | [6 empty] | 0.05
| 16 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Miscellaneous / unforeseen expenditures not included in above | [6 empty] | 0.75
| 17 | 1x660 MW Bhusawal Project - Other misc Expenditure | RWP R&M Works | [6 empty] | 40.66
List of Works to be taken up in FY 27-28 under add cap
| 1 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of Office furniture viz. Cupboard, almirah, Chairs, Tables etc. for project and O&M | [6 empty] | 0.8
| 2 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Procurement of stationary for project & O&M | [6 empty] | 0.03
| 3 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Cabin partitions, ceiling repairing/replacement etc. | [6 empty] | 0.03
| 4 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicles for SE | [6 empty] | 0.12
| 5 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicles for Dy.CE | [6 empty] | 0.12
| 6 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of vehicles for Security | [6 empty] | 0.0944
| 7 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of TUV/Bolero/Eq. for project staff | [6 empty] | 0.14716
| 8 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of desert cooler for office and site | [6 empty] | 0.03
| 9 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Services of housekeeping | [6 empty] | 0.3
| 10 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Hiring of drivers for departmental vehicles | [6 empty] | 0.25
| 11 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Photography and video shooting | [6 empty] | 0.03
| 12 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Safety sergeants | [6 empty] | 0.06
| 13 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Services of computer operators | [6 empty] | 0.3
| 14 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Xerox machine operator | [6 empty] | 0.01
| 15 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Miscellaneous (office establishment, VIP entertainment etc.related) | [6 empty] | 0.05
| 16 | 1x660 MW Bhusawal Project - Eshtablishment related Expenditure | Miscellaneous / unforeseen expenditures not included in above | [6 empty] | 0.75
| 17 | 1x660 MW Bhusawal Project - Other misc Expenditure | CHP Inter connection | [6 empty] | 60
List of Works to be taken up in FY 25-26 under add cap
| 1 | CCC Bhusawal - ESTABLISHMENT | Procurement of Office furniture viz. Cupboard, almirah, Chairs, Tables etc. for project and O&M | [6 empty] | 0.1
| 2 | CCC Bhusawal - ESTABLISHMENT | Procurement of stationary for project & O&M | [6 empty] | 0.03
| 3 | CCC Bhusawal - ESTABLISHMENT | Cabin partitions, ceiling repairing/replacement etc. | [6 empty] | 0.03
| 4 | CCC Bhusawal - ESTABLISHMENT | Hiring of vehicles for SE | [6 empty] | 0.1
| 5 | CCC Bhusawal - ESTABLISHMENT | Hiring of vehicles for Dy.CE | [6 empty] | 0.1
| 6 | CCC Bhusawal - ESTABLISHMENT | Hiring of TUV/Bolero/Eq. for project staff | [6 empty] | 0.5
| 7 | CCC Bhusawal - ESTABLISHMENT | Hiring of desert cooler for office and site | [6 empty] | 0.03
| 8 | CCC Bhusawal - ESTABLISHMENT | Services of housekeeping | [6 empty] | 0.1
| 9 | CCC Bhusawal - ESTABLISHMENT | Photography and video shooting | [6 empty] | 0.05
| 10 | CCC Bhusawal - ESTABLISHMENT | Safety sergeants | [6 empty] | 0.06
| 11 | CCC Bhusawal - ESTABLISHMENT | Services of computer operators/office assistants/driver | [6 empty] | 0.5
| 12 | CCC Bhusawal - ESTABLISHMENT | Miscellaneous (office establishment, VIP entertainment etc.related) | [6 empty] | 0.05
| 13 | CCC Bhusawal - ESTABLISHMENT | Miscellaneous / unforeseen expenditures not included in above | [6 empty] | 0.8
| 14 | CCC Bhusawal - OTHER MISC | Under Passfor bulker Road / concretisation of Road | [6 empty] | 5
| 15 | CCC Bhusawal - OTHER MISC | Construction of Major Store | [6 empty] | 5
| 16 | CCC Bhusawal - OTHER MISC | Sudgaon Barrage | [6 empty] | 4
| 17 | CCC Bhusawal - OTHER MISC | Works Other than above | [6 empty] | 5.38
| 18 | CCC Bhusawal - OTHER MISC | Railway siding | [6 empty] | 128.6
| 19 | CCC Bhusawal - OTHER MISC | Admin Building (Block Estimate) | [6 empty] | 30
| 20 | CCC Bhusawal - OTHER MISC | Ash bund raising & Push through pipe culvert at railway crossing for ADPL line | [6 empty] | 32
| 21 | CCC Bhusawal - OTHER MISC | Hospital Building | [6 empty] | 9
List of Works to be taken up in FY 26-27 under add cap
| 1 | CCC Bhusawal - ESTABLISHMENT | Procurement of Office furniture viz. Cupboard, almirah, Chairs, Tables etc. for project and O&M | [6 empty] | 0.106
| 2 | CCC Bhusawal - ESTABLISHMENT | Procurement of stationary for project & O&M | [6 empty] | 0.0318
| 3 | CCC Bhusawal - ESTABLISHMENT | Cabin partitions, ceiling repairing/replacement etc. | [6 empty] | 0.0318
| 4 | CCC Bhusawal - ESTABLISHMENT | Hiring of vehicles for SE | [6 empty] | 0.106
| 5 | CCC Bhusawal - ESTABLISHMENT | Hiring of vehicles for Dy.CE | [6 empty] | 0.106
| 6 | CCC Bhusawal - ESTABLISHMENT | Hiring of TUV/Bolero/Eq. for project staff | [6 empty] | 0.53
| 7 | CCC Bhusawal - ESTABLISHMENT | Hiring of desert cooler for office and site | [6 empty] | 0.0318
| 8 | CCC Bhusawal - ESTABLISHMENT | Services of housekeeping | [6 empty] | 0.106
| 9 | CCC Bhusawal - ESTABLISHMENT | Photography and video shooting | [6 empty] | 0.053
| 10 | CCC Bhusawal - ESTABLISHMENT | Safety sergeants | [6 empty] | 0.0636
| 11 | CCC Bhusawal - ESTABLISHMENT | Services of computer operators/office assistants/driver | [6 empty] | 0.53
| 12 | CCC Bhusawal - ESTABLISHMENT | Miscellaneous (office establishment, VIP entertainment etc.related) | [6 empty] | 0.053
| 13 | CCC Bhusawal - ESTABLISHMENT | Miscellaneous / unforeseen expenditures not included in above | [6 empty] | 0.848
List of Works to be taken up in FY 27-28 under add cap
| 1 | CCC Bhusawal - ESTABLISHMENT | Procurement of Office furniture viz. Cupboard, almirah, Chairs, Tables etc. for project and O&M | [6 empty] | 0.11236
| 2 | CCC Bhusawal - ESTABLISHMENT | Procurement of stationary for project & O&M | [6 empty] | 0.033708
| 3 | CCC Bhusawal - ESTABLISHMENT | Cabin partitions, ceiling repairing/replacement etc. | [6 empty] | 0.033708
| 4 | CCC Bhusawal - ESTABLISHMENT | Hiring of vehicles for SE | [6 empty] | 0.11236
| 5 | CCC Bhusawal - ESTABLISHMENT | Hiring of vehicles for Dy.CE | [6 empty] | 0.11236
| 6 | CCC Bhusawal - ESTABLISHMENT | Hiring of TUV/Bolero/Eq. for project staff | [6 empty] | 0.5618
| 7 | CCC Bhusawal - ESTABLISHMENT | Hiring of desert cooler for office and site | [6 empty] | 0.033708
| 8 | CCC Bhusawal - ESTABLISHMENT | Services of housekeeping | [6 empty] | 0.11236
| 9 | CCC Bhusawal - ESTABLISHMENT | Photography and video shooting | [6 empty] | 0.05618
| 10 | CCC Bhusawal - ESTABLISHMENT | Safety sergeants | [6 empty] | 0.067416
| 11 | CCC Bhusawal - ESTABLISHMENT | Services of computer operators/office assistants/driver | [6 empty] | 0.5618
| 12 | CCC Bhusawal - ESTABLISHMENT | Miscellaneous (office establishment, VIP entertainment etc.related) | [6 empty] | 0.05618
| 13 | CCC Bhusawal - ESTABLISHMENT | Miscellaneous / unforeseen expenditures not included in above | [6 empty] | 0.89888