## F4
MSPGCL: Khaperkheda U # 5
MTR Petition Formats - Generation
Form 4: Summary of Capital Expenditure and Capitalisation
(Rs. Crore)
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-25 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (g) | (h) | (i) | (j) = (h) + (i) | (k) = (j) - (g) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 74.6248 | 74.6248 |  | 88.7972 | 88.7972 |  |  |  | 396.1197 | 396.1197 | 454.27 | 926.8 | 91.029 | 165.8 | 37
2 | Capitalisation | 22.1 | 152.0771 | 129.9771 | 269.41 | 91.407 | -178.003 | 282.01 | 0 | 382.94 | 382.9447 | 100.9347 | 471.28 | 877 | 91.029 | 215.6 | 37
3 | IDC |  |  | 0 |  |  | 0 |  |  |  |  | 0
4 | Capitalisation + IDC | 22.1 | 152.0771 | 129.9771 | 269.41 | 91.407 | -178.003 | 282.01 | 0 | 382.94 | 382.9447 | 100.9347 | 471.28 | 877 | 91.029 | 215.6 | 37
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2019 with reference to amounts approved in the MYT Order for FY 2019-20 to FY 2024-25
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1
MSPGCL: Khaperkheda U # 5
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) Submitted to MERC
12 | Ash Disposal Scheme from K’kheda 1 X 500 MW Unit to Nandgaon Ash Bund | DPR | MERC/CAPEX/20162017 | 2017-09-22 |  | 2017-09-22 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
12.1 | 1. Construction of RCC pedestals for laying of ADP Lines from Khaperkheda TPS to Nandgaon Ash Bund. 2. Providing &Laying of ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 2a) Supply of MSERW and Seamless Pipes 2b) Laying of Ash Disposal & Recovery Pipe Line. 3. Construction of Service road for ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 4. Design, Engineering & construction of minor bridge, road crossing and culverts in the alignment of ash disposal pipe line from TPS Khaperkheda to Nandgaon Ash Bund 5. Construction of ash water recovery pump house at Nandgaon | Scheme | MERC/CAPEX/20162017 | 2017-09-22 |  | 2017-09-22 |  | 2017-09-30 | 2019-09-22 |  | 2021-03-31 | 65.7755 | 95.6643 |  | -29.8888 |  |  | -29.8888
0 | IDC | IDC | MERC/CAPEX/20162017 | 2017-09-22 |  | 2017-09-22 |  | - | - |  | - | 3.41 | 0 |  | 3.41 |  |  | 3.41
14 | Procurement of Bulldozer, Wheel axel final drive assembly & refurbishment of apron feeder at Khaperkheda TPS | DPR | MERC/CAPEX/20162017/01341 | 2017-10-11 |  | 2017-10-11 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
14.1 | Procurement of Bulldozers(02 No.’s) | Scheme | MERC/CAPEX/20162017/01341 | 2017-10-11 |  | 2017-10-11 |  | 2017-08-18 | 2019-03-31 |  | 2018-03-31 | 3.75 | 4.2044 |  | -0.4544 |  |  | -0.4544
14.2 | Procurement of wheel axel final drive assembly (02 No.’s) | 0 | MERC/CAPEX/20162017/01341 | 2017-10-11 |  | 2017-10-11 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
14.3 | Refurbishment of apron feeder | Scheme | MERC/CAPEX/20162017/01341 | 2017-10-11 |  | 2017-10-11 |  | 2018-06-15 | 2019-03-31 |  | 2021-08-19 | 7.36 | 6.8736 |  | 0.48636 |  |  | 0.48636
0 | IDC | IDC | MERC/CAPEX/20162017/01341 | 2017-10-11 |  | 2017-10-11 |  | - | - |  | - | 0.7 | 0 |  | 0.7 |  |  | 0.7
15 | Procurement of Battery Set, PA Fan assembly, Jack Oil Pump, Turbo Driven BFP Cartridge and Restoration of ESP internals for 500 MW at Khaperkheda TPS | DPR | MERC/CAPEX/20172018/04320 | 2017-10-11 |  | 2017-10-11 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
15.1 | Procurement, erection, commissioning & testing of 220V, 2190AH & 24V Battery set: | Scheme | MERC/CAPEX/20172018/04320 | 2017-10-11 |  | 2017-10-11 |  | 2018-12-01 | 2019-10-11 |  | 2021-01-27 | 5.6 | 6.2928 |  | -0.69279 |  |  | -0.69279
15.2 | Procurement of PA Fan assembly | Scheme | MERC/CAPEX/20172018/04320 | 2017-10-11 |  | 2017-10-11 |  | 2020-01-29 | 2019-10-11 |  | 2021-02-06 | 3.1 | 3.3713 |  | -0.27135 |  |  | -0.27135
15.3 | Restoration of ESP internals | Scheme | MERC/CAPEX/20172018/04320 | 2017-10-11 |  | 2017-10-11 |  | 2020-01-17 | 2019-10-11 |  | 2021-01-22 | 3.7 | 1.6097 |  | 2.0903 |  |  | 2.0903
15.4 | Procurement of Jacking Oil Pump | Scheme | MERC/CAPEX/20172018/04320 | 2017-10-11 |  | 2017-10-11 |  | 2018-05-24 | 2019-10-11 |  | 2019-03-31 | 0.18 | 0.27 |  | -0.09 |  |  | -0.09
15.5 | Procurement of turbo driven BFP Cartridge Assembly (FK4E36) | Scheme | MERC/CAPEX/20172018/04320 | 2017-10-11 |  | 2017-10-11 |  | 2019-01-14 | 2019-10-11 |  | 2021-02-06 | 2.1 | 1.8279 |  | 0.27213 |  |  | 0.27213
0 | IDC | IDC | MERC/CAPEX/20172018/04320 | 2017-10-11 |  | 2017-10-11 |  | - | - |  | - | 0.17 | 0 |  | 0.17 |  |  | 0.17
17 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | DPR | MERC/CAPEX/20172018/04072 | 2017-08-18 |  | 2017-08-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
17.1 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | Scheme | MERC/CAPEX/20172018/04072 | 2017-08-18 |  | 2017-08-18 |  | 2018-02-27 | 2019-08-18 |  | 2019-08-06 | 11.3 | 12.8838 |  | -1.5838 |  |  | -1.5838
18 | Provision of S&T System for In Plant Yard Khaperkheda & Kalumni Yard (Depository Work) and Modification of Kalumna Yard Alteration No. 5 (Depository Work) | DPR | MERC/CAPEX/20172018/4779 | 2017-11-28 |  | 2017-11-28 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
18.1 | Provision of S & T System to Khaperkheda TPS In-Plant yard and Kalumna Yard (Depository Work) | Scheme | MERC/CAPEX/20172018/4779 | 2017-11-28 |  | 2017-11-28 |  | - | 2019-03-31 |  | - | 17.75 | 0.041975 |  | 17.708 |  |  | 17.708
18.2 | Modification of Kalumna Yard Alternation no. 5 in connection with Khaperkheda TPS Expansion Project (1x500 MW) construction of B.G. Railway Siding | Scheme | MERC/CAPEX/20172018/4779 | 2017-11-28 |  | 2017-11-28 |  | 2017-04-24 | 2019-03-31 |  | 2022-02-22 | 13.77 | 27.2859 |  | -13.5159 |  |  | -13.5159
19 | Construction of Limited Height Subway (LHS) at unmanned road level crossing by Railway on cost sharing basis with MSPGCL on Khaperkheda-Kalumna railway siding and saoner-Khaperkheda railway siding | DPR | MERC/CAPEX/20172018/0178 | 2018-02-02 |  | 2018-02-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
19.1 | Construction of LHS on Khaperkheda Kalumna railway side | Scheme | MERC/CAPEX/20172018/0178 | 2018-02-02 |  | 2018-02-02 |  | 2018-03-23 | 2019-03-31 |  | 2021-07-27 | 5.94 | 4.9899 |  | 0.9501 |  |  | 0.9501
19.2 | Construction of LHS on Khaperkheda Saoner railway line | Scheme | MERC/CAPEX/20172018/0178 | 2018-02-02 |  | 2018-02-02 |  | 2018-03-23 | 2019-03-31 |  | 2021-07-27 | 10.87 | 9.78 |  | 1.09 |  |  | 1.09
20 | Utilisation of unused water scheme from Bhanegaon open cast mine & construction of RCC internal roads at Khaperkheda TPS | DPR | MERC/CAPEX/20172018/0197 | 2018-02-06 |  | 2018-02-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
20.1 | Utilization of unused water scheme from Bhanegaon Open cast mine | Scheme | MERC/CAPEX/20172018/0197 | 2018-02-06 |  | 2018-02-06 |  | 2018-05-22 | 2020-02-06 |  | 2019-08-09 | 7.5469 | 12.9367 |  | -5.3898 |  |  | -5.3898
20.2 | Construction of Cement Concrete Road Inside Part Of Power House | Scheme | MERC/CAPEX/20172018/0197 | 2018-02-06 |  | 2018-02-06 |  | 2018-06-29 | 2020-02-06 |  | 2019-04-27 | 2.906 | 2.6732 |  | 0.23279 |  |  | 0.23279
0 | IDC | IDC | MERC/CAPEX/20172018/0197 | 2018-02-06 |  | 2018-02-06 |  | - | - |  | - | 1.08 | 0 |  | 1.08 |  |  | 1.08
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | DPR | MERC/CAPEX/2018-2019/105 | 2019-04-05 |  | 2019-04-05 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
21.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIMT 2000 (72° PA) | Scheme | MERC/CAPEX/2018-2019/105 | 2019-04-05 |  | 2019-04-05 |  | 2021-11-26 | 2021-04-05 |  | - | 3.4 | 3.835 |  | -0.435 |  |  | -0.435
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | DPR | MERC/CAPEX/2019-2020/799 | 2019-09-27 |  | 2019-09-27 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | Scheme | MERC/CAPEX/2019-2020/799 | 2019-09-27 |  | 2019-09-27 |  | 2021-01-22 | 2021-09-27 |  | - | 5.18 | 3.2027 |  | 1.9773 |  |  | 1.9773
27 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | DPR | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 |  | 2021-01-25 |  | - | - |  | - | 0 | 2.2126 |  | -2.2126 |  |  | -2.2126
27.1 | Flue Gas Desulphurization (FGD) System for KPKD 5 | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 |  | 2021-01-25 |  | - | - |  | - | 260.21 | 0 |  | 260.21 |  |  | 260.21
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 |  | 2021-01-25 |  | - | - |  | - | 20.61 | 0 |  | 20.61 |  |  | 20.61
BSL DPR-10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | DPR | MERC/CAPEX/20172018/4782 | 2017-11-28 |  | 2017-11-28 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
BSL DPR-10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | Scheme | MERC/CAPEX/20172018/4782 | 2017-11-28 |  | 2017-11-28 |  | 2019-04-20 | 2019-11-28 |  | 2020-08-07 | 4.24 | 0 |  | 4.24 |  |  | 4.24
0 | IDC | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 |  | 2017-11-28 |  | - | - |  | - | 0 | 4.5033 |  | -4.5033 |  |  | -4.5033
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | DPR | MERC/CAPEX/2017-18/0208 | 2018-02-08 |  | 2018-02-08 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | Scheme | MERC/CAPEX/2017-18/0208 | 2018-02-08 |  | 2018-02-08 |  | 2018-08-03 | 2019-11-08 |  | 2024-03-31 | 269.4076 | 0 |  | 269.4076 |  |  | 269.4076
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | DPR | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 |  | 2018-07-24 |  | - | - |  | - | 0 | 381.02 |  | -381.02 |  |  | -381.02
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | Scheme | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 |  | 2018-07-24 |  | 2019-02-25 | 2020-07-24 |  | 2021-11-07 | 1.23 | 0 |  | 1.23 |  |  | 1.23
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 |  | 2018-07-24 |  | - | - |  | - | 0.11 | 1.8042 |  | -1.6942 |  |  | -1.6942
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | DPR | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 15.5 | Electromagnetic Flow meters at various lines & Locations of 500 MW | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | 2021-10-27 |  | - | 3.2497 | 0 |  | 3.2497 |  |  | 3.2497
HO DPR 15.6 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | 2021-10-27 |  | - | 0.84252 | 0 |  | 0.84252 |  |  | 0.84252
0 | IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 |  | 2020-10-27 |  | - | 2021-10-27 |  | - | 0 | 0 |  | 0 |  |  | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | DPR | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 31.0231 | 0 |  | 31.0231 |  |  | 31.0231
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 1.6569 | 0 |  | 1.6569 |  |  | 1.6569
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 10.1857 | 0 |  | 10.1857 |  |  | 10.1857
0 | 0 | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 |  | 2023-10-09 |  | - | - |  | - | 2.1878 | 0 |  | 2.1878 |  |  | 2.1878
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 54.24 | 0 |  | 54.24 |  |  | 54.24
0 | IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 2.76 | 0 |  | 2.76 |  |  | 2.76
HO DPR 16 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 66.009 | 0 |  | 66.009 |  |  | 66.009
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 3.3 | 0 |  | 3.3 |  |  | 3.3
35 | Boiler Performance improvement Six Schemes at Unit-5 Khaperkheda TPS | DPR | Yet to be approved | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
35.1 | Sch-1: Procurement & Replacement of LTSH coils at U#5 | Scheme | Yet to be approved | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
35.2 | Sch-2: Procurement & Replacement of Economizer coils at U#5 | Scheme | Yet to be approved | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
35.3 | Sch-3: Procurement & Replacement of Water wall Z-Panels & Soot blower Panels at U#5: | Scheme | Yet to be approved | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
35.4 | Sch-4 : Supply and erection of APH Inlet & Outlet Flue Gas Damper Assemblies along with actuators at U#5 | Scheme | Yet to be approved | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
35.5 | Sch-5 : Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines at U#5. | Scheme | Yet to be approved | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
0 | IDC | IDC | Yet to be approved | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | DPR | MERC/CAPEX/2018-2019/1242 | 2018-09-22 |  | 2018-09-22 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | Scheme | MERC/CAPEX/2018-2019/1242 | 2018-09-22 |  | 2018-09-22 |  | - | - |  | - | 4.2068 | 0 |  | 4.2068 |  |  | 4.2068
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | Scheme | MERC/CAPEX/2018-2019/1242 | 2018-09-22 |  | 2018-09-22 |  | - | - |  | - | 11.5375 | 0 |  | 11.5375 |  |  | 11.5375
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | DPR | MERC/CAPEX/2024-2025/478 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
2.1 | Up-gradation of maxDNA DCS system (HMI Up-gradation) at Unit-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 7.29 | 0 |  | 7.29 |  |  | 7.29
2.2 | Up-gradation of PLC (GE FANUC make) SYSTEM (HMI & hardware up-gradation) at Ash Handling Plant, Compressor Plant, and Condensate Polishing Unit (CPU) at Unit-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 1.14 | 0 |  | 1.14 |  |  | 1.14
2.3 | Up-gradation of PLC (Schneider make) system (HMI & HARDWARE Up-gradation) at DM Plant, PTP, FF plant, CMRH System, HVAC System, FOPH system at U-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 4.26 | 0 |  | 4.26 |  |  | 4.26
2.4 | Up-gradation of SWAS (STEAM WATER ANALYSIS SYSTEM) Installed at Unit-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 4.71 | 0 |  | 4.71 |  |  | 4.71
2.5 | Up-gradation of Carbon monoxide analyzer in Flue Gas Installed at Unit-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 1.02 | 0 |  | 1.02 |  |  | 1.02
2.6 | Up-gradation of Coal feeder Controller at U-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 7.01 | 0 |  | 7.01 |  |  | 7.01
0 | IDC | 0 | MERC/CAPEX/2024-2025/478 | 2024-08-06 |  | 2024-08-06 |  | - | - |  | - | 0.86 | 0 |  | 0.86 |  |  | 0.86
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | DPR | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 |  | 2024-04-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
35.1 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 |  | 2024-04-18 |  | - | - |  | - | 0.89 | 0 |  | 0.89 |  |  | 0.89
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | DPR | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 |  | 2024-02-27 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 |  | 2024-02-27 |  | - | - |  | - | 5.43 | 0 |  | 5.43 |  |  | 5.43
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2
|  |  | MSPGCL: Khaperkheda U # 5 | [47 empty] | DPR | Not Initiated
|  |  | MTR Petition Formats - Generation | [47 empty] | Scheme | WIP
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [19 empty] | (Rs. Crore) | [8 empty] | IDC | Partially Capitalized
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [6 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Projected | Projected | Projected | Projected | Projected |  |  |  |  | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  |  |  |  | To be cancelled
[50 empty] | N.A. |  | N.A.
| A) DPR Schemes | [48 empty] | N.A. |  | To be confirmed
| (i) Submitted to MERC | [48 empty] | N.A.
12 | Ash Disposal Scheme from K’kheda 1 X 500 MW Unit to Nandgaon Ash Bund | DPR | MERC/CAPEX/20162017 | 2016-10-03 | 2017-09-22 | 69.1855 | 69.1855 |  |  | 2017-09-22 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
12.1 | 1. Construction of RCC pedestals for laying of ADP Lines from Khaperkheda TPS to Nandgaon Ash Bund. 2. Providing &Laying of ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 2a) Supply of MSERW and Seamless Pipes 2b) Laying of Ash Disposal & Recovery Pipe Line. 3. Construction of Service road for ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 4. Design, Engineering & construction of minor bridge, road crossing and culverts in the alignment of ash disposal pipe line from TPS Khaperkheda to Nandgaon Ash Bund 5. Construction of ash water recovery pump house at Nandgaon | Scheme | MERC/CAPEX/20162017 | 2016-10-03 | 2017-09-22 | 65.7755 | 65.7755 |  |  | 2017-09-22 | 2017-09-30 | 2019-09-22 | 2021-03-31 | 1. Presently ash generated from 1X500MW is disposed off in Waregaon ash bund as a stand by arrangement. After implementation of this scheme, the generated ash will be disposed off in Nadgaon ash bund. 2.By implementation of this scheme, the waregaon ash bund capacity can be used for additional period. Hence, the periodic raising of waregaon ash bund will be increased. 3. The ash management of 500MW will work more efficiently and hence, power generation will enhance. 4. Recovered water from nadgaon ash bund will utilized for various activities of TPS khaperkheda. | 54.1551 | 12.2366 | 12.83 | 10.0891 | 89.3108 |  | 6.3535 | [9 empty] | 100% |  |  |  | 45.4852 | 0 | 0 | 43.8256 | 89.3108 |  | 6.3535 | [8 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20162017 | 2016-10-03 | 2017-09-22 | 3.41 | 3.41 |  |  | 2017-09-22 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
14 | Procurement of Bulldozer, Wheel axel final drive assembly & refurbishment of apron feeder at Khaperkheda TPS | DPR | MERC/CAPEX/20162017/01341 | 2017-03-21 | 2017-10-11 | 13.14 | 11.81 |  |  | 2017-10-11 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
14.1 | Procurement of Bulldozers(02 No.’s) | Scheme | MERC/CAPEX/20162017/01341 | 2017-03-21 | 2017-10-11 | 3.75 | 3.75 |  |  | 2017-10-11 | 2017-08-18 | 2019-03-31 | 2018-03-31 | The projected benefits by implementation of schemes under 1. Availability of Dozers will improved 2. Bunker levels will be improved 3. Oil and Diesel consumption will be reduced. 4. Coal stock will improve. 5. Coal unloading at CHP yard will improved. 6. Due to less maintenance cost of proposed dozers manpower & spares cost will be reduced. 7. Higher availability & load-ability will meet coal requirement of plant by quantity & quality. 8. Higher availability & load-ability will reduce wagon detention period, reduce wagons demurrage charges and prevent generation loss. 9. It will improve performance parameters like auxiliary power consumption. 10. Reduce breakdown maintenance cost. 11. Fast restoration of apron feeders in case of unexpected break down. | 4.2044 |  |  |  | 4.2044 | [8 empty] | 100% | [6 empty] | 4.2044 |  |  |  | 4.2044 | [10 empty] | Capitalised
14.2 | Procurement of wheel axel final drive assembly (02 No.’s) |  | MERC/CAPEX/20162017/01341 | 2017-03-21 | 2017-10-11 | 1.33 | 0 |  |  | 2017-10-11 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | Cancelled
14.3 | Refurbishment of apron feeder | Scheme | MERC/CAPEX/20162017/01341 | 2017-03-21 | 2017-10-11 | 7.36 | 7.36 |  |  |  | 2018-06-15 | 2019-03-31 | 2021-08-19 | • Presently the machine is running with wear under permissible limit & it will continue satisfactorily further for next one & half year. • Being metallic rotating component under high impact & abrasion the components get worn out & need replacement after one or one & half year >Availability of apron feeder will be improved. >Break-down with non availability of spares will result in outage of the machine for a very long period. During this outage period wagon unloading will be totally stopped by that stream resulting into heavy demurrage, short of coal supply to bunkers, eventually in generation loss. > Presently the machine is running quite satisfactorily, however it will start posing problems after one & half year i.e. after about 5 years of service . Availability of spares will help to restore the machine in a short time & will help to run the machine smoothly, without trouble & with full efficiency for further 4 to 5 years. > Demurrage will be reduced considerably on account of Apron feeder failure which is about 518.40 Lac per incidence as calculated below. >Chances of generation loss due to failure of Apron feeder will also be prevented. | 6.16 | 0 | 0.71364 |  | 6.8736 | [8 empty] | 80% |  | 100% |  |  |  |  | 4.9154 | 0 | 0 | 0.71364 | 5.629 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20162017/01341 | 2017-03-21 | 2017-10-11 | 0.7 | 0.7 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
15 | Procurement of Battery Set, PA Fan assembly, Jack Oil Pump, Turbo Driven BFP Cartridge and Restoration of ESP internals for 500 MW at Khaperkheda TPS | DPR | MERC/CAPEX/20172018/04320 | 2017-03-21 | 2017-10-11 | 14.85 | 14.85 |  |  | 2017-10-11 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
15.1 | Procurement, erection, commissioning & testing of 220V, 2190AH & 24V Battery set: | Scheme | MERC/CAPEX/20172018/04320 | 2017-03-21 | 2017-10-11 | 5.6 | 5.6 |  |  | 2017-10-11 | 2018-12-01 | 2019-10-11 | 2021-01-27 | The projected benefits by implementation of this schemes are as under: a) For safe running of unit, 220 VDC supply should be 100% available to all HT auxiliaries and DC JOP, EOP and other emergency auxiliaries. Generator protection system. b) 24 V DC supply is used to DCS system for motoring and controlling the important plant parameters if battery fails then heavy Generation loss may be occurred due to non availability of DCS battery. Hence it is very urgent need to install these batteries at earliest to avoid generation loss. c) In case of AC failure DC lubrication pumps & seal oil pumps will be available for safe guarding TG set. | 0 | 6.2928 |  |  | 6.2928 | [9 empty] | 100% | [5 empty] | 0 | 0 | 6.2928 |  | 6.2928 | [10 empty] | Capitalised
15.2 | Procurement of PA Fan assembly | Scheme | MERC/CAPEX/20172018/04320 | 2017-03-21 | 2017-10-11 | 3.1 | 3.1 |  |  |  | 2020-01-29 | 2019-10-11 | 2021-02-06 | • Reduction in generation loss due to non-availability of PA Fan – 5B & unit is running on partial load. • Reductionin vibration of PA Fan – A & increase life of auxiliary bearings & overall life of fans. • The load ability of unit will be increase by making auxiliary available. | 0 | 0 | 3.3713 |  | 3.3713 | [10 empty] | 100% |  |  |  |  | 0 | 0 | 3.3713 |  | 3.3713 | [10 empty] | Capitalised
15.3 | Restoration of ESP internals | Scheme | MERC/CAPEX/20172018/04320 | 2017-03-21 | 2017-10-11 | 3.7 | 3.7 |  |  |  | 2020-01-17 | 2019-10-11 | 2021-01-22 | • The procurement will help to maintain load-ability of the plant. • It will minimize generation loss. • It will help in availability of auxiliary in healthy condition. • It will maintain highest operational overhaul efficiency of the system and environment. | 0 | 1.6097 |  |  | 1.6097 | [9 empty] | 100% | [5 empty] | 0 | 0 | 1.6097 |  | 1.6097 | [10 empty] | Capitalised
15.4 | Procurement of Jacking Oil Pump | Scheme | MERC/CAPEX/20172018/04320 | 2017-03-21 | 2017-10-11 | 0.18 | 0.18 |  |  |  | 2018-05-24 | 2019-10-11 | 2019-03-31 | • Reduction in forced outages of TDBFP. • Reduction in downtime of machine during repair works. • Increase in availability of the auxiliaries. • Reduction in auxiliary power consumption due to increase in efficiency of respective auxiliaries. | 0.27 | 0 |  |  | 0.27 | [8 empty] | 100% | [6 empty] | 0.27 |  |  |  | 0.27 | [10 empty] | Capitalised
15.5 | Procurement of turbo driven BFP Cartridge Assembly (FK4E36) | Scheme | MERC/CAPEX/20172018/04320 | 2017-03-21 | 2017-10-11 | 2.1 | 2.1 |  |  |  | 2019-01-14 | 2019-10-11 | 2021-02-06 | • Reduction in forced outages of pumps. • Reduction in downtime of machine during repair works. • Increase in availability / healthiness of the pumps. • Reduction in auxiliary power consumption due to increase in efficiency of pumps. | 0 | 1.8279 |  |  | 1.8279 | [9 empty] | 100% | [5 empty] | 0 | 0 | 1.8279 |  | 1.8279 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/04320 | 2017-03-21 | 2017-10-11 | 0.17 | 0.17 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
17 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | DPR | MERC/CAPEX/20172018/04072 | 2017-07-18 | 2017-08-18 | 11.3 | 11.3 |  |  | 2017-08-18 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
17.1 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | Scheme | MERC/CAPEX/20172018/04072 | 2017-07-18 | 2017-08-18 | 11.3 | 11.3 |  |  | 2017-08-18 | 2018-02-27 | 2019-08-18 | 2019-08-06 | A) By implementation of this scheme, directives of ministry of environment, Forest and climate change dt. 07-12-15 on consumption of water by thermal power plant will be achieved. B) After implemantion of the said scheme, estimated annual saving of Rs.40.88 lakhs (considering concessional rates is envisaged) | 12.8838 |  |  |  | 12.8838 | [8 empty] | 100% | [6 empty] | 12.8838 |  |  |  | 12.8838 | [10 empty] | Capitalised
18 | Provision of S&T System for In Plant Yard Khaperkheda & Kalumni Yard (Depository Work) and Modification of Kalumna Yard Alteration No. 5 (Depository Work) | DPR | MERC/CAPEX/20172018/4779 | 2017-09-06 | 2017-11-28 | 31.52 | 31.52 |  |  | 2017-11-28 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
18.1 | Provision of S & T System to Khaperkheda TPS In-Plant yard and Kalumna Yard (Depository Work) | Scheme | MERC/CAPEX/20172018/4779 | 2017-09-06 | 2017-11-28 | 17.75 | 17.75 |  |  | 2017-11-28 |  | 2019-03-31 |  | 1. Increase in operational efficiency of existing system; 2. It helps to reduce rail accident & derailment. 3. It will help to reduce demurages. 4.Railway wagons can be load directly on tippler A&B. 5. It will be operate from control room & it reduce human intervention. 6.Consultancy services help to compelte the project with quality monitoring. | 0.041975 | 0 | 0 | 0 | 0.041975 | 0 | 0 | 17.01 | 3 | [10 empty] | 100% | 0.041975 |  |  |  | 0.041975 |  |  |  | 20.01 | [6 empty] | WIP
18.2 | Modification of Kalumna Yard Alternation no. 5 in connection with Khaperkheda TPS Expansion Project (1x500 MW) construction of B.G. Railway Siding | Scheme | MERC/CAPEX/20172018/4779 | 2017-09-06 | 2017-11-28 | 13.77 | 13.77 |  |  | 2017-11-28 | 2017-04-24 | 2019-03-31 | 2022-02-22 |  | 0 | 13.77 |  |  | 13.77 | 13.5159 | [10 empty] | 100% |  |  |  | 0 | 0 | 0 | 0 | 0 | 13.5159 | [8 empty] | DEPOSITORY WORK.WCR RECEIVED FROM RAILWAY ON DT 12 MARCH 2022 | Capitalised
19 | Construction of Limited Height Subway (LHS) at unmanned road level crossing by Railway on cost sharing basis with MSPGCL on Khaperkheda-Kalumna railway siding and saoner-Khaperkheda railway siding | DPR | MERC/CAPEX/20172018/0178 | 2017-12-16 | 2018-02-02 | 16.81 | 16.81 |  |  | 2018-02-02 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
19.1 | Construction of LHS on Khaperkheda Kalumna railway side | Scheme | MERC/CAPEX/20172018/0178 | 2017-12-16 | 2018-02-02 | 5.94 | 5.94 |  |  | 2018-02-02 | 2018-03-23 | 2019-03-31 | 2021-07-27 | The benefits expected by implementation of the proposed schemes are as follows: Construction of Limited Height Subway (LHS) at Unmanned road Level Crossing by Railway on Cost sharing basis with MSPGCL on Khaperkheda – Kalumna railway siding and Saoner – Khaperkheda railway siding. 1. LHS have less fixed cost as compared to Manning (for a period of 20 year) 2. Average cost of construction, maintenance & operation of RUB Rs. 3.85 Cr. 3. Cost of construction, maintenance & operation of level crossing Rs. 10.69 crores which is much more in compare to LHS 4. LHS improves operational efficiency. Presence of manned LCs increases work load of SS. It also causes slowing down of trains due to delay in closure of gates, Loco pilots also have psychological pressure to observe LC hence they tend to loose speed. 5. Due to failure of signal, tele-communication, gate boom the railway traffic suffer badly. Trains to be controlled piloted leading to extra burden on station staff detention to traffic. Though this can’t be qualified in financial terms but it will give substantial benefits in terms of improved average speed less failure etc. 6. Presence of LC poses hindrance to smooth maintenance of track. Due to rigid structure it is a potential bad riding location and need frequent attention by deployment of skilled resources. This also necessitates imposition of speed restriction for overhauling. Check rail replacement and other maintenance works. Special resources and efforts are required to be deployed for carrying out maintenance of track involving LCs. 7. Presence of LCs is a potential safety threat. In past many accidents involving loss of lives, property detention to traffic has taken place on the LCs of Railway. 8. Due to huge bearing on safety, LCs are one of the most inspected asset on Railway. Hence railway has to consume huge resources in their inspections. 9. Provision of LHS eliminates detention to road users, reduces fuel consumption and environmental pollution | 0 | 0 | 0 | 4.9899 | 4.9899 | [11 empty] | 100% |  |  |  | 0 | 0 | 0 | 4.9899 | 4.9899 | [9 empty] | WCR RECEIVED FROM RAILWAY DEPARTMENT | Capitalised
19.2 | Construction of LHS on Khaperkheda Saoner railway line | Scheme | MERC/CAPEX/20172018/0178 | 2017-12-16 | 2018-02-02 | 10.87 | 10.87 |  |  |  | 2018-03-23 | 2019-03-31 | 2021-07-27 | The benefits expected by implementation of the proposed schemes are as follows: Construction of Limited Height Subway (LHS) at Unmanned road Level Crossing by Railway on Cost sharing basis with MSPGCL on Khaperkheda – Kalumna railway siding and Saoner – Khaperkheda railway siding. 1. LHS have less fixed cost as compared to Manning (for a period of 20 year) 2. Average cost of construction, maintenance & operation of RUB Rs. 3.85 Cr. 3. Cost of construction, maintenance & operation of level crossing Rs. 10.69 crores which is much more in compare to LHS 4. LHS improves operational efficiency. Presence of manned LCs increases work load of SS. It also causes slowing down of trains due to delay in closure of gates, Loco pilots also have psychological pressure to observe LC hence they tend to loose speed. 5. Due to failure of signal, tele-communication, gate boom the railway traffic suffer badly. Trains to be controlled piloted leading to extra burden on station staff detention to traffic. Though this can’t be qualified in financial terms but it will give substantial benefits in terms of improved average speed less failure etc. 6. Presence of LC poses hindrance to smooth maintenance of track. Due to rigid structure it is a potential bad riding location and need frequent attention by deployment of skilled resources. This also necessitates imposition of speed restriction for overhauling. Check rail replacement and other maintenance works. Special resources and efforts are required to be deployed for carrying out maintenance of track involving LCs. 7. Presence of LCs is a potential safety threat. In past many accidents involving loss of lives, property detention to traffic has taken place on the LCs of Railway. 8. Due to huge bearing on safety, LCs are one of the most inspected asset on Railway. Hence railway has to consume huge resources in their inspections. 9. Provision of LHS eliminates detention to road users, reduces fuel consumption and environmental pollution | 0 | 0 | 0 | 9.78 | 9.78 | [11 empty] | 100% |  |  |  | 0 | 0 | 0 | 9.78 | 9.78 | [9 empty] | WORK COMPLETED BUT WCR IS AWAITED FROM RAILWAY DEPARTMENT.They demanded additional amount for 10th LHS consructed by them.As per BR Total 10 LHS are approved and as per MERC approval 9 LHS are approved .Letter send to CE Civil 3 for approval of additional amount and letter given to railway for submission of WCR for 9 LHS only.Both reply awaited. | Capitalised
20 | Utilisation of unused water scheme from Bhanegaon open cast mine & construction of RCC internal roads at Khaperkheda TPS | DPR | MERC/CAPEX/20172018/0197 | 2017-12-16 | 2018-02-06 | 11.5329 | 11.5329 |  |  | 2018-02-06 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
20.1 | Utilization of unused water scheme from Bhanegaon Open cast mine | Scheme | MERC/CAPEX/20172018/0197 | 2017-12-16 | 2018-02-06 | 7.5469 | 7.5469 |  |  | 2018-02-06 | 2018-05-22 | 2020-02-06 | 2019-08-09 | 1. Additional water supply to Khaperkheda TPS, free of cost from WCL. 2. Land acquisition is not required.. 3. As pipe line is proposed to lay underground, access across the pipeline alignment is not disturbed or affected. 4. Expensive expansion joints and pipe line supports are not required. 5. Maintenance cost is reduced. 6. The passive pressure from the ground provides extra strength to the pipe. | 4.0571 | 5.4293 | 0 | 3.2136 | 12.7 | 0.23666 | [10 empty] | 100% |  |  |  | 0 | 0 | 0 | 12.7036 | 12.7036 | 0.23666 | [9 empty] | Capitalised
20.2 | Construction of Cement Concrete Road Inside Part Of Power House | Scheme | MERC/CAPEX/20172018/0197 | 2017-12-16 | 2018-02-06 | 2.906 | 2.906 |  |  | 2018-02-06 | 2018-06-29 | 2020-02-06 | 2019-04-27 | a) Vehicle will move in safe condition. b) Accidents / Casualties will be avoided by providing the Cement Concrete. c) The expenditure of regular maintenance of road will be zero. d) This rout can be use as internal shortest route. e) It will reduce regular maintenance costs on vehicle plying through this route. f) Air / Environment pollution will be minimum. | 1.867 | 0.80621 |  |  | 2.6732 | [9 empty] | 100% | [5 empty] | 0 | 2.6732 |  |  | 2.6732 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/0197 | 2017-12-16 | 2018-02-06 | 1.08 | 1.08 |  |  | 2018-02-06 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | DPR | MERC/CAPEX/2018-2019/105 | 2018-08-23 | 2019-04-05 | 3.4 | 3.4 |  |  | 2019-04-05 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
21.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIMT 2000 (72° PA) | Scheme | MERC/CAPEX/2018-2019/105 | 2018-08-23 | 2019-04-05 | 3.4 | 3.4 |  |  | 2019-04-05 | 2021-11-26 | 2021-04-05 |  | To maintain APH performance & boiler efficiency |  | 0 | 0 | 0 | 0 | 3.835 | [11 empty] | 100% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.835 | [7 empty] | WIP
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | DPR | MERC/CAPEX/2019-2020/799 | 2019-04-03 | 2019-09-27 | 5.18 | 5.18 |  |  | 2019-09-27 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | Scheme | MERC/CAPEX/2019-2020/799 | 2019-04-03 | 2019-09-27 | 4.17 | 4.17 |  |  | 2019-09-27 | 2021-01-22 | 2021-09-27 |  | 1. Overall reliability of power plant will be increased due to 100% availibility of breakers 2. Life of breaker system will be enhanced. |  |  |  | 2.7397 | 2.7397 | 0.46296 | [18 empty] | 0 | 3.2027 | [8 empty] | capitalised in FY 2022-23 | Capitalised | capitalised
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | Scheme | MERC/CAPEX/2019-2020/799 | 2019-04-03 | 2019-09-27 | 5.18 | 5.18 |  |  | 2019-09-27 | 2021-01-22 | 2021-09-27 |  | 1. Overall reliability of power plant will be increased due to 100% availibility of breakers 2. Life of breaker system will be enhanced. |  | 0 | 0 | 0 | 0 | 1.9759 | 0.23671 | [10 empty] | 100% | [6 empty] | 0 |  | 2.2126 | [7 empty] | capitalised in FY 2023-24 | Capitalised
27 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | DPR | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2019-12-09 | 2021-01-25 | 280.82 | 280.82 |  |  | 2021-01-25 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
27.1 | Flue Gas Desulphurization (FGD) System for KPKD 5 | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2019-12-09 | 2021-01-25 | 260.21 | 260.21 |  |  | 2021-01-25 | [7 empty] | 0 | 0 |  |  | 84.92 | 311.36 | 169.83 | [9 empty] | 100% |  |  |  | 0 | 0 | 0 | 0 | 84.92 | 311.36 | 169.83 |  |  |  |  | NIT Issued on: 08.12.2021. Price bid opened on 09.05.2022. GoM directives are awaited for further tender activities. | WIP
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2019-12-09 | 2021-01-25 | 20.61 | 20.61 |  |  | 2021-01-25 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
BSL DPR-10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | DPR | MERC/CAPEX/20172018/4782 | 2017-05-20 | 2017-11-28 | 4.24 | 4.24 |  |  | 2017-11-28 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
BSL DPR-10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | Scheme | MERC/CAPEX/20172018/4782 | 2017-05-20 | 2017-11-28 | 4.24 | 4.24 |  |  | 2017-11-28 | 2019-04-20 | 2019-11-28 | 2020-08-07 | recommended Electrical & C&I spares for Khaparkheda TPS 500MW | 0 | 0 | 4.5033 |  | 4.5033 | [10 empty] | 100% |  |  |  |  | 0 | 0 | 4.5033 |  | 4.5033 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/4782 | 2017-05-20 | 2017-11-28 | 0.20576 | 0 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | DPR | MERC/CAPEX/2017-18/0208 | 2017-12-13 | 2018-02-08 | 269.4076 | 269.4076 |  |  | 2018-02-08 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | Scheme | MERC/CAPEX/2017-18/0208 | 2017-12-13 | 2018-02-08 | 269.4076 | 269.4076 |  |  | 2018-02-08 | 2018-08-03 | 2019-11-08 | 2024-03-31 | The key benefit of this conveying system is as follows: o Lesser cost of transport per Km / Ton. o Social benefit by eliminating congestion of connected road. o Environmentally more friendly. o More reliable, does not depend on vagaries of weather. o Less pilferage. | 27.18 | 114.61 | 78.52 | 48.99 | 269.3 | 44.28 | 67.44 | 196.92 | [5 empty] | 16% | 48% | 70% | 90% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 124.5068 | 67.6265 | 196.92 | [6 empty] | Scheme wil be capitalised in FY 2024-25 December-24.Please obtain further details from CE(P&P)/CE(Project),Koradi. | Partially Capitalized
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | DPR | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-04-18 | 2018-07-24 | 1.34 | 1.34 |  |  | 2018-07-24 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | Scheme | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-04-18 | 2018-07-24 | 1.23 | 1.23 |  |  | 2018-07-24 | 2019-02-25 | 2020-07-24 | 2021-11-07 | As per national & state water policy, priority is to be given to drinking use & agricultaral use of water. Mspgcl will be using GOI & GOM policy to use treated sewage water for therma plants to minimize the use of fresh water & to reduce pollutions in rivers of nagpur & gosi khurd dam.Also, to avoid situation to stop thermal plants due to non availibility of water. |  | 1.1995 | 0.48314 | 0.12161 | 1.8042 | [11 empty] | 100% |  |  |  | 0 | 0 | 0 | 1.8042 | 1.8042 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-04-18 | 2018-07-24 | 0.11 | 0.11 |  |  | 2018-07-24 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | DPR | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 4.0922 | 4.0922 |  |  | 2020-10-27 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 15.5 | Electromagnetic Flow meters at various lines & Locations of 500 MW | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 3.2497 | 3.2497 |  |  | 2020-10-27 |  | 2021-10-27 |  | As per recommendation of MPCB, online water flow monitoring system is required for carrying out Water Audit. This scheme comes under category No. 3.1(l) Fulfilment of any statutory compliance requirement. |  |  |  |  | 0 |  |  | 3.2497 | [10 empty] | 100% | [5 empty] | 0 |  |  | 3.2497 | [7 empty] | WIP
HO DPR 15.6 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | Scheme | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 0.84252 | 0.84252 |  |  | 2020-10-27 |  | 2021-10-27 |  | As per recommendation of MPCB, online water flow monitoring system is required for carrying out Water Audit. This scheme comes under category No. 3.1(l) Fulfilment of any statutory compliance requirement. |  |  |  |  | 0 |  |  | 0.84 | [10 empty] | 100% | [5 empty] | 0 |  |  | 0.84 | [7 empty] | WIP
| IDC | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2019-10-14 | 2020-10-27 | 0 | 0 |  |  | 2020-10-27 |  | 2021-10-27 | [6 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | DPR | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2022-11-26 | 2023-10-09 | 45.0535 | 45.0535 | [11 empty] | 0 | [19 empty] | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2022-11-26 | 2023-10-09 | 31.0231 | 31.0231 | [11 empty] | 0 |  |  | 45.31 | [16 empty] | 0 |  |  | 45.31 | [6 empty] | Scheme will be capitalised in FY 2024-25 (60% cost considered in 500MW) | WIP
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2022-11-26 | 2023-10-09 | 1.6569 | 1.6569 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | WIP
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2022-11-26 | 2023-10-09 | 10.1857 | 10.1857 | [11 empty] | 0 | [19 empty] | 0 | [10 empty] | WIP
|  | IDC | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2022-11-26 | 2023-10-09 | 2.1878 | 2.1878 | [11 empty] | 0 | [19 empty] | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 113.91 | 57 | [11 empty] | 0 | [19 empty] | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 108.48 | 54.24 | [11 empty] | 0 | [19 empty] | 0 | [9 empty] | No data available to this office regarding this DPR | To be confirmed
| IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 5.43 | 2.76 | [11 empty] | 0 | [19 empty] | 0
HO DPR 16 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 69.309 | 69.309 | [11 empty] | 0 | [19 empty] | 0
1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 66.009 | 66.009 | [11 empty] | 0 | [19 empty] | 0 | [9 empty] | No data available to this office regarding this DPR | To be confirmed
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 3.3 | 3.3 | [11 empty] | 0 | [19 empty] | 0
35 | Boiler Performance improvement Six Schemes at Unit-5 Khaperkheda TPS | DPR | Yet to be approved | 2022-05-26 |  | 65.36 | [12 empty] | 0 | [19 empty] | 0
35.1 | Sch-1: Procurement & Replacement of LTSH coils at U#5 | Scheme | Yet to be approved | 2022-05-26 |  | 17.52 | [7 empty] | 1.For reducing generation loss on account of BTL. 2.For ensuring reliability of operation. |  |  |  |  | 0 |  |  |  |  | 17.52 | [14 empty] | 0 |  |  |  |  | 17.52 |  |  |  |  | This DPR was rejected by Hon MERC as per reference No.MERC/CAPEX/2024-2025/MSPGCL/0480 Dtd. 06.08.2024 | Not Initiated
35.2 | Sch-2: Procurement & Replacement of Economizer coils at U#5 | Scheme | Yet to be approved | 2022-05-26 |  | 33.91 | [7 empty] | 1.For reducing generation loss on account of BTL. 2. For ensuring reliability of operation. |  |  |  |  | 0 |  |  |  |  | 33.91 | [14 empty] | 0 |  |  |  |  | 33.91 |  |  |  |  | This DPR was rejected by Hon MERC as per reference No.MERC/CAPEX/2024-2025/MSPGCL/0480 Dtd. 06.08.2024 | Not Initiated
35.3 | Sch-3: Procurement & Replacement of Water wall Z-Panels & Soot blower Panels at U#5: | Scheme | Yet to be approved | 2022-05-26 |  | 7.06 | [7 empty] | 1. For reducing generation loss on account of BTL. 2.For ensuring reliability of operation. |  |  |  |  | 0 |  |  |  |  | 7.06 | [14 empty] | 0 |  |  |  |  | 7.06 |  |  |  |  | This DPR was rejected by Hon MERC as per reference No.MERC/CAPEX/2024-2025/MSPGCL/0480 Dtd. 06.08.2024 | Not Initiated
35.4 | Sch-4 : Supply and erection of APH Inlet & Outlet Flue Gas Damper Assemblies along with actuators at U#5 | Scheme | Yet to be approved | 2022-05-26 |  | 2.08 | [7 empty] | 1. For reducing generation loss on account of BTL. 2. For ensuring reliability of operation. |  |  |  |  | 0 |  |  |  |  | 2.08 | [14 empty] | 0 |  |  |  |  | 2.08 |  |  |  |  | This DPR was rejected by Hon MERC as per reference No.MERC/CAPEX/2024-2025/MSPGCL/0480 Dtd. 06.08.2024 | Not Initiated
35.5 | Sch-5 : Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines at U#5. | Scheme | Yet to be approved | 2022-05-26 |  | 3.58 | [7 empty] | 1. The heat loss will be reduced. |  |  |  |  | 0 |  |  |  |  | 3.58 | [14 empty] | 0 |  |  |  |  | 3.58 |  |  |  |  | This DPR was rejected by Hon MERC as per reference No.MERC/CAPEX/2024-2025/MSPGCL/0480 Dtd. 06.08.2024 | Not Initiated
| IDC | IDC | Yet to be approved | 2022-05-26 |  | 1.21 | [12 empty] | 0 |  |  |  |  | 1.21 | [14 empty] | 0 |  |  |  |  | 1.21
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | DPR | MERC/CAPEX/2018-2019/1242 | 2018-07-10 | 2018-09-22 | 15.7443 | 15.7443 |  |  | 2018-09-22 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | N.A.
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | Scheme | MERC/CAPEX/2018-2019/1242 | 2018-07-10 | 2018-09-22 | 4.2068 | 4.2068 |  |  | 2018-09-22 |  |  |  |  | 0 |  |  |  | 0 | [19 empty] | 0 | [10 empty] | To be confirmed
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | Scheme | MERC/CAPEX/2018-2019/1242 | 2018-07-10 | 2018-09-22 | 11.5375 | 11.5375 |  |  | 2018-09-22 | [8 empty] | 0 | [19 empty] | 0 | [10 empty] | To be confirmed
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | DPR | MERC/CAPEX/2024-2025/478 | 2024-01-31 | 2024-08-06 | 33.76 | 25.43 | [11 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
2.1 | Up-gradation of maxDNA DCS system (HMI Up-gradation) at Unit-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-01-31 | 2024-08-06 | 7.29 | 7.29 | [6 empty] | Microsoft has already withdrawn Window XP and its product support, and it has been replaced with latest version OS with 64-bit architecture. Outdated Hardware needs upgradation in order to reduce breakdown. It will come under 3.2 (g) Obsolescence of assets and absence of support from Original Equipment Manufacturer. |  |  |  |  | 0 |  |  |  | 7.29 | [15 empty] | 0 |  |  |  | 7.29 | [6 empty] | Not Initiated
2.2 | Up-gradation of PLC (GE FANUC make) SYSTEM (HMI & hardware up-gradation) at Ash Handling Plant, Compressor Plant, and Condensate Polishing Unit (CPU) at Unit-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-01-31 | 2024-08-06 | 1.14 | 1.14 | [6 empty] | Microsoft has already withdrawn Window XP and its product support, and it has been replaced with latest version OS with 64-bit architecture. It will come under 3.2 (g) Obsolescence of assets and absence of support from Original Equipment Manufacturer. |  |  |  |  | 0 |  |  |  | 1.14 | [15 empty] | 0 |  |  |  | 1.14 | [6 empty] | Not Initiated
2.3 | Up-gradation of PLC (Schneider make) system (HMI & HARDWARE Up-gradation) at DM Plant, PTP, FF plant, CMRH System, HVAC System, FOPH system at U-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-01-31 | 2024-08-06 | 4.26 | 4.26 | [6 empty] | Microsoft has discontinued the product support for XP operating system and disabled automatic security updates. Microsoft have advised users to go for the latest OS. This will ensure safe and better response of PLC. It will come under 3.2 (g) Obsolescence of assets and absence of support from Original Equipment Manufacturer. |  |  |  |  | 0 |  |  |  | 4.26 | [15 empty] | 0 |  |  |  | 4.26 | [6 empty] | Not Initiated
2.4 | Up-gradation of SWAS (STEAM WATER ANALYSIS SYSTEM) Installed at Unit-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-01-31 | 2024-08-06 | 4.71 | 4.71 | [6 empty] | 3.1(e)This will Increase in operational efficiency of existing system; Also this will Increase in the 3.1(f)Useful Life of the entire project/scheme/assets; After upgradation3.1(k) Improvement in system parameters |  |  |  |  | 0 |  |  |  | 4.71 | [15 empty] | 0 |  |  |  | 4.71 | [6 empty] | Not Initiated
2.5 | Up-gradation of Carbon monoxide analyzer in Flue Gas Installed at Unit-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-01-31 | 2024-08-06 | 1.02 | 1.02 | [6 empty] | Carbon monoxide Analyser improves combustion efficiency resulting in heat rate improvement. CO monitoring and control, reduces heat loss in flue gas of second pass. This scheme comes under category No 3.1(e) Increase in operational efficiency of existing system; 3.1(k) Improvement in system parameters. |  |  |  |  | 0 |  |  |  | 1.02 | [15 empty] | 0 |  |  |  | 1.02 | [6 empty] | Not Initiated
2.6 | Up-gradation of Coal feeder Controller at U-5. | Scheme | MERC/CAPEX/2024-2025/478 | 2024-01-31 | 2024-08-06 | 7.01 | 7.01 | [6 empty] | Upgradation of coal feeder controller results in 3.1(e) Increase in operational efficiency of existing system along with 3.1(k) Improvement in system parameters. |  |  |  |  | 0 |  |  |  | 7.01 | [15 empty] | 0 |  |  |  | 7.01 | [6 empty] | Not Initiated
| IDC |  | MERC/CAPEX/2024-2025/478 | 2024-01-31 | 2024-08-06 | 0.86 | 0.86 | [11 empty] | 0 |  |  |  | 0.86 | [15 empty] | 0 |  |  |  | 0.86 | [6 empty] | Not Initiated
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | DPR | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2022-11-16 | 2024-04-18 | 11.75 | 11.75 | [11 empty] | 0 | [19 empty] | 0
35.1 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | Scheme | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2022-11-16 | 2024-04-18 | 0.89 | 0.89 | [11 empty] | 0 |  |  | 0.89 | [16 empty] | 0 |  |  | 0.89 | [6 empty] | Expected to be capitalised in FY 2024-25.PROCUREMENT IS IN PROCESS AT HO CE(CPA) | WIP
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | DPR | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2023-07-24 | 2024-02-27 | 5.43 | 5.43 | [11 empty] | 0 | [19 empty] | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | Scheme | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2023-07-24 | 2024-02-27 | 5.43 | 5.43 | [11 empty] | 0 |  |  |  | 5.34 | [15 empty] | 0 |  |  |  | 5.34 | [6 empty] | WIP
[19 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0
| (ii) Submitted to MERC, Yet to receive approval | [17 empty] | 0 | [19 empty] | 0
[19 empty] | 0 | [19 empty] | 0
| (ii) Yet to be submitted to MERC | [17 empty] | 0 | [19 empty] | 0
1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | DPR |  |  |  | 230 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
1.1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | Scheme |  |  |  | 230 | [7 empty] | • It helps to avoid contamination of sub-soil and water table at ash bund. • To minimize water pollution in nearby wells and Pench river. • Additional well provides ease to quick discharge of slurry water into the sump of pump house. • Lagoon construction will provide easy movement of vehicle inside the bund required for inspection frequently. • Nallah diversion work will be helpful to quick discharge of seepage water, • It will also helpful to protect the surrounding farms land from submergence. • Dependency on Waregaon ash bund decreases *Statutary requirement as per MPCB guidelines. |  |  |  |  | 0 |  |  |  |  | 230 | [14 empty] | 0 |  |  |  |  | 230 | [5 empty] | N.A.
2 | DPR7 SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | DPR |  |  |  | 29.71 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
2.1 | Supply Installation Testing & Commissioning , Revamping of fire detection & alarm and protection system from fire and providing rapid extinguishing clean agent (CA) system at unit # 5 at 500 MW khaperkheda TPS | Scheme |  |  |  | 23.21 | [7 empty] | 1.Statutary requirement 2.To increase human and machine safety |  |  |  |  | 0 |  |  |  |  | 23.21 | [14 empty] | 0 |  |  |  |  | 23.21 | [5 empty] | Not Initiated
3 | Restoration of various Fire protection system at Khaperkheda TPS | DPR |  |  |  | 60.63 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
3.1 | Restoration of fire alarm valve with water spray system (DV) at CHP-II 500 MW | Scheme |  |  |  | 22.05 | [7 empty] | 1.Statutary requirement 2.To increase human and machine safety |  |  |  |  | 0 |  |  |  |  | 22.05 | [14 empty] | 0 |  |  |  |  | 22.05 | [5 empty] | Not Initiated
4 | Boiler Performance improvement scheme | DPR |  |  |  | 47.55 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
4.1 | Modular Duct | Scheme |  |  |  | 21.5 | [7 empty] | 1.APC disallowance will be reduced. 2.Normative 6% APC will be achieved by reducing ID current. |  |  |  |  | 0 |  |  |  |  | 21.5 | [14 empty] | 0 |  |  |  |  | 21.5 | [5 empty] | Not Initiated
4.2 | PA Fan Rotor Assy. | Scheme |  |  |  | 3.5 | [7 empty] | 1. Generation loss on account of PA Fan will be reduced. |  |  |  |  | 0 |  |  |  |  | 3.5 | [14 empty] | 0 |  |  |  |  | 3.5 | [5 empty] | Not Initiated
4.3 | Bottom ash & coarse ash system | Scheme |  |  |  | 3 | [7 empty] | 1) increase in operational efficiency of existing system 2) Increase in the Useful Life of the entire project/scheme/assets; 3): Reduction in maintenance requirements 4): improvement of system parameters |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
4.4 | Design Supply and erection of bottom ash hopper and Coarse ash hoppers. | Scheme |  |  |  | 10 | [7 empty] | 1) increase in operational efficiency of existing system 2) Increase in the Useful Life of the entire project/scheme/assets; 3): Reduction in maintenance requirements 4): improvement of system parameters |  |  |  |  | 0 |  |  |  |  | 10 | [14 empty] | 0 |  |  |  |  | 10 | [5 empty] | Not Initiated
4.5 | Platform | Scheme |  |  |  | 3.96 | [7 empty] | 1.Zero mandays loss due to safe platform erection. 2.Timely attending duct leakages and works at height. |  |  |  |  | 0 |  |  |  |  | 3.96 | [14 empty] | 0 |  |  |  |  | 3.96 | [5 empty] | Not Initiated
4.6 | Refurbishment of BCW | Scheme |  |  |  | 3.59 | [7 empty] | 1. To reduce/avoid the generation loss due to non availability of BCW drive. 2.To increase the reliability and availability |  |  |  |  | 0 |  |  |  |  | 3.59 | [14 empty] | 0 |  |  |  |  | 3.59 | [5 empty] | Not Initiated
4.7 | Boiler Lift performance | Scheme |  |  |  | 2 | [7 empty] | 1.Availability of lifts will curtail the heavy material transportation time to boiler during shut down/AOH/COH/running plant. 2.Statutory requirement. |  |  |  |  | 0 |  |  |  |  | 2 | [14 empty] | 0 |  |  |  |  | 2 | [5 empty] | Not Initiated
5 | Boiler Performance improvement scheme | DPR |  |  |  | 25 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
5.1 | Water Wall Soot Blower Panels | Scheme |  |  |  | 8.5 | [7 empty] | 1. For reduction in generation loss due to BTL in Water Wall Soot Blower zone. 2. For ensuring reliability of Operation in future. 3.AOH to AOH water wall soot blower panels are replaced due to steam erosion and substantial repairing time reduced due to availability of water wall soot blower panels. |  |  |  |  | 0 | [6 empty] | 8.5 | [12 empty] | 0 | [6 empty] | 8.5 |  |  |  | Not Initiated
5.2 | Thermal Insulation | Scheme |  |  |  | 3.7 | [7 empty] | 1.The heat loss will be reduced. |  |  |  |  | 0 | [6 empty] | 3.7 | [12 empty] | 0 | [6 empty] | 3.7 |  |  |  | Not Initiated
5.3 | APH Baskets | Scheme |  |  |  | 6 | [7 empty] | 1. APH baskets are replaced after @ 4 to 5 years on the basis of replacement criteria by OEM. 2. APH efficiency will be improve. |  |  |  |  | 0 | [6 empty] | 6 | [12 empty] | 0 | [6 empty] | 6 |  |  |  | Not Initiated
5.4 | Errection & Commisioning of Additional Soot blower | Scheme |  |  |  | 1.8 | [7 empty] | 1. Temp. excursion and overheating will be reduced. 2. Reheat spray will be reduced. |  |  |  |  | 0 | [6 empty] | 1.8 | [12 empty] | 0 | [6 empty] | 1.8 |  |  |  | Not Initiated
5.5 | PA Fan Rotor | Scheme |  |  |  | 3.5 | [7 empty] | 1. Generation loss on account of PA Fan will be reduced. |  |  |  |  | 0 | [6 empty] | 3.5 | [12 empty] | 0 | [6 empty] | 3.5 |  |  |  | Not Initiated
5.6 | Coal Compartment Assembly | Scheme |  |  |  | 1.5 | [7 empty] | 1. For combustion optimization. |  |  |  |  | 0 | [6 empty] | 1.5 | [12 empty] | 0 | [6 empty] | 1.5 |  |  |  | Not Initiated
6 | Upgradation of Process field instruments and PLCs hardware for performance improvement . | DPR |  |  |  | 38 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
6.1 | Upgradation of Emerson make PLC controllers and I/O (AHP) | Scheme |  |  |  | 5 | [7 empty] | Outdated Hardware needs upgradation in order to reduce breakdown. 3.2 (g) Obsolescence of assets and absence of support from Original Equipment Manufacturer. |  |  |  |  | 0 | [5 empty] | 5 | [13 empty] | 0 | [5 empty] | 5 |  |  |  |  | Not Initiated
6.2 | Upgradation of WTP & CHP PLC I/O and network accessories (BOP & CHP) | Scheme |  |  |  | 10 | [7 empty] | OEM has discontinued the product support forexisting I/Os cards, network modules, backplanes. OEM have advised users to go for the upgradation of latest hardware. Due to Obsolescence of assets and absence of support from Original Equipment Manufacturer. |  |  |  |  | 0 | [6 empty] | 10 | [12 empty] | 0 | [6 empty] | 10 |  |  |  | Not Initiated
6.3 | Upgradation of Pressure, flow, level transmitter, hydrastep, | Scheme |  |  |  | 3 | [7 empty] | This scheme will increase operation efficiency of existing system as per clause no.3.1(e). |  |  |  |  | 0 | [6 empty] | 3 | [12 empty] | 0 | [6 empty] | 3 |  |  |  | Not Initiated
6.4 | Upgradation of Scanner , Ignitors, Solonoid system , relay of FSSS | Scheme |  |  |  | 3.5 | [7 empty] | This scheme will increase operation efficiency of existing system and improve in reliability as per clause no.3.1(e, g). Upgradation of new technologically advance scanner, ignitors and solonoids results in efficient combustion. |  |  |  |  | 0 | [5 empty] | 3.5 | [13 empty] | 0 | [5 empty] | 3.5 |  |  |  |  | Not Initiated
6.5 | Upgradation of control valves and cylinders instrumentation | Scheme |  |  |  | 5 | [7 empty] | Upgradation of new technologically advance instrumentation results in efficient and fast control.This scheme will increase operation efficiency of existing system and improve in reliability as per clause no.3.1(e, g). |  |  |  |  | 0 | [6 empty] | 5 | [12 empty] | 0 | [6 empty] | 5 |  |  |  | Not Initiated
6.6 | Upgradation of ETP, Debris ,OLCC plc system | Scheme |  |  |  | 3 | [7 empty] | Upgradation of new technologically advance PLC results in efficient and fast control which can increase condenser efficiency. OEM has discontinued the product support forexisting I/Os cards, network modules, backplanes. OEM have advised users to go for the upgradation of latest hardware. This will ensure safe and better response of PLC. 3.1(e) & 3.2 (g) Obsolescence of assets and absence of support from Original Equipment Manufacturer. . |  |  |  |  | 0 | [6 empty] | 3 | [12 empty] | 0 | [6 empty] | 3 |  |  |  | Not Initiated
6.7 | Upgradation of Nucleonic density meter | Scheme |  |  |  | 2 | [7 empty] | Nucleonic Density meter needs upgradation due to fulfilment of its statutory compliance requirement. 3.1(l). |  |  |  |  | 0 | [6 empty] | 2 | [12 empty] | 0 | [6 empty] | 2 |  |  |  | Not Initiated
6.8 | Upgradation of environment related instruments | Scheme |  |  |  | 2.5 | [7 empty] | Upgradation of Environmental instruments such as Flue gas , Effluent analyser and various parameters which is hazardous to environment is must due to strict environment norms. Flue gas and Effluent meter needs upgradation due to fulfilment of its statutory compliance requirement. 3.1(l). |  |  |  |  | 0 | [6 empty] | 2.5 | [12 empty] | 0 | [6 empty] | 2.5 |  |  |  | Not Initiated
6.9 | Installation of Furnace camera | Scheme |  |  |  | 2 | [7 empty] | Furnace camera is must to monitor quality of flame in order to confirm complete combustion which result in reduction in coal and Air consumption.This scheme falls under 3.1(e) which will increase operational efficiency. |  |  |  |  | 0 | [5 empty] | 2 | [13 empty] | 0 | [5 empty] | 2 |  |  |  |  | Not Initiated
6.1 | Installation of Flue gas exit temperature probe | Scheme |  |  |  | 2 | [7 empty] | Measurement of Flue gas Exit temperature play crucial role to ensure complete combution in first pass , avoid heat loss in furnace ,overheating of boiler tube. This scheme falls under 3.1(e) which will increase operational efficiency. |  |  |  |  | 0 | [7 empty] | 2 | [11 empty] | 0 | [7 empty] | 2 |  |  | Not Initiated
7 | Upgradation of Electrical Protection Systems | DPR |  |  |  | 44.5 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
7.1 | Upgradation of UPS system at 1X500MW KPKD TPS | Scheme |  |  |  | 10 | [7 empty] | 1.Increase in the Useful Life of the entire project/scheme/assets; 2. Replacement of Battery Sets and battery charger after completion of Useful Life and assets becoming irreparable; 3. Installation or upgradation of control and/or protection equipment ; |  |  |  |  | 0 | [6 empty] | 10 | [12 empty] | 0 | [6 empty] | 10 |  |  |  | Not Initiated
7.2 | Upgradation of battery charger system at 1X500MW KPKD TPS | Scheme |  |  |  | 10 | [7 empty] | 1. Increase in the Useful Life of the entire project/scheme/assets; 2. Replacement of Battery Sets and battery charger after completion of Useful Life and assets becoming irreparable; 3. Installation or upgradation of control and/or protection equipment ; |  |  |  |  | 0 | [7 empty] | 10 | [11 empty] | 0 | [7 empty] | 10 |  |  | Not Initiated
7.3 | Upgradation of ID Fan VFD system at 1X500MW KPKD TPS | Scheme |  |  |  | 5 | [7 empty] | 1. Increase in the Useful Life of the entire project/scheme/assets; 2.Replacement of Asset on account of inter-alia, completion of Useful Life and in beyond repairable condition, performance degradation, need for induction of new efficient technology; |  |  |  |  | 0 | [7 empty] | 5 | [11 empty] | 0 | [7 empty] | 5 |  |  | Not Initiated
7.4 | Upgradation of DAVR system at 1X500MW KPKD TPS | Scheme |  |  |  | 2.5 | [7 empty] | 1. Increase in the Useful Life of the entire project/scheme/assets; 2.Replacement of Asset on account of inter-alia, completion of Useful Life and in beyond repairable condition, performance degradation, need for induction of new efficient technology; |  |  |  |  | 0 | [7 empty] | 2.5 | [11 empty] | 0 | [7 empty] | 2.5 |  |  | Not Initiated
7.5 | Upgradation of protection relays at 1X500MW KPKD TPS | Scheme |  |  |  | 2.5 | [7 empty] | 1.Improvement in power quality and reliability 2.Installation or upgradation of control and/or protection equipment ; |  |  |  |  | 0 | [7 empty] | 2.5 | [11 empty] | 0 | [7 empty] | 2.5 |  |  | Not Initiated
7.6 | Retrofittiing of complete GE make panels | Scheme |  |  |  | 8 | [7 empty] | 1. Increase in the Useful Life of the entire project/scheme/assets; 2. Obsolescence of assets and absence of support from Original Equipment Manufacturer; |  |  |  |  | 0 | [6 empty] | 8 | [12 empty] | 0 | [6 empty] | 8 |  |  |  | Not Initiated
7.7 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP area at Unit# 5,Khaperkheda TPS. | Scheme |  |  |  | 1.5 | [7 empty] | 1.Increase in operational efficiency of existing system; 2. Replacement of Battery Sets and battery charger after completion of Useful Life and assets becoming irreparable; |  |  |  |  | 0 | [6 empty] | 1.5 | [12 empty] | 0 | [6 empty] | 1.5 |  |  |  | Not Initiated
7.8 | Retrofittiing of complete GE make panels | Scheme |  |  |  | 5 | [7 empty] | 1. Increase in the Useful Life of the entire project/scheme/assets; 2. Obsolescence of assets and absence of support from Original Equipment Manufacturer; |  |  |  |  | 0 | [7 empty] | 5 | [11 empty] | 0 | [7 empty] | 5 |  |  | Not Initiated
8 | Enhancement of HT/ LT Auxillaries and Illumination for betterment availability and reliability | DPR |  |  |  | 30.8 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
8.1 | Supply of 6.6 KV, 220 KW Ash Slurry Pump Motor for Unit # 5, TPS Khaperkheda | Scheme |  |  |  | 2 | [7 empty] | 1.Improvement in power quality and reliability 2. Reduction in maintenance requirements; |  |  |  |  | 0 | [6 empty] | 2 | [12 empty] | 0 | [6 empty] | 2 |  |  |  | Not Initiated
8.2 | Supply of 6.6 KV, 200 KW Fire Hydrant motor for Unit # 5, TPS Khaperkheda | Scheme |  |  |  | 0.6 | [7 empty] | 1.Improvement in power quality and reliability 2.Reduction in maintenance requirements; |  |  |  |  | 0 | [6 empty] | 0.6 | [12 empty] | 0 | [6 empty] | 0.6 |  |  |  | Not Initiated
8.3 | Supply of 690V, 800 KW GEHO Pump motor for Unit # 5, TPS Khaperkheda | Scheme |  |  |  | 1 | [7 empty] | 1.Improvement in power quality and reliability 2. Reduction in maintenance requirements; |  |  |  |  | 0 | [6 empty] | 1 | [12 empty] | 0 | [6 empty] | 1 |  |  |  | Not Initiated
8.4 | Refurbishment of BCW Pump Motor Sr. No. AP460044-3-2 | Scheme |  |  |  | 3.8 | [7 empty] | 1.Improvement in power quality and reliability 2. Reduction in maintenance requirements; |  |  |  |  | 0 | [6 empty] | 3.8 | [12 empty] | 0 | [6 empty] | 3.8 |  |  |  | Not Initiated
8.5 | Supply of Dry Type Transformers of Different Ratings for Unit # 5, TPS Khaperkheda. (Rates are inclusive of 2% Packing and forwarding charges & 2% Freight Charges) | Scheme |  |  |  | 3.4 | [7 empty] | 1.Improvement in power quality and reliability 2.Reduction in maintenance requirements; |  |  |  |  | 0 | [6 empty] | 3.4 | [12 empty] | 0 | [6 empty] | 3.4 |  |  |  | Not Initiated
8.6 | Supply of 3250KVA, 6.6/2.3 KV Oil Cooled VFD Transformer Of Vector Group Dyn11 and Ydn 11 & 25 MVA UAT For Unit# 5 At Khaperkheda TPS. (Including Packing and forwarding charges 2%, Freight Charges 2%) | Scheme |  |  |  | 7 | [7 empty] | 1.Improvement in power quality and reliability 2.Reduction in maintenance requirements; |  |  |  |  | 0 | [6 empty] | 7 | [12 empty] | 0 | [6 empty] | 7 |  |  |  | Not Initiated
8.7 | Enhancing conventional lighting system at by retrofitting and replacement with energy efficient LED Lighting system | Scheme |  |  |  | 9 | [7 empty] | 1. Reduction in maintenance requirements; 2.Replacement of Asset on account of inter-alia, completion of Useful Life and in beyond repairable condition, performance degradation, need for induction of new efficient technology; |  |  |  |  | 0 | [6 empty] | 9 | [12 empty] | 0 | [6 empty] | 9 |  |  |  | Not Initiated
8.8 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP & CHP area at Unit# 5,Khaperkheda TPS. | Scheme |  |  |  | 3 | [7 empty] | 1.Increase in operational efficiency of existing system; 2. Replacement of Battery Sets and battery charger after completion of Useful Life and assets becoming irreparable; |  |  |  |  | 0 | [6 empty] | 3 | [12 empty] | 0 | [6 empty] | 3 |  |  |  | Not Initiated
8.9 | supply of integrated solar light and CCTV Camera | Scheme |  |  |  | 1 | [7 empty] | 1.Fulfilment of any statutory compliance requirement; |  |  |  |  | 0 | [6 empty] | 1 | [12 empty] | 0 | [6 empty] | 1 |  |  |  | Not Initiated
9 | colony electrical renovation, switchgear, Energy meter, breaker,street light, 11 KV cable ,High Mast | DPR |  |  |  | 50 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
9.1 | Electrical Rennovation and mordernization of various tenaments buildings,offices, recreation clubs, Hospital, Domestic Pump House, PTP Plant and Admin Building | Scheme |  |  |  | 20 | [7 empty] | 1. Reduction in maintenance requirements; 2. Replacement of Asset on account of inter-alia, completion of Useful Life and in beyond repairable condition, performance degradation, need for induction of new efficient technology; |  |  |  |  | 0 | [6 empty] | 20 | [12 empty] | 0 | [6 empty] | 20 |  |  |  | Not Initiated
9.2 | Replacement of Distibution board, High Mast and switchgear at different areas of colony | Scheme |  |  |  | 10 | [7 empty] | 1. Reduction in maintenance requirements; 2. Replacement of Asset on account of inter-alia, completion of Useful Life and in beyond repairable condition, performance degradation, need for induction of new efficient technology; |  |  |  |  | 0 | [6 empty] | 10 | [12 empty] | 0 | [6 empty] | 10 |  |  |  | Not Initiated
9.3 | Replacement of Energy meter and various LT Motors at Domestic Pump House and PTP | Scheme |  |  |  | 3 | [7 empty] | 1. Reduction in maintenance requirements; 2.Replacement of Asset on account of inter-alia, completion of Useful Life and in beyond repairable condition, performance degradation, need for induction of new efficient technology; |  |  |  |  | 0 | [6 empty] | 3 | [12 empty] | 0 | [6 empty] | 3 |  |  |  | Not Initiated
9.4 | 11 KV Cable Work and various 11 KV Structure Rennovation Work | Scheme |  |  |  | 7 | [7 empty] | 1.Reduction in maintenance requirements; 2. Replacement of Asset on account of inter-alia, completion of Useful Life and in beyond repairable condition, performance degradation, need for induction of new efficient technology; |  |  |  |  | 0 | [6 empty] | 7 | [12 empty] | 0 | [6 empty] | 7 |  |  |  | Not Initiated
9.5 | Various Street Light Refurbishment Work | Scheme |  |  |  | 10 | [7 empty] | 1.Reduction in maintenance requirements; 2.Replacement of Asset on account of inter-alia, completion of Useful Life and in beyond repairable condition, performance degradation, need for induction of new efficient technology; |  |  |  |  | 0 | [7 empty] | 10 | [11 empty] | 0 | [7 empty] | 10 |  |  | Not Initiated
10 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | DPR |  |  |  | 25 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
10.1 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | Scheme |  |  |  | 25 | [7 empty] | 1. It will restrict ash mix water to the Kanhan river. 2. Proper lifting of settle fly ash from natural nallah may takes place. 3. The contamination of fly ash to atmosphere and adjacent farm may be minimized. 4. It will be avoid the environmental issue of pollution of ash mixed water to natural stream. 5. It will be avoid pollution of land. 6.Construction of Civil infrastructure |  |  |  |  | 0 | [6 empty] | 25 | [12 empty] | 0 | [6 empty] | 25 |  |  |  | Not Initiated
11 | AHP Performance improvement Scheme for Dry fly ash evacuation system | DPR |  |  |  | 36.7 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
11.1 | Procurement of Vacuum Pumps | Scheme |  |  |  | 2 | [7 empty] | 1) increase in operational efficiency of existing system 2)Reduction in maintenance requirements 3) improvement of system parameters |  |  |  |  | 0 |  |  |  |  | 2 | [14 empty] | 0 |  |  |  |  | 2 | [5 empty] | Not Initiated
11.2 | Procurement of Complete Assembly of Energy Efficient Air Compressors | Scheme |  |  |  | 9.7 | [7 empty] | 1) Augmentation of capacity of the existing project/system; 2) increase in operational efficiency of existing system 3)Reduction in maintenance requirements 4) improvement of system parameters 5) Reduction in maintenance requirements; |  |  |  |  | 0 |  |  |  |  | 9.7 | [14 empty] | 0 |  |  |  |  | 9.7 | [5 empty] | Not Initiated
11.3 | Procurement of ESP evacuation pipelines, valves and blowers | Scheme |  |  |  | 6 | [7 empty] | 1): increase in operational efficiency of existing system 2): Reduction in maintenance requirements 3) Improvement in system parameters; |  |  |  |  | 0 |  |  |  |  | 6 | [14 empty] | 0 |  |  |  |  | 6 | [5 empty] | Not Initiated
11.4 | Complete Refurbishment Work of 1st & 2nd Row Fields of ESP | Scheme |  |  |  | 14 | [7 empty] | 1) Increase in the Useful Life of the entire project/scheme/assets 2) Fulfilment of any statutory compliance requirement; 3) Reduction in maintenance requirements; 4) Renovation and Modernisation for life extension of entire project; 5) Improvement in system parameters; |  |  |  |  | 0 |  |  |  |  | 14 | [14 empty] | 0 |  |  |  |  | 14 | [5 empty] | Not Initiated
11.5 | Procurement of ESP CERM and EERM gear boxes | Scheme |  |  |  | 5 | [7 empty] | 1) Increase in the Useful Life of the entire project/scheme/assets 2) Fulfilment of any statutory compliance requirement; 3) Reduction in maintenance requirements; 4) Renovation and Modernisation for life extension of entire project; 5) Improvement in system parameters; |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Not Initiated
12 | AHP Performance improvement Scheme for Wet ash Disposal System | DPR |  |  |  | 40.75 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
12.1 | Upgradation of Slurry Series System and HP Seal System | Scheme |  |  |  | 5 | [7 empty] | 1): increase in operational efficiency of existing system 2): Reduction in maintenance requirements 3) Improvement in system parameters; |  |  |  |  | 0 | [5 empty] | 5 | [13 empty] | 0 | [5 empty] | 5 |  |  |  |  | Not Initiated
12.2 | Procurement of Fluid Couplings & Gearboxes for Slurry Series Pumps | Scheme |  |  |  | 4 | [7 empty] | 1): increase in operational efficiency of existing system 2): Reduction in maintenance requirements 3) Improvement in system parameters; |  |  |  |  | 0 | [5 empty] | 4 | [13 empty] | 0 | [5 empty] | 4 |  |  |  |  | Not Initiated
12.3 | Procurement of Vertical slurry pumps & Goodwin Submersible pumps | Scheme |  |  |  | 1.5 | [7 empty] | 1): increase in operational efficiency of existing system 2): Reduction in maintenance requirements |  |  |  |  | 0 |  |  |  |  | 1.5 | [14 empty] | 0 |  |  |  |  | 1.5 | [5 empty] | Not Initiated
12.4 | Procurement of Complete Assemblies of GEHO systems | Scheme |  |  |  | 14.029 | [7 empty] | 1): increase in operational efficiency of existing system 2): Reduction in maintenance requirements 3) Improvement in system parameters; |  |  |  |  | 0 | [5 empty] | 14.029 | [13 empty] | 0 | [5 empty] | 14.029 |  |  |  |  | Not Initiated
12.5 | Procurement & Replacement of Slurry Disposal Pipelines | Scheme |  |  |  | 14.72 | [7 empty] | 1): increase in operational efficiency of existing system 2): Reduction in maintenance requirements 3) Improvement in system parameters; |  |  |  |  | 0 |  |  |  |  | 14.72 | [14 empty] | 0 |  |  |  |  | 14.72 | [5 empty] | Not Initiated
12.6 | Modification of Bottom ash overflow water clarification system | Scheme |  |  |  | 1.5 | [7 empty] | 1): increase in operational efficiency of existing system 2): Reduction in maintenance requirements 3) Improvement in system parameters; |  |  |  |  | 0 |  |  |  |  | 1.5 | [14 empty] | 0 |  |  |  |  | 1.5 | [5 empty] | Not Initiated
13 | ENAHANCMENT AND RELIABILITY IMPROVELMENT OF TURBINE AUXILIARIES | DPR |  |  |  | 29 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
13.1 | PROCUREMENT OF HPCV 2 SERVO MOTOR | Scheme |  |  |  | 1 | [7 empty] | 1) The overall reliability of power plant will increase due to smooth operation of control valve. 2) New assembly will help to enhance the life of valve cones as jerks are avoided. 3) Smooth operation of DSM, drum level and load control. 4) Smooth response to grid frequency variation. |  |  |  |  | 0 |  |  |  |  | 1 | [14 empty] | 0 |  |  |  |  | 1 | [5 empty] | Not Initiated
13.2 | Procurement of BFP-A cartridge | Scheme |  |  |  | 2 | [7 empty] | 1) The overall reliability of power plant will increase due to 100% availability of Boiler Feed Pump. 2) New assembly will help to enhance the life of Boiler Feed Pump. 3) There will be proper maintenance of Boiler Feed Pumps. This will help in reducing auxiliary power consumption. 4) Improvement in flow as short circuiting due to cavitation is avoided |  |  |  |  | 0 |  |  |  |  | 2 | [14 empty] | 0 |  |  |  |  | 2 | [5 empty] | Not Initiated
13.3 | Procurement of TDBFP turbine rotor | Scheme |  |  |  | 7.5 | [7 empty] | 1) Reduction in downtime of machine during repair works. 2) Increase in availability / healthiness of the TDBFPs. 3) Reduction in auxiliary steam consumption due to increase in efficiency of TDBFPs. 4) Reduction in steam consumption on account of TDBFP |  |  |  |  | 0 |  |  |  |  | 7.5 | [14 empty] | 0 |  |  |  |  | 7.5 | [5 empty] | Not Initiated
13.4 | Procurement of CEP-B Cartridge Assembly without motor | Scheme |  |  |  | 3 | [7 empty] | 1) 100% availability of Condensate Extraction Pump. 2) There will be proper maintenance of Condensate Extraction Pumps. This will help in reducing auxiliary power consumption. 4) Being critical auxiliary overhauling period will be reduced, which will increase availability of extraction pumps |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
13.5 | Procurement and commissioning of service and instrument air atlas copco compressor | Scheme |  |  |  | 5.7 | [7 empty] | 1) Reduction in failure of Instrument and service air compressors. 2) Increasing loadability of compressors. 3) Increasing availability of compressors. 4) Improving reliability of compressors and unit thereof. 5) Reduction in currant drawn by continuous running compressors (Auxiliary consumption). 6) Improvement in performance of unit. 7) The scheme is for system reliability and service and instrument air compressors are essential auxiliaries of plant, their failure will render the generation to nil. |  |  |  |  | 0 |  |  |  |  | 5.7 | [14 empty] | 0 |  |  |  |  | 5.7 | [5 empty] | Not Initiated
13.6 | Procurement of vacuum pump | Scheme |  |  |  | 1.3 | [7 empty] | 1) Being critical auxiliary overhauling period will be reduced, which will increase availability of vacuum pumps. 2) The overall reliability of power plant will increase due to 100% availability of Vacuum Pump for condenser vacuum system of plant. 3) Reliability of Vacuum pumps will increase 4) Improvement in condenser vacuum leading to increased load |  |  |  |  | 0 |  |  |  |  | 1.3 | [14 empty] | 0 |  |  |  |  | 1.3 | [5 empty] | Not Initiated
13.7 | Procurement of Water treatment plant pumps for effluenet treatement , filter water Raw water, srewage treatement plant pumps, etc. | Scheme |  |  |  | 3 | [7 empty] | 1) Improvement in auxiliary power consumption of ODP pumps, being existing pumps are twelve year old. 2) Reduction in outages of pumps 3) Reduction in down time of maintenance work |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
13.8 | Procurement and replacement of ACW Pump | Scheme |  |  |  | 1.5 | [7 empty] | 1) 100% availability of ACW pump will ensure 100% availability of plant 2) Being HT auxiliary, will reflect in reduction of auxiliary consumption 3) Healthiness of ACW pump will ensure healthiness of various plant cooling systems such as lube oil, seal oil, etc. |  |  |  |  | 0 |  |  |  |  | 1.5 | [14 empty] | 0 |  |  |  |  | 1.5 | [5 empty] | Not Initiated
13.9 | Procurement of regulating BFP Recirculation valve A & B with actuator for flexible operation. | Scheme |  |  |  | 2 | [7 empty] | 1) Statutory requirement for flexible operation |  |  |  |  | 0 |  |  |  |  | 2 | [14 empty] | 0 |  |  |  |  | 2 | [5 empty] | Not Initiated
13.1 | Procurement of ASV-22 and spray control valve | Scheme |  |  |  | 2 | [7 empty] | 1) For process improvement during rollng activities 2) Auxiliary PRDS pressure and temp. will be maintain as per set point |  |  |  |  | 0 |  |  |  |  | 2 | [14 empty] | 0 |  |  |  |  | 2 | [5 empty] | Not Initiated
14 | NDCT EFFICENCY IMPROVEMENT | DPR |  |  |  | 36.5 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
14.1 | Complete replacement of NDCT fills | Scheme |  |  |  | 25 | [7 empty] | 1) Improve the effectiveness of Natural Draught Cooling Tower. 2) Prevents carryover of damaged film fills through cooling water. 3) Choking up of NDCT outlet strainers and CW suction strainers will be reduced. 4) Distribution of hot water through fills will be uniform. 5) Improvement in condenser vacuum. 6) Chances of choke up of condenser water box reduced which also reduces impact of back pressure on CW pumps. 7) Air flow through NDCT will increase which will decrease NDCT outlet temp 8) Weight on NDCT beams will reduce increasing concrete life of NDCT. |  |  |  |  | 0 | [5 empty] | 25 | [13 empty] | 0 | [5 empty] | 25 |  |  |  |  | Not Initiated
14.2 | Procurement of clarifloculator and flash mixer gear box | Scheme |  |  |  | 1.5 | [7 empty] | 1) Will improve availability of DM, Non-DM & ETP flash mixer and clarifloculators 2) Improvement in water quality and reduction in chemicals required at WTP 3) Reduction in down time of maintenance work |  |  |  |  | 0 | [5 empty] | 1.5 | [13 empty] | 0 | [5 empty] | 1.5 |  |  |  |  | Not Initiated
14.3 | Supply, Installation & Commisioning of NDCT side stream filters | Scheme |  |  |  | 10 | [7 empty] | 1) Improve the effectiveness of Natural Draught Cooling Tower. 2) Prevents carryover of damaged film fills through cooling water. 3) Choking up of NDCT outlet strainers and CW suction strainers will be reduced. 4) Distribution of hot water through fills will be uniform. 5) Improvement in condenser vacuum. 6) Chances of choke up of condenser water box reduced which also reduces impact of back pressure on CW pumps. 7) Air flow through NDCT will increase which will decrease NDCT outlet temp 8) Weight on NDCT beams will reduce increasing concrete life of NDCT. |  |  |  |  | 0 | [5 empty] | 10 | [13 empty] | 0 | [5 empty] | 10 |  |  |  |  | Not Initiated
15 | IMPROVEMENT OF TURBINE AND PUMPS EFFICENCY | DPR |  |  |  | 55 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
15.1 | Procurement of HPT module including Turbo visory instruments (TM-II & C&I-II) | Scheme |  |  |  | 50 | [7 empty] | 1) Increasing availability of plant 2) Decrease in turbine heat rate 3) Decrease in down time of capital overhaul work 4) Will facilitate in refurbishment of existing twelve units of 500MW of MAHAGENCO |  |  |  |  | 0 |  |  |  |  | 50 | [14 empty] | 0 |  |  |  |  | 50 | [5 empty] | Not Initiated
15.2 | Procurement and replacement of ACW Pump | Scheme |  |  |  | 1.5 | [7 empty] | 1) 100% availability of ACW pump will ensure 100% availability of plant 2) Being HT auxiliary, will reflect in reduction of auxiliary consumption 3) Healthiness of ACW pump will ensure healthiness of various plant cooling systems such as lube oil, seal oil, etc. |  |  |  |  | 0 |  |  |  |  | 1.5 | [14 empty] | 0 |  |  |  |  | 1.5 | [5 empty] | Not Initiated
15.3 | Procurement of CEP-C Cartridge Assembly with out motor | Scheme |  |  |  | 3.5 | [7 empty] | 1) 100% availability of Condensate Extraction Pump. 2) There will be proper maintenance of Condensate Extraction Pumps. This will help in reducing auxiliary power consumption. 4) Being critical auxiliary overhauling period will be reduced, which will increase availability of extraction pumps |  |  |  |  | 0 |  |  |  |  | 3.5 | [14 empty] | 0 |  |  |  |  | 3.5 | [5 empty] | Not Initiated
16 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Wagon tippler installed in CHP-II,Khaperkheda TPS. | DPR |  |  |  | 42 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
16.1 | Renovation and modanisation of wagen tipler concrete hopper | Scheme |  |  |  | 4 | [7 empty] | 1.Wagon unloading will be improved. 2.Demurage hrs will be reduced 3.Improvement in reliablity and availability |  |  |  |  | 0 |  |  |  |  | 4 | [14 empty] | 0 |  |  |  |  | 4 | [5 empty] | Not Initiated
16.2 | Supply and errection of Wagon tipplers | Scheme |  |  |  | 10 | [7 empty] | 1.For reduce the demmurage hours. 2.For reducing generation loss on account of wagon tippler. 3.For imrove the relaibility and availability of Wagon tipplers. |  |  |  |  | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [5 empty] | scheme name change | Not Initiated
16.3 | Upgradation of hydraulic systems with safety mechanism for Wagon unloading | Scheme |  |  |  | 8 | [7 empty] | 1. For imrove the relaibility and availability of Hydraulic system installed in CHP-II. 2.For reduce the demmurage hours. 3. For maximize the wagon unloading. |  |  |  |  | 0 |  |  |  |  | 8 | [14 empty] | 0 |  |  |  |  | 8 | [5 empty] | Not Initiated
16.4 | Capacity enhancement of side arm charger | Scheme |  |  |  | 10 | [7 empty] | 1. For imrove the relaibility and availability of side arm charger. 2. for improve the wagon unloading rate. |  |  |  |  | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [6 empty] | Not Initiated
16.5 | Capacity enhancement of Apron feeder | Scheme |  |  |  | 10 | [7 empty] | 1. For imrove the relaibility and availability of Apron feeder. 2. For reducing generation loss on account of Apron feeder. 3. For better feed rate management as per requirment. |  |  |  |  | 0 |  |  |  | 10 | [15 empty] | 0 |  |  |  | 10 | [6 empty] | Not Initiated
17 | CHP-II Performance improvement scheme installed in CHP-II,Khaperkheda TPS. | DPR |  |  |  | 42 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
17.1 | Supply and installeation of impact crusher spares | Scheme |  |  |  | 9 | [7 empty] | 1. For reduce the down time by improve relaibility and availability off impact crusher. 2.For reducing generation loss on account of Impact crusher. 3. For reduce demmurage charges. |  |  |  |  | 0 |  |  |  | 9 | [15 empty] | 0 |  |  |  | 9 | [5 empty] | Scheme name changed | Not Initiated
17.2 | Replacement of scoop coupling | Scheme |  |  |  | 5 | [7 empty] | 1.For reduce the demmurage hours. 2.For reducing generation loss on account of scoop coupling installed in CHP-II 3.For imrove the relaibility and availability of scoop. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 |  |  |  |  | Scheme name changed | Not Initiated
17.3 | Renovation stacker reclaimer | Scheme |  |  |  | 2 | [7 empty] | 1. For improve relaibility and availability of stacker reclaimer. 2.For reducing generation loss on account of stacker reclaimer. 3. For maintain bunker level and maximize stacking while receive excess coal. |  |  |  |  | 0 | [5 empty] | 2 | [13 empty] | 0 | [5 empty] | 2 |  |  |  |  | Not Initiated
17.4 | Complete overhauling of Wobbler feeder | Scheme |  |  |  | 6 | [7 empty] | 1. For improve relaibility and availability of wobbler feeder. 2.Reduction in demmurrage charges |  |  |  |  | 0 |  |  |  |  | 6 | [14 empty] | 0 |  |  |  |  | 6 |  |  |  |  | Scheme name changed | Not Initiated
17.5 | Procurement of Gear boxes | Scheme |  |  |  | 8 | [7 empty] | 1.For reduce the demmurage hours. 2.For reducing generation loss on account of gear box installed in CHP-II 3To improve the relaibility and availability of drive systems. |  |  |  |  | 0 |  |  |  | 8 | [15 empty] | 0 |  |  |  | 8 | [5 empty] | Scheme name changed | Not Initiated
17.6 | Structure Strengthening and modification work of Conveyors. | Scheme |  |  |  | 12 | [7 empty] | 1.For imrove the relaibility and availability of conveyor system installed in CHP-II. 2. For improve the wagon unloading . |  |  |  |  | 0 |  |  |  | 12 | [15 empty] | 0 |  |  |  | 12 | [6 empty] | Not Initiated
18 | Infrastructure Development Schemes & Electrical schemes for improvement in availability & Reliability of auxilliaries installed in CHP-II,Khaperkheda TPS. | DPR |  |  |  | 41 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
18.1 | Procurement of EOT cranes and hoist installed in CHP-II. | Scheme |  |  |  | 12 | [7 empty] | 1.Reduce down time during maintenance or unexpected equipment failure. 2.To improve material handling during maintainence work. 3.Reduction in demmurrage chareges and associated generation loss 4.Reducing downtime of CHP |  |  |  |  | 0 |  |  |  |  | 12 | [14 empty] | 0 |  |  |  |  | 12 | [5 empty] | Not Initiated
18.2 | Modification of DE and DS system | Scheme |  |  |  | 14 | [7 empty] | 1.To reduce respirable dust. 2.Improve productivity by reducing equipment downtime and on job injuries. 3.minimising risk of dust explossion and associated fire incidences. 4.To improve overall health and safety at workplace. |  |  |  |  | 0 | [5 empty] | 14 | [13 empty] | 0 | [5 empty] | 14 |  |  |  |  | Not Initiated
18.3 | Procuremnet of HT Motors | Scheme |  |  |  | 5 | [7 empty] | 1.Reduction in APC 2.Increasing availability of drives. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Not Initiated
18.4 | Procuremnet of VFD for LT motors | Scheme |  |  |  | 3 | [7 empty] | 1.Reduce maintence time 2.Reduce energy consumption of coal handling plant. 3.Reduce generation loss due to electrical outage of CHP |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
18.5 | upgradation of wagon tippler PLC | Scheme |  |  |  | 2 | [7 empty] | 1.Reduce downtime of WT due to PLC failure. 2. Increse in monitoring of sytem. 3.Reduction in Demmurrage. |  |  |  |  | 0 |  |  |  |  | 2 | [14 empty] | 0 |  |  |  |  | 2 | [5 empty] | Not Initiated
18.6 | Reconditioning of MCC Boards and feeder panels | Scheme |  |  |  | 5 | [7 empty] | 1.Provsion of redudndancy and backup system 2.Reduction in Generation loss and demmurrage charges due to electrical charges. |  |  |  |  | 0 |  |  |  |  | 5 | [14 empty] | 0 |  |  |  |  | 5 | [5 empty] | Not Initiated
18.7 | Provision of ceramic lagging to pulleyes ,belt tracker system and mechanise spillage free control system for various conveyor systems |  |  |  |  | 3 | [7 empty] | 1.Reduce downtime of belt conveyors. 2.Reduction in associated generation loss. 3.Reduction in coal spillage. |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 |  |  |  |  | Newly added scheme | Not Initiated
19 | Work of Design engineering , supply and installation of modular chutes with Liners of various belt conveyor installed in CHP-II . | DPR |  |  |  | 28.5 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
19.1 | Apron feeder-101/102 to Conv-102A/B transfer chute | Scheme |  |  |  | 3.5 | [7 empty] | 1. For minimize the coal spillage ,So that cleaning/labour cost and transportation cost will reduced. 2.For imrove the relaibility and availability of auxiliaries installed in CHP-II. 3. For reduce generation loss and maintain bunker level. 4. For reduce demmurage hours and improve wagon unloading. |  |  |  |  | 0 |  |  |  |  | 3.5 | [14 empty] | 0 |  |  |  |  | 3.5 | [5 empty] | Not Initiated
19.2 | Conv-103A/B to wobbler feeder-101/102 to Crusher -101/102 to Belt feeder-101/102 to conv-104A/B transfer chute | Scheme |  |  |  | 12.5 | [7 empty] | 1. For minimize the coal spillage ,So that cleaning/labour cost and transportation cost will reduced. 2.For imrove the relaibility and availability of auxiliaries installed in CHP-II. 3. For reduce generation loss and maintain bunker level. 4. For reduce demmurage hours and improve wagon unloading. |  |  |  |  | 0 |  |  |  |  | 12.5 | [14 empty] | 0 |  |  |  |  | 12.5 | [5 empty] | Not Initiated
19.3 | Conv-104A/B to Conv-105A/B and Conv-113 to Conv-105A/B,BF-105/106 to BF-107 to conv-107 transfer chute | Scheme |  |  |  | 5.5 | [7 empty] | 1. For minimize the coal spillage ,So that cleaning/labour cost and transportation cost will reduced. 2.For imrove the relaibility and availability of auxiliaries installed in CHP-II. 3. For reduce generation loss and maintain bunker level. 4. For reduce demmurage hours and improve wagon unloading. |  |  |  |  | 0 |  |  |  |  | 5.5 | [14 empty] | 0 |  |  |  |  | 5.5 | [5 empty] | Not Initiated
19.4 | Conv-105A/B to Cov-106A and Conv-105A/B to Cov-106B transfer chute | Scheme |  |  |  | 2.5 | [7 empty] | 1. For minimize the coal spillage ,So that cleaning/labour cost and transportation cost will reduced. 2.For imrove the relaibility and availability of auxiliaries installed in CHP-II. 3. For reduce generation loss and maintain bunker level. 4. For reduce demmurage hours and improve wagon unloading. |  |  |  |  | 0 |  |  |  |  | 2.5 | [14 empty] | 0 |  |  |  |  | 2.5 | [5 empty] | Not Initiated
19.5 | Conv-107 to Conv-108,Conv-112 to Conv-113,Conv-111 to Con-112,Conv-108 to conv-109,conv-109 to conv-110, conveyor transfer chute | Scheme |  |  |  | 4.5 | [7 empty] | 1. For minimize the coal spillage ,So that cleaning/labour cost and transportation cost will reduced. 2.For imrove the relaibility and availability of auxiliaries installed in CHP-II. 3. For reduce generation loss and maintain bunker level. 4. For reduce demmurage hours and improve wagon unloading. |  |  |  |  | 0 |  |  |  |  | 4.5 | [14 empty] | 0 |  |  |  |  | 4.5 | [5 empty] | Not Initiated
20 | Comprehensive enhancement infrastructure of green Corridor | DPR |  |  |  | 28.5 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
20.1 | Providing and construction of Cement road at various location at 500 MW KPKD, TPS | Scheme |  |  |  | 11 | [7 empty] | 1. Communication route will be helpful for easy mobilizations of vehicle & machinery result in efficient work may takes place. 2. Risk of reptiles & other dangerous living will be minimized. 3. Water logging & formation of marshy land will get avoided. 4. It will helpful for patrolling team also. 5. Marking of crossings and intersections of different roads to minimize accidents |  |  |  |  | 0 |  |  |  |  | 11 | [14 empty] | 0 |  |  |  |  | 11 | [5 empty] | Not Initiated
20.2 | Constructions of RCC Drains at various locations in 500 MW KPKD TPS | Scheme |  |  |  | 7 | [7 empty] | 1. Construction of RCC drain will be helpful for easy mobilizations of vehicle & machinery result in efficient work may takes place. 2. Risk of reptiles & other dangerous living will be minimized. 3. Water logging & formation of marshy land will get avoided. 4. Non-interruption in conveyance throughout the year |  |  |  |  | 0 |  |  |  |  | 7 | [14 empty] | 0 |  |  |  |  | 7 | [5 empty] | Not Initiated
20.3 | Landscaping | Scheme |  |  |  | 3 | [7 empty] | 1. Enhancement in the asthetic view of premises. 2. Reduce air pollution to certain extend. 3. It will help to increase enthusiasism among employee. |  |  |  |  | 0 |  |  |  |  | 3 | [14 empty] | 0 |  |  |  |  | 3 | [5 empty] | Not Initiated
20.4 | Dust Suppression | Scheme |  |  |  | 5 | [7 empty] | 1. It willl reduce air pollution. 2. It will helps to maintain cleanliness. 3. It will reduce the chances of air borne disease. 4. It will reduce man power requirement. |  |  |  |  | 0 | [5 empty] | 5 | [13 empty] | 0 | [5 empty] | 5 |  |  |  |  | Not Initiated
20.5 | Road Cleaning Machine | Scheme |  |  |  | 2.5 | [7 empty] | 1. It will helps to maintain cleanliness. 2. It will reduce the chances of air borne disease. 3. It will reduce man power requirement for housekeeping. |  |  |  |  | 0 |  |  |  |  | 2.5 | [14 empty] | 0 |  |  |  |  | 2.5 | [5 empty] | Not Initiated
21 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | DPR |  |  |  | 25 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
21.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | Scheme |  |  |  | 25 | [7 empty] | As per CEA guidelines for Phasing_Plan for implementation of 40% Technical Minimum load . This scheme falls under fulfilment of statutory compliance requirement. 3.1(l). |  |  |  |  | 0 |  |  |  | 25 | [15 empty] | 0 |  |  |  | 25 | [6 empty] | Not Initiated
22 | CHP Improvement Schemes for 500MW unit | DPR |  |  |  | 50 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
22.1 | CHP Improvement Schemes for 500MW unit | Scheme |  |  |  | 50 | [12 empty] | 0 |  |  |  |  | 50 | [14 empty] | 0 |  |  |  |  | 50 | [5 empty] | Not Initiated
23 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | DPR |  |  |  | 387.8 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | AS PER APPROVED CAPEX PLAN
23.1 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | Scheme |  |  |  | 387.8 | [12 empty] | 0 | [19 empty] | 0 | [9 empty] | NOTE:-THIS SCHEME IS ALREADY TAKEN AT ABOVE ON SR. NO. 27 .IT WAS REPEATED HERE HENCE COST NOT ENCORPORATED HERE TO AVOID DUPLICATION | N.A.
24 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | DPR |  |  |  | 25.58 | [12 empty] | 0 | [19 empty] | 0
24.1 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | Scheme |  |  |  | 25.58 | [7 empty] | 1. Capacity addition in the existing system. 2. Easy mobilization with railway transport. |  |  |  |  | 0 |  |  |  |  | 25.58 | [14 empty] | 0 |  |  |  |  | 25.58 |  |  |  |  | Newly added DPR | Not Initiated
25 | Construction of LHS on Saoner & Kalumna siding of Khaperkheda TPS. | DPR |  |  |  | 49.8 | [12 empty] | 0 | [19 empty] | 0
25.1 | Construction of Limited Height Subway at Pandhrakhedi, Patkakhedi (Saoner siding) & Suradevi (Kalumna siding) on depositary basis at Khaperkheda TPS. | Scheme |  |  |  | 49.8 | [7 empty] | 1. It will eleminate the round the clock manpower at LC gate. 2. It will minimize the chances of accident. 3. It will reduce the waiting period for vehicle & pedestrians. |  |  |  |  | 0 |  |  |  |  | 49.8 | [14 empty] | 0 | [6 empty] | 49.8 |  |  | Newly added DPR | Not Initiated
[19 empty] | 0 | [19 empty] | 0
| B) Non-DPR Schemes | [17 empty] | 0 | [19 empty] | 0
1 | ID fan motor rotor refurbishment of 500 MW | Non-DPR | N.A. | [13 empty] | 1.0962 |  | 1.0962 | [17 empty] | 1.0962 |  | 1.0962 | [10 empty] | Capitalised
2 | Procurement of Spare TDBFP Gear Box | Non-DPR | N.A. | [14 empty] | 0.58994 | 0.58994 | [18 empty] | 0.58994 | 0.58994 | [10 empty] | Capitalised
3 | PISTON CYLINDER ASSEMBLY, DIAPHRAM ASSEMBLY | Non-DPR | N.A. | [15 empty] | 0 | 5.9274 | 0.042685 | [17 empty] | 0 | 5.9274 | 0.042685 | [8 empty] | Capitalised
4 | GT-R Phase Transformer#6006501 of U#5 (Spare) | Non-DPR | N.A. | [15 empty] | 0 |  | 6.241 | [17 empty] | 0 |  | 6.241 | [7 empty] | All documents related to this N-DPR scheme Appendix I,WCR etc submitted to O/o. CE(Works) | Partially Capitalized
5 | GT-R Phase Transformer#6006501U#5 (Core Replace) | Non-DPR | N.A. | [15 empty] | 0 |  | 3.1304 | [11 empty] | 100% | [5 empty] | 0 |  | 3.1304 | [7 empty] | All documents related to this N-DPR scheme Appendix I,WCR etc submitted to O/o. CE(Works) | Capitalised
6 | BCW Pump Motor Model HLAV (Refurbishment) U#5 | Non-DPR | N.A. | [15 empty] | 0 |  | 2.8718 | [11 empty] | 100% | [5 empty] | 0 |  | 2.8718 | [7 empty] | All documents related to this N-DPR scheme Appendix I,WCR etc submitted to O/o. CE(Works) | Capitalised
7 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM CHP-II | Non-DPR | N.A. | [15 empty] | 0 | 2.1501 | [18 empty] | 0 | 2.1501 | [9 empty] | Capitalised
8 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM C&I-2 | Non-DPR | N.A. | [15 empty] | 0 | 2.2408 | [18 empty] | 0 | 2.2408 | [9 empty] | Capitalised
9 | Land for Nandgaon ash band | Non-DPR | N.A. | [15 empty] | 0 |  | 0.267 | [17 empty] | 0 |  | 0.267 | [8 empty] | Capitalised
10 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-II | Non-DPR | N.A. | [15 empty] | 0 |  | 1.5824 | [17 empty] | 0 |  | 1.5824 | [7 empty] | CE(FMC) capitalised by Account section as per HO. This scheme is under DPR/Non DPR MPD Khaperklheda not received any details please confirm at your end.Such N-DPR schemes added by HO without MPD Knoledge through N-DPR may leads to disallowance | Capitalised
11 | Fire Fighting equipment(Conveyors galleries CHPII) | Non-DPR | N.A. | [15 empty] | 0 |  | 0.57643 | [17 empty] | 0 |  | 0.57643 | [7 empty] | capitalised by Account section as per HO. This scheme is under DPR/Non DPR MPD Khaperklheda not received any details please confirm at your end.Such N-DPR schemes added by HO without MPD Knoledge through N-DPR may leads to disallowance | Capitalised
12 | PROCUREMENT OF COMPLETE SET OF SKY CLIMBER FOR UNIT-5 (500 MW), TPS KHAPERKHEDA | Non-DPR | N.A. | [15 empty] | 0 |  |  | 0.86 | [16 empty] | 0 |  |  | 0.86 | [6 empty] | Admin approval is received | WIP
13 | Supply & Erection of Duct, Diverter Plate, and Expansion Joints for Extensive Replacement of Flue Gas Duct at Unit-5,500 MW Khaperkheda TPS | Non-DPR | N.A. | [15 empty] | 0 |  |  | 4.09 | [16 empty] | 0 |  |  | 4.09 | [6 empty] | Admin approval is received | WIP
14 | Stacker Relaimer Refurbishment | Non-DPR | N.A. | [15 empty] | 0 |  |  | 20.2 | [16 empty] | 0 |  |  | 20.2 | [6 empty] | Admin approval is received | WIP
15 | Work of design, Engineering, Supply & Installation along with capacity enhancement of drive unit of conveyor belt 103A,103B & 105B installed at CHP 500MW, Khaperkheda TPS | Non-DPR | N.A. | [15 empty] | 0 |  |  | 4.08 | [16 empty] | 0 |  |  | 4.08 | [6 empty] | Admin approval is received | WIP
16 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 500MW | Non-DPR | N.A. | [15 empty] | 0 |  |  | 1.21 | [16 empty] | 0 |  |  | 1.21 | [6 empty] | Admin approval is received | WIP
17 | work of Refurbishment/Modification of Air ventilation system at wagon tippler tunnel area, Apron feeder floor area, Wagon tippler control room, CHP control room and short conveyor area in CHP500 MW) | Non-DPR | N.A. | [15 empty] | 0 |  |  | 2.06 | [16 empty] | 0 |  |  | 2.06 | [6 empty] | Admin approval is received | WIP
18 | Work of design Engineering, Refurbishment & structural strenghthning along with replacement of damaged spares of conveyor belt 110 installed at coal handling plant 500MW . | Non-DPR | N.A. | [15 empty] | 0 |  |  | 2.21 | [16 empty] | 0 |  |  | 2.21 | [6 empty] | Admin approval is received | WIP
19 | GTR Refurbishment | Non-DPR | N.A. | [15 empty] | 0 |  |  | 0.33 | [16 empty] | 0 |  |  | 0.33 | [6 empty] | Admin approval is received | WIP
20 | SUPPLY,ERECTION ,COMMISSIONING AND TESTING OF 360V,750AH PLANTE TYPE UPS BATTERY SET AT UNIT 5 500MW | Non-DPR | N.A. | [15 empty] | 0 |  |  | 2.87 | [16 empty] | 0 |  |  | 2.87 | [6 empty] | Admin approval is received | WIP
21 | Up-gradation of Generator Protection System and Feeder protection relays at 1X500MW Khaperkheda TPS. | Non-DPR | N.A. | [15 empty] | 0 |  |  | 2.09 | [16 empty] | 0 |  |  | 2.09 | [6 empty] | Admin approval is received | WIP
22 | BFP Booster pump | Non-DPR | N.A. | [15 empty] | 0 |  |  | 1.4 | [16 empty] | 0 |  |  | 1.4 | [6 empty] | Admin approval is received | WIP
23 | Submission for approval of Non-DPR “Supply of Complete Cartridge Assemblies (1 Nos) for Boiler Feed Pump FK 4E 36 at (Unit#5, 500MW), Khaperkheda T.P.S. | Non-DPR | N.A. | [15 empty] | 0 |  |  | 1.99 | [16 empty] | 0 |  |  | 1.99 | [6 empty] | Admin approval is received | WIP
24 | Procuremet of Portable Reclaimer | Non-DPR | N.A. | [15 empty] | 0 |  |  |  | 8.92 | [15 empty] | 0 |  |  |  | 8.92 | [5 empty] | Admin approval is received(Will be capitalised against the margin of FGD Unit #5) | WIP
25 | Work of Design, Fabrication ,Erection & commissioning of Wobbler feeder and crusher bypass chute with provision of hydraulic actuator installed at coal handling plant 500MW, Khaperkheda TPS | Non-DPR | N.A. | [15 empty] | 0 |  |  |  | 2.89 | [15 empty] | 0 |  |  |  | 2.89 | [5 empty] | Admin approval is received(Will be capitalised against the margin of FGD Unit #5) | WIP
26 | Work of Revamping, Modification & Upgradation with Testing & Commissioning of Fire Detection and Alarm System including supply of Material for Unit # 5 BTG area at 500MW TPS Khaperkheda. | Non-DPR | N.A. | [15 empty] | 0 |  |  |  | 5.2 | [15 empty] | 0 |  |  |  | 5.2 | [5 empty] | Admin approval is received(Will be capitalised against the margin of FGD Unit #5) | WIP
27 | HPCV2 Servomotor | Non-DPR | N.A. | [15 empty] | 0 |  |  |  | 1.2 | [15 empty] | 0 |  |  |  | 1.2 | [5 empty] | Admin approval is received(Will be capitalised against the margin of FGD Unit #5) | WIP
28 | Refurbishment of BCW pump Motor Model HLAV 2X300-460/1C (Rated 350 KW, 6.6 KV ,4 Pole, Sr. No. AP460044-3-1) of U#5 (500 MW) TPS, Khaperkheda. | Non-DPR | N.A. | [15 empty] | 0 |  |  | 3.59 | [16 empty] | 0 |  |  | 3.59 | [6 empty] | approval not received yet .Need to expedite the approval for capitalisation in FY 24-25. | N.A.
29 | Procurement of Complete Rotor Assy. along with 1st and 2nd stage blade set of PA Fan Type AP2 20/12 for Unit#5 (500 MW) TPS, Khaperkheda | Non-DPR | N.A. | [15 empty] | 0 |  |  |  | 3.37 | [15 empty] | 0 |  |  |  | 3.37 | [5 empty] | approval not received yet(Will be capitalised against the margin of FGD Unit #5) | N.A.
30 | Up-gradation of VFD system for GEHO Pump-2 at 1X500MW Khaperkheda TPS. | Non-DPR | N.A. | [15 empty] | 0 |  |  |  | 2.7 | [15 empty] | 0 |  |  |  | 2.7 | [5 empty] | approval not received yet(Will be capitalised against the margin of FGD Unit #5) | N.A.
31 | General Asset Furniture | Non-DPR | N.A. | [15 empty] | 0 |  | 0.011682 | [17 empty] | 0 |  | 0.011682 | [8 empty] | Capitalised
32 | General Asset AC, Fans, Air coolers, water filter etc. | Non-DPR | N.A. | [15 empty] | 0 |  | 0 | [17 empty] | 0 |  | 0.12056 | [8 empty] | Capitalised
33 | General Asset Computer, scanners, etc. | Non-DPR | N.A. | [15 empty] | 0 |  | 0.043476 | [17 empty] | 0 | 0.29668 | 0.37035 | [8 empty] | Capitalised
| Total | [13 empty] | 110.8193 | 157.7819 | 101.5176 | 80.5139 | 450.6327 | 74.6248 | 88.7972 | 396.1197 | 454.27 | 926.8 | 91.029 | 165.8 | 37 | [7 empty] | 67.8007 | 2.6732 | 18.7012 | 74.4069 | 163.582 | 152.0771 | 91.407 | 382.9447 | 471.28 | 877 | 91.029 | 215.6 | 37 | 0
[40 empty] | 10.6151 | 15.2144 | 46.98
Formulas:
Date of Submission = [Date of Submission, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
MERC Approval Date = [MERC Approval Date, row above]
Note on G49: SSP-RCD: Total Expenditure is booked on 2 units of kpkd 1-4 & 1 unit of kpkd 5. i.e. 2*210+1*500
Note on G51: SSP-RCD: Share of KPKD 5 to be confirmed
Note on G53: SSP-RCD: Including 18% GST & 2% P&F Charges
Note on G75: SSP-RCD: Share of Koradi 6-7, Kpkd 1-4 & kpkd 5 to be confirmed
Note on H49: SSP-RCD: Total Expenditure is booked on 2 units of kpkd 1-4 & 1 unit of kpkd 5. i.e. 2*210+1*500
Note on H51: SSP-RCD: Share of KPKD 5 to be confirmed
Note on H75: SSP-RCD: Share of Koradi 6-7, Kpkd 1-4 & kpkd 5 to be confirmed
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC
Note on P28: SSP-RCD: FY 2016-17
Note on AJ28: SSP-RCD: FY 2016-17

## F4.3
MSPGCL: Khaperkheda U # 5
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) Submitted to MERC
12 | Ash Disposal Scheme from K’kheda 1 X 500 MW Unit to Nandgaon Ash Bund | MERC/CAPEX/20162017 | 2017-09-22 | 69.1855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | 1. Construction of RCC pedestals for laying of ADP Lines from Khaperkheda TPS to Nandgaon Ash Bund. 2. Providing &Laying of ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 2a) Supply of MSERW and Seamless Pipes 2b) Laying of Ash Disposal & Recovery Pipe Line. 3. Construction of Service road for ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 4. Design, Engineering & construction of minor bridge, road crossing and culverts in the alignment of ash disposal pipe line from TPS Khaperkheda to Nandgaon Ash Bund 5. Construction of ash water recovery pump house at Nandgaon | MERC/CAPEX/20162017 | 2017-09-22 | 65.7755 | 89.3108 | 89.3108 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017 | 2017-09-22 | 3.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Bulldozer, Wheel axel final drive assembly & refurbishment of apron feeder at Khaperkheda TPS | MERC/CAPEX/20162017/01341 | 2017-10-11 | 11.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Procurement of Bulldozers(02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 3.75 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Procurement of wheel axel final drive assembly (02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Refurbishment of apron feeder | MERC/CAPEX/20162017/01341 | 2017-10-11 | 7.36 | 6.8736 | 5.629 | 1.2446 | 0 | 0 |  |  | 0 | 1.2446 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Procurement of Battery Set, PA Fan assembly, Jack Oil Pump, Turbo Driven BFP Cartridge and Restoration of ESP internals for 500 MW at Khaperkheda TPS | MERC/CAPEX/20172018/04320 | 2017-10-11 | 14.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Procurement, erection, commissioning & testing of 220V, 2190AH & 24V Battery set: | MERC/CAPEX/20172018/04320 | 2017-10-11 | 5.6 | 6.2928 | 6.2928 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Procurement of PA Fan assembly | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.1 | 3.3713 | 3.3713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Restoration of ESP internals | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.7 | 1.6097 | 1.6097 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Procurement of Jacking Oil Pump | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.18 | 0.27 | 0.27 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.5 | Procurement of turbo driven BFP Cartridge Assembly (FK4E36) | MERC/CAPEX/20172018/04320 | 2017-10-11 | 2.1 | 1.8279 | 1.8279 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 12.8838 | 12.8838 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Provision of S&T System for In Plant Yard Khaperkheda & Kalumni Yard (Depository Work) and Modification of Kalumna Yard Alteration No. 5 (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 31.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Provision of S & T System to Khaperkheda TPS In-Plant yard and Kalumna Yard (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 17.75 | 0.041975 | 0.041975 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Modification of Kalumna Yard Alternation no. 5 in connection with Khaperkheda TPS Expansion Project (1x500 MW) construction of B.G. Railway Siding | MERC/CAPEX/20172018/4779 | 2017-11-28 | 13.77 | 13.77 | 0 | 13.77 | 13.5159 | 13.5159 |  |  | 13.5159 | 13.77 | 13.5159 | 0
19 | Construction of Limited Height Subway (LHS) at unmanned road level crossing by Railway on cost sharing basis with MSPGCL on Khaperkheda-Kalumna railway siding and saoner-Khaperkheda railway siding | MERC/CAPEX/20172018/0178 | 2018-02-02 | 16.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Construction of LHS on Khaperkheda Kalumna railway side | MERC/CAPEX/20172018/0178 | 2018-02-02 | 5.94 | 4.9899 | 4.9899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Construction of LHS on Khaperkheda Saoner railway line | MERC/CAPEX/20172018/0178 | 2018-02-02 | 10.87 | 9.78 | 9.78 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Utilisation of unused water scheme from Bhanegaon open cast mine & construction of RCC internal roads at Khaperkheda TPS | MERC/CAPEX/20172018/0197 | 2018-02-06 | 11.5329 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Utilization of unused water scheme from Bhanegaon Open cast mine | MERC/CAPEX/20172018/0197 | 2018-02-06 | 7.5469 | 12.7 | 12.7036 | -0.0036201 | 0.23666 | 0.23666 |  |  | 0.23666 | -0.0036201 | 0 | 0.23666
20.2 | Construction of Cement Concrete Road Inside Part Of Power House | MERC/CAPEX/20172018/0197 | 2018-02-06 | 2.906 | 2.6732 | 2.6732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0197 | 2018-02-06 | 1.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIMT 2000 (72° PA) | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 0 | 0 | 0 | 3.835 | 0 |  |  | 0 | 3.835 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 2.7397 | 0 | 2.7397 | 0.46296 | 3.2027 |  |  | 3.2027 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 0 | 0 | 0 | 1.9759 | 0 |  |  | 0 | 1.9759 | 0 | 0
27 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 280.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | Flue Gas Desulphurization (FGD) System for KPKD 5 | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 260.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 20.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.5033 | 4.5033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 269.3 | 0 | 269.3 | 44.28 | 124.5068 |  |  | 124.5068 | 189.0732 | 124.5068 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.23 | 1.8042 | 1.8042 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 4.0922 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.5 | Electromagnetic Flow meters at various lines & Locations of 500 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.2497 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.6 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Boiler Performance improvement Six Schemes at Unit-5 Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Sch-1: Procurement & Replacement of LTSH coils at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Sch-2: Procurement & Replacement of Economizer coils at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Sch-3: Procurement & Replacement of Water wall Z-Panels & Soot blower Panels at U#5: | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Sch-4 : Supply and erection of APH Inlet & Outlet Flue Gas Damper Assemblies along with actuators at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Sch-5 : Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines at U#5. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 25.43 | 0 | 0 | 0 | 0 | 0
2.1 | Up-gradation of maxDNA DCS system (HMI Up-gradation) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.29 | 0 | 0 | 0 | 0 | 0
2.2 | Up-gradation of PLC (GE FANUC make) SYSTEM (HMI & hardware up-gradation) at Ash Handling Plant, Compressor Plant, and Condensate Polishing Unit (CPU) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.14 | 0 | 0 | 0 | 0 | 0
2.3 | Up-gradation of PLC (Schneider make) system (HMI & HARDWARE Up-gradation) at DM Plant, PTP, FF plant, CMRH System, HVAC System, FOPH system at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.26 | 0 | 0 | 0 | 0 | 0
2.4 | Up-gradation of SWAS (STEAM WATER ANALYSIS SYSTEM) Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.71 | 0 | 0 | 0 | 0 | 0
2.5 | Up-gradation of Carbon monoxide analyzer in Flue Gas Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.02 | 0 | 0 | 0 | 0 | 0
2.6 | Up-gradation of Coal feeder Controller at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.01 | 0 | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 0.86 | 0 | 0 | 0 | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 11.75 | 0 | 0 | 0 | 0 | 0
35.1 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 0.89 | 0 | 0 | 0 | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
2 | DPR7 SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Supply Installation Testing & Commissioning , Revamping of fire detection & alarm and protection system from fire and providing rapid extinguishing clean agent (CA) system at unit # 5 at 500 MW khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
3 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Restoration of fire alarm valve with water spray system (DV) at CHP-II 500 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
4 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Modular Duct | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
4.2 | PA Fan Rotor Assy. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Bottom ash & coarse ash system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Design Supply and erection of bottom ash hopper and Coarse ash hoppers. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
4.5 | Platform | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
4.6 | Refurbishment of BCW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
4.7 | Boiler Lift performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
5 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
5.1 | Water Wall Soot Blower Panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
5.2 | Thermal Insulation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
5.3 | APH Baskets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
5.4 | Errection & Commisioning of Additional Soot blower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
5.5 | PA Fan Rotor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
5.6 | Coal Compartment Assembly | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6 | Upgradation of Process field instruments and PLCs hardware for performance improvement . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Upgradation of Emerson make PLC controllers and I/O (AHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6.2 | Upgradation of WTP & CHP PLC I/O and network accessories (BOP & CHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6.3 | Upgradation of Pressure, flow, level transmitter, hydrastep, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6.4 | Upgradation of Scanner , Ignitors, Solonoid system , relay of FSSS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6.5 | Upgradation of control valves and cylinders instrumentation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6.6 | Upgradation of ETP, Debris ,OLCC plc system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6.7 | Upgradation of Nucleonic density meter | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6.8 | Upgradation of environment related instruments | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6.9 | Installation of Furnace camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Installation of Flue gas exit temperature probe | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
7 | Upgradation of Electrical Protection Systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
7.1 | Upgradation of UPS system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
7.2 | Upgradation of battery charger system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
7.3 | Upgradation of ID Fan VFD system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
7.4 | Upgradation of DAVR system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
7.5 | Upgradation of protection relays at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
7.6 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
7.7 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
7.8 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
8 | Enhancement of HT/ LT Auxillaries and Illumination for betterment availability and reliability | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
8.1 | Supply of 6.6 KV, 220 KW Ash Slurry Pump Motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
8.2 | Supply of 6.6 KV, 200 KW Fire Hydrant motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
8.3 | Supply of 690V, 800 KW GEHO Pump motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
8.4 | Refurbishment of BCW Pump Motor Sr. No. AP460044-3-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
8.5 | Supply of Dry Type Transformers of Different Ratings for Unit # 5, TPS Khaperkheda. (Rates are inclusive of 2% Packing and forwarding charges & 2% Freight Charges) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
8.6 | Supply of 3250KVA, 6.6/2.3 KV Oil Cooled VFD Transformer Of Vector Group Dyn11 and Ydn 11 & 25 MVA UAT For Unit# 5 At Khaperkheda TPS. (Including Packing and forwarding charges 2%, Freight Charges 2%) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
8.7 | Enhancing conventional lighting system at by retrofitting and replacement with energy efficient LED Lighting system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
8.8 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP & CHP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
8.9 | supply of integrated solar light and CCTV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
9 | colony electrical renovation, switchgear, Energy meter, breaker,street light, 11 KV cable ,High Mast | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
9.1 | Electrical Rennovation and mordernization of various tenaments buildings,offices, recreation clubs, Hospital, Domestic Pump House, PTP Plant and Admin Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
9.2 | Replacement of Distibution board, High Mast and switchgear at different areas of colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
9.3 | Replacement of Energy meter and various LT Motors at Domestic Pump House and PTP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
9.4 | 11 KV Cable Work and various 11 KV Structure Rennovation Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
9.5 | Various Street Light Refurbishment Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
10 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
10.1 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
11 | AHP Performance improvement Scheme for Dry fly ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
11.1 | Procurement of Vacuum Pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
11.2 | Procurement of Complete Assembly of Energy Efficient Air Compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
11.3 | Procurement of ESP evacuation pipelines, valves and blowers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
11.4 | Complete Refurbishment Work of 1st & 2nd Row Fields of ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
11.5 | Procurement of ESP CERM and EERM gear boxes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
12 | AHP Performance improvement Scheme for Wet ash Disposal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
12.1 | Upgradation of Slurry Series System and HP Seal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
12.2 | Procurement of Fluid Couplings & Gearboxes for Slurry Series Pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
12.3 | Procurement of Vertical slurry pumps & Goodwin Submersible pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
12.4 | Procurement of Complete Assemblies of GEHO systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
12.5 | Procurement & Replacement of Slurry Disposal Pipelines | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
12.6 | Modification of Bottom ash overflow water clarification system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13 | ENAHANCMENT AND RELIABILITY IMPROVELMENT OF TURBINE AUXILIARIES | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13.1 | PROCUREMENT OF HPCV 2 SERVO MOTOR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13.2 | Procurement of BFP-A cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13.3 | Procurement of TDBFP turbine rotor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13.4 | Procurement of CEP-B Cartridge Assembly without motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13.5 | Procurement and commissioning of service and instrument air atlas copco compressor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13.6 | Procurement of vacuum pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13.7 | Procurement of Water treatment plant pumps for effluenet treatement , filter water Raw water, srewage treatement plant pumps, etc. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13.8 | Procurement and replacement of ACW Pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13.9 | Procurement of regulating BFP Recirculation valve A & B with actuator for flexible operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
13.1 | Procurement of ASV-22 and spray control valve | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
14 | NDCT EFFICENCY IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
14.1 | Complete replacement of NDCT fills | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
14.2 | Procurement of clarifloculator and flash mixer gear box | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
14.3 | Supply, Installation & Commisioning of NDCT side stream filters | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
15 | IMPROVEMENT OF TURBINE AND PUMPS EFFICENCY | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
15.1 | Procurement of HPT module including Turbo visory instruments (TM-II & C&I-II) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
15.2 | Procurement and replacement of ACW Pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
15.3 | Procurement of CEP-C Cartridge Assembly with out motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
16 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Wagon tippler installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
16.1 | Renovation and modanisation of wagen tipler concrete hopper | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
16.2 | Supply and errection of Wagon tipplers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
16.3 | Upgradation of hydraulic systems with safety mechanism for Wagon unloading | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
16.4 | Capacity enhancement of side arm charger | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
16.5 | Capacity enhancement of Apron feeder | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
17 | CHP-II Performance improvement scheme installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
17.1 | Supply and installeation of impact crusher spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
17.2 | Replacement of scoop coupling | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
17.3 | Renovation stacker reclaimer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
17.4 | Complete overhauling of Wobbler feeder | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
17.5 | Procurement of Gear boxes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
17.6 | Structure Strengthening and modification work of Conveyors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
18 | Infrastructure Development Schemes & Electrical schemes for improvement in availability & Reliability of auxilliaries installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
18.1 | Procurement of EOT cranes and hoist installed in CHP-II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
18.2 | Modification of DE and DS system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
18.3 | Procuremnet of HT Motors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
18.4 | Procuremnet of VFD for LT motors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
18.5 | upgradation of wagon tippler PLC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
18.6 | Reconditioning of MCC Boards and feeder panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
18.7 | Provision of ceramic lagging to pulleyes ,belt tracker system and mechanise spillage free control system for various conveyor systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
19 | Work of Design engineering , supply and installation of modular chutes with Liners of various belt conveyor installed in CHP-II . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
19.1 | Apron feeder-101/102 to Conv-102A/B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
19.2 | Conv-103A/B to wobbler feeder-101/102 to Crusher -101/102 to Belt feeder-101/102 to conv-104A/B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
19.3 | Conv-104A/B to Conv-105A/B and Conv-113 to Conv-105A/B,BF-105/106 to BF-107 to conv-107 transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
19.4 | Conv-105A/B to Cov-106A and Conv-105A/B to Cov-106B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
19.5 | Conv-107 to Conv-108,Conv-112 to Conv-113,Conv-111 to Con-112,Conv-108 to conv-109,conv-109 to conv-110, conveyor transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
20 | Comprehensive enhancement infrastructure of green Corridor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
20.1 | Providing and construction of Cement road at various location at 500 MW KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
20.2 | Constructions of RCC Drains at various locations in 500 MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
20.3 | Landscaping | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
20.4 | Dust Suppression | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
20.5 | Road Cleaning Machine | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
21 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
21.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
22 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
22.1 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
23 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
23.1 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
24 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
24.1 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
25 | Construction of LHS on Saoner & Kalumna siding of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
25.1 | Construction of Limited Height Subway at Pandhrakhedi, Patkakhedi (Saoner siding) & Suradevi (Kalumna siding) on depositary basis at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | ID fan motor rotor refurbishment of 500 MW | N.A. | - | 0 | 1.0962 | 1.0962 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Spare TDBFP Gear Box | N.A. | - | 0 | 0.58994 | 0.58994 | 0 | 0 | 0 |  |  | 0 | 0
3 | PISTON CYLINDER ASSEMBLY, DIAPHRAM ASSEMBLY | N.A. | - | 0 | 0 | 0 | 0 | 5.9274 | 5.9274 |  |  | 5.9274 | 0
4 | GT-R Phase Transformer#6006501 of U#5 (Spare) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | GT-R Phase Transformer#6006501U#5 (Core Replace) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | BCW Pump Motor Model HLAV (Refurbishment) U#5 | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM CHP-II | N.A. | - | 0 | 0 | 0 | 0 | 2.1501 | 2.1501 |  |  | 2.1501 | 0
8 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM C&I-2 | N.A. | - | 0 | 0 | 0 | 0 | 2.2408 | 2.2408 |  |  | 2.2408 | 0
9 | Land for Nandgaon ash band | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-II | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Fire Fighting equipment(Conveyors galleries CHPII) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF COMPLETE SET OF SKY CLIMBER FOR UNIT-5 (500 MW), TPS KHAPERKHEDA | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Supply & Erection of Duct, Diverter Plate, and Expansion Joints for Extensive Replacement of Flue Gas Duct at Unit-5,500 MW Khaperkheda TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Stacker Relaimer Refurbishment | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Work of design, Engineering, Supply & Installation along with capacity enhancement of drive unit of conveyor belt 103A,103B & 105B installed at CHP 500MW, Khaperkheda TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 500MW | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | work of Refurbishment/Modification of Air ventilation system at wagon tippler tunnel area, Apron feeder floor area, Wagon tippler control room, CHP control room and short conveyor area in CHP500 MW) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of design Engineering, Refurbishment & structural strenghthning along with replacement of damaged spares of conveyor belt 110 installed at coal handling plant 500MW . | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | GTR Refurbishment | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | SUPPLY,ERECTION ,COMMISSIONING AND TESTING OF 360V,750AH PLANTE TYPE UPS BATTERY SET AT UNIT 5 500MW | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Up-gradation of Generator Protection System and Feeder protection relays at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | BFP Booster pump | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Submission for approval of Non-DPR “Supply of Complete Cartridge Assemblies (1 Nos) for Boiler Feed Pump FK 4E 36 at (Unit#5, 500MW), Khaperkheda T.P.S. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procuremet of Portable Reclaimer | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Work of Design, Fabrication ,Erection & commissioning of Wobbler feeder and crusher bypass chute with provision of hydraulic actuator installed at coal handling plant 500MW, Khaperkheda TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Work of Revamping, Modification & Upgradation with Testing & Commissioning of Fire Detection and Alarm System including supply of Material for Unit # 5 BTG area at 500MW TPS Khaperkheda. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | HPCV2 Servomotor | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | Refurbishment of BCW pump Motor Model HLAV 2X300-460/1C (Rated 350 KW, 6.6 KV ,4 Pole, Sr. No. AP460044-3-1) of U#5 (500 MW) TPS, Khaperkheda. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Procurement of Complete Rotor Assy. along with 1st and 2nd stage blade set of PA Fan Type AP2 20/12 for Unit#5 (500 MW) TPS, Khaperkheda | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | Up-gradation of VFD system for GEHO Pump-2 at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | General Asset Furniture | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
32 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
33 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0.29668 |  |  | 0.29668 | -0.29668
| Total |  |  |  | 450.6327 | 163.582 | 287.0507 | 74.6248 | 152.0771 | 0 | 0 | 152.0771 | 209.5985
FY 2023-24
a) DPR Schemes
(i) Submitted to MERC
12 | Ash Disposal Scheme from K’kheda 1 X 500 MW Unit to Nandgaon Ash Bund | MERC/CAPEX/20162017 | 2017-09-22 | 69.1855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | 1. Construction of RCC pedestals for laying of ADP Lines from Khaperkheda TPS to Nandgaon Ash Bund. 2. Providing &Laying of ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 2a) Supply of MSERW and Seamless Pipes 2b) Laying of Ash Disposal & Recovery Pipe Line. 3. Construction of Service road for ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 4. Design, Engineering & construction of minor bridge, road crossing and culverts in the alignment of ash disposal pipe line from TPS Khaperkheda to Nandgaon Ash Bund 5. Construction of ash water recovery pump house at Nandgaon | MERC/CAPEX/20162017 | 2017-09-22 | 65.7755 | 89.3108 | 89.3108 | 0 | 6.3535 | 6.3535 |  |  | 6.3535 | 0 | 0 | 6.3535
0 | IDC | MERC/CAPEX/20162017 | 2017-09-22 | 3.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Bulldozer, Wheel axel final drive assembly & refurbishment of apron feeder at Khaperkheda TPS | MERC/CAPEX/20162017/01341 | 2017-10-11 | 11.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Procurement of Bulldozers(02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 3.75 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Procurement of wheel axel final drive assembly (02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Refurbishment of apron feeder | MERC/CAPEX/20162017/01341 | 2017-10-11 | 7.36 | 6.8736 | 5.629 | 1.2446 | 0 | 0 |  |  | 0 | 1.2446 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Procurement of Battery Set, PA Fan assembly, Jack Oil Pump, Turbo Driven BFP Cartridge and Restoration of ESP internals for 500 MW at Khaperkheda TPS | MERC/CAPEX/20172018/04320 | 2017-10-11 | 14.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Procurement, erection, commissioning & testing of 220V, 2190AH & 24V Battery set: | MERC/CAPEX/20172018/04320 | 2017-10-11 | 5.6 | 6.2928 | 6.2928 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Procurement of PA Fan assembly | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.1 | 3.3713 | 3.3713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Restoration of ESP internals | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.7 | 1.6097 | 1.6097 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Procurement of Jacking Oil Pump | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.18 | 0.27 | 0.27 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.5 | Procurement of turbo driven BFP Cartridge Assembly (FK4E36) | MERC/CAPEX/20172018/04320 | 2017-10-11 | 2.1 | 1.8279 | 1.8279 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 12.8838 | 12.8838 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Provision of S&T System for In Plant Yard Khaperkheda & Kalumni Yard (Depository Work) and Modification of Kalumna Yard Alteration No. 5 (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 31.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Provision of S & T System to Khaperkheda TPS In-Plant yard and Kalumna Yard (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 17.75 | 0.041975 | 0.041975 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Modification of Kalumna Yard Alternation no. 5 in connection with Khaperkheda TPS Expansion Project (1x500 MW) construction of B.G. Railway Siding | MERC/CAPEX/20172018/4779 | 2017-11-28 | 13.77 | 27.2859 | 13.5159 | 13.77 | 0 | 0 |  |  | 0 | 13.77 | 0 | 0
19 | Construction of Limited Height Subway (LHS) at unmanned road level crossing by Railway on cost sharing basis with MSPGCL on Khaperkheda-Kalumna railway siding and saoner-Khaperkheda railway siding | MERC/CAPEX/20172018/0178 | 2018-02-02 | 16.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Construction of LHS on Khaperkheda Kalumna railway side | MERC/CAPEX/20172018/0178 | 2018-02-02 | 5.94 | 4.9899 | 4.9899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Construction of LHS on Khaperkheda Saoner railway line | MERC/CAPEX/20172018/0178 | 2018-02-02 | 10.87 | 9.78 | 9.78 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Utilisation of unused water scheme from Bhanegaon open cast mine & construction of RCC internal roads at Khaperkheda TPS | MERC/CAPEX/20172018/0197 | 2018-02-06 | 11.5329 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Utilization of unused water scheme from Bhanegaon Open cast mine | MERC/CAPEX/20172018/0197 | 2018-02-06 | 7.5469 | 12.9367 | 12.9403 | -0.0036201 | 0 | 0 |  |  | 0 | -0.0036201 | 0 | 0
20.2 | Construction of Cement Concrete Road Inside Part Of Power House | MERC/CAPEX/20172018/0197 | 2018-02-06 | 2.906 | 2.6732 | 2.6732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0197 | 2018-02-06 | 1.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIMT 2000 (72° PA) | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 3.835 | 0 | 3.835 | 0 | 0 |  |  | 0 | 3.835 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.2027 | 3.2027 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 1.9759 | 0 | 1.9759 | 0.23671 | 2.2126 |  |  | 2.2126 | 0 | 2.2126 | 0
27 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 280.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | Flue Gas Desulphurization (FGD) System for KPKD 5 | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 260.21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 20.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.5033 | 4.5033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 313.58 | 124.5068 | 189.0732 | 67.44 | 67.6265 |  |  | 67.6265 | 188.8868 | 67.6265 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.23 | 1.8042 | 1.8042 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 4.0922 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.5 | Electromagnetic Flow meters at various lines & Locations of 500 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.2497 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.6 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Boiler Performance improvement Six Schemes at Unit-5 Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Sch-1: Procurement & Replacement of LTSH coils at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Sch-2: Procurement & Replacement of Economizer coils at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Sch-3: Procurement & Replacement of Water wall Z-Panels & Soot blower Panels at U#5: | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Sch-4 : Supply and erection of APH Inlet & Outlet Flue Gas Damper Assemblies along with actuators at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Sch-5 : Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines at U#5. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 25.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Up-gradation of maxDNA DCS system (HMI Up-gradation) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of PLC (GE FANUC make) SYSTEM (HMI & hardware up-gradation) at Ash Handling Plant, Compressor Plant, and Condensate Polishing Unit (CPU) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up-gradation of PLC (Schneider make) system (HMI & HARDWARE Up-gradation) at DM Plant, PTP, FF plant, CMRH System, HVAC System, FOPH system at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Up-gradation of SWAS (STEAM WATER ANALYSIS SYSTEM) Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.71 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Up-gradation of Carbon monoxide analyzer in Flue Gas Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Up-gradation of Coal feeder Controller at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 0.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 11.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 0.89 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR7 SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Supply Installation Testing & Commissioning , Revamping of fire detection & alarm and protection system from fire and providing rapid extinguishing clean agent (CA) system at unit # 5 at 500 MW khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Restoration of fire alarm valve with water spray system (DV) at CHP-II 500 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Modular Duct | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | PA Fan Rotor Assy. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Bottom ash & coarse ash system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Design Supply and erection of bottom ash hopper and Coarse ash hoppers. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Platform | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Refurbishment of BCW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Boiler Lift performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Water Wall Soot Blower Panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Thermal Insulation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | APH Baskets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Errection & Commisioning of Additional Soot blower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | PA Fan Rotor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.6 | Coal Compartment Assembly | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Process field instruments and PLCs hardware for performance improvement . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Upgradation of Emerson make PLC controllers and I/O (AHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of WTP & CHP PLC I/O and network accessories (BOP & CHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Upgradation of Pressure, flow, level transmitter, hydrastep, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Upgradation of Scanner , Ignitors, Solonoid system , relay of FSSS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Upgradation of control valves and cylinders instrumentation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Upgradation of ETP, Debris ,OLCC plc system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of Nucleonic density meter | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Upgradation of environment related instruments | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Installation of Furnace camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Installation of Flue gas exit temperature probe | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Electrical Protection Systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Upgradation of UPS system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of battery charger system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of ID Fan VFD system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Upgradation of DAVR system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of protection relays at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Enhancement of HT/ LT Auxillaries and Illumination for betterment availability and reliability | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply of 6.6 KV, 220 KW Ash Slurry Pump Motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Supply of 6.6 KV, 200 KW Fire Hydrant motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Supply of 690V, 800 KW GEHO Pump motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Refurbishment of BCW Pump Motor Sr. No. AP460044-3-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Supply of Dry Type Transformers of Different Ratings for Unit # 5, TPS Khaperkheda. (Rates are inclusive of 2% Packing and forwarding charges & 2% Freight Charges) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.6 | Supply of 3250KVA, 6.6/2.3 KV Oil Cooled VFD Transformer Of Vector Group Dyn11 and Ydn 11 & 25 MVA UAT For Unit# 5 At Khaperkheda TPS. (Including Packing and forwarding charges 2%, Freight Charges 2%) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.7 | Enhancing conventional lighting system at by retrofitting and replacement with energy efficient LED Lighting system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.8 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP & CHP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.9 | supply of integrated solar light and CCTV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | colony electrical renovation, switchgear, Energy meter, breaker,street light, 11 KV cable ,High Mast | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Electrical Rennovation and mordernization of various tenaments buildings,offices, recreation clubs, Hospital, Domestic Pump House, PTP Plant and Admin Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Replacement of Distibution board, High Mast and switchgear at different areas of colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Replacement of Energy meter and various LT Motors at Domestic Pump House and PTP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.4 | 11 KV Cable Work and various 11 KV Structure Rennovation Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.5 | Various Street Light Refurbishment Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | AHP Performance improvement Scheme for Dry fly ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Vacuum Pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Complete Assembly of Energy Efficient Air Compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of ESP evacuation pipelines, valves and blowers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Complete Refurbishment Work of 1st & 2nd Row Fields of ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.5 | Procurement of ESP CERM and EERM gear boxes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | AHP Performance improvement Scheme for Wet ash Disposal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Upgradation of Slurry Series System and HP Seal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of Fluid Couplings & Gearboxes for Slurry Series Pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Procurement of Vertical slurry pumps & Goodwin Submersible pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Procurement of Complete Assemblies of GEHO systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.5 | Procurement & Replacement of Slurry Disposal Pipelines | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.6 | Modification of Bottom ash overflow water clarification system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | ENAHANCMENT AND RELIABILITY IMPROVELMENT OF TURBINE AUXILIARIES | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | PROCUREMENT OF HPCV 2 SERVO MOTOR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of BFP-A cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Procurement of TDBFP turbine rotor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of CEP-B Cartridge Assembly without motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Procurement and commissioning of service and instrument air atlas copco compressor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Procurement of vacuum pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.7 | Procurement of Water treatment plant pumps for effluenet treatement , filter water Raw water, srewage treatement plant pumps, etc. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.8 | Procurement and replacement of ACW Pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.9 | Procurement of regulating BFP Recirculation valve A & B with actuator for flexible operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of ASV-22 and spray control valve | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | NDCT EFFICENCY IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Complete replacement of NDCT fills | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Procurement of clarifloculator and flash mixer gear box | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Supply, Installation & Commisioning of NDCT side stream filters | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | IMPROVEMENT OF TURBINE AND PUMPS EFFICENCY | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Procurement of HPT module including Turbo visory instruments (TM-II & C&I-II) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Procurement and replacement of ACW Pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Procurement of CEP-C Cartridge Assembly with out motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Wagon tippler installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Renovation and modanisation of wagen tipler concrete hopper | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Supply and errection of Wagon tipplers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of hydraulic systems with safety mechanism for Wagon unloading | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Capacity enhancement of side arm charger | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Capacity enhancement of Apron feeder | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | CHP-II Performance improvement scheme installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Supply and installeation of impact crusher spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Replacement of scoop coupling | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Renovation stacker reclaimer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Complete overhauling of Wobbler feeder | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Procurement of Gear boxes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Structure Strengthening and modification work of Conveyors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Infrastructure Development Schemes & Electrical schemes for improvement in availability & Reliability of auxilliaries installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of EOT cranes and hoist installed in CHP-II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Modification of DE and DS system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Procuremnet of HT Motors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Procuremnet of VFD for LT motors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | upgradation of wagon tippler PLC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Reconditioning of MCC Boards and feeder panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Provision of ceramic lagging to pulleyes ,belt tracker system and mechanise spillage free control system for various conveyor systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design engineering , supply and installation of modular chutes with Liners of various belt conveyor installed in CHP-II . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Apron feeder-101/102 to Conv-102A/B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Conv-103A/B to wobbler feeder-101/102 to Crusher -101/102 to Belt feeder-101/102 to conv-104A/B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Conv-104A/B to Conv-105A/B and Conv-113 to Conv-105A/B,BF-105/106 to BF-107 to conv-107 transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Conv-105A/B to Cov-106A and Conv-105A/B to Cov-106B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Conv-107 to Conv-108,Conv-112 to Conv-113,Conv-111 to Con-112,Conv-108 to conv-109,conv-109 to conv-110, conveyor transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Comprehensive enhancement infrastructure of green Corridor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Providing and construction of Cement road at various location at 500 MW KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Constructions of RCC Drains at various locations in 500 MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Landscaping | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Dust Suppression | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Road Cleaning Machine | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Construction of LHS on Saoner & Kalumna siding of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Construction of Limited Height Subway at Pandhrakhedi, Patkakhedi (Saoner siding) & Suradevi (Kalumna siding) on depositary basis at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | ID fan motor rotor refurbishment of 500 MW | N.A. | - | 0 | 1.0962 | 1.0962 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Spare TDBFP Gear Box | N.A. | - | 0 | 0.58994 | 0.58994 | 0 | 0 | 0 |  |  | 0 | 0
3 | PISTON CYLINDER ASSEMBLY, DIAPHRAM ASSEMBLY | N.A. | - | 0 | 5.9274 | 5.9274 | 0 | 0.042685 | 0.042685 |  |  | 0.042685 | 0
4 | GT-R Phase Transformer#6006501 of U#5 (Spare) | N.A. | - | 0 | 0 | 0 | 0 | 6.241 | 6.241 |  |  | 6.241 | 0
5 | GT-R Phase Transformer#6006501U#5 (Core Replace) | N.A. | - | 0 | 0 | 0 | 0 | 3.1304 | 3.1304 |  |  | 3.1304 | 0
6 | BCW Pump Motor Model HLAV (Refurbishment) U#5 | N.A. | - | 0 | 0 | 0 | 0 | 2.8718 | 2.8718 |  |  | 2.8718 | 0
7 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM CHP-II | N.A. | - | 0 | 2.1501 | 2.1501 | 0 | 0 | 0 |  |  | 0 | 0
8 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM C&I-2 | N.A. | - | 0 | 2.2408 | 2.2408 | 0 | 0 | 0 |  |  | 0 | 0
9 | Land for Nandgaon ash band | N.A. | - | 0 | 0 | 0 | 0 | 0.267 | 0.267 |  |  | 0.267 | 0
10 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-II | N.A. | - | 0 | 0 | 0 | 0 | 1.5824 | 1.5824 |  |  | 1.5824 | 0
11 | Fire Fighting equipment(Conveyors galleries CHPII) | N.A. | - | 0 | 0 | 0 | 0 | 0.57643 | 0.57643 |  |  | 0.57643 | 0
12 | PROCUREMENT OF COMPLETE SET OF SKY CLIMBER FOR UNIT-5 (500 MW), TPS KHAPERKHEDA | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Supply & Erection of Duct, Diverter Plate, and Expansion Joints for Extensive Replacement of Flue Gas Duct at Unit-5,500 MW Khaperkheda TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Stacker Relaimer Refurbishment | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Work of design, Engineering, Supply & Installation along with capacity enhancement of drive unit of conveyor belt 103A,103B & 105B installed at CHP 500MW, Khaperkheda TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 500MW | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | work of Refurbishment/Modification of Air ventilation system at wagon tippler tunnel area, Apron feeder floor area, Wagon tippler control room, CHP control room and short conveyor area in CHP500 MW) | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of design Engineering, Refurbishment & structural strenghthning along with replacement of damaged spares of conveyor belt 110 installed at coal handling plant 500MW . | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | GTR Refurbishment | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | SUPPLY,ERECTION ,COMMISSIONING AND TESTING OF 360V,750AH PLANTE TYPE UPS BATTERY SET AT UNIT 5 500MW | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Up-gradation of Generator Protection System and Feeder protection relays at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | BFP Booster pump | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Submission for approval of Non-DPR “Supply of Complete Cartridge Assemblies (1 Nos) for Boiler Feed Pump FK 4E 36 at (Unit#5, 500MW), Khaperkheda T.P.S. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procuremet of Portable Reclaimer | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Work of Design, Fabrication ,Erection & commissioning of Wobbler feeder and crusher bypass chute with provision of hydraulic actuator installed at coal handling plant 500MW, Khaperkheda TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Work of Revamping, Modification & Upgradation with Testing & Commissioning of Fire Detection and Alarm System including supply of Material for Unit # 5 BTG area at 500MW TPS Khaperkheda. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | HPCV2 Servomotor | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | Refurbishment of BCW pump Motor Model HLAV 2X300-460/1C (Rated 350 KW, 6.6 KV ,4 Pole, Sr. No. AP460044-3-1) of U#5 (500 MW) TPS, Khaperkheda. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
29 | Procurement of Complete Rotor Assy. along with 1st and 2nd stage blade set of PA Fan Type AP2 20/12 for Unit#5 (500 MW) TPS, Khaperkheda | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | Up-gradation of VFD system for GEHO Pump-2 at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | General Asset Furniture | N.A. | - | 0 | 0 | 0 | 0 | 0.011682 | 0.011682 |  |  | 0.011682 | 0
32 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0.12056 |  |  | 0.12056 | -0.12056
33 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 0 | 0.29668 | -0.29668 | 0.043476 | 0.37035 |  |  | 0.37035 | -0.62355
| Total |  |  | 0 | 525.2576 | 315.6591 | 209.5985 | 88.7972 | 91.407 | 0 | 0 | 91.407 | 206.9886
FY 2024-25
a) DPR Schemes
(i) Submitted to MERC
12 | Ash Disposal Scheme from K’kheda 1 X 500 MW Unit to Nandgaon Ash Bund | MERC/CAPEX/20162017 | 2017-09-22 | 69.1855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | 1. Construction of RCC pedestals for laying of ADP Lines from Khaperkheda TPS to Nandgaon Ash Bund. 2. Providing &Laying of ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 2a) Supply of MSERW and Seamless Pipes 2b) Laying of Ash Disposal & Recovery Pipe Line. 3. Construction of Service road for ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 4. Design, Engineering & construction of minor bridge, road crossing and culverts in the alignment of ash disposal pipe line from TPS Khaperkheda to Nandgaon Ash Bund 5. Construction of ash water recovery pump house at Nandgaon | MERC/CAPEX/20162017 | 2017-09-22 | 65.7755 | 95.6643 | 95.6643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017 | 2017-09-22 | 3.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Bulldozer, Wheel axel final drive assembly & refurbishment of apron feeder at Khaperkheda TPS | MERC/CAPEX/20162017/01341 | 2017-10-11 | 11.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Procurement of Bulldozers(02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 3.75 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Procurement of wheel axel final drive assembly (02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Refurbishment of apron feeder | MERC/CAPEX/20162017/01341 | 2017-10-11 | 7.36 | 6.8736 | 5.629 | 1.2446 | 0 | 0 |  |  | 0 | 1.2446 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Procurement of Battery Set, PA Fan assembly, Jack Oil Pump, Turbo Driven BFP Cartridge and Restoration of ESP internals for 500 MW at Khaperkheda TPS | MERC/CAPEX/20172018/04320 | 2017-10-11 | 14.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Procurement, erection, commissioning & testing of 220V, 2190AH & 24V Battery set: | MERC/CAPEX/20172018/04320 | 2017-10-11 | 5.6 | 6.2928 | 6.2928 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Procurement of PA Fan assembly | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.1 | 3.3713 | 3.3713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Restoration of ESP internals | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.7 | 1.6097 | 1.6097 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Procurement of Jacking Oil Pump | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.18 | 0.27 | 0.27 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.5 | Procurement of turbo driven BFP Cartridge Assembly (FK4E36) | MERC/CAPEX/20172018/04320 | 2017-10-11 | 2.1 | 1.8279 | 1.8279 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 12.8838 | 12.8838 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Provision of S&T System for In Plant Yard Khaperkheda & Kalumni Yard (Depository Work) and Modification of Kalumna Yard Alteration No. 5 (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 31.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Provision of S & T System to Khaperkheda TPS In-Plant yard and Kalumna Yard (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 17.75 | 0.041975 | 0.041975 | 0 | 17.01 | 0 |  |  | 0 | 17.01 | 0 | 0
18.2 | Modification of Kalumna Yard Alternation no. 5 in connection with Khaperkheda TPS Expansion Project (1x500 MW) construction of B.G. Railway Siding | MERC/CAPEX/20172018/4779 | 2017-11-28 | 13.77 | 27.2859 | 13.5159 | 13.77 | 0 | 0 |  |  | 0 | 13.77 | 0 | 0
19 | Construction of Limited Height Subway (LHS) at unmanned road level crossing by Railway on cost sharing basis with MSPGCL on Khaperkheda-Kalumna railway siding and saoner-Khaperkheda railway siding | MERC/CAPEX/20172018/0178 | 2018-02-02 | 16.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Construction of LHS on Khaperkheda Kalumna railway side | MERC/CAPEX/20172018/0178 | 2018-02-02 | 5.94 | 4.9899 | 4.9899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Construction of LHS on Khaperkheda Saoner railway line | MERC/CAPEX/20172018/0178 | 2018-02-02 | 10.87 | 9.78 | 9.78 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Utilisation of unused water scheme from Bhanegaon open cast mine & construction of RCC internal roads at Khaperkheda TPS | MERC/CAPEX/20172018/0197 | 2018-02-06 | 11.5329 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Utilization of unused water scheme from Bhanegaon Open cast mine | MERC/CAPEX/20172018/0197 | 2018-02-06 | 7.5469 | 12.9367 | 12.9403 | -0.0036201 | 0 | 0 |  |  | 0 | -0.0036201 | 0 | 0
20.2 | Construction of Cement Concrete Road Inside Part Of Power House | MERC/CAPEX/20172018/0197 | 2018-02-06 | 2.906 | 2.6732 | 2.6732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0197 | 2018-02-06 | 1.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIMT 2000 (72° PA) | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 3.835 | 0 | 3.835 | 0 | 3.835 |  |  | 3.835 | 0 | 3.4 | 0.435
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.2027 | 3.2027 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 2.2126 | 2.2126 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 280.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | Flue Gas Desulphurization (FGD) System for KPKD 5 | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 260.21 | 0 | 0 | 0 | 84.92 | 84.92 |  |  | 84.92 | 0 | 84.92 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 20.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.5033 | 4.5033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 381.02 | 192.1332 | 188.8868 | 196.92 | 196.92 |  |  | 196.92 | 188.8868 | 77.2744 | 119.6456
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.23 | 1.8042 | 1.8042 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 4.0922 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.5 | Electromagnetic Flow meters at various lines & Locations of 500 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.2497 | 0 | 0 | 0 | 3.2497 | 3.2497 |  |  | 3.2497 | 0 | 3.2497 | 0
HO DPR 15.6 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0 | 0 | 0 | 0.84 | 0.84 |  |  | 0.84 | 0 | 0.84 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 0 | 0 | 0 | 45.31 | 45.31 |  |  | 45.31 | 0 | 31.0231 | 14.2869
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Boiler Performance improvement Six Schemes at Unit-5 Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Sch-1: Procurement & Replacement of LTSH coils at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Sch-2: Procurement & Replacement of Economizer coils at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Sch-3: Procurement & Replacement of Water wall Z-Panels & Soot blower Panels at U#5: | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Sch-4 : Supply and erection of APH Inlet & Outlet Flue Gas Damper Assemblies along with actuators at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Sch-5 : Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines at U#5. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 25.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Up-gradation of maxDNA DCS system (HMI Up-gradation) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of PLC (GE FANUC make) SYSTEM (HMI & hardware up-gradation) at Ash Handling Plant, Compressor Plant, and Condensate Polishing Unit (CPU) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up-gradation of PLC (Schneider make) system (HMI & HARDWARE Up-gradation) at DM Plant, PTP, FF plant, CMRH System, HVAC System, FOPH system at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Up-gradation of SWAS (STEAM WATER ANALYSIS SYSTEM) Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.71 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Up-gradation of Carbon monoxide analyzer in Flue Gas Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.02 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Up-gradation of Coal feeder Controller at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 0.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 11.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 0.89 | 0 | 0 | 0 | 0.89 | 0.89 |  |  | 0.89 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR7 SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Supply Installation Testing & Commissioning , Revamping of fire detection & alarm and protection system from fire and providing rapid extinguishing clean agent (CA) system at unit # 5 at 500 MW khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Restoration of fire alarm valve with water spray system (DV) at CHP-II 500 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Modular Duct | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | PA Fan Rotor Assy. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Bottom ash & coarse ash system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Design Supply and erection of bottom ash hopper and Coarse ash hoppers. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Platform | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Refurbishment of BCW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Boiler Lift performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Water Wall Soot Blower Panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Thermal Insulation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | APH Baskets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Errection & Commisioning of Additional Soot blower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | PA Fan Rotor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.6 | Coal Compartment Assembly | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Process field instruments and PLCs hardware for performance improvement . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Upgradation of Emerson make PLC controllers and I/O (AHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of WTP & CHP PLC I/O and network accessories (BOP & CHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Upgradation of Pressure, flow, level transmitter, hydrastep, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Upgradation of Scanner , Ignitors, Solonoid system , relay of FSSS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Upgradation of control valves and cylinders instrumentation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Upgradation of ETP, Debris ,OLCC plc system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of Nucleonic density meter | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Upgradation of environment related instruments | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Installation of Furnace camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Installation of Flue gas exit temperature probe | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Electrical Protection Systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Upgradation of UPS system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of battery charger system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of ID Fan VFD system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Upgradation of DAVR system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of protection relays at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Enhancement of HT/ LT Auxillaries and Illumination for betterment availability and reliability | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply of 6.6 KV, 220 KW Ash Slurry Pump Motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Supply of 6.6 KV, 200 KW Fire Hydrant motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Supply of 690V, 800 KW GEHO Pump motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Refurbishment of BCW Pump Motor Sr. No. AP460044-3-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Supply of Dry Type Transformers of Different Ratings for Unit # 5, TPS Khaperkheda. (Rates are inclusive of 2% Packing and forwarding charges & 2% Freight Charges) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.6 | Supply of 3250KVA, 6.6/2.3 KV Oil Cooled VFD Transformer Of Vector Group Dyn11 and Ydn 11 & 25 MVA UAT For Unit# 5 At Khaperkheda TPS. (Including Packing and forwarding charges 2%, Freight Charges 2%) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.7 | Enhancing conventional lighting system at by retrofitting and replacement with energy efficient LED Lighting system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.8 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP & CHP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.9 | supply of integrated solar light and CCTV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | colony electrical renovation, switchgear, Energy meter, breaker,street light, 11 KV cable ,High Mast | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Electrical Rennovation and mordernization of various tenaments buildings,offices, recreation clubs, Hospital, Domestic Pump House, PTP Plant and Admin Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Replacement of Distibution board, High Mast and switchgear at different areas of colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Replacement of Energy meter and various LT Motors at Domestic Pump House and PTP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.4 | 11 KV Cable Work and various 11 KV Structure Rennovation Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.5 | Various Street Light Refurbishment Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | AHP Performance improvement Scheme for Dry fly ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Vacuum Pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Complete Assembly of Energy Efficient Air Compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of ESP evacuation pipelines, valves and blowers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Complete Refurbishment Work of 1st & 2nd Row Fields of ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.5 | Procurement of ESP CERM and EERM gear boxes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | AHP Performance improvement Scheme for Wet ash Disposal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Upgradation of Slurry Series System and HP Seal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of Fluid Couplings & Gearboxes for Slurry Series Pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Procurement of Vertical slurry pumps & Goodwin Submersible pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Procurement of Complete Assemblies of GEHO systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.5 | Procurement & Replacement of Slurry Disposal Pipelines | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.6 | Modification of Bottom ash overflow water clarification system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | ENAHANCMENT AND RELIABILITY IMPROVELMENT OF TURBINE AUXILIARIES | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | PROCUREMENT OF HPCV 2 SERVO MOTOR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of BFP-A cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Procurement of TDBFP turbine rotor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of CEP-B Cartridge Assembly without motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Procurement and commissioning of service and instrument air atlas copco compressor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Procurement of vacuum pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.7 | Procurement of Water treatment plant pumps for effluenet treatement , filter water Raw water, srewage treatement plant pumps, etc. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.8 | Procurement and replacement of ACW Pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.9 | Procurement of regulating BFP Recirculation valve A & B with actuator for flexible operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of ASV-22 and spray control valve | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | NDCT EFFICENCY IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Complete replacement of NDCT fills | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Procurement of clarifloculator and flash mixer gear box | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Supply, Installation & Commisioning of NDCT side stream filters | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | IMPROVEMENT OF TURBINE AND PUMPS EFFICENCY | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Procurement of HPT module including Turbo visory instruments (TM-II & C&I-II) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Procurement and replacement of ACW Pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Procurement of CEP-C Cartridge Assembly with out motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Wagon tippler installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Renovation and modanisation of wagen tipler concrete hopper | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Supply and errection of Wagon tipplers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of hydraulic systems with safety mechanism for Wagon unloading | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Capacity enhancement of side arm charger | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Capacity enhancement of Apron feeder | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | CHP-II Performance improvement scheme installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Supply and installeation of impact crusher spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Replacement of scoop coupling | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Renovation stacker reclaimer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Complete overhauling of Wobbler feeder | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Procurement of Gear boxes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Structure Strengthening and modification work of Conveyors. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18 | Infrastructure Development Schemes & Electrical schemes for improvement in availability & Reliability of auxilliaries installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of EOT cranes and hoist installed in CHP-II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Modification of DE and DS system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Procuremnet of HT Motors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Procuremnet of VFD for LT motors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | upgradation of wagon tippler PLC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Reconditioning of MCC Boards and feeder panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Provision of ceramic lagging to pulleyes ,belt tracker system and mechanise spillage free control system for various conveyor systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design engineering , supply and installation of modular chutes with Liners of various belt conveyor installed in CHP-II . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Apron feeder-101/102 to Conv-102A/B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Conv-103A/B to wobbler feeder-101/102 to Crusher -101/102 to Belt feeder-101/102 to conv-104A/B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Conv-104A/B to Conv-105A/B and Conv-113 to Conv-105A/B,BF-105/106 to BF-107 to conv-107 transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Conv-105A/B to Cov-106A and Conv-105A/B to Cov-106B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Conv-107 to Conv-108,Conv-112 to Conv-113,Conv-111 to Con-112,Conv-108 to conv-109,conv-109 to conv-110, conveyor transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Comprehensive enhancement infrastructure of green Corridor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Providing and construction of Cement road at various location at 500 MW KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Constructions of RCC Drains at various locations in 500 MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Landscaping | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Dust Suppression | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Road Cleaning Machine | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Construction of LHS on Saoner & Kalumna siding of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Construction of Limited Height Subway at Pandhrakhedi, Patkakhedi (Saoner siding) & Suradevi (Kalumna siding) on depositary basis at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | ID fan motor rotor refurbishment of 500 MW | N.A. | - | 0 | 1.0962 | 1.0962 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Spare TDBFP Gear Box | N.A. | - | 0 | 0.58994 | 0.58994 | 0 | 0 | 0 |  |  | 0 | 0
3 | PISTON CYLINDER ASSEMBLY, DIAPHRAM ASSEMBLY | N.A. | - | 0 | 5.9701 | 5.9701 | 0 | 0 | 0 |  |  | 0 | 0
4 | GT-R Phase Transformer#6006501 of U#5 (Spare) | N.A. | - | 0 | 6.241 | 6.241 | 0 | 0 | 0 |  |  | 0 | 0
5 | GT-R Phase Transformer#6006501U#5 (Core Replace) | N.A. | - | 0 | 3.1304 | 3.1304 | 0 | 0 | 0 |  |  | 0 | 0
6 | BCW Pump Motor Model HLAV (Refurbishment) U#5 | N.A. | - | 0 | 2.8718 | 2.8718 | 0 | 0 | 0 |  |  | 0 | 0
7 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM CHP-II | N.A. | - | 0 | 2.1501 | 2.1501 | 0 | 0 | 0 |  |  | 0 | 0
8 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM C&I-2 | N.A. | - | 0 | 2.2408 | 2.2408 | 0 | 0 | 0 |  |  | 0 | 0
9 | Land for Nandgaon ash band | N.A. | - | 0 | 0.267 | 0.267 | 0 | 0 | 0 |  |  | 0 | 0
10 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-II | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
11 | Fire Fighting equipment(Conveyors galleries CHPII) | N.A. | - | 0 | 0.57643 | 0.57643 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF COMPLETE SET OF SKY CLIMBER FOR UNIT-5 (500 MW), TPS KHAPERKHEDA | N.A. | - | 0 | 0 | 0 | 0 | 0.86 | 0.86 |  |  | 0.86 | 0
13 | Supply & Erection of Duct, Diverter Plate, and Expansion Joints for Extensive Replacement of Flue Gas Duct at Unit-5,500 MW Khaperkheda TPS | N.A. | - | 0 | 0 | 0 | 0 | 4.09 | 4.09 |  |  | 4.09 | 0
14 | Stacker Relaimer Refurbishment | N.A. | - | 0 | 0 | 0 | 0 | 20.2 | 20.2 |  |  | 20.2 | 0
15 | Work of design, Engineering, Supply & Installation along with capacity enhancement of drive unit of conveyor belt 103A,103B & 105B installed at CHP 500MW, Khaperkheda TPS | N.A. | - | 0 | 0 | 0 | 0 | 4.08 | 4.08 |  |  | 4.08 | 0
16 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 500MW | N.A. | - | 0 | 0 | 0 | 0 | 1.21 | 1.21 |  |  | 1.21 | 0
17 | work of Refurbishment/Modification of Air ventilation system at wagon tippler tunnel area, Apron feeder floor area, Wagon tippler control room, CHP control room and short conveyor area in CHP500 MW) | N.A. | - | 0 | 0 | 0 | 0 | 2.06 | 2.06 |  |  | 2.06 | 0
18 | Work of design Engineering, Refurbishment & structural strenghthning along with replacement of damaged spares of conveyor belt 110 installed at coal handling plant 500MW . | N.A. | - | 0 | 0 | 0 | 0 | 2.21 | 2.21 |  |  | 2.21 | 0
19 | GTR Refurbishment | N.A. | - | 0 | 0 | 0 | 0 | 0.33 | 0.33 |  |  | 0.33 | 0
20 | SUPPLY,ERECTION ,COMMISSIONING AND TESTING OF 360V,750AH PLANTE TYPE UPS BATTERY SET AT UNIT 5 500MW | N.A. | - | 0 | 0 | 0 | 0 | 2.87 | 2.87 |  |  | 2.87 | 0
21 | Up-gradation of Generator Protection System and Feeder protection relays at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 0 | 0 | 0 | 2.09 | 2.09 |  |  | 2.09 | 0
22 | BFP Booster pump | N.A. | - | 0 | 0 | 0 | 0 | 1.4 | 1.4 |  |  | 1.4 | 0
23 | Submission for approval of Non-DPR “Supply of Complete Cartridge Assemblies (1 Nos) for Boiler Feed Pump FK 4E 36 at (Unit#5, 500MW), Khaperkheda T.P.S. | N.A. | - | 0 | 0 | 0 | 0 | 1.99 | 1.99 |  |  | 1.99 | 0
24 | Procuremet of Portable Reclaimer | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Work of Design, Fabrication ,Erection & commissioning of Wobbler feeder and crusher bypass chute with provision of hydraulic actuator installed at coal handling plant 500MW, Khaperkheda TPS | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
26 | Work of Revamping, Modification & Upgradation with Testing & Commissioning of Fire Detection and Alarm System including supply of Material for Unit # 5 BTG area at 500MW TPS Khaperkheda. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
27 | HPCV2 Servomotor | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
28 | Refurbishment of BCW pump Motor Model HLAV 2X300-460/1C (Rated 350 KW, 6.6 KV ,4 Pole, Sr. No. AP460044-3-1) of U#5 (500 MW) TPS, Khaperkheda. | N.A. | - | 0 | 0 | 0 | 0 | 3.59 | 3.59 |  |  | 3.59 | 0
29 | Procurement of Complete Rotor Assy. along with 1st and 2nd stage blade set of PA Fan Type AP2 20/12 for Unit#5 (500 MW) TPS, Khaperkheda | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
30 | Up-gradation of VFD system for GEHO Pump-2 at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
31 | General Asset Furniture | N.A. | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
32 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0 | 0.12056 | -0.12056 | 0 | 0 |  |  | 0 | -0.12056
33 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 0.043476 | 0.66703 | -0.62355 | 0 | 0 |  |  | 0 | -0.62355
| Total |  |  | 0 | 614.0547 | 407.0661 | 206.9886 | 396.1197 | 382.9447 | 0 | 0 | 382.9447 | 220.1636
FY 2025-26
a) DPR Schemes
(i) Submitted to MERC
12 | Ash Disposal Scheme from K’kheda 1 X 500 MW Unit to Nandgaon Ash Bund | MERC/CAPEX/20162017 | 2017-09-22 | 69.1855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | 1. Construction of RCC pedestals for laying of ADP Lines from Khaperkheda TPS to Nandgaon Ash Bund. 2. Providing &Laying of ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 2a) Supply of MSERW and Seamless Pipes 2b) Laying of Ash Disposal & Recovery Pipe Line. 3. Construction of Service road for ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 4. Design, Engineering & construction of minor bridge, road crossing and culverts in the alignment of ash disposal pipe line from TPS Khaperkheda to Nandgaon Ash Bund 5. Construction of ash water recovery pump house at Nandgaon | MERC/CAPEX/20162017 | 2017-09-22 | 65.7755 | 95.6643 | 95.6643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017 | 2017-09-22 | 3.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Bulldozer, Wheel axel final drive assembly & refurbishment of apron feeder at Khaperkheda TPS | MERC/CAPEX/20162017/01341 | 2017-10-11 | 11.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Procurement of Bulldozers(02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 3.75 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Procurement of wheel axel final drive assembly (02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Refurbishment of apron feeder | MERC/CAPEX/20162017/01341 | 2017-10-11 | 7.36 | 6.8736 | 5.629 | 1.2446 | 0 | 0 |  |  | 0 | 1.2446 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Procurement of Battery Set, PA Fan assembly, Jack Oil Pump, Turbo Driven BFP Cartridge and Restoration of ESP internals for 500 MW at Khaperkheda TPS | MERC/CAPEX/20172018/04320 | 2017-10-11 | 14.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Procurement, erection, commissioning & testing of 220V, 2190AH & 24V Battery set: | MERC/CAPEX/20172018/04320 | 2017-10-11 | 5.6 | 6.2928 | 6.2928 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Procurement of PA Fan assembly | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.1 | 3.3713 | 3.3713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Restoration of ESP internals | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.7 | 1.6097 | 1.6097 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Procurement of Jacking Oil Pump | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.18 | 0.27 | 0.27 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.5 | Procurement of turbo driven BFP Cartridge Assembly (FK4E36) | MERC/CAPEX/20172018/04320 | 2017-10-11 | 2.1 | 1.8279 | 1.8279 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 12.8838 | 12.8838 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Provision of S&T System for In Plant Yard Khaperkheda & Kalumni Yard (Depository Work) and Modification of Kalumna Yard Alteration No. 5 (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 31.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Provision of S & T System to Khaperkheda TPS In-Plant yard and Kalumna Yard (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 17.75 | 17.052 | 0.041975 | 17.01 | 3 | 20.01 |  |  | 20.01 | 0 | 17.708 | 2.302
18.2 | Modification of Kalumna Yard Alternation no. 5 in connection with Khaperkheda TPS Expansion Project (1x500 MW) construction of B.G. Railway Siding | MERC/CAPEX/20172018/4779 | 2017-11-28 | 13.77 | 27.2859 | 13.5159 | 13.77 | 0 | 0 |  |  | 0 | 13.77 | 0 | 0
19 | Construction of Limited Height Subway (LHS) at unmanned road level crossing by Railway on cost sharing basis with MSPGCL on Khaperkheda-Kalumna railway siding and saoner-Khaperkheda railway siding | MERC/CAPEX/20172018/0178 | 2018-02-02 | 16.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Construction of LHS on Khaperkheda Kalumna railway side | MERC/CAPEX/20172018/0178 | 2018-02-02 | 5.94 | 4.9899 | 4.9899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Construction of LHS on Khaperkheda Saoner railway line | MERC/CAPEX/20172018/0178 | 2018-02-02 | 10.87 | 9.78 | 9.78 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Utilisation of unused water scheme from Bhanegaon open cast mine & construction of RCC internal roads at Khaperkheda TPS | MERC/CAPEX/20172018/0197 | 2018-02-06 | 11.5329 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Utilization of unused water scheme from Bhanegaon Open cast mine | MERC/CAPEX/20172018/0197 | 2018-02-06 | 7.5469 | 12.9367 | 12.9403 | -0.0036201 | 0 | 0 |  |  | 0 | -0.0036201 | 0 | 0
20.2 | Construction of Cement Concrete Road Inside Part Of Power House | MERC/CAPEX/20172018/0197 | 2018-02-06 | 2.906 | 2.6732 | 2.6732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0197 | 2018-02-06 | 1.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIMT 2000 (72° PA) | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 3.835 | 3.835 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.2027 | 3.2027 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 2.2126 | 2.2126 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 280.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | Flue Gas Desulphurization (FGD) System for KPKD 5 | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 260.21 | 84.92 | 84.92 | 0 | 311.36 | 311.36 |  |  | 311.36 | 0 | 175.29 | 136.07
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 20.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.5033 | 4.5033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 577.94 | 389.0532 | 188.8868 | 0 | 0 |  |  | 0 | 188.8868 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.23 | 1.8042 | 1.8042 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 4.0922 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.5 | Electromagnetic Flow meters at various lines & Locations of 500 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.2497 | 3.2497 | 3.2497 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.6 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84 | 0.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 45.31 | 45.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Boiler Performance improvement Six Schemes at Unit-5 Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Sch-1: Procurement & Replacement of LTSH coils at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Sch-2: Procurement & Replacement of Economizer coils at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Sch-3: Procurement & Replacement of Water wall Z-Panels & Soot blower Panels at U#5: | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Sch-4 : Supply and erection of APH Inlet & Outlet Flue Gas Damper Assemblies along with actuators at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Sch-5 : Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines at U#5. | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 25.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Up-gradation of maxDNA DCS system (HMI Up-gradation) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.29 | 0 | 0 | 0 | 7.29 | 7.29 |  |  | 7.29 | 0
2.2 | Up-gradation of PLC (GE FANUC make) SYSTEM (HMI & hardware up-gradation) at Ash Handling Plant, Compressor Plant, and Condensate Polishing Unit (CPU) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.14 | 0 | 0 | 0 | 1.14 | 1.14 |  |  | 1.14 | 0
2.3 | Up-gradation of PLC (Schneider make) system (HMI & HARDWARE Up-gradation) at DM Plant, PTP, FF plant, CMRH System, HVAC System, FOPH system at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.26 | 0 | 0 | 0 | 4.26 | 4.26 |  |  | 4.26 | 0
2.4 | Up-gradation of SWAS (STEAM WATER ANALYSIS SYSTEM) Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.71 | 0 | 0 | 0 | 4.71 | 4.71 |  |  | 4.71 | 0
2.5 | Up-gradation of Carbon monoxide analyzer in Flue Gas Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.02 | 0 | 0 | 0 | 1.02 | 1.02 |  |  | 1.02 | 0
2.6 | Up-gradation of Coal feeder Controller at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.01 | 0 | 0 | 0 | 7.01 | 7.01 |  |  | 7.01 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 0.86 | 0 | 0 | 0 | 0.86 | 0.86 |  |  | 0.86 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 11.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 0.89 | 0.89 | 0.89 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 5.34 | 5.34 |  |  | 5.34 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR7 SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Supply Installation Testing & Commissioning , Revamping of fire detection & alarm and protection system from fire and providing rapid extinguishing clean agent (CA) system at unit # 5 at 500 MW khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Restoration of fire alarm valve with water spray system (DV) at CHP-II 500 MW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Modular Duct | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | PA Fan Rotor Assy. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Bottom ash & coarse ash system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Design Supply and erection of bottom ash hopper and Coarse ash hoppers. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Platform | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Refurbishment of BCW | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Boiler Lift performance | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Water Wall Soot Blower Panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Thermal Insulation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | APH Baskets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Errection & Commisioning of Additional Soot blower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | PA Fan Rotor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.6 | Coal Compartment Assembly | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Process field instruments and PLCs hardware for performance improvement . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Upgradation of Emerson make PLC controllers and I/O (AHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of WTP & CHP PLC I/O and network accessories (BOP & CHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Upgradation of Pressure, flow, level transmitter, hydrastep, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Upgradation of Scanner , Ignitors, Solonoid system , relay of FSSS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Upgradation of control valves and cylinders instrumentation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Upgradation of ETP, Debris ,OLCC plc system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of Nucleonic density meter | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Upgradation of environment related instruments | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Installation of Furnace camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Installation of Flue gas exit temperature probe | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Electrical Protection Systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Upgradation of UPS system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of battery charger system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of ID Fan VFD system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Upgradation of DAVR system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of protection relays at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Enhancement of HT/ LT Auxillaries and Illumination for betterment availability and reliability | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply of 6.6 KV, 220 KW Ash Slurry Pump Motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Supply of 6.6 KV, 200 KW Fire Hydrant motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Supply of 690V, 800 KW GEHO Pump motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Refurbishment of BCW Pump Motor Sr. No. AP460044-3-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Supply of Dry Type Transformers of Different Ratings for Unit # 5, TPS Khaperkheda. (Rates are inclusive of 2% Packing and forwarding charges & 2% Freight Charges) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.6 | Supply of 3250KVA, 6.6/2.3 KV Oil Cooled VFD Transformer Of Vector Group Dyn11 and Ydn 11 & 25 MVA UAT For Unit# 5 At Khaperkheda TPS. (Including Packing and forwarding charges 2%, Freight Charges 2%) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.7 | Enhancing conventional lighting system at by retrofitting and replacement with energy efficient LED Lighting system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.8 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP & CHP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.9 | supply of integrated solar light and CCTV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | colony electrical renovation, switchgear, Energy meter, breaker,street light, 11 KV cable ,High Mast | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Electrical Rennovation and mordernization of various tenaments buildings,offices, recreation clubs, Hospital, Domestic Pump House, PTP Plant and Admin Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Replacement of Distibution board, High Mast and switchgear at different areas of colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Replacement of Energy meter and various LT Motors at Domestic Pump House and PTP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.4 | 11 KV Cable Work and various 11 KV Structure Rennovation Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.5 | Various Street Light Refurbishment Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | AHP Performance improvement Scheme for Dry fly ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Vacuum Pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Complete Assembly of Energy Efficient Air Compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of ESP evacuation pipelines, valves and blowers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Complete Refurbishment Work of 1st & 2nd Row Fields of ESP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.5 | Procurement of ESP CERM and EERM gear boxes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | AHP Performance improvement Scheme for Wet ash Disposal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Upgradation of Slurry Series System and HP Seal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of Fluid Couplings & Gearboxes for Slurry Series Pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Procurement of Vertical slurry pumps & Goodwin Submersible pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Procurement of Complete Assemblies of GEHO systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.5 | Procurement & Replacement of Slurry Disposal Pipelines | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.6 | Modification of Bottom ash overflow water clarification system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | ENAHANCMENT AND RELIABILITY IMPROVELMENT OF TURBINE AUXILIARIES | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | PROCUREMENT OF HPCV 2 SERVO MOTOR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of BFP-A cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Procurement of TDBFP turbine rotor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of CEP-B Cartridge Assembly without motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Procurement and commissioning of service and instrument air atlas copco compressor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Procurement of vacuum pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.7 | Procurement of Water treatment plant pumps for effluenet treatement , filter water Raw water, srewage treatement plant pumps, etc. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.8 | Procurement and replacement of ACW Pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.9 | Procurement of regulating BFP Recirculation valve A & B with actuator for flexible operation. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of ASV-22 and spray control valve | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | NDCT EFFICENCY IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Complete replacement of NDCT fills | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Procurement of clarifloculator and flash mixer gear box | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Supply, Installation & Commisioning of NDCT side stream filters | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | IMPROVEMENT OF TURBINE AND PUMPS EFFICENCY | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Procurement of HPT module including Turbo visory instruments (TM-II & C&I-II) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Procurement and replacement of ACW Pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Procurement of CEP-C Cartridge Assembly with out motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Wagon tippler installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Renovation and modanisation of wagen tipler concrete hopper | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Supply and errection of Wagon tipplers | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
16.3 | Upgradation of hydraulic systems with safety mechanism for Wagon unloading | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Capacity enhancement of side arm charger | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
16.5 | Capacity enhancement of Apron feeder | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
17 | CHP-II Performance improvement scheme installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Supply and installeation of impact crusher spares | 0 | - | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
17.2 | Replacement of scoop coupling | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Renovation stacker reclaimer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Complete overhauling of Wobbler feeder | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Procurement of Gear boxes | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
17.6 | Structure Strengthening and modification work of Conveyors. | 0 | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
18 | Infrastructure Development Schemes & Electrical schemes for improvement in availability & Reliability of auxilliaries installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of EOT cranes and hoist installed in CHP-II. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Modification of DE and DS system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Procuremnet of HT Motors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Procuremnet of VFD for LT motors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | upgradation of wagon tippler PLC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Reconditioning of MCC Boards and feeder panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Provision of ceramic lagging to pulleyes ,belt tracker system and mechanise spillage free control system for various conveyor systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design engineering , supply and installation of modular chutes with Liners of various belt conveyor installed in CHP-II . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Apron feeder-101/102 to Conv-102A/B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Conv-103A/B to wobbler feeder-101/102 to Crusher -101/102 to Belt feeder-101/102 to conv-104A/B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Conv-104A/B to Conv-105A/B and Conv-113 to Conv-105A/B,BF-105/106 to BF-107 to conv-107 transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Conv-105A/B to Cov-106A and Conv-105A/B to Cov-106B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Conv-107 to Conv-108,Conv-112 to Conv-113,Conv-111 to Con-112,Conv-108 to conv-109,conv-109 to conv-110, conveyor transfer chute | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20 | Comprehensive enhancement infrastructure of green Corridor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Providing and construction of Cement road at various location at 500 MW KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Constructions of RCC Drains at various locations in 500 MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Landscaping | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Dust Suppression | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Road Cleaning Machine | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
22 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25 | Construction of LHS on Saoner & Kalumna siding of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Construction of Limited Height Subway at Pandhrakhedi, Patkakhedi (Saoner siding) & Suradevi (Kalumna siding) on depositary basis at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | ID fan motor rotor refurbishment of 500 MW | N.A. | - | 0 | 1.0962 | 1.0962 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Spare TDBFP Gear Box | N.A. | - | 0 | 0.58994 | 0.58994 | 0 | 0 | 0 |  |  | 0 | 0
3 | PISTON CYLINDER ASSEMBLY, DIAPHRAM ASSEMBLY | N.A. | - | 0 | 5.9701 | 5.9701 | 0 | 0 | 0 |  |  | 0 | 0
4 | GT-R Phase Transformer#6006501 of U#5 (Spare) | N.A. | - | 0 | 6.241 | 6.241 | 0 | 0 | 0 |  |  | 0 | 0
5 | GT-R Phase Transformer#6006501U#5 (Core Replace) | N.A. | - | 0 | 3.1304 | 3.1304 | 0 | 0 | 0 |  |  | 0 | 0
6 | BCW Pump Motor Model HLAV (Refurbishment) U#5 | N.A. | - | 0 | 2.8718 | 2.8718 | 0 | 0 | 0 |  |  | 0 | 0
7 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM CHP-II | N.A. | - | 0 | 2.1501 | 2.1501 | 0 | 0 | 0 |  |  | 0 | 0
8 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM C&I-2 | N.A. | - | 0 | 2.2408 | 2.2408 | 0 | 0 | 0 |  |  | 0 | 0
9 | Land for Nandgaon ash band | N.A. | - | 0 | 0.267 | 0.267 | 0 | 0 | 0 |  |  | 0 | 0
10 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-II | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
11 | Fire Fighting equipment(Conveyors galleries CHPII) | N.A. | - | 0 | 0.57643 | 0.57643 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF COMPLETE SET OF SKY CLIMBER FOR UNIT-5 (500 MW), TPS KHAPERKHEDA | N.A. | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
13 | Supply & Erection of Duct, Diverter Plate, and Expansion Joints for Extensive Replacement of Flue Gas Duct at Unit-5,500 MW Khaperkheda TPS | N.A. | - | 0 | 4.09 | 4.09 | 0 | 0 | 0 |  |  | 0 | 0
14 | Stacker Relaimer Refurbishment | N.A. | - | 0 | 20.2 | 20.2 | 0 | 0 | 0 |  |  | 0 | 0
15 | Work of design, Engineering, Supply & Installation along with capacity enhancement of drive unit of conveyor belt 103A,103B & 105B installed at CHP 500MW, Khaperkheda TPS | N.A. | - | 0 | 4.08 | 4.08 | 0 | 0 | 0 |  |  | 0 | 0
16 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 500MW | N.A. | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
17 | work of Refurbishment/Modification of Air ventilation system at wagon tippler tunnel area, Apron feeder floor area, Wagon tippler control room, CHP control room and short conveyor area in CHP500 MW) | N.A. | - | 0 | 2.06 | 2.06 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of design Engineering, Refurbishment & structural strenghthning along with replacement of damaged spares of conveyor belt 110 installed at coal handling plant 500MW . | N.A. | - | 0 | 2.21 | 2.21 | 0 | 0 | 0 |  |  | 0 | 0
19 | GTR Refurbishment | N.A. | - | 0 | 0.33 | 0.33 | 0 | 0 | 0 |  |  | 0 | 0
20 | SUPPLY,ERECTION ,COMMISSIONING AND TESTING OF 360V,750AH PLANTE TYPE UPS BATTERY SET AT UNIT 5 500MW | N.A. | - | 0 | 2.87 | 2.87 | 0 | 0 | 0 |  |  | 0 | 0
21 | Up-gradation of Generator Protection System and Feeder protection relays at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0
22 | BFP Booster pump | N.A. | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
23 | Submission for approval of Non-DPR “Supply of Complete Cartridge Assemblies (1 Nos) for Boiler Feed Pump FK 4E 36 at (Unit#5, 500MW), Khaperkheda T.P.S. | N.A. | - | 0 | 1.99 | 1.99 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procuremet of Portable Reclaimer | N.A. | - | 0 | 0 | 0 | 0 | 8.92 | 8.92 |  |  | 8.92 | 0
25 | Work of Design, Fabrication ,Erection & commissioning of Wobbler feeder and crusher bypass chute with provision of hydraulic actuator installed at coal handling plant 500MW, Khaperkheda TPS | N.A. | - | 0 | 0 | 0 | 0 | 2.89 | 2.89 |  |  | 2.89 | 0
26 | Work of Revamping, Modification & Upgradation with Testing & Commissioning of Fire Detection and Alarm System including supply of Material for Unit # 5 BTG area at 500MW TPS Khaperkheda. | N.A. | - | 0 | 0 | 0 | 0 | 5.2 | 5.2 |  |  | 5.2 | 0
27 | HPCV2 Servomotor | N.A. | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
28 | Refurbishment of BCW pump Motor Model HLAV 2X300-460/1C (Rated 350 KW, 6.6 KV ,4 Pole, Sr. No. AP460044-3-1) of U#5 (500 MW) TPS, Khaperkheda. | N.A. | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
29 | Procurement of Complete Rotor Assy. along with 1st and 2nd stage blade set of PA Fan Type AP2 20/12 for Unit#5 (500 MW) TPS, Khaperkheda | N.A. | - | 0 | 0 | 0 | 0 | 3.37 | 3.37 |  |  | 3.37 | 0
30 | Up-gradation of VFD system for GEHO Pump-2 at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 0 | 0 | 0 | 2.7 | 2.7 |  |  | 2.7 | 0
31 | General Asset Furniture | N.A. | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
32 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0 | 0.12056 | -0.12056 | 0 | 0 |  |  | 0 | -0.12056
33 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 0.043476 | 0.66703 | -0.62355 | 0 | 0 |  |  | 0 | -0.62355
| Total |  |  | 0 | 1010.1744 | 790.0108 | 220.1636 | 454.27 | 471.28 | 0 | 0 | 471.28 | 203.1536
FY 2026-27
a) DPR Schemes
(i) Submitted to MERC
12 | Ash Disposal Scheme from K’kheda 1 X 500 MW Unit to Nandgaon Ash Bund | MERC/CAPEX/20162017 | 2017-09-22 | 69.1855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | 1. Construction of RCC pedestals for laying of ADP Lines from Khaperkheda TPS to Nandgaon Ash Bund. 2. Providing &Laying of ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 2a) Supply of MSERW and Seamless Pipes 2b) Laying of Ash Disposal & Recovery Pipe Line. 3. Construction of Service road for ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 4. Design, Engineering & construction of minor bridge, road crossing and culverts in the alignment of ash disposal pipe line from TPS Khaperkheda to Nandgaon Ash Bund 5. Construction of ash water recovery pump house at Nandgaon | MERC/CAPEX/20162017 | 2017-09-22 | 65.7755 | 95.6643 | 95.6643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017 | 2017-09-22 | 3.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Bulldozer, Wheel axel final drive assembly & refurbishment of apron feeder at Khaperkheda TPS | MERC/CAPEX/20162017/01341 | 2017-10-11 | 11.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Procurement of Bulldozers(02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 3.75 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Procurement of wheel axel final drive assembly (02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Refurbishment of apron feeder | MERC/CAPEX/20162017/01341 | 2017-10-11 | 7.36 | 6.8736 | 5.629 | 1.2446 | 0 | 0 |  |  | 0 | 1.2446 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Procurement of Battery Set, PA Fan assembly, Jack Oil Pump, Turbo Driven BFP Cartridge and Restoration of ESP internals for 500 MW at Khaperkheda TPS | MERC/CAPEX/20172018/04320 | 2017-10-11 | 14.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Procurement, erection, commissioning & testing of 220V, 2190AH & 24V Battery set: | MERC/CAPEX/20172018/04320 | 2017-10-11 | 5.6 | 6.2928 | 6.2928 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Procurement of PA Fan assembly | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.1 | 3.3713 | 3.3713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Restoration of ESP internals | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.7 | 1.6097 | 1.6097 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Procurement of Jacking Oil Pump | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.18 | 0.27 | 0.27 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.5 | Procurement of turbo driven BFP Cartridge Assembly (FK4E36) | MERC/CAPEX/20172018/04320 | 2017-10-11 | 2.1 | 1.8279 | 1.8279 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 12.8838 | 12.8838 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Provision of S&T System for In Plant Yard Khaperkheda & Kalumni Yard (Depository Work) and Modification of Kalumna Yard Alteration No. 5 (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 31.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Provision of S & T System to Khaperkheda TPS In-Plant yard and Kalumna Yard (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 17.75 | 20.052 | 20.052 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Modification of Kalumna Yard Alternation no. 5 in connection with Khaperkheda TPS Expansion Project (1x500 MW) construction of B.G. Railway Siding | MERC/CAPEX/20172018/4779 | 2017-11-28 | 13.77 | 27.2859 | 13.5159 | 13.77 | 0 | 0 |  |  | 0 | 13.77 | 0 | 0
19 | Construction of Limited Height Subway (LHS) at unmanned road level crossing by Railway on cost sharing basis with MSPGCL on Khaperkheda-Kalumna railway siding and saoner-Khaperkheda railway siding | MERC/CAPEX/20172018/0178 | 2018-02-02 | 16.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Construction of LHS on Khaperkheda Kalumna railway side | MERC/CAPEX/20172018/0178 | 2018-02-02 | 5.94 | 4.9899 | 4.9899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Construction of LHS on Khaperkheda Saoner railway line | MERC/CAPEX/20172018/0178 | 2018-02-02 | 10.87 | 9.78 | 9.78 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Utilisation of unused water scheme from Bhanegaon open cast mine & construction of RCC internal roads at Khaperkheda TPS | MERC/CAPEX/20172018/0197 | 2018-02-06 | 11.5329 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Utilization of unused water scheme from Bhanegaon Open cast mine | MERC/CAPEX/20172018/0197 | 2018-02-06 | 7.5469 | 12.9367 | 12.9403 | -0.0036201 | 0 | 0 |  |  | 0 | -0.0036201 | 0 | 0
20.2 | Construction of Cement Concrete Road Inside Part Of Power House | MERC/CAPEX/20172018/0197 | 2018-02-06 | 2.906 | 2.6732 | 2.6732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0197 | 2018-02-06 | 1.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIMT 2000 (72° PA) | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 3.835 | 3.835 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.2027 | 3.2027 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 2.2126 | 2.2126 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 280.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | Flue Gas Desulphurization (FGD) System for KPKD 5 | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 260.21 | 396.28 | 396.28 | 0 | 169.83 | 169.83 |  |  | 169.83 | 0 | 0 | 169.83
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 20.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.5033 | 4.5033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 577.94 | 389.0532 | 188.8868 | 0 | 0 |  |  | 0 | 188.8868 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.23 | 1.8042 | 1.8042 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 4.0922 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.5 | Electromagnetic Flow meters at various lines & Locations of 500 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.2497 | 3.2497 | 3.2497 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.6 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84 | 0.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 45.31 | 45.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Boiler Performance improvement Six Schemes at Unit-5 Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Sch-1: Procurement & Replacement of LTSH coils at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 17.52 | 17.52 |  |  | 17.52 | 0
35.2 | Sch-2: Procurement & Replacement of Economizer coils at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 33.91 | 33.91 |  |  | 33.91 | 0
35.3 | Sch-3: Procurement & Replacement of Water wall Z-Panels & Soot blower Panels at U#5: | Yet to be approved | - | 0 | 0 | 0 | 0 | 7.06 | 7.06 |  |  | 7.06 | 0
35.4 | Sch-4 : Supply and erection of APH Inlet & Outlet Flue Gas Damper Assemblies along with actuators at U#5 | Yet to be approved | - | 0 | 0 | 0 | 0 | 2.08 | 2.08 |  |  | 2.08 | 0
35.5 | Sch-5 : Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines at U#5. | Yet to be approved | - | 0 | 0 | 0 | 0 | 3.58 | 3.58 |  |  | 3.58 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 1.21 | 1.21 |  |  | 1.21 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 25.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Up-gradation of maxDNA DCS system (HMI Up-gradation) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.29 | 7.29 | 7.29 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of PLC (GE FANUC make) SYSTEM (HMI & hardware up-gradation) at Ash Handling Plant, Compressor Plant, and Condensate Polishing Unit (CPU) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.14 | 1.14 | 1.14 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up-gradation of PLC (Schneider make) system (HMI & HARDWARE Up-gradation) at DM Plant, PTP, FF plant, CMRH System, HVAC System, FOPH system at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.26 | 4.26 | 4.26 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Up-gradation of SWAS (STEAM WATER ANALYSIS SYSTEM) Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.71 | 4.71 | 4.71 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Up-gradation of Carbon monoxide analyzer in Flue Gas Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.02 | 1.02 | 1.02 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Up-gradation of Coal feeder Controller at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.01 | 7.01 | 7.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 0.86 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 11.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 0.89 | 0.89 | 0.89 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 5.34 | 5.34 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 230 | 230 |  |  | 230 | 0
2 | DPR7 SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Supply Installation Testing & Commissioning , Revamping of fire detection & alarm and protection system from fire and providing rapid extinguishing clean agent (CA) system at unit # 5 at 500 MW khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 23.21 | 23.21 |  |  | 23.21 | 0
3 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Restoration of fire alarm valve with water spray system (DV) at CHP-II 500 MW | 0 | - | 0 | 0 | 0 | 0 | 22.05 | 22.05 |  |  | 22.05 | 0
4 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Modular Duct | 0 | - | 0 | 0 | 0 | 0 | 21.5 | 21.5 |  |  | 21.5 | 0
4.2 | PA Fan Rotor Assy. | 0 | - | 0 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0
4.3 | Bottom ash & coarse ash system | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
4.4 | Design Supply and erection of bottom ash hopper and Coarse ash hoppers. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
4.5 | Platform | 0 | - | 0 | 0 | 0 | 0 | 3.96 | 3.96 |  |  | 3.96 | 0
4.6 | Refurbishment of BCW | 0 | - | 0 | 0 | 0 | 0 | 3.59 | 3.59 |  |  | 3.59 | 0
4.7 | Boiler Lift performance | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
5 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Water Wall Soot Blower Panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Thermal Insulation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | APH Baskets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Errection & Commisioning of Additional Soot blower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | PA Fan Rotor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.6 | Coal Compartment Assembly | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Process field instruments and PLCs hardware for performance improvement . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Upgradation of Emerson make PLC controllers and I/O (AHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of WTP & CHP PLC I/O and network accessories (BOP & CHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Upgradation of Pressure, flow, level transmitter, hydrastep, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Upgradation of Scanner , Ignitors, Solonoid system , relay of FSSS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Upgradation of control valves and cylinders instrumentation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Upgradation of ETP, Debris ,OLCC plc system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of Nucleonic density meter | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Upgradation of environment related instruments | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Installation of Furnace camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Installation of Flue gas exit temperature probe | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Electrical Protection Systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Upgradation of UPS system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of battery charger system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of ID Fan VFD system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Upgradation of DAVR system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of protection relays at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Enhancement of HT/ LT Auxillaries and Illumination for betterment availability and reliability | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply of 6.6 KV, 220 KW Ash Slurry Pump Motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Supply of 6.6 KV, 200 KW Fire Hydrant motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Supply of 690V, 800 KW GEHO Pump motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Refurbishment of BCW Pump Motor Sr. No. AP460044-3-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Supply of Dry Type Transformers of Different Ratings for Unit # 5, TPS Khaperkheda. (Rates are inclusive of 2% Packing and forwarding charges & 2% Freight Charges) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.6 | Supply of 3250KVA, 6.6/2.3 KV Oil Cooled VFD Transformer Of Vector Group Dyn11 and Ydn 11 & 25 MVA UAT For Unit# 5 At Khaperkheda TPS. (Including Packing and forwarding charges 2%, Freight Charges 2%) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.7 | Enhancing conventional lighting system at by retrofitting and replacement with energy efficient LED Lighting system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.8 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP & CHP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.9 | supply of integrated solar light and CCTV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | colony electrical renovation, switchgear, Energy meter, breaker,street light, 11 KV cable ,High Mast | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Electrical Rennovation and mordernization of various tenaments buildings,offices, recreation clubs, Hospital, Domestic Pump House, PTP Plant and Admin Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Replacement of Distibution board, High Mast and switchgear at different areas of colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Replacement of Energy meter and various LT Motors at Domestic Pump House and PTP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.4 | 11 KV Cable Work and various 11 KV Structure Rennovation Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.5 | Various Street Light Refurbishment Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | AHP Performance improvement Scheme for Dry fly ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Vacuum Pumps | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
11.2 | Procurement of Complete Assembly of Energy Efficient Air Compressors | 0 | - | 0 | 0 | 0 | 0 | 9.7 | 9.7 |  |  | 9.7 | 0
11.3 | Procurement of ESP evacuation pipelines, valves and blowers | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
11.4 | Complete Refurbishment Work of 1st & 2nd Row Fields of ESP | 0 | - | 0 | 0 | 0 | 0 | 14 | 14 |  |  | 14 | 0
11.5 | Procurement of ESP CERM and EERM gear boxes | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
12 | AHP Performance improvement Scheme for Wet ash Disposal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Upgradation of Slurry Series System and HP Seal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of Fluid Couplings & Gearboxes for Slurry Series Pumps | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Procurement of Vertical slurry pumps & Goodwin Submersible pumps | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
12.4 | Procurement of Complete Assemblies of GEHO systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.5 | Procurement & Replacement of Slurry Disposal Pipelines | 0 | - | 0 | 0 | 0 | 0 | 14.72 | 14.72 |  |  | 14.72 | 0
12.6 | Modification of Bottom ash overflow water clarification system | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
13 | ENAHANCMENT AND RELIABILITY IMPROVELMENT OF TURBINE AUXILIARIES | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | PROCUREMENT OF HPCV 2 SERVO MOTOR | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
13.2 | Procurement of BFP-A cartridge | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
13.3 | Procurement of TDBFP turbine rotor | 0 | - | 0 | 0 | 0 | 0 | 7.5 | 7.5 |  |  | 7.5 | 0
13.4 | Procurement of CEP-B Cartridge Assembly without motor | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
13.5 | Procurement and commissioning of service and instrument air atlas copco compressor | 0 | - | 0 | 0 | 0 | 0 | 5.7 | 5.7 |  |  | 5.7 | 0
13.6 | Procurement of vacuum pump | 0 | - | 0 | 0 | 0 | 0 | 1.3 | 1.3 |  |  | 1.3 | 0
13.7 | Procurement of Water treatment plant pumps for effluenet treatement , filter water Raw water, srewage treatement plant pumps, etc. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
13.8 | Procurement and replacement of ACW Pump | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
13.9 | Procurement of regulating BFP Recirculation valve A & B with actuator for flexible operation. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
13.1 | Procurement of ASV-22 and spray control valve | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
14 | NDCT EFFICENCY IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Complete replacement of NDCT fills | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Procurement of clarifloculator and flash mixer gear box | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Supply, Installation & Commisioning of NDCT side stream filters | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | IMPROVEMENT OF TURBINE AND PUMPS EFFICENCY | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Procurement of HPT module including Turbo visory instruments (TM-II & C&I-II) | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
15.2 | Procurement and replacement of ACW Pump | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
15.3 | Procurement of CEP-C Cartridge Assembly with out motor | 0 | - | 0 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0
16 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Wagon tippler installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Renovation and modanisation of wagen tipler concrete hopper | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
16.2 | Supply and errection of Wagon tipplers | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of hydraulic systems with safety mechanism for Wagon unloading | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
16.4 | Capacity enhancement of side arm charger | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Capacity enhancement of Apron feeder | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
17 | CHP-II Performance improvement scheme installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Supply and installeation of impact crusher spares | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Replacement of scoop coupling | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
17.3 | Renovation stacker reclaimer | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Complete overhauling of Wobbler feeder | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
17.5 | Procurement of Gear boxes | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Structure Strengthening and modification work of Conveyors. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
18 | Infrastructure Development Schemes & Electrical schemes for improvement in availability & Reliability of auxilliaries installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of EOT cranes and hoist installed in CHP-II. | 0 | - | 0 | 0 | 0 | 0 | 12 | 12 |  |  | 12 | 0
18.2 | Modification of DE and DS system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Procuremnet of HT Motors | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
18.4 | Procuremnet of VFD for LT motors | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
18.5 | upgradation of wagon tippler PLC | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
18.6 | Reconditioning of MCC Boards and feeder panels | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
18.7 | Provision of ceramic lagging to pulleyes ,belt tracker system and mechanise spillage free control system for various conveyor systems | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
19 | Work of Design engineering , supply and installation of modular chutes with Liners of various belt conveyor installed in CHP-II . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Apron feeder-101/102 to Conv-102A/B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0
19.2 | Conv-103A/B to wobbler feeder-101/102 to Crusher -101/102 to Belt feeder-101/102 to conv-104A/B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 12.5 | 12.5 |  |  | 12.5 | 0
19.3 | Conv-104A/B to Conv-105A/B and Conv-113 to Conv-105A/B,BF-105/106 to BF-107 to conv-107 transfer chute | 0 | - | 0 | 0 | 0 | 0 | 5.5 | 5.5 |  |  | 5.5 | 0
19.4 | Conv-105A/B to Cov-106A and Conv-105A/B to Cov-106B transfer chute | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
19.5 | Conv-107 to Conv-108,Conv-112 to Conv-113,Conv-111 to Con-112,Conv-108 to conv-109,conv-109 to conv-110, conveyor transfer chute | 0 | - | 0 | 0 | 0 | 0 | 4.5 | 4.5 |  |  | 4.5 | 0
20 | Comprehensive enhancement infrastructure of green Corridor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Providing and construction of Cement road at various location at 500 MW KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 11 | 11 |  |  | 11 | 0
20.2 | Constructions of RCC Drains at various locations in 500 MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
20.3 | Landscaping | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
20.4 | Dust Suppression | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Road Cleaning Machine | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
21 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 50 | 50 |  |  | 50 | 0
23 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 25.58 | 25.58 |  |  | 25.58 | 0
25 | Construction of LHS on Saoner & Kalumna siding of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Construction of Limited Height Subway at Pandhrakhedi, Patkakhedi (Saoner siding) & Suradevi (Kalumna siding) on depositary basis at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 49.8 | 0 |  |  | 0 | 49.8
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | ID fan motor rotor refurbishment of 500 MW | N.A. | - | 0 | 1.0962 | 1.0962 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Spare TDBFP Gear Box | N.A. | - | 0 | 0.58994 | 0.58994 | 0 | 0 | 0 |  |  | 0 | 0
3 | PISTON CYLINDER ASSEMBLY, DIAPHRAM ASSEMBLY | N.A. | - | 0 | 5.9701 | 5.9701 | 0 | 0 | 0 |  |  | 0 | 0
4 | GT-R Phase Transformer#6006501 of U#5 (Spare) | N.A. | - | 0 | 6.241 | 6.241 | 0 | 0 | 0 |  |  | 0 | 0
5 | GT-R Phase Transformer#6006501U#5 (Core Replace) | N.A. | - | 0 | 3.1304 | 3.1304 | 0 | 0 | 0 |  |  | 0 | 0
6 | BCW Pump Motor Model HLAV (Refurbishment) U#5 | N.A. | - | 0 | 2.8718 | 2.8718 | 0 | 0 | 0 |  |  | 0 | 0
7 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM CHP-II | N.A. | - | 0 | 2.1501 | 2.1501 | 0 | 0 | 0 |  |  | 0 | 0
8 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM C&I-2 | N.A. | - | 0 | 2.2408 | 2.2408 | 0 | 0 | 0 |  |  | 0 | 0
9 | Land for Nandgaon ash band | N.A. | - | 0 | 0.267 | 0.267 | 0 | 0 | 0 |  |  | 0 | 0
10 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-II | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
11 | Fire Fighting equipment(Conveyors galleries CHPII) | N.A. | - | 0 | 0.57643 | 0.57643 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF COMPLETE SET OF SKY CLIMBER FOR UNIT-5 (500 MW), TPS KHAPERKHEDA | N.A. | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
13 | Supply & Erection of Duct, Diverter Plate, and Expansion Joints for Extensive Replacement of Flue Gas Duct at Unit-5,500 MW Khaperkheda TPS | N.A. | - | 0 | 4.09 | 4.09 | 0 | 0 | 0 |  |  | 0 | 0
14 | Stacker Relaimer Refurbishment | N.A. | - | 0 | 20.2 | 20.2 | 0 | 0 | 0 |  |  | 0 | 0
15 | Work of design, Engineering, Supply & Installation along with capacity enhancement of drive unit of conveyor belt 103A,103B & 105B installed at CHP 500MW, Khaperkheda TPS | N.A. | - | 0 | 4.08 | 4.08 | 0 | 0 | 0 |  |  | 0 | 0
16 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 500MW | N.A. | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
17 | work of Refurbishment/Modification of Air ventilation system at wagon tippler tunnel area, Apron feeder floor area, Wagon tippler control room, CHP control room and short conveyor area in CHP500 MW) | N.A. | - | 0 | 2.06 | 2.06 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of design Engineering, Refurbishment & structural strenghthning along with replacement of damaged spares of conveyor belt 110 installed at coal handling plant 500MW . | N.A. | - | 0 | 2.21 | 2.21 | 0 | 0 | 0 |  |  | 0 | 0
19 | GTR Refurbishment | N.A. | - | 0 | 0.33 | 0.33 | 0 | 0 | 0 |  |  | 0 | 0
20 | SUPPLY,ERECTION ,COMMISSIONING AND TESTING OF 360V,750AH PLANTE TYPE UPS BATTERY SET AT UNIT 5 500MW | N.A. | - | 0 | 2.87 | 2.87 | 0 | 0 | 0 |  |  | 0 | 0
21 | Up-gradation of Generator Protection System and Feeder protection relays at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0
22 | BFP Booster pump | N.A. | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
23 | Submission for approval of Non-DPR “Supply of Complete Cartridge Assemblies (1 Nos) for Boiler Feed Pump FK 4E 36 at (Unit#5, 500MW), Khaperkheda T.P.S. | N.A. | - | 0 | 1.99 | 1.99 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procuremet of Portable Reclaimer | N.A. | - | 0 | 8.92 | 8.92 | 0 | 0 | 0 |  |  | 0 | 0
25 | Work of Design, Fabrication ,Erection & commissioning of Wobbler feeder and crusher bypass chute with provision of hydraulic actuator installed at coal handling plant 500MW, Khaperkheda TPS | N.A. | - | 0 | 2.89 | 2.89 | 0 | 0 | 0 |  |  | 0 | 0
26 | Work of Revamping, Modification & Upgradation with Testing & Commissioning of Fire Detection and Alarm System including supply of Material for Unit # 5 BTG area at 500MW TPS Khaperkheda. | N.A. | - | 0 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
27 | HPCV2 Servomotor | N.A. | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
28 | Refurbishment of BCW pump Motor Model HLAV 2X300-460/1C (Rated 350 KW, 6.6 KV ,4 Pole, Sr. No. AP460044-3-1) of U#5 (500 MW) TPS, Khaperkheda. | N.A. | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
29 | Procurement of Complete Rotor Assy. along with 1st and 2nd stage blade set of PA Fan Type AP2 20/12 for Unit#5 (500 MW) TPS, Khaperkheda | N.A. | - | 0 | 3.37 | 3.37 | 0 | 0 | 0 |  |  | 0 | 0
30 | Up-gradation of VFD system for GEHO Pump-2 at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 2.7 | 2.7 | 0 | 0 | 0 |  |  | 0 | 0
31 | General Asset Furniture | N.A. | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
32 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0 | 0.12056 | -0.12056 | 0 | 0 |  |  | 0 | -0.12056
33 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 0.043476 | 0.66703 | -0.62355 | 0 | 0 |  |  | 0 | -0.62355
| Total |  |  | 0 | 1464.4444 | 1261.2908 | 203.1536 | 926.8 | 877 | 0 | 0 | 877 | 252.9536
FY 2027-28
a) DPR Schemes
(i) Submitted to MERC
12 | Ash Disposal Scheme from K’kheda 1 X 500 MW Unit to Nandgaon Ash Bund | MERC/CAPEX/20162017 | 2017-09-22 | 69.1855 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | 1. Construction of RCC pedestals for laying of ADP Lines from Khaperkheda TPS to Nandgaon Ash Bund. 2. Providing &Laying of ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 2a) Supply of MSERW and Seamless Pipes 2b) Laying of Ash Disposal & Recovery Pipe Line. 3. Construction of Service road for ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 4. Design, Engineering & construction of minor bridge, road crossing and culverts in the alignment of ash disposal pipe line from TPS Khaperkheda to Nandgaon Ash Bund 5. Construction of ash water recovery pump house at Nandgaon | MERC/CAPEX/20162017 | 2017-09-22 | 65.7755 | 95.6643 | 95.6643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017 | 2017-09-22 | 3.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Bulldozer, Wheel axel final drive assembly & refurbishment of apron feeder at Khaperkheda TPS | MERC/CAPEX/20162017/01341 | 2017-10-11 | 11.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Procurement of Bulldozers(02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 3.75 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Procurement of wheel axel final drive assembly (02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Refurbishment of apron feeder | MERC/CAPEX/20162017/01341 | 2017-10-11 | 7.36 | 6.8736 | 5.629 | 1.2446 | 0 | 0 |  |  | 0 | 1.2446 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Procurement of Battery Set, PA Fan assembly, Jack Oil Pump, Turbo Driven BFP Cartridge and Restoration of ESP internals for 500 MW at Khaperkheda TPS | MERC/CAPEX/20172018/04320 | 2017-10-11 | 14.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Procurement, erection, commissioning & testing of 220V, 2190AH & 24V Battery set: | MERC/CAPEX/20172018/04320 | 2017-10-11 | 5.6 | 6.2928 | 6.2928 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Procurement of PA Fan assembly | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.1 | 3.3713 | 3.3713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Restoration of ESP internals | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.7 | 1.6097 | 1.6097 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Procurement of Jacking Oil Pump | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.18 | 0.27 | 0.27 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.5 | Procurement of turbo driven BFP Cartridge Assembly (FK4E36) | MERC/CAPEX/20172018/04320 | 2017-10-11 | 2.1 | 1.8279 | 1.8279 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 12.8838 | 12.8838 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Provision of S&T System for In Plant Yard Khaperkheda & Kalumni Yard (Depository Work) and Modification of Kalumna Yard Alteration No. 5 (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 31.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Provision of S & T System to Khaperkheda TPS In-Plant yard and Kalumna Yard (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 17.75 | 20.052 | 20.052 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Modification of Kalumna Yard Alternation no. 5 in connection with Khaperkheda TPS Expansion Project (1x500 MW) construction of B.G. Railway Siding | MERC/CAPEX/20172018/4779 | 2017-11-28 | 13.77 | 27.2859 | 13.5159 | 13.77 | 0 | 0 |  |  | 0 | 13.77 | 0 | 0
19 | Construction of Limited Height Subway (LHS) at unmanned road level crossing by Railway on cost sharing basis with MSPGCL on Khaperkheda-Kalumna railway siding and saoner-Khaperkheda railway siding | MERC/CAPEX/20172018/0178 | 2018-02-02 | 16.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Construction of LHS on Khaperkheda Kalumna railway side | MERC/CAPEX/20172018/0178 | 2018-02-02 | 5.94 | 4.9899 | 4.9899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Construction of LHS on Khaperkheda Saoner railway line | MERC/CAPEX/20172018/0178 | 2018-02-02 | 10.87 | 9.78 | 9.78 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Utilisation of unused water scheme from Bhanegaon open cast mine & construction of RCC internal roads at Khaperkheda TPS | MERC/CAPEX/20172018/0197 | 2018-02-06 | 11.5329 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Utilization of unused water scheme from Bhanegaon Open cast mine | MERC/CAPEX/20172018/0197 | 2018-02-06 | 7.5469 | 12.9367 | 12.9403 | -0.0036201 | 0 | 0 |  |  | 0 | -0.0036201 | 0 | 0
20.2 | Construction of Cement Concrete Road Inside Part Of Power House | MERC/CAPEX/20172018/0197 | 2018-02-06 | 2.906 | 2.6732 | 2.6732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0197 | 2018-02-06 | 1.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIMT 2000 (72° PA) | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 3.835 | 3.835 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.2027 | 3.2027 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 2.2126 | 2.2126 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 280.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | Flue Gas Desulphurization (FGD) System for KPKD 5 | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 260.21 | 566.11 | 566.11 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 20.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.5033 | 4.5033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 577.94 | 389.0532 | 188.8868 | 0 | 0 |  |  | 0 | 188.8868 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.23 | 1.8042 | 1.8042 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 4.0922 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.5 | Electromagnetic Flow meters at various lines & Locations of 500 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.2497 | 3.2497 | 3.2497 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.6 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84 | 0.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 45.31 | 45.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Boiler Performance improvement Six Schemes at Unit-5 Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Sch-1: Procurement & Replacement of LTSH coils at U#5 | Yet to be approved | - | 0 | 17.52 | 17.52 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Sch-2: Procurement & Replacement of Economizer coils at U#5 | Yet to be approved | - | 0 | 33.91 | 33.91 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Sch-3: Procurement & Replacement of Water wall Z-Panels & Soot blower Panels at U#5: | Yet to be approved | - | 0 | 7.06 | 7.06 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Sch-4 : Supply and erection of APH Inlet & Outlet Flue Gas Damper Assemblies along with actuators at U#5 | Yet to be approved | - | 0 | 2.08 | 2.08 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Sch-5 : Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines at U#5. | Yet to be approved | - | 0 | 3.58 | 3.58 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 25.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Up-gradation of maxDNA DCS system (HMI Up-gradation) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.29 | 7.29 | 7.29 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of PLC (GE FANUC make) SYSTEM (HMI & hardware up-gradation) at Ash Handling Plant, Compressor Plant, and Condensate Polishing Unit (CPU) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.14 | 1.14 | 1.14 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up-gradation of PLC (Schneider make) system (HMI & HARDWARE Up-gradation) at DM Plant, PTP, FF plant, CMRH System, HVAC System, FOPH system at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.26 | 4.26 | 4.26 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Up-gradation of SWAS (STEAM WATER ANALYSIS SYSTEM) Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.71 | 4.71 | 4.71 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Up-gradation of Carbon monoxide analyzer in Flue Gas Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.02 | 1.02 | 1.02 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Up-gradation of Coal feeder Controller at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.01 | 7.01 | 7.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 0.86 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 11.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 0.89 | 0.89 | 0.89 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 5.34 | 5.34 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 230 | 230 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR7 SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Supply Installation Testing & Commissioning , Revamping of fire detection & alarm and protection system from fire and providing rapid extinguishing clean agent (CA) system at unit # 5 at 500 MW khaperkheda TPS | 0 | - | 0 | 23.21 | 23.21 | 0 | 0 | 0 |  |  | 0 | 0
3 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Restoration of fire alarm valve with water spray system (DV) at CHP-II 500 MW | 0 | - | 0 | 22.05 | 22.05 | 0 | 0 | 0 |  |  | 0 | 0
4 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Modular Duct | 0 | - | 0 | 21.5 | 21.5 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | PA Fan Rotor Assy. | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Bottom ash & coarse ash system | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Design Supply and erection of bottom ash hopper and Coarse ash hoppers. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Platform | 0 | - | 0 | 3.96 | 3.96 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Refurbishment of BCW | 0 | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Boiler Lift performance | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
5 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Water Wall Soot Blower Panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Thermal Insulation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | APH Baskets | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Errection & Commisioning of Additional Soot blower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | PA Fan Rotor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.6 | Coal Compartment Assembly | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Process field instruments and PLCs hardware for performance improvement . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Upgradation of Emerson make PLC controllers and I/O (AHP) | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
6.2 | Upgradation of WTP & CHP PLC I/O and network accessories (BOP & CHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Upgradation of Pressure, flow, level transmitter, hydrastep, | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Upgradation of Scanner , Ignitors, Solonoid system , relay of FSSS | 0 | - | 0 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0
6.5 | Upgradation of control valves and cylinders instrumentation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Upgradation of ETP, Debris ,OLCC plc system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of Nucleonic density meter | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Upgradation of environment related instruments | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Installation of Furnace camera | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
6.1 | Installation of Flue gas exit temperature probe | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Electrical Protection Systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Upgradation of UPS system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of battery charger system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.3 | Upgradation of ID Fan VFD system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Upgradation of DAVR system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of protection relays at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Enhancement of HT/ LT Auxillaries and Illumination for betterment availability and reliability | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply of 6.6 KV, 220 KW Ash Slurry Pump Motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Supply of 6.6 KV, 200 KW Fire Hydrant motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Supply of 690V, 800 KW GEHO Pump motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Refurbishment of BCW Pump Motor Sr. No. AP460044-3-2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Supply of Dry Type Transformers of Different Ratings for Unit # 5, TPS Khaperkheda. (Rates are inclusive of 2% Packing and forwarding charges & 2% Freight Charges) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.6 | Supply of 3250KVA, 6.6/2.3 KV Oil Cooled VFD Transformer Of Vector Group Dyn11 and Ydn 11 & 25 MVA UAT For Unit# 5 At Khaperkheda TPS. (Including Packing and forwarding charges 2%, Freight Charges 2%) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.7 | Enhancing conventional lighting system at by retrofitting and replacement with energy efficient LED Lighting system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.8 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP & CHP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.9 | supply of integrated solar light and CCTV Camera | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | colony electrical renovation, switchgear, Energy meter, breaker,street light, 11 KV cable ,High Mast | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Electrical Rennovation and mordernization of various tenaments buildings,offices, recreation clubs, Hospital, Domestic Pump House, PTP Plant and Admin Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Replacement of Distibution board, High Mast and switchgear at different areas of colony | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Replacement of Energy meter and various LT Motors at Domestic Pump House and PTP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.4 | 11 KV Cable Work and various 11 KV Structure Rennovation Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.5 | Various Street Light Refurbishment Work | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | AHP Performance improvement Scheme for Dry fly ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Vacuum Pumps | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Complete Assembly of Energy Efficient Air Compressors | 0 | - | 0 | 9.7 | 9.7 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of ESP evacuation pipelines, valves and blowers | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Complete Refurbishment Work of 1st & 2nd Row Fields of ESP | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
11.5 | Procurement of ESP CERM and EERM gear boxes | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
12 | AHP Performance improvement Scheme for Wet ash Disposal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Upgradation of Slurry Series System and HP Seal System | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
12.2 | Procurement of Fluid Couplings & Gearboxes for Slurry Series Pumps | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
12.3 | Procurement of Vertical slurry pumps & Goodwin Submersible pumps | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Procurement of Complete Assemblies of GEHO systems | 0 | - | 0 | 0 | 0 | 0 | 14.029 | 14.029 |  |  | 14.029 | 0
12.5 | Procurement & Replacement of Slurry Disposal Pipelines | 0 | - | 0 | 14.72 | 14.72 | 0 | 0 | 0 |  |  | 0 | 0
12.6 | Modification of Bottom ash overflow water clarification system | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
13 | ENAHANCMENT AND RELIABILITY IMPROVELMENT OF TURBINE AUXILIARIES | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | PROCUREMENT OF HPCV 2 SERVO MOTOR | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of BFP-A cartridge | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Procurement of TDBFP turbine rotor | 0 | - | 0 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of CEP-B Cartridge Assembly without motor | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Procurement and commissioning of service and instrument air atlas copco compressor | 0 | - | 0 | 5.7 | 5.7 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Procurement of vacuum pump | 0 | - | 0 | 1.3 | 1.3 | 0 | 0 | 0 |  |  | 0 | 0
13.7 | Procurement of Water treatment plant pumps for effluenet treatement , filter water Raw water, srewage treatement plant pumps, etc. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
13.8 | Procurement and replacement of ACW Pump | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
13.9 | Procurement of regulating BFP Recirculation valve A & B with actuator for flexible operation. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of ASV-22 and spray control valve | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
14 | NDCT EFFICENCY IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Complete replacement of NDCT fills | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
14.2 | Procurement of clarifloculator and flash mixer gear box | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
14.3 | Supply, Installation & Commisioning of NDCT side stream filters | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
15 | IMPROVEMENT OF TURBINE AND PUMPS EFFICENCY | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Procurement of HPT module including Turbo visory instruments (TM-II & C&I-II) | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Procurement and replacement of ACW Pump | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Procurement of CEP-C Cartridge Assembly with out motor | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
16 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Wagon tippler installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Renovation and modanisation of wagen tipler concrete hopper | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Supply and errection of Wagon tipplers | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of hydraulic systems with safety mechanism for Wagon unloading | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Capacity enhancement of side arm charger | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Capacity enhancement of Apron feeder | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
17 | CHP-II Performance improvement scheme installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Supply and installeation of impact crusher spares | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Replacement of scoop coupling | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Renovation stacker reclaimer | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
17.4 | Complete overhauling of Wobbler feeder | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Procurement of Gear boxes | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Structure Strengthening and modification work of Conveyors. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
18 | Infrastructure Development Schemes & Electrical schemes for improvement in availability & Reliability of auxilliaries installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of EOT cranes and hoist installed in CHP-II. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Modification of DE and DS system | 0 | - | 0 | 0 | 0 | 0 | 14 | 14 |  |  | 14 | 0
18.3 | Procuremnet of HT Motors | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Procuremnet of VFD for LT motors | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | upgradation of wagon tippler PLC | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Reconditioning of MCC Boards and feeder panels | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Provision of ceramic lagging to pulleyes ,belt tracker system and mechanise spillage free control system for various conveyor systems | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design engineering , supply and installation of modular chutes with Liners of various belt conveyor installed in CHP-II . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Apron feeder-101/102 to Conv-102A/B transfer chute | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Conv-103A/B to wobbler feeder-101/102 to Crusher -101/102 to Belt feeder-101/102 to conv-104A/B transfer chute | 0 | - | 0 | 12.5 | 12.5 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Conv-104A/B to Conv-105A/B and Conv-113 to Conv-105A/B,BF-105/106 to BF-107 to conv-107 transfer chute | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Conv-105A/B to Cov-106A and Conv-105A/B to Cov-106B transfer chute | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Conv-107 to Conv-108,Conv-112 to Conv-113,Conv-111 to Con-112,Conv-108 to conv-109,conv-109 to conv-110, conveyor transfer chute | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
20 | Comprehensive enhancement infrastructure of green Corridor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Providing and construction of Cement road at various location at 500 MW KPKD, TPS | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Constructions of RCC Drains at various locations in 500 MW KPKD TPS | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Landscaping | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Dust Suppression | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
20.5 | Road Cleaning Machine | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
21 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
23 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 25.58 | 25.58 | 0 | 0 | 0 |  |  | 0 | 0
25 | Construction of LHS on Saoner & Kalumna siding of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Construction of Limited Height Subway at Pandhrakhedi, Patkakhedi (Saoner siding) & Suradevi (Kalumna siding) on depositary basis at Khaperkheda TPS. | 0 | - | 0 | 49.8 | 0 | 49.8 | 0 | 0 |  |  | 0 | 49.8
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | ID fan motor rotor refurbishment of 500 MW | N.A. | - | 0 | 1.0962 | 1.0962 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Spare TDBFP Gear Box | N.A. | - | 0 | 0.58994 | 0.58994 | 0 | 0 | 0 |  |  | 0 | 0
3 | PISTON CYLINDER ASSEMBLY, DIAPHRAM ASSEMBLY | N.A. | - | 0 | 5.9701 | 5.9701 | 0 | 0 | 0 |  |  | 0 | 0
4 | GT-R Phase Transformer#6006501 of U#5 (Spare) | N.A. | - | 0 | 6.241 | 6.241 | 0 | 0 | 0 |  |  | 0 | 0
5 | GT-R Phase Transformer#6006501U#5 (Core Replace) | N.A. | - | 0 | 3.1304 | 3.1304 | 0 | 0 | 0 |  |  | 0 | 0
6 | BCW Pump Motor Model HLAV (Refurbishment) U#5 | N.A. | - | 0 | 2.8718 | 2.8718 | 0 | 0 | 0 |  |  | 0 | 0
7 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM CHP-II | N.A. | - | 0 | 2.1501 | 2.1501 | 0 | 0 | 0 |  |  | 0 | 0
8 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM C&I-2 | N.A. | - | 0 | 2.2408 | 2.2408 | 0 | 0 | 0 |  |  | 0 | 0
9 | Land for Nandgaon ash band | N.A. | - | 0 | 0.267 | 0.267 | 0 | 0 | 0 |  |  | 0 | 0
10 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-II | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
11 | Fire Fighting equipment(Conveyors galleries CHPII) | N.A. | - | 0 | 0.57643 | 0.57643 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF COMPLETE SET OF SKY CLIMBER FOR UNIT-5 (500 MW), TPS KHAPERKHEDA | N.A. | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
13 | Supply & Erection of Duct, Diverter Plate, and Expansion Joints for Extensive Replacement of Flue Gas Duct at Unit-5,500 MW Khaperkheda TPS | N.A. | - | 0 | 4.09 | 4.09 | 0 | 0 | 0 |  |  | 0 | 0
14 | Stacker Relaimer Refurbishment | N.A. | - | 0 | 20.2 | 20.2 | 0 | 0 | 0 |  |  | 0 | 0
15 | Work of design, Engineering, Supply & Installation along with capacity enhancement of drive unit of conveyor belt 103A,103B & 105B installed at CHP 500MW, Khaperkheda TPS | N.A. | - | 0 | 4.08 | 4.08 | 0 | 0 | 0 |  |  | 0 | 0
16 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 500MW | N.A. | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
17 | work of Refurbishment/Modification of Air ventilation system at wagon tippler tunnel area, Apron feeder floor area, Wagon tippler control room, CHP control room and short conveyor area in CHP500 MW) | N.A. | - | 0 | 2.06 | 2.06 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of design Engineering, Refurbishment & structural strenghthning along with replacement of damaged spares of conveyor belt 110 installed at coal handling plant 500MW . | N.A. | - | 0 | 2.21 | 2.21 | 0 | 0 | 0 |  |  | 0 | 0
19 | GTR Refurbishment | N.A. | - | 0 | 0.33 | 0.33 | 0 | 0 | 0 |  |  | 0 | 0
20 | SUPPLY,ERECTION ,COMMISSIONING AND TESTING OF 360V,750AH PLANTE TYPE UPS BATTERY SET AT UNIT 5 500MW | N.A. | - | 0 | 2.87 | 2.87 | 0 | 0 | 0 |  |  | 0 | 0
21 | Up-gradation of Generator Protection System and Feeder protection relays at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0
22 | BFP Booster pump | N.A. | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
23 | Submission for approval of Non-DPR “Supply of Complete Cartridge Assemblies (1 Nos) for Boiler Feed Pump FK 4E 36 at (Unit#5, 500MW), Khaperkheda T.P.S. | N.A. | - | 0 | 1.99 | 1.99 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procuremet of Portable Reclaimer | N.A. | - | 0 | 8.92 | 8.92 | 0 | 0 | 0 |  |  | 0 | 0
25 | Work of Design, Fabrication ,Erection & commissioning of Wobbler feeder and crusher bypass chute with provision of hydraulic actuator installed at coal handling plant 500MW, Khaperkheda TPS | N.A. | - | 0 | 2.89 | 2.89 | 0 | 0 | 0 |  |  | 0 | 0
26 | Work of Revamping, Modification & Upgradation with Testing & Commissioning of Fire Detection and Alarm System including supply of Material for Unit # 5 BTG area at 500MW TPS Khaperkheda. | N.A. | - | 0 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
27 | HPCV2 Servomotor | N.A. | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
28 | Refurbishment of BCW pump Motor Model HLAV 2X300-460/1C (Rated 350 KW, 6.6 KV ,4 Pole, Sr. No. AP460044-3-1) of U#5 (500 MW) TPS, Khaperkheda. | N.A. | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
29 | Procurement of Complete Rotor Assy. along with 1st and 2nd stage blade set of PA Fan Type AP2 20/12 for Unit#5 (500 MW) TPS, Khaperkheda | N.A. | - | 0 | 3.37 | 3.37 | 0 | 0 | 0 |  |  | 0 | 0
30 | Up-gradation of VFD system for GEHO Pump-2 at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 2.7 | 2.7 | 0 | 0 | 0 |  |  | 0 | 0
31 | General Asset Furniture | N.A. | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
32 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0 | 0.12056 | -0.12056 | 0 | 0 |  |  | 0 | -0.12056
33 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 0.043476 | 0.66703 | -0.62355 | 0 | 0 |  |  | 0 | -0.62355
| Total |  |  | 0 | 2391.2444 | 2138.2908 | 252.9536 | 91.029 | 91.029 | 0 | 0 | 91.029 | 252.9536
FY 2028-29
a) DPR Schemes
(i) Submitted to MERC
Ash Disposal Scheme from K’kheda 1 X 500 MW Unit to Nandgaon Ash Bund
12.1 | 1. Construction of RCC pedestals for laying of ADP Lines from Khaperkheda TPS to Nandgaon Ash Bund. 2. Providing &Laying of ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 2a) Supply of MSERW and Seamless Pipes 2b) Laying of Ash Disposal & Recovery Pipe Line. 3. Construction of Service road for ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 4. Design, Engineering & construction of minor bridge, road crossing and culverts in the alignment of ash disposal pipe line from TPS Khaperkheda to Nandgaon Ash Bund 5. Construction of ash water recovery pump house at Nandgaon | MERC/CAPEX/20162017 | 2017-09-22 | 65.7755 | 95.6643 | 95.6643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017 | 2017-09-22 | 3.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Bulldozer, Wheel axel final drive assembly & refurbishment of apron feeder at Khaperkheda TPS | MERC/CAPEX/20162017/01341 | 2017-10-11 | 11.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Procurement of Bulldozers(02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 3.75 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Procurement of wheel axel final drive assembly (02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Refurbishment of apron feeder | MERC/CAPEX/20162017/01341 | 2017-10-11 | 7.36 | 6.8736 | 5.629 | 1.2446 | 0 | 0 |  |  | 0 | 1.2446 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Procurement of Battery Set, PA Fan assembly, Jack Oil Pump, Turbo Driven BFP Cartridge and Restoration of ESP internals for 500 MW at Khaperkheda TPS | MERC/CAPEX/20172018/04320 | 2017-10-11 | 14.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Procurement, erection, commissioning & testing of 220V, 2190AH & 24V Battery set: | MERC/CAPEX/20172018/04320 | 2017-10-11 | 5.6 | 6.2928 | 6.2928 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Procurement of PA Fan assembly | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.1 | 3.3713 | 3.3713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Restoration of ESP internals | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.7 | 1.6097 | 1.6097 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Procurement of Jacking Oil Pump | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.18 | 0.27 | 0.27 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.5 | Procurement of turbo driven BFP Cartridge Assembly (FK4E36) | MERC/CAPEX/20172018/04320 | 2017-10-11 | 2.1 | 1.8279 | 1.8279 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 12.8838 | 12.8838 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Provision of S&T System for In Plant Yard Khaperkheda & Kalumni Yard (Depository Work) and Modification of Kalumna Yard Alteration No. 5 (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 31.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Provision of S & T System to Khaperkheda TPS In-Plant yard and Kalumna Yard (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 17.75 | 20.052 | 20.052 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Modification of Kalumna Yard Alternation no. 5 in connection with Khaperkheda TPS Expansion Project (1x500 MW) construction of B.G. Railway Siding | MERC/CAPEX/20172018/4779 | 2017-11-28 | 13.77 | 27.2859 | 13.5159 | 13.77 | 0 | 0 |  |  | 0 | 13.77 | 0 | 0
19 | Construction of Limited Height Subway (LHS) at unmanned road level crossing by Railway on cost sharing basis with MSPGCL on Khaperkheda-Kalumna railway siding and saoner-Khaperkheda railway siding | MERC/CAPEX/20172018/0178 | 2018-02-02 | 16.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Construction of LHS on Khaperkheda Kalumna railway side | MERC/CAPEX/20172018/0178 | 2018-02-02 | 5.94 | 4.9899 | 4.9899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Construction of LHS on Khaperkheda Saoner railway line | MERC/CAPEX/20172018/0178 | 2018-02-02 | 10.87 | 9.78 | 9.78 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Utilisation of unused water scheme from Bhanegaon open cast mine & construction of RCC internal roads at Khaperkheda TPS | MERC/CAPEX/20172018/0197 | 2018-02-06 | 11.5329 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Utilization of unused water scheme from Bhanegaon Open cast mine | MERC/CAPEX/20172018/0197 | 2018-02-06 | 7.5469 | 12.9367 | 12.9403 | -0.0036201 | 0 | 0 |  |  | 0 | -0.0036201 | 0 | 0
20.2 | Construction of Cement Concrete Road Inside Part Of Power House | MERC/CAPEX/20172018/0197 | 2018-02-06 | 2.906 | 2.6732 | 2.6732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0197 | 2018-02-06 | 1.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIMT 2000 (72° PA) | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 3.835 | 3.835 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.2027 | 3.2027 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 2.2126 | 2.2126 | 0 | 0 | 0 |  |  | 0 | 0
27 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 280.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | Flue Gas Desulphurization (FGD) System for KPKD 5 | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 260.21 | 566.11 | 566.11 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 20.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.5033 | 4.5033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 577.94 | 389.0532 | 188.8868 | 0 | 0 |  |  | 0 | 188.8868 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.23 | 1.8042 | 1.8042 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 4.0922 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.5 | Electromagnetic Flow meters at various lines & Locations of 500 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.2497 | 3.2497 | 3.2497 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.6 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84 | 0.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 45.31 | 45.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Boiler Performance improvement Six Schemes at Unit-5 Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Sch-1: Procurement & Replacement of LTSH coils at U#5 | Yet to be approved | - | 0 | 17.52 | 17.52 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Sch-2: Procurement & Replacement of Economizer coils at U#5 | Yet to be approved | - | 0 | 33.91 | 33.91 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Sch-3: Procurement & Replacement of Water wall Z-Panels & Soot blower Panels at U#5: | Yet to be approved | - | 0 | 7.06 | 7.06 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Sch-4 : Supply and erection of APH Inlet & Outlet Flue Gas Damper Assemblies along with actuators at U#5 | Yet to be approved | - | 0 | 2.08 | 2.08 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Sch-5 : Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines at U#5. | Yet to be approved | - | 0 | 3.58 | 3.58 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 25.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Up-gradation of maxDNA DCS system (HMI Up-gradation) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.29 | 7.29 | 7.29 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of PLC (GE FANUC make) SYSTEM (HMI & hardware up-gradation) at Ash Handling Plant, Compressor Plant, and Condensate Polishing Unit (CPU) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.14 | 1.14 | 1.14 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up-gradation of PLC (Schneider make) system (HMI & HARDWARE Up-gradation) at DM Plant, PTP, FF plant, CMRH System, HVAC System, FOPH system at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.26 | 4.26 | 4.26 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Up-gradation of SWAS (STEAM WATER ANALYSIS SYSTEM) Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.71 | 4.71 | 4.71 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Up-gradation of Carbon monoxide analyzer in Flue Gas Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.02 | 1.02 | 1.02 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Up-gradation of Coal feeder Controller at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.01 | 7.01 | 7.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 0.86 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 11.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 0.89 | 0.89 | 0.89 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 5.34 | 5.34 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 230 | 230 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR7 SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Supply Installation Testing & Commissioning , Revamping of fire detection & alarm and protection system from fire and providing rapid extinguishing clean agent (CA) system at unit # 5 at 500 MW khaperkheda TPS | 0 | - | 0 | 23.21 | 23.21 | 0 | 0 | 0 |  |  | 0 | 0
3 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Restoration of fire alarm valve with water spray system (DV) at CHP-II 500 MW | 0 | - | 0 | 22.05 | 22.05 | 0 | 0 | 0 |  |  | 0 | 0
4 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Modular Duct | 0 | - | 0 | 21.5 | 21.5 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | PA Fan Rotor Assy. | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Bottom ash & coarse ash system | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Design Supply and erection of bottom ash hopper and Coarse ash hoppers. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Platform | 0 | - | 0 | 3.96 | 3.96 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Refurbishment of BCW | 0 | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Boiler Lift performance | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
5 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Water Wall Soot Blower Panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Thermal Insulation | 0 | - | 0 | 0 | 0 | 0 | 8.5 | 8.5 |  |  | 8.5 | 0
5.3 | APH Baskets | 0 | - | 0 | 0 | 0 | 0 | 3.7 | 3.7 |  |  | 3.7 | 0
5.4 | Errection & Commisioning of Additional Soot blower | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
5.5 | PA Fan Rotor | 0 | - | 0 | 0 | 0 | 0 | 1.8 | 1.8 |  |  | 1.8 | 0
5.6 | Coal Compartment Assembly | 0 | - | 0 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | 3.5 | 0
6 | Upgradation of Process field instruments and PLCs hardware for performance improvement . | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
6.1 | Upgradation of Emerson make PLC controllers and I/O (AHP) | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of WTP & CHP PLC I/O and network accessories (BOP & CHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Upgradation of Pressure, flow, level transmitter, hydrastep, | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
6.4 | Upgradation of Scanner , Ignitors, Solonoid system , relay of FSSS | 0 | - | 0 | 3.5 | 3.5 | 0 | 3 | 3 |  |  | 3 | 0
6.5 | Upgradation of control valves and cylinders instrumentation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Upgradation of ETP, Debris ,OLCC plc system | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
6.7 | Upgradation of Nucleonic density meter | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
6.8 | Upgradation of environment related instruments | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
6.9 | Installation of Furnace camera | 0 | - | 0 | 2 | 2 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
6.1 | Installation of Flue gas exit temperature probe | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Upgradation of Electrical Protection Systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Upgradation of UPS system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of battery charger system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
7.3 | Upgradation of ID Fan VFD system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.4 | Upgradation of DAVR system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.5 | Upgradation of protection relays at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.6 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 8 | 8 |  |  | 8 | 0
7.8 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
8 | Enhancement of HT/ LT Auxillaries and Illumination for betterment availability and reliability | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply of 6.6 KV, 220 KW Ash Slurry Pump Motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Supply of 6.6 KV, 200 KW Fire Hydrant motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
8.3 | Supply of 690V, 800 KW GEHO Pump motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  |  | 0.6 | 0
8.4 | Refurbishment of BCW Pump Motor Sr. No. AP460044-3-2 | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
8.5 | Supply of Dry Type Transformers of Different Ratings for Unit # 5, TPS Khaperkheda. (Rates are inclusive of 2% Packing and forwarding charges & 2% Freight Charges) | 0 | - | 0 | 0 | 0 | 0 | 3.8 | 3.8 |  |  | 3.8 | 0
8.6 | Supply of 3250KVA, 6.6/2.3 KV Oil Cooled VFD Transformer Of Vector Group Dyn11 and Ydn 11 & 25 MVA UAT For Unit# 5 At Khaperkheda TPS. (Including Packing and forwarding charges 2%, Freight Charges 2%) | 0 | - | 0 | 0 | 0 | 0 | 3.4 | 3.4 |  |  | 3.4 | 0
8.7 | Enhancing conventional lighting system at by retrofitting and replacement with energy efficient LED Lighting system | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
8.8 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP & CHP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 9 | 0
8.9 | supply of integrated solar light and CCTV Camera | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
9 | colony electrical renovation, switchgear, Energy meter, breaker,street light, 11 KV cable ,High Mast | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
9.1 | Electrical Rennovation and mordernization of various tenaments buildings,offices, recreation clubs, Hospital, Domestic Pump House, PTP Plant and Admin Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Replacement of Distibution board, High Mast and switchgear at different areas of colony | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
9.3 | Replacement of Energy meter and various LT Motors at Domestic Pump House and PTP | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
9.4 | 11 KV Cable Work and various 11 KV Structure Rennovation Work | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
9.5 | Various Street Light Refurbishment Work | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
10 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | AHP Performance improvement Scheme for Dry fly ash evacuation system | 0 | - | 0 | 0 | 0 | 0 | 25 | 25 |  |  | 25 | 0
11.1 | Procurement of Vacuum Pumps | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Complete Assembly of Energy Efficient Air Compressors | 0 | - | 0 | 9.7 | 9.7 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of ESP evacuation pipelines, valves and blowers | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Complete Refurbishment Work of 1st & 2nd Row Fields of ESP | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
11.5 | Procurement of ESP CERM and EERM gear boxes | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
12 | AHP Performance improvement Scheme for Wet ash Disposal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Upgradation of Slurry Series System and HP Seal System | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of Fluid Couplings & Gearboxes for Slurry Series Pumps | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Procurement of Vertical slurry pumps & Goodwin Submersible pumps | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Procurement of Complete Assemblies of GEHO systems | 0 | - | 0 | 14.029 | 14.029 | 0 | 0 | 0 |  |  | 0 | 0
12.5 | Procurement & Replacement of Slurry Disposal Pipelines | 0 | - | 0 | 14.72 | 14.72 | 0 | 0 | 0 |  |  | 0 | 0
12.6 | Modification of Bottom ash overflow water clarification system | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
13 | ENAHANCMENT AND RELIABILITY IMPROVELMENT OF TURBINE AUXILIARIES | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | PROCUREMENT OF HPCV 2 SERVO MOTOR | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of BFP-A cartridge | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Procurement of TDBFP turbine rotor | 0 | - | 0 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of CEP-B Cartridge Assembly without motor | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Procurement and commissioning of service and instrument air atlas copco compressor | 0 | - | 0 | 5.7 | 5.7 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Procurement of vacuum pump | 0 | - | 0 | 1.3 | 1.3 | 0 | 0 | 0 |  |  | 0 | 0
13.7 | Procurement of Water treatment plant pumps for effluenet treatement , filter water Raw water, srewage treatement plant pumps, etc. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
13.8 | Procurement and replacement of ACW Pump | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
13.9 | Procurement of regulating BFP Recirculation valve A & B with actuator for flexible operation. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of ASV-22 and spray control valve | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
14 | NDCT EFFICENCY IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Complete replacement of NDCT fills | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Procurement of clarifloculator and flash mixer gear box | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Supply, Installation & Commisioning of NDCT side stream filters | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
15 | IMPROVEMENT OF TURBINE AND PUMPS EFFICENCY | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Procurement of HPT module including Turbo visory instruments (TM-II & C&I-II) | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Procurement and replacement of ACW Pump | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Procurement of CEP-C Cartridge Assembly with out motor | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
16 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Wagon tippler installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Renovation and modanisation of wagen tipler concrete hopper | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Supply and errection of Wagon tipplers | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of hydraulic systems with safety mechanism for Wagon unloading | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Capacity enhancement of side arm charger | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Capacity enhancement of Apron feeder | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
17 | CHP-II Performance improvement scheme installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Supply and installeation of impact crusher spares | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Replacement of scoop coupling | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Renovation stacker reclaimer | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Complete overhauling of Wobbler feeder | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Procurement of Gear boxes | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Structure Strengthening and modification work of Conveyors. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
18 | Infrastructure Development Schemes & Electrical schemes for improvement in availability & Reliability of auxilliaries installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of EOT cranes and hoist installed in CHP-II. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Modification of DE and DS system | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Procuremnet of HT Motors | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Procuremnet of VFD for LT motors | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | upgradation of wagon tippler PLC | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Reconditioning of MCC Boards and feeder panels | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Provision of ceramic lagging to pulleyes ,belt tracker system and mechanise spillage free control system for various conveyor systems | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design engineering , supply and installation of modular chutes with Liners of various belt conveyor installed in CHP-II . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Apron feeder-101/102 to Conv-102A/B transfer chute | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Conv-103A/B to wobbler feeder-101/102 to Crusher -101/102 to Belt feeder-101/102 to conv-104A/B transfer chute | 0 | - | 0 | 12.5 | 12.5 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Conv-104A/B to Conv-105A/B and Conv-113 to Conv-105A/B,BF-105/106 to BF-107 to conv-107 transfer chute | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Conv-105A/B to Cov-106A and Conv-105A/B to Cov-106B transfer chute | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Conv-107 to Conv-108,Conv-112 to Conv-113,Conv-111 to Con-112,Conv-108 to conv-109,conv-109 to conv-110, conveyor transfer chute | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
20 | Comprehensive enhancement infrastructure of green Corridor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Providing and construction of Cement road at various location at 500 MW KPKD, TPS | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Constructions of RCC Drains at various locations in 500 MW KPKD TPS | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Landscaping | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Dust Suppression | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Road Cleaning Machine | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
21 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
23 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 25.58 | 25.58 | 0 | 0 | 0 |  |  | 0 | 0
25 | Construction of LHS on Saoner & Kalumna siding of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Construction of Limited Height Subway at Pandhrakhedi, Patkakhedi (Saoner siding) & Suradevi (Kalumna siding) on depositary basis at Khaperkheda TPS. | 0 | - | 0 | 49.8 | 0 | 49.8 | 0 | 0 |  |  | 0 | 49.8
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 49.8 |  |  | 49.8 | -49.8
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | ID fan motor rotor refurbishment of 500 MW | N.A. | - | 0 | 1.0962 | 1.0962 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Spare TDBFP Gear Box | N.A. | - | 0 | 0.58994 | 0.58994 | 0 | 0 | 0 |  |  | 0 | 0
3 | PISTON CYLINDER ASSEMBLY, DIAPHRAM ASSEMBLY | N.A. | - | 0 | 5.9701 | 5.9701 | 0 | 0 | 0 |  |  | 0 | 0
4 | GT-R Phase Transformer#6006501 of U#5 (Spare) | N.A. | - | 0 | 6.241 | 6.241 | 0 | 0 | 0 |  |  | 0 | 0
5 | GT-R Phase Transformer#6006501U#5 (Core Replace) | N.A. | - | 0 | 3.1304 | 3.1304 | 0 | 0 | 0 |  |  | 0 | 0
6 | BCW Pump Motor Model HLAV (Refurbishment) U#5 | N.A. | - | 0 | 2.8718 | 2.8718 | 0 | 0 | 0 |  |  | 0 | 0
7 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM CHP-II | N.A. | - | 0 | 2.1501 | 2.1501 | 0 | 0 | 0 |  |  | 0 | 0
8 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM C&I-2 | N.A. | - | 0 | 2.2408 | 2.2408 | 0 | 0 | 0 |  |  | 0 | 0
9 | Land for Nandgaon ash band | N.A. | - | 0 | 0.267 | 0.267 | 0 | 0 | 0 |  |  | 0 | 0
10 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-II | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
11 | Fire Fighting equipment(Conveyors galleries CHPII) | N.A. | - | 0 | 0.57643 | 0.57643 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF COMPLETE SET OF SKY CLIMBER FOR UNIT-5 (500 MW), TPS KHAPERKHEDA | N.A. | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
13 | Supply & Erection of Duct, Diverter Plate, and Expansion Joints for Extensive Replacement of Flue Gas Duct at Unit-5,500 MW Khaperkheda TPS | N.A. | - | 0 | 4.09 | 4.09 | 0 | 0 | 0 |  |  | 0 | 0
14 | Stacker Relaimer Refurbishment | N.A. | - | 0 | 20.2 | 20.2 | 0 | 0 | 0 |  |  | 0 | 0
15 | Work of design, Engineering, Supply & Installation along with capacity enhancement of drive unit of conveyor belt 103A,103B & 105B installed at CHP 500MW, Khaperkheda TPS | N.A. | - | 0 | 4.08 | 4.08 | 0 | 0 | 0 |  |  | 0 | 0
16 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 500MW | N.A. | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
17 | work of Refurbishment/Modification of Air ventilation system at wagon tippler tunnel area, Apron feeder floor area, Wagon tippler control room, CHP control room and short conveyor area in CHP500 MW) | N.A. | - | 0 | 2.06 | 2.06 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of design Engineering, Refurbishment & structural strenghthning along with replacement of damaged spares of conveyor belt 110 installed at coal handling plant 500MW . | N.A. | - | 0 | 2.21 | 2.21 | 0 | 0 | 0 |  |  | 0 | 0
19 | GTR Refurbishment | N.A. | - | 0 | 0.33 | 0.33 | 0 | 0 | 0 |  |  | 0 | 0
20 | SUPPLY,ERECTION ,COMMISSIONING AND TESTING OF 360V,750AH PLANTE TYPE UPS BATTERY SET AT UNIT 5 500MW | N.A. | - | 0 | 2.87 | 2.87 | 0 | 0 | 0 |  |  | 0 | 0
21 | Up-gradation of Generator Protection System and Feeder protection relays at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0
22 | BFP Booster pump | N.A. | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
23 | Submission for approval of Non-DPR “Supply of Complete Cartridge Assemblies (1 Nos) for Boiler Feed Pump FK 4E 36 at (Unit#5, 500MW), Khaperkheda T.P.S. | N.A. | - | 0 | 1.99 | 1.99 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procuremet of Portable Reclaimer | N.A. | - | 0 | 8.92 | 8.92 | 0 | 0 | 0 |  |  | 0 | 0
25 | Work of Design, Fabrication ,Erection & commissioning of Wobbler feeder and crusher bypass chute with provision of hydraulic actuator installed at coal handling plant 500MW, Khaperkheda TPS | N.A. | - | 0 | 2.89 | 2.89 | 0 | 0 | 0 |  |  | 0 | 0
26 | Work of Revamping, Modification & Upgradation with Testing & Commissioning of Fire Detection and Alarm System including supply of Material for Unit # 5 BTG area at 500MW TPS Khaperkheda. | N.A. | - | 0 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
27 | HPCV2 Servomotor | N.A. | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
28 | Refurbishment of BCW pump Motor Model HLAV 2X300-460/1C (Rated 350 KW, 6.6 KV ,4 Pole, Sr. No. AP460044-3-1) of U#5 (500 MW) TPS, Khaperkheda. | N.A. | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
29 | Procurement of Complete Rotor Assy. along with 1st and 2nd stage blade set of PA Fan Type AP2 20/12 for Unit#5 (500 MW) TPS, Khaperkheda | N.A. | - | 0 | 3.37 | 3.37 | 0 | 0 | 0 |  |  | 0 | 0
30 | Up-gradation of VFD system for GEHO Pump-2 at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 2.7 | 2.7 | 0 | 0 | 0 |  |  | 0 | 0
31 | General Asset Furniture | N.A. | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
32 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0 | 0.12056 | -0.12056 | 0 | 0 |  |  | 0 | -0.12056
33 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 0.043476 | 0.66703 | -0.62355 | 0 | 0 |  |  | 0 | -0.62355
| Total |  |  | #REF! | 2482.2734 | 2229.3198 | 252.9536 | 165.8 | 215.6 | 0 | 0 | 215.6 | 203.1536
FY 2028-29
a) DPR Schemes
(i) Submitted to MERC
0 | Ash Disposal Scheme from K’kheda 1 X 500 MW Unit to Nandgaon Ash Bund | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | 1. Construction of RCC pedestals for laying of ADP Lines from Khaperkheda TPS to Nandgaon Ash Bund. 2. Providing &Laying of ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 2a) Supply of MSERW and Seamless Pipes 2b) Laying of Ash Disposal & Recovery Pipe Line. 3. Construction of Service road for ash disposal pipe lines from TPS Khaperkheda to Nandgaon ash bund. 4. Design, Engineering & construction of minor bridge, road crossing and culverts in the alignment of ash disposal pipe line from TPS Khaperkheda to Nandgaon Ash Bund 5. Construction of ash water recovery pump house at Nandgaon | MERC/CAPEX/20162017 | 2017-09-22 | 65.7755 | 95.6643 | 95.6643 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20162017 | 2017-09-22 | 3.41 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | Procurement of Bulldozer, Wheel axel final drive assembly & refurbishment of apron feeder at Khaperkheda TPS | MERC/CAPEX/20162017/01341 | 2017-10-11 | 11.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | Procurement of Bulldozers(02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 3.75 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.2 | Procurement of wheel axel final drive assembly (02 No.’s) | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.3 | Refurbishment of apron feeder | MERC/CAPEX/20162017/01341 | 2017-10-11 | 7.36 | 6.8736 | 5.629 | 1.2446 | 0 | 0 |  |  | 0 | 1.2446 | 0 | 0
0 | IDC | MERC/CAPEX/20162017/01341 | 2017-10-11 | 0.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | Procurement of Battery Set, PA Fan assembly, Jack Oil Pump, Turbo Driven BFP Cartridge and Restoration of ESP internals for 500 MW at Khaperkheda TPS | MERC/CAPEX/20172018/04320 | 2017-10-11 | 14.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Procurement, erection, commissioning & testing of 220V, 2190AH & 24V Battery set: | MERC/CAPEX/20172018/04320 | 2017-10-11 | 5.6 | 6.2928 | 6.2928 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Procurement of PA Fan assembly | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.1 | 3.3713 | 3.3713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Restoration of ESP internals | MERC/CAPEX/20172018/04320 | 2017-10-11 | 3.7 | 1.6097 | 1.6097 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Procurement of Jacking Oil Pump | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.18 | 0.27 | 0.27 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.5 | Procurement of turbo driven BFP Cartridge Assembly (FK4E36) | MERC/CAPEX/20172018/04320 | 2017-10-11 | 2.1 | 1.8279 | 1.8279 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/04320 | 2017-10-11 | 0.17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Providing, lowering, laying & jointing M.S. Pipelines from Waregaon ash bund leading towards Khaperkheda TPS for additional recovery of water from Waregaon ash bund including ancillary works of RCC pedestals | MERC/CAPEX/20172018/04072 | 2017-08-18 | 11.3 | 12.8838 | 12.8838 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Provision of S&T System for In Plant Yard Khaperkheda & Kalumni Yard (Depository Work) and Modification of Kalumna Yard Alteration No. 5 (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 31.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Provision of S & T System to Khaperkheda TPS In-Plant yard and Kalumna Yard (Depository Work) | MERC/CAPEX/20172018/4779 | 2017-11-28 | 17.75 | 20.052 | 20.052 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Modification of Kalumna Yard Alternation no. 5 in connection with Khaperkheda TPS Expansion Project (1x500 MW) construction of B.G. Railway Siding | MERC/CAPEX/20172018/4779 | 2017-11-28 | 13.77 | 27.2859 | 13.5159 | 13.77 | 0 | 0 |  |  | 0 | 13.77 | 0 | 0
19 | Construction of Limited Height Subway (LHS) at unmanned road level crossing by Railway on cost sharing basis with MSPGCL on Khaperkheda-Kalumna railway siding and saoner-Khaperkheda railway siding | MERC/CAPEX/20172018/0178 | 2018-02-02 | 16.81 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Construction of LHS on Khaperkheda Kalumna railway side | MERC/CAPEX/20172018/0178 | 2018-02-02 | 5.94 | 4.9899 | 4.9899 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Construction of LHS on Khaperkheda Saoner railway line | MERC/CAPEX/20172018/0178 | 2018-02-02 | 10.87 | 9.78 | 9.78 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Utilisation of unused water scheme from Bhanegaon open cast mine & construction of RCC internal roads at Khaperkheda TPS | MERC/CAPEX/20172018/0197 | 2018-02-06 | 11.5329 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Utilization of unused water scheme from Bhanegaon Open cast mine | MERC/CAPEX/20172018/0197 | 2018-02-06 | 7.5469 | 12.9367 | 12.9403 | -0.0036201 | 0 | 0 |  |  | 0 | -0.0036201 | 0 | 0
20.2 | Construction of Cement Concrete Road Inside Part Of Power House | MERC/CAPEX/20172018/0197 | 2018-02-06 | 2.906 | 2.6732 | 2.6732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/0197 | 2018-02-06 | 1.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21 | Procurement of APH Basket for unit # 1 to 5 and Up-gradation of HT Motor Protection Relay in Unit # 1 to 4 at Khaperkheda TPS | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
21.2 | Procurement of assembly of baskets & seals for Air Preheater of type 31.5 VIMT 2000 (72° PA) | MERC/CAPEX/2018-2019/105 | 2019-04-05 | 3.4 | 3.835 | 3.835 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23 | Supply, Erection & commissioning of HT Vacuum circuit Breakers & SF6 contactors at AHP (U#1-4) & CHP (U#1 to 5) and 160 KW VFD Panel with Motor for fire-fighting pumps at U#1 to 4 at Khaperkheda TPS | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
23.1 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at AHP (Unit#1 to 4, 210MW), Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 4.17 | 3.2027 | 3.2027 | 0 | 0 | 0 |  |  | 0 | 0
23.2 | Supply, erection & commissioning of HT Vacuum Circuit Breakers & SF6 contactors at CHP (Unit#1 to 4, 210MW) and CHP (Unit#5, 500MW) Khaperkheda T.P.S. | MERC/CAPEX/2019-2020/799 | 2019-09-27 | 5.18 | 2.2126 | 2.2126 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27 | Flue Gas Desulphurization (FGD) System for 500 MW Units (Total 8 Nos) of MSPGCL | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 280.82 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
27.1 | Flue Gas Desulphurization (FGD) System for KPKD 5 | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 260.21 | 566.11 | 566.11 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/44 | 2021-01-25 | 20.61 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10 | Augmentation of Ash Evacuation System & Procurement of BCW Pump Motors at Bhusawal & Khaperkheda TPS 500 MW Units | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
BSL DPR-10.3 | Procurement of 02 Nos of M/s Torishima, Japan make, 350 KW, 6.6KV, Boiler Circulating Water (BCW) Pump Motors (without pump casing) with 02 lots of recommended Electrical & C&I spares for Bhusawal and Khaparkheda TPS 500MW. | MERC/CAPEX/20172018/4782 | 2017-11-28 | 4.24 | 4.5033 | 4.5033 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4782 | 2017-11-28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 9.1 | Pipe conveyor system for transporting Coal from WCL Coal mines to Koradi & Khaperkheda TPS | MERC/CAPEX/2017-18/0208 | 2018-02-08 | 269.4076 | 577.94 | 389.0532 | 188.8868 | 0 | 0 |  |  | 0 | 188.8868 | 0 | 0
HO DPR 11 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 11.1 | Reuse of tertiary treated water for Koradi and Khaperkheda Thermal Power Plant from Bhandewadi STP | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 1.23 | 1.8042 | 1.8042 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2018-19/1156 | 2018-07-24 | 0.11 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Implementation of Water Flow Monitoring system at Chandrapur STPS & Khaperkheda TPS | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 4.0922 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.5 | Electromagnetic Flow meters at various lines & Locations of 500 MW | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 3.2497 | 3.2497 | 3.2497 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.6 | Automation: Centralized SCADA, RTU, MODBUS Cable, Power cable & mandatory spares | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0.84252 | 0.84 | 0.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2020-2021/WFH/SBR/37 | 2020-10-27 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M with raising of drain wells and modification of Masonary Dam (Waste Weir), 4 x210 MW, TPS, Khaperkheda | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 45.0535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.1 | Construction of 4th upstream raising of Waregaon Ash Bund from T.B.L 302.50 M to T.B.L. 305.50 M at TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 31.0231 | 45.31 | 45.31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.2 | Raising of drain wells of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 1.6569 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
31.3 | Modification of Masonary Dam (Waste Weir) of Waregaon Ash Bund TPS, Khaperkheda. | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 10.1857 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | MERC/CAPEX/2023-2024/MSPGCL/0510 | 2023-10-09 | 2.1878 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 13 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35 | Boiler Performance improvement Six Schemes at Unit-5 Khaperkheda TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Sch-1: Procurement & Replacement of LTSH coils at U#5 | Yet to be approved | - | 0 | 17.52 | 17.52 | 0 | 0 | 0 |  |  | 0 | 0
35.2 | Sch-2: Procurement & Replacement of Economizer coils at U#5 | Yet to be approved | - | 0 | 33.91 | 33.91 | 0 | 0 | 0 |  |  | 0 | 0
35.3 | Sch-3: Procurement & Replacement of Water wall Z-Panels & Soot blower Panels at U#5: | Yet to be approved | - | 0 | 7.06 | 7.06 | 0 | 0 | 0 |  |  | 0 | 0
35.4 | Sch-4 : Supply and erection of APH Inlet & Outlet Flue Gas Damper Assemblies along with actuators at U#5 | Yet to be approved | - | 0 | 2.08 | 2.08 | 0 | 0 | 0 |  |  | 0 | 0
35.5 | Sch-5 : Supply and Replacement of Thermal Insulation of Boiler, Ducts & Steam Pipelines at U#5. | Yet to be approved | - | 0 | 3.58 | 3.58 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR-17 | Various DPR Schemes for The work of maintaining the zero discharge condition of Pond No. 2 & Pond No.3 and providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 15.7443 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | The work of maintaining the zero discharge condition of Pond No.2 & Pond No.3 at KTPS Koradi | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 4.2068 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.2 | Providing the facilities on peripheral area of Pond No.3 such as roads / bridges with lightening arrangement at Koradi TPS | MERC/CAPEX/2018-2019/1242 | 2018-09-22 | 11.5375 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Scheme of HMI upgradation of unit 5 DCS along with Max Links , HART Scheme , PADO , all BOP PLCs , SWAS system, CO analyser & Coal feeder controller to match with the external aspect , process improvement & Up gradation of Generator Protections Relays in unit 1 to 4 of 210 MW at khaperkheda TPS | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 25.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Up-gradation of maxDNA DCS system (HMI Up-gradation) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.29 | 7.29 | 7.29 | 0 | 0 | 0 |  |  | 0 | 0
2.2 | Up-gradation of PLC (GE FANUC make) SYSTEM (HMI & hardware up-gradation) at Ash Handling Plant, Compressor Plant, and Condensate Polishing Unit (CPU) at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.14 | 1.14 | 1.14 | 0 | 0 | 0 |  |  | 0 | 0
2.3 | Up-gradation of PLC (Schneider make) system (HMI & HARDWARE Up-gradation) at DM Plant, PTP, FF plant, CMRH System, HVAC System, FOPH system at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.26 | 4.26 | 4.26 | 0 | 0 | 0 |  |  | 0 | 0
2.4 | Up-gradation of SWAS (STEAM WATER ANALYSIS SYSTEM) Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 4.71 | 4.71 | 4.71 | 0 | 0 | 0 |  |  | 0 | 0
2.5 | Up-gradation of Carbon monoxide analyzer in Flue Gas Installed at Unit-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 1.02 | 1.02 | 1.02 | 0 | 0 | 0 |  |  | 0 | 0
2.6 | Up-gradation of Coal feeder Controller at U-5. | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 7.01 | 7.01 | 7.01 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2024-2025/478 | 2024-08-06 | 0.86 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
35 | 5 Nos. of Boiler Improvement Schemes for Unit No. 1 to 4 | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 11.75 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
35.1 | Procurement Complete Set of Sky Climber For Unit#1 To 5 Boilers. | MERC/CAPEX/2024-2025/MSPGCL/0251 | 2024-04-18 | 0.89 | 0.89 | 0.89 | 0 | 0 | 0 |  |  | 0 | 0
34 | Supply & commissioning of interconnection conveyor belt, Elecon make complete impact type crusher, Procurement of 4 NOs. Bull Dozer BEML BD-155 and Eco friendly and power efficient chiller system at Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
34.1 | Design, engineering, manufacturing, supply, erection & commissioning of interconnection conveyor belt from 1 X 500MW to 4 X 210MW stack yard at CHP Khaperkheda TPS | MERC/CAPEX/2023-2024/MSPGCL/0142 | 2024-02-27 | 5.43 | 5.34 | 5.34 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Submitted to MERC, Yet to receive approval | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1.1 | Construction of HDPE liner system for Nandgaon Ash Bund at 1X 500 MW TPS Khaperkheda | 0 | - | 0 | 230 | 230 | 0 | 0 | 0 |  |  | 0 | 0
2 | DPR7 SUPPLY INSTALLATION TESTING & COMMISSIONING REVAMPING OF FIRE DETECTION & ALARM AND PROTECTION SYSTEM FROM FIRE AND PROVIDING RAPID EXTINGUISHING CLEAN AGENT (CA) SYSTEM AT UNIT -3,4 & 5 ATKPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2.1 | Supply Installation Testing & Commissioning , Revamping of fire detection & alarm and protection system from fire and providing rapid extinguishing clean agent (CA) system at unit # 5 at 500 MW khaperkheda TPS | 0 | - | 0 | 23.21 | 23.21 | 0 | 0 | 0 |  |  | 0 | 0
3 | Restoration of various Fire protection system at Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3.1 | Restoration of fire alarm valve with water spray system (DV) at CHP-II 500 MW | 0 | - | 0 | 22.05 | 22.05 | 0 | 0 | 0 |  |  | 0 | 0
4 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.1 | Modular Duct | 0 | - | 0 | 21.5 | 21.5 | 0 | 0 | 0 |  |  | 0 | 0
4.2 | PA Fan Rotor Assy. | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
4.3 | Bottom ash & coarse ash system | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
4.4 | Design Supply and erection of bottom ash hopper and Coarse ash hoppers. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Platform | 0 | - | 0 | 3.96 | 3.96 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Refurbishment of BCW | 0 | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
4.7 | Boiler Lift performance | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
5 | Boiler Performance improvement scheme | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.1 | Water Wall Soot Blower Panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5.2 | Thermal Insulation | 0 | - | 0 | 8.5 | 8.5 | 0 | 0 | 0 |  |  | 0 | 0
5.3 | APH Baskets | 0 | - | 0 | 3.7 | 3.7 | 0 | 0 | 0 |  |  | 0 | 0
5.4 | Errection & Commisioning of Additional Soot blower | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
5.5 | PA Fan Rotor | 0 | - | 0 | 1.8 | 1.8 | 0 | 0 | 0 |  |  | 0 | 0
5.6 | Coal Compartment Assembly | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Process field instruments and PLCs hardware for performance improvement . | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Upgradation of Emerson make PLC controllers and I/O (AHP) | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Upgradation of WTP & CHP PLC I/O and network accessories (BOP & CHP) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.3 | Upgradation of Pressure, flow, level transmitter, hydrastep, | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
6.4 | Upgradation of Scanner , Ignitors, Solonoid system , relay of FSSS | 0 | - | 0 | 6.5 | 6.5 | 0 | 0 | 0 |  |  | 0 | 0
6.5 | Upgradation of control valves and cylinders instrumentation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.6 | Upgradation of ETP, Debris ,OLCC plc system | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
6.7 | Upgradation of Nucleonic density meter | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
6.8 | Upgradation of environment related instruments | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6.9 | Installation of Furnace camera | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Installation of Flue gas exit temperature probe | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
7 | Upgradation of Electrical Protection Systems | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.1 | Upgradation of UPS system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.2 | Upgradation of battery charger system at 1X500MW KPKD TPS | 0 | - | 0 | 10 | 10 | 0 | 10 | 10 |  |  | 10 | 0
7.3 | Upgradation of ID Fan VFD system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
7.4 | Upgradation of DAVR system at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
7.5 | Upgradation of protection relays at 1X500MW KPKD TPS | 0 | - | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | 2.5 | 0
7.6 | Retrofittiing of complete GE make panels | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7.7 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
7.8 | Retrofittiing of complete GE make panels | 0 | - | 0 | 1.5 | 1.5 | 0 | 5 | 5 |  |  | 5 | 0
8 | Enhancement of HT/ LT Auxillaries and Illumination for betterment availability and reliability | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.1 | Supply of 6.6 KV, 220 KW Ash Slurry Pump Motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8.2 | Supply of 6.6 KV, 200 KW Fire Hydrant motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
8.3 | Supply of 690V, 800 KW GEHO Pump motor for Unit # 5, TPS Khaperkheda | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
8.4 | Refurbishment of BCW Pump Motor Sr. No. AP460044-3-2 | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
8.5 | Supply of Dry Type Transformers of Different Ratings for Unit # 5, TPS Khaperkheda. (Rates are inclusive of 2% Packing and forwarding charges & 2% Freight Charges) | 0 | - | 0 | 3.8 | 3.8 | 0 | 0 | 0 |  |  | 0 | 0
8.6 | Supply of 3250KVA, 6.6/2.3 KV Oil Cooled VFD Transformer Of Vector Group Dyn11 and Ydn 11 & 25 MVA UAT For Unit# 5 At Khaperkheda TPS. (Including Packing and forwarding charges 2%, Freight Charges 2%) | 0 | - | 0 | 3.4 | 3.4 | 0 | 0 | 0 |  |  | 0 | 0
8.7 | Enhancing conventional lighting system at by retrofitting and replacement with energy efficient LED Lighting system | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
8.8 | Supply, Erection, Commissioning And SiteTesting Of 220V DC Battery Set at PTP & CHP area at Unit# 5,Khaperkheda TPS. | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
8.9 | supply of integrated solar light and CCTV Camera | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
9 | colony electrical renovation, switchgear, Energy meter, breaker,street light, 11 KV cable ,High Mast | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
9.1 | Electrical Rennovation and mordernization of various tenaments buildings,offices, recreation clubs, Hospital, Domestic Pump House, PTP Plant and Admin Building | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9.2 | Replacement of Distibution board, High Mast and switchgear at different areas of colony | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
9.3 | Replacement of Energy meter and various LT Motors at Domestic Pump House and PTP | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
9.4 | 11 KV Cable Work and various 11 KV Structure Rennovation Work | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
9.5 | Various Street Light Refurbishment Work | 0 | - | 0 | 7 | 7 | 0 | 10 | 10 |  |  | 10 | 0
10 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10.1 | Construction of RCC Nallah adjacent to security wall alongwith RCC Petroling Road from Bhanegaon Gate to Parshivni Bridge at 500 MW, KPKD, TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | AHP Performance improvement Scheme for Dry fly ash evacuation system | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
11.1 | Procurement of Vacuum Pumps | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
11.2 | Procurement of Complete Assembly of Energy Efficient Air Compressors | 0 | - | 0 | 9.7 | 9.7 | 0 | 0 | 0 |  |  | 0 | 0
11.3 | Procurement of ESP evacuation pipelines, valves and blowers | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
11.4 | Complete Refurbishment Work of 1st & 2nd Row Fields of ESP | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
11.5 | Procurement of ESP CERM and EERM gear boxes | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
12 | AHP Performance improvement Scheme for Wet ash Disposal System | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12.1 | Upgradation of Slurry Series System and HP Seal System | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
12.2 | Procurement of Fluid Couplings & Gearboxes for Slurry Series Pumps | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
12.3 | Procurement of Vertical slurry pumps & Goodwin Submersible pumps | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
12.4 | Procurement of Complete Assemblies of GEHO systems | 0 | - | 0 | 14.029 | 14.029 | 0 | 0 | 0 |  |  | 0 | 0
12.5 | Procurement & Replacement of Slurry Disposal Pipelines | 0 | - | 0 | 14.72 | 14.72 | 0 | 0 | 0 |  |  | 0 | 0
12.6 | Modification of Bottom ash overflow water clarification system | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
13 | ENAHANCMENT AND RELIABILITY IMPROVELMENT OF TURBINE AUXILIARIES | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | PROCUREMENT OF HPCV 2 SERVO MOTOR | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
13.2 | Procurement of BFP-A cartridge | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
13.3 | Procurement of TDBFP turbine rotor | 0 | - | 0 | 7.5 | 7.5 | 0 | 0 | 0 |  |  | 0 | 0
13.4 | Procurement of CEP-B Cartridge Assembly without motor | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
13.5 | Procurement and commissioning of service and instrument air atlas copco compressor | 0 | - | 0 | 5.7 | 5.7 | 0 | 0 | 0 |  |  | 0 | 0
13.6 | Procurement of vacuum pump | 0 | - | 0 | 1.3 | 1.3 | 0 | 0 | 0 |  |  | 0 | 0
13.7 | Procurement of Water treatment plant pumps for effluenet treatement , filter water Raw water, srewage treatement plant pumps, etc. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
13.8 | Procurement and replacement of ACW Pump | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
13.9 | Procurement of regulating BFP Recirculation valve A & B with actuator for flexible operation. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
13.1 | Procurement of ASV-22 and spray control valve | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
14 | NDCT EFFICENCY IMPROVEMENT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14.1 | Complete replacement of NDCT fills | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
14.2 | Procurement of clarifloculator and flash mixer gear box | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
14.3 | Supply, Installation & Commisioning of NDCT side stream filters | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
15 | IMPROVEMENT OF TURBINE AND PUMPS EFFICENCY | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Procurement of HPT module including Turbo visory instruments (TM-II & C&I-II) | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Procurement and replacement of ACW Pump | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
15.3 | Procurement of CEP-C Cartridge Assembly with out motor | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
16 | Upgardation and Capacity Enhancement of Side Arm Charger Apron Feeder and Wagon tippler installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16.1 | Renovation and modanisation of wagen tipler concrete hopper | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
16.2 | Supply and errection of Wagon tipplers | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
16.3 | Upgradation of hydraulic systems with safety mechanism for Wagon unloading | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
16.4 | Capacity enhancement of side arm charger | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
16.5 | Capacity enhancement of Apron feeder | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
17 | CHP-II Performance improvement scheme installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17.1 | Supply and installeation of impact crusher spares | 0 | - | 0 | 9 | 9 | 0 | 0 | 0 |  |  | 0 | 0
17.2 | Replacement of scoop coupling | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Renovation stacker reclaimer | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
17.4 | Complete overhauling of Wobbler feeder | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
17.5 | Procurement of Gear boxes | 0 | - | 0 | 8 | 8 | 0 | 0 | 0 |  |  | 0 | 0
17.6 | Structure Strengthening and modification work of Conveyors. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
18 | Infrastructure Development Schemes & Electrical schemes for improvement in availability & Reliability of auxilliaries installed in CHP-II,Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Procurement of EOT cranes and hoist installed in CHP-II. | 0 | - | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Modification of DE and DS system | 0 | - | 0 | 14 | 14 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Procuremnet of HT Motors | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Procuremnet of VFD for LT motors | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
18.5 | upgradation of wagon tippler PLC | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
18.6 | Reconditioning of MCC Boards and feeder panels | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
18.7 | Provision of ceramic lagging to pulleyes ,belt tracker system and mechanise spillage free control system for various conveyor systems | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
19 | Work of Design engineering , supply and installation of modular chutes with Liners of various belt conveyor installed in CHP-II . | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.1 | Apron feeder-101/102 to Conv-102A/B transfer chute | 0 | - | 0 | 3.5 | 3.5 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Conv-103A/B to wobbler feeder-101/102 to Crusher -101/102 to Belt feeder-101/102 to conv-104A/B transfer chute | 0 | - | 0 | 12.5 | 12.5 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Conv-104A/B to Conv-105A/B and Conv-113 to Conv-105A/B,BF-105/106 to BF-107 to conv-107 transfer chute | 0 | - | 0 | 5.5 | 5.5 | 0 | 0 | 0 |  |  | 0 | 0
19.4 | Conv-105A/B to Cov-106A and Conv-105A/B to Cov-106B transfer chute | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
19.5 | Conv-107 to Conv-108,Conv-112 to Conv-113,Conv-111 to Con-112,Conv-108 to conv-109,conv-109 to conv-110, conveyor transfer chute | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
20 | Comprehensive enhancement infrastructure of green Corridor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
20.1 | Providing and construction of Cement road at various location at 500 MW KPKD, TPS | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
20.2 | Constructions of RCC Drains at various locations in 500 MW KPKD TPS | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
20.3 | Landscaping | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
20.4 | Dust Suppression | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
20.5 | Road Cleaning Machine | 0 | - | 0 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 0 | 0
21 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
21.1 | Implementation of Flexible Operation Solutions – 40% Technical Minimum Loading with minimum 3% ramp rate during 70-100% loading, minimum 2% ramp rate during 55-70% loading and minimum 1% ramp rate during 40-55% loading at Unit#5 Khaperkheda TPS | 0 | - | 0 | 25 | 25 | 0 | 0 | 0 |  |  | 0 | 0
22 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
22.1 | CHP Improvement Schemes for 500MW unit | 0 | - | 0 | 50 | 50 | 0 | 0 | 0 |  |  | 0 | 0
23 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
23.1 | Flue Gas Desulphirization (FGD) Khaperkheda U-5 (500 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
24.1 | Construction of 02 nos. of additional ash silo & RCC Drain at Khaperkheda TPS. | 0 | - | 0 | 25.58 | 25.58 | 0 | 0 | 0 |  |  | 0 | 0
25 | Construction of LHS on Saoner & Kalumna siding of Khaperkheda TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
25.1 | Construction of Limited Height Subway at Pandhrakhedi, Patkakhedi (Saoner siding) & Suradevi (Kalumna siding) on depositary basis at Khaperkheda TPS. | 0 | - | 0 | 49.8 | 0 | 49.8 | 0 | 0 |  |  | 0 | 49.8
0 | 0 | 0 | - | 0 | 0 | 49.8 | -49.8 | 0 | 0 |  |  | 0 | -49.8
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | ID fan motor rotor refurbishment of 500 MW | N.A. | - | 0 | 1.0962 | 1.0962 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Spare TDBFP Gear Box | N.A. | - | 0 | 0.58994 | 0.58994 | 0 | 0 | 0 |  |  | 0 | 0
3 | PISTON CYLINDER ASSEMBLY, DIAPHRAM ASSEMBLY | N.A. | - | 0 | 5.9701 | 5.9701 | 0 | 0 | 0 |  |  | 0 | 0
4 | GT-R Phase Transformer#6006501 of U#5 (Spare) | N.A. | - | 0 | 6.241 | 6.241 | 0 | 0 | 0 |  |  | 0 | 0
5 | GT-R Phase Transformer#6006501U#5 (Core Replace) | N.A. | - | 0 | 3.1304 | 3.1304 | 0 | 0 | 0 |  |  | 0 | 0
6 | BCW Pump Motor Model HLAV (Refurbishment) U#5 | N.A. | - | 0 | 2.8718 | 2.8718 | 0 | 0 | 0 |  |  | 0 | 0
7 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM CHP-II | N.A. | - | 0 | 2.1501 | 2.1501 | 0 | 0 | 0 |  |  | 0 | 0
8 | RF CONNECTIVITY AND SURVEILLANCE SYSTEM C&I-2 | N.A. | - | 0 | 2.2408 | 2.2408 | 0 | 0 | 0 |  |  | 0 | 0
9 | Land for Nandgaon ash band | N.A. | - | 0 | 0.267 | 0.267 | 0 | 0 | 0 |  |  | 0 | 0
10 | MOBILE COAL SAMPLING EQUIP-AUGER (FMC) CHP-II | N.A. | - | 0 | 1.5824 | 1.5824 | 0 | 0 | 0 |  |  | 0 | 0
11 | Fire Fighting equipment(Conveyors galleries CHPII) | N.A. | - | 0 | 0.57643 | 0.57643 | 0 | 0 | 0 |  |  | 0 | 0
12 | PROCUREMENT OF COMPLETE SET OF SKY CLIMBER FOR UNIT-5 (500 MW), TPS KHAPERKHEDA | N.A. | - | 0 | 0.86 | 0.86 | 0 | 0 | 0 |  |  | 0 | 0
13 | Supply & Erection of Duct, Diverter Plate, and Expansion Joints for Extensive Replacement of Flue Gas Duct at Unit-5,500 MW Khaperkheda TPS | N.A. | - | 0 | 4.09 | 4.09 | 0 | 0 | 0 |  |  | 0 | 0
14 | Stacker Relaimer Refurbishment | N.A. | - | 0 | 20.2 | 20.2 | 0 | 0 | 0 |  |  | 0 | 0
15 | Work of design, Engineering, Supply & Installation along with capacity enhancement of drive unit of conveyor belt 103A,103B & 105B installed at CHP 500MW, Khaperkheda TPS | N.A. | - | 0 | 4.08 | 4.08 | 0 | 0 | 0 |  |  | 0 | 0
16 | PROCUREMENT OF OIL COOLED SUSPENSION MAGNET FOR 500MW | N.A. | - | 0 | 1.21 | 1.21 | 0 | 0 | 0 |  |  | 0 | 0
17 | work of Refurbishment/Modification of Air ventilation system at wagon tippler tunnel area, Apron feeder floor area, Wagon tippler control room, CHP control room and short conveyor area in CHP500 MW) | N.A. | - | 0 | 2.06 | 2.06 | 0 | 0 | 0 |  |  | 0 | 0
18 | Work of design Engineering, Refurbishment & structural strenghthning along with replacement of damaged spares of conveyor belt 110 installed at coal handling plant 500MW . | N.A. | - | 0 | 2.21 | 2.21 | 0 | 0 | 0 |  |  | 0 | 0
19 | GTR Refurbishment | N.A. | - | 0 | 0.33 | 0.33 | 0 | 0 | 0 |  |  | 0 | 0
20 | SUPPLY,ERECTION ,COMMISSIONING AND TESTING OF 360V,750AH PLANTE TYPE UPS BATTERY SET AT UNIT 5 500MW | N.A. | - | 0 | 2.87 | 2.87 | 0 | 0 | 0 |  |  | 0 | 0
21 | Up-gradation of Generator Protection System and Feeder protection relays at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 2.09 | 2.09 | 0 | 0 | 0 |  |  | 0 | 0
22 | BFP Booster pump | N.A. | - | 0 | 1.4 | 1.4 | 0 | 0 | 0 |  |  | 0 | 0
23 | Submission for approval of Non-DPR “Supply of Complete Cartridge Assemblies (1 Nos) for Boiler Feed Pump FK 4E 36 at (Unit#5, 500MW), Khaperkheda T.P.S. | N.A. | - | 0 | 1.99 | 1.99 | 0 | 0 | 0 |  |  | 0 | 0
24 | Procuremet of Portable Reclaimer | N.A. | - | 0 | 8.92 | 8.92 | 0 | 0 | 0 |  |  | 0 | 0
25 | Work of Design, Fabrication ,Erection & commissioning of Wobbler feeder and crusher bypass chute with provision of hydraulic actuator installed at coal handling plant 500MW, Khaperkheda TPS | N.A. | - | 0 | 2.89 | 2.89 | 0 | 0 | 0 |  |  | 0 | 0
26 | Work of Revamping, Modification & Upgradation with Testing & Commissioning of Fire Detection and Alarm System including supply of Material for Unit # 5 BTG area at 500MW TPS Khaperkheda. | N.A. | - | 0 | 5.2 | 5.2 | 0 | 0 | 0 |  |  | 0 | 0
27 | HPCV2 Servomotor | N.A. | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
28 | Refurbishment of BCW pump Motor Model HLAV 2X300-460/1C (Rated 350 KW, 6.6 KV ,4 Pole, Sr. No. AP460044-3-1) of U#5 (500 MW) TPS, Khaperkheda. | N.A. | - | 0 | 3.59 | 3.59 | 0 | 0 | 0 |  |  | 0 | 0
29 | Procurement of Complete Rotor Assy. along with 1st and 2nd stage blade set of PA Fan Type AP2 20/12 for Unit#5 (500 MW) TPS, Khaperkheda | N.A. | - | 0 | 3.37 | 3.37 | 0 | 0 | 0 |  |  | 0 | 0
30 | Up-gradation of VFD system for GEHO Pump-2 at 1X500MW Khaperkheda TPS. | N.A. | - | 0 | 2.7 | 2.7 | 0 | 0 | 0 |  |  | 0 | 0
31 | General Asset Furniture | N.A. | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
32 | General Asset AC, Fans, Air coolers, water filter etc. | N.A. | - | 0 | 0 | 0.12056 | -0.12056 | 0 | 0 |  |  | 0 | -0.12056
33 | General Asset Computer, scanners, etc. | N.A. | - | 0 | 0.043476 | 0.66703 | -0.62355 | 0 | 0 |  |  | 0 | -0.62355
| Total |  |  | 0 | 2648.0734 | 2444.9198 | 203.1536 | 37 | 37 | 0 | 0 | 37 | 203.1536