## F4
MSPGCL: Nashik TPS
MTR Petition Formats - Generation
Form 4: Summary of Capital Expenditure and Capitalisation
(Rs. Crore)
Sr. No. | Particulars | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-25 |  |  |  |  | Ensuing Years |  |  |  |  | Remarks
|  | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | April-March (Audited ) | True-Up requirement | MYT Order (227 of 2022) | Apr-Sep (Estimated) | Oct-Mar (Projected) | April - March (Projected) | Provisional True-Up requirement | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
|  | (a) | (b) | (c) = (b) - (a) | (d) | (e) | (f) = (e) - (d) | (g) | (h) | (i) | (j) = (h) + (i) | (k) = (j) - (g) | Projected | Projected | Projected | Projected | Projected
1 | Capital Expenditure |  | 9.45 | 9.45 |  | 8.2467 | 8.2467 |  |  |  | 6.5675 | 6.5675 | 711.384 | 1040.6982 | 89.2414 | 9.102 | 0.5
2 | Capitalisation | 6.19 | 6.9245 | 0.73447 | 29.76 | 5.1124 | -24.6476 | 10.72 | 1.31 | 8.355 | 9.6648 | -1.0552 | 735.654 | 1040.6982 | 89.2414 | 9.102 | 0.5
3 | IDC |  |  | 0 |  |  | 0 |  |  |  |  | 0
4 | Capitalisation + IDC | 6.19 | 6.9245 | 0.73447 | 29.76 | 5.1124 | -24.6476 | 10.72 | 1.31 | 8.355 | 9.6648 | -1.0552 | 735.654 | 1040.6982 | 89.2414 | 9.102 | 0.5
Note: * - Truing Up for FY 2022-23 & FY 2023-24 to be done under MERC MYT Regulations 2019 with reference to amounts approved in the MYT Order for FY 2020-21 to FY 2024-25
Detailed Justification shall be provided for variation in approved capital expenditure and capitalisation vis-a-vis actual capital expenditure and capitalisation

## F4.1
MSPGCL: Nashik TPS
MTR Petition Formats - Generation
| Project Details |  | Form 4.1: Capital Expenditure Plan | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
A) DPR Schemes
(i) Submitted to MERC
1 | Essential Works at Stage I | DPR | MERC/CAPEX /20112012/01181 | 2011-08-03 |  | 2011-08-03 |  | - | - |  | - | 0 | 0 |  |  |  |  | 0
1.1 | Essential Works at Stage I | Scheme | MERC/CAPEX /20112012/01181 | 2011-08-03 |  | 2011-08-03 |  | - | - |  | - | 30.32 | 0 |  |  |  |  | 30.32
2 | Measuring & Monitoring of Coal consumption | DPR | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
2.1 | Belt Weighers | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | 2009-01-01 | 2012-06-24 |  | 2012-07-14 | 0.3295 | 0.3295 |  | 0 |  |  | 0
2.2 | Fully automatic pit-less in motion weigh bridges | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | - | - |  | - | 0.793 | 0 |  | 0.793 |  |  | 0.793
2.3 | Installation of inhaul outhaul betel chargers | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | 2014-06-26 | 2012-09-24 |  | 2018-03-09 | 6 | 8.5943 |  | -2.5943 |  |  | -2.5943
2.4 | Dust Extraction System | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | 2012-09-26 | 2011-12-24 |  | 2016-05-09 | 1.65 | 1.713 |  | -0.063038 |  |  | -0.063038
2.5 | Fogging system | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | 2015-02-18 | 2012-12-24 |  | 2020-07-22 | 2.44 | 2.59 |  | -0.14996 |  |  | -0.14996
2.6 | Bunker level montoring system | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | 2012-08-30 | 2012-03-24 |  | 2012-12-15 | 0.54 | 0.0694 |  | 0.4706 |  |  | 0.4706
2.7 | Rotary pneumatic or electrical hammers | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | Deferred | 2011-09-24 |  | Deferred | 0.169 | 0 |  | 0.169 |  |  | 0.169
2.8 | Operating the CHP near to its full capacity | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | Deferred | 2013-09-24 |  | Deferred | 7.3 | 0 |  | 7.3 |  |  | 7.3
2.9 | Motor controller | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | 2010-03-23 | 2011-12-24 |  | 2011-05-28 | 0.3732 | 0.3732 |  | 0 |  |  | 0
0 | IDC | IDC | MERC/CAPEX/ 20112012/01775 | 2010-12-24 |  | 2010-12-24 |  | - | - |  | - | 3.4218 | 0 |  | 3.4218 |  |  | 3.4218
3 | Renovation & Modernization of Nasik U-3 | DPR | MERC/CAPEX/ 20112012/07 | 2011-04-01 |  | 2011-04-01 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
3.1 | Renovation & Modernization of Nasik U-3 | Scheme | MERC/CAPEX/ 20112012/07 | 2011-04-01 |  | 2011-04-01 |  | - | - |  | - | 481.46 | 0 |  | 481.46 |  |  | 481.46
4 | Combustion optimization & Process improvement | DPR | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
4.1 | Improvement in tooling techniques Power tools like cut off machines and surface grinders. | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | 2012-09-03 | 2012-06-22 |  | Aug-14 | 0.52821 | 0.3388 |  | 0.18941 |  |  | 0.18941
4.2 | Total replacement of boiler related skin insulation as well as skin cladding of furnace, Air pre heaters,air ducts and flue gas ducts Unit-4 &5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | 2017-03-03 | 2011-08-22 |  | 2019-12-01 | 4.5892 | 4.7188 |  | -0.12963 |  |  | -0.12963
4.3 | Painting of Boiler ,bunker structure and other structure.Unit-3,4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | Deferred | 2016-12-22 |  | Deferred | 7.775 | 0 |  | 7.775 |  |  | 7.775
4.4 | Dynamic coal flow measurement and control (balancing) system (one) | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | Deferred | 2011-12-22 |  | Deferred | 8.14 | 0 |  | 8.14 |  |  | 8.14
4.5 | Retrofitting of Gas proportioning dampers, flue gas, primary and secondary air dampers. (SADC) for Unit-4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | 2017-01-04 | 2011-12-22 |  | 2024-03-01 | 2.456 | 1.2566 |  | 1.1994 |  |  | 1.1994
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0.41356 |  | -0.41356 |  |  | -0.41356
4.6 | Replacement of flue gas ducting zone prone to erosion with 6 to 8 mm high grade material & insulation of flue gas ducts. (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 4 and 5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | Deferred | 2011-12-22 |  | Deferred | 4 | 0 |  | 4 |  |  | 4
4.7 | Replacement of boiler outlet valves and damaged valves of units 4 & 5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | 2012-03-31 | 2012-08-22 |  | 2014-08-01 | 2.349 | 1.4313 |  | 0.9177 |  |  | 0.9177
4.8 | Replacement of coal pipe at direction changing sections & flow curvature zone by upgraded material. Unit-4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | Deferred | 2012-08-22 |  | Deferred | 2.3292 | 0 |  | 2.3292 |  |  | 2.3292
4.9 | Installation of Smart soot blower system for Unit- 4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | Deferred | 2015-12-22 |  | Deferred | 5.6 | 0 |  | 5.6 |  |  | 5.6
4.10 | Installation of Sonic soot blowers for second pass for Unit-4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | Deferred | 2012-08-22 |  | Deferred | 0.83184 | 0 |  | 0.83184 |  |  | 0.83184
4.11 | Air pre heater upgradation of heat exchanger matrix &regenerative dynamic sealing for Unit-4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | Deferred | 2014-12-22 |  | Deferred | 6 | 0 |  | 6 |  |  | 6
4.12 | Replacement Platen water wall for Unit-3. | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | 2011-04-30 | 2012-04-22 |  | 2014-08-01 | 0.60762 | 0.6964 |  | -0.088776 |  |  | -0.088776
0 | IDC | IDC | MERC/CAPEX/ 20102011/01756 | 2010-12-22 |  | 2010-12-22 |  | - | - |  | - | 13.57 | 0 |  | 13.57 |  |  | 13.57
5 | Turbine Auxiliary Consumption Improvement | DPR | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
5.1 | Installation of Turbo vaned fly wheeling eco ventilators to all Units 3, 4, 5. | Scheme | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | 2010-09-18 | 2012-10-05 |  | Partially Deferred | 0.09 | 0 |  | 0.09 |  |  | 0.09
5.2 | Replacement of selected old brass impellers of pumps with SS304 impellers. H.T. Auxiliary C.W. Pump and G.S. Water Pumps are selected. | Scheme | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | 2010-07-07 | 2013-04-05 |  | 2015-12-15 | 2.4 | 0.8251 |  | 1.5749 |  |  | 1.5749
5.3 | Improving the BFP efficiency by replacing eroded internals of pump. | Scheme | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | 2010-09-13 | 2012-10-05 |  | 2016-07-08 | 0.75 | 0.48804 |  | 0.26196 |  |  | 0.26196
5.4 | Replacement of BFP (200 KHI) cartridge with energy efficient cartridge. | Scheme | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | 2014-09-20 | 2014-04-05 |  | 2022-03-31 | 14.4456 | 13.85 |  | 0.59557 |  |  | 0.59557
5.5 | Improving the CEP efficiency by replacing eroded internals of pump. | Scheme | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | 2014-12-09 | 2012-10-05 |  | 2015-03-31 | 0.9 | 0.6018 |  | 0.2982 |  |  | 0.2982
5.6 | Replacement of CEP with energy efficient pump. | Scheme | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | Deferred | 2013-04-05 |  | Deferred | 2.7 | 0 |  | 2.7 |  |  | 2.7
5.7 | Replacement of Pumps - GS Pumps, H2Cooler booster pump, DM/DM pumps, DM Makeup pumps, Emergency lift pumps, Drip pumps, BFP Booster pumps with energy efficient pumps. | Scheme | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | 2007-08-22 | 2013-04-05 |  | 2020-04-01 | 4.2733 | 2.3608 |  | 1.9125 |  |  | 1.9125
5.8 | Replacement of valves – MS - 3 to 8 , HD – 22,23,24 , MC- 36 , ES 3,4 and BFP Recirculation Valves. | Scheme | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | 2006-09-06 | 2013-07-05 |  | 2019-06-19 | 3.0852 | 1.3148 |  | 1.7704 |  |  | 1.7704
5.9 | Replacement of tube nest of LP Heater no.3 of unit no.3, LP Heater no.4 of unit no.5, Main ejector 3B, GC2 of unit no.5, Seal oil coolers, H2 Coolers, BFP working and lub oil coolers, DM/GS plate type coolers. | Scheme | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | 2009-09-01 | 2013-04-05 |  | WIP | 6.5962 | 1.4406 |  | 5.1556 |  |  | 5.1556
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0.11461 |  | -0.11461 |  |  | -0.11461
5.10 | Steam path audit of Unit no,4,5 | Scheme | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | Deferred | 2013-01-05 |  | Deferred | 0.5 | 0 |  | 0.5 |  |  | 0.5
0 | IDC | IDC | MERC/CAPEX/ 20112012/00024 | 2011-04-05 |  | 2011-04-05 |  | - | - |  | - | 3.55 | 0 |  | 3.55 |  |  | 3.55
6 | EMS, Numeric relays, Microprocessor DVR & VFD | DPR | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 |  | 2014-01-17 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
6.1 | Design, manufacture, supply, erection, commissioning & testing of Variable Frequency Drives (VFD) with latest design and technology super premium efficiency motors for 415 V LT Auxiliaries (Total 50 No) of 210 MW Unit 3, 4 & 5. | Scheme | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 |  | 2014-01-17 |  | 2013-08-22 | 2013-12-01 |  | WIP | 6.3 | 7.4321 |  | -1.1321 |  |  | -1.1321
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0.66 | 0.74645 |  | -0.086454 |  |  | -0.086454
6.2 | Replacement of old EE make Generator Protection Relays with Numerical Generator Protection Relays for unit no. 3, 4 & 5 | Scheme | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 |  | 2014-01-17 |  | 2012-02-28 | 2013-12-01 |  | 2014-08-10 | 1.7 | 1.7029 |  | -0.002914 |  |  | -0.002914
6.3 | Replacement of old AVR with Microprocessor based Digital Voltage Regulator for unit no. 3 & 5 | Scheme | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 |  | 2014-01-17 |  | 2012-01-20 | 2013-12-01 |  | 2014-08-10 | 2.44 | 1.7055 |  | 0.73447 |  |  | 0.73447
6.4 | Installation and commissioning of Energy Management System for unit no. 3, 4 & 5 | Scheme | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 |  | 2014-01-17 |  | 2015-07-13 | 2013-12-01 |  | 2022-03-31 | 0.81 | 0.8313 |  | -0.021298 |  |  | -0.021298
0 | IDC | IDC | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 |  | 2014-01-17 |  | - | - |  | - | 0.66 | 0 |  | 0.66 |  |  | 0.66
7 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | DPR | MERC/CAPEX/ 20122013/00149 | 2012-05-30 |  | 2012-05-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
7.1 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | Scheme | MERC/CAPEX/ 20122013/00149 | 2012-05-30 |  | 2012-05-30 |  | 2013-04-01 | 2014-03-01 |  | 2016-09-30 | 11.95 | 14.5069 |  | -2.5569 |  |  | -2.5569
8 | Renovation of Rail System | DPR | MERC/CAPEX/ 20112012/02118 | 2012-12-21 |  | 2012-12-21 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
8.1 | Renovation of Rail System | Scheme | MERC/CAPEX/ 20112012/02118 | 2012-12-21 |  | 2012-12-21 |  | - | - |  | - | 57.915 | 57.9147 |  | 0.0003 |  |  | 0.0003
9 | Faster unloading of coal wagons by upgrading existing system (Post Facto) | DPR | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 |  | 2013-10-04 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
9.1 | Re-design, Supply, Erection and commissioning of modified Apron Feeder. | Scheme | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 |  | 2013-10-04 |  | - | - |  | - | 5.7219 | 5.4 |  | 0.3219 |  |  | 0.3219
9.2 | Design, manufacture, supply, erection and commissioning of modified bunker outlet cone of Unit 3, 4 and 5. | Scheme | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 |  | 2013-10-04 |  | - | - |  | - | 2.3295 | 2.3196 |  | 0.0099 |  |  | 0.0099
9.3 | Design, manufacture, Supply & Erection Of Components Suitable For Modification Of Wagon Tipplers to Handle BOXNHL , BOX-H,BOX-NR,BOX-NJLSR1 & 25 T AXLE WAGONS | Scheme | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 |  | 2013-10-04 |  | 2013-04-01 | 2013-04-01 |  | 2014-03-01 | 5.1298 | 4.413 |  | 0.7168 |  |  | 0.7168
9.4 | Procurement of SAN Loco - 650-700 HP. | Scheme | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 |  | 2013-10-04 |  | 2012-10-01 | 2012-10-01 |  | 2013-12-01 | 2.8627 | 2.81 |  | 0.0527 |  |  | 0.0527
9.5 | Revamping of CHP II Wagon Tippler by replacing the Split Wheel Assembly, Pawl Lever, Pinion Shaft Assembly, Toe, Spur Gear Shaft, W.T Drive Assembly, Rack Segment, Rail Table Assembly Of Wagon Tippler and Dismantling & Replacement of above parts | Scheme | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 |  | 2013-10-04 |  | - | - |  | - | 2.8042 | 2.81 |  | -0.0058 |  |  | -0.0058
10 | Procurement of 6.6 Kv HT motors as spare motors /for replacement | DPR | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
10.1 | ID FAN MOTOR (1700 kW) | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 1.3125 | 0 |  | 1.3125 |  |  | 1.3125
10.2 | ID FAN MOTOR (1700 kW) | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 1.1025 | 0 |  | 1.1025 |  |  | 1.1025
10.3 | FD FAN MOTOR 650 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.7875 | 0 |  | 0.7875 |  |  | 0.7875
10.4 | FD FAN MOTOR 750 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.8505 | 0 |  | 0.8505 |  |  | 0.8505
10.5 | PA FAN MOTOR 1250 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 1.029 | 0 |  | 1.029 |  |  | 1.029
10.6 | BFP MOTOR 4000 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 4.5528 | 0 |  | 4.5528 |  |  | 4.5528
10.7 | C/MILL MOTOR 320 kW (3 Nos) | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 1.3356 | 0 |  | 1.3356 |  |  | 1.3356
10.8 | SOP MOTOR 200 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.2276 | 0 |  | 0.2276 |  |  | 0.2276
10.9 | CWP MOTOR 950 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.8942 | 0 |  | 0.8942 |  |  | 0.8942
10.10 | CTLP MOTOR 710 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.8081 | 0 |  | 0.8081 |  |  | 0.8081
10.11 | RWP MOTOR 335 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.4861 | 0 |  | 0.4861 |  |  | 0.4861
10.12 | HP PUMP MOTOR 258 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.3083 | 0 |  | 0.3083 |  |  | 0.3083
10.13 | CEP MOTOR 220 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.2629 | 0 |  | 0.2629 |  |  | 0.2629
10.14 | GS PUMP MOTOR 260 kW | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.3107 | 0 |  | 0.3107 |  |  | 0.3107
10.15 | Testing charges | Scheme | MERC/CAPEX/20152016/00422 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0.088 | 0 |  | 0.088 |  |  | 0.088
11 | Replacement of complete LTSH coils at Unit-3 Boiler & Economiser coils at Unit-5 Boiler | DPR | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 |  | 2014-10-16 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
11.1 | Complete Supply & Erection of LTSH coils at Unit-3 210 MW Boiler (67 nos. upper and lower modules each. 01 module = 02 coils) | Scheme | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 |  | 2014-10-16 |  | 2016-11-01 | 2016-03-01 |  | 2017-09-01 | 16.43 | 4.6378 |  | 11.7922 |  |  | 11.7922
11.2 | Complete Supply & Erection of 270 nos. Economizer coils in second pass of Unit-5 210 MW Boiler at Nasik TPS. | Scheme | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 |  | 2014-10-16 |  | 2016-11-01 | 2017-03-01 |  | 2019-01-01 | 9.57 | 3.0104 |  | 6.5596 |  |  | 6.5596
0 | IDC | IDC | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 |  | 2014-10-16 |  | - | - |  | - | 1.44 | 0 |  | 1.44 |  |  | 1.44
12 | Enhancement of performance & life of Coal Handling plant | DPR | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 |  | 2015-02-23 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
12.1 | Procurement of 02 nos of 320 hp bull dozers for Nasik TPS | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 |  | 2015-02-23 |  | 2017-08-18 | 2016-11-23 |  | 2017-10-01 | 3.2 | 4.2044 |  | -1.0044 |  |  | -1.0044
12.2 | Procurement of gear box for Apron Feeder in CHP III | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 |  | 2015-02-23 |  | 2015-07-05 | 2016-11-23 |  | 2016-01-29 | 1.59 | 1.6043 |  | -0.014278 |  |  | -0.014278
12.3 | Procurement of gear box and 30 KW DC motor for Pedal Feeder in CHP III | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 |  | 2015-02-23 |  | 2015-11-19 | 2016-11-23 |  | 2016-06-30 | 0.46 | 0.45847 |  | 0.0015298 |  |  | 0.0015298
12.4 | Procurement of Assembly of Impact Crusher Complete set, with Rotor Assembly and bearing Block. | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 |  | 2015-02-23 |  | 2015-03-31 | 2016-11-23 |  | 2016-01-19 | 2.3 | 2.3366 |  | -0.036571 |  |  | -0.036571
12.5 | Procurement of 10 KW Inline Magnetic Separator for CHP III | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 |  | 2015-02-23 |  | 2015-03-07 | 2016-11-23 |  | 2016-11-30 | 0.4 | 0.54718 |  | -0.14718 |  |  | -0.14718
12.6 | Restoration of RBCR by replacing feed end Spider (Drg. No. 400-1428-01/A) & Discharge end Spider (400-1428-02) suitable to rotary Bradford breaker machine No.CR/634 along with support wheels. | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 |  | 2015-02-23 |  | 2015-08-31 | 2016-11-23 |  | 2019-01-28 | 8.14 | 10.2287 |  | -2.0887 |  |  | -2.0887
12.7 | Procurement of 750 KW Impactor Motor for CHP III | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 |  | 2015-02-23 |  | 2015-04-27 | 2016-11-23 |  | 2017-02-28 | 0.49 | 0.22635 |  | 0.26365 |  |  | 0.26365
12.8 | Supply of Metal Detectors for CHP | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 |  | 2015-02-23 |  | 2015-03-07 | 2016-11-23 |  | 2016-11-30 | 0.14 | 0.09152 |  | 0.04848 |  |  | 0.04848
0 | IDC | IDC | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 |  | 2015-02-23 |  | - | - |  | - | 0.8 | 0 |  | 0.8 |  |  | 0.8
13 | Retrofitting of 6.6 kV Breakers, Battery Replacement, System Improvement & MPCB Related schemes | DPR | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 |  | 2014-12-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
13.1 | Retrofitting of 6.6 kV HT MOCB/SF6 Breakers by VCB | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 |  | 2014-12-03 |  | 2016-05-20 | 2016-12-03 |  | 2016-10-05 | 3.57 | 5.0621 |  | -1.4921 |  |  | -1.4921
13.2a | A) Procurement & Replacement of 220V/ 1285 AH Battery set for U#3 | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 |  | 2014-12-03 |  | 2017-06-17 | 2016-06-03 |  | 2017-09-30 | 1.11 | 1.0493 |  | 0.060697 |  |  | 0.060697
13.2b | B) Procurement & Replacement of 220V/ 1285 AH Battery set for U#4 | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 |  | 2014-12-03 |  | 2015-06-05 | 2016-06-03 |  | 2017-10-30 | 1.11 | 1.0047 |  | 0.10528 |  |  | 0.10528
13.3 | O2 Measurement System in the furnace & flue gas ducting | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 |  | 2014-12-03 |  | 2016-08-04 | 2015-12-03 |  | 2022-01-27 | 2.17 | 1.2966 |  | 0.87345 |  |  | 0.87345
13.4 | Supply, erection, commissioning & testing of online CO, SO2, NOX Analyser for U#3/4/5 | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 |  | 2014-12-03 |  | 2017-01-01 | 2015-12-03 |  | 2019-02-28 | 1.6511 | 1.6846 |  | -0.03346 |  |  | -0.03346
13.5 | A) Replacement of static Flame Monitoring System with Microprocessor based Flame Monitoring & Analyzing System | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 |  | 2014-12-03 |  | 2013-06-25 | 2016-03-03 |  | 2019-01-31 | 2.27 | 2.4267 |  | -0.15667 |  |  | -0.15667
13.6 | CAAQMS monitoring of ambient air quality around the NTPS. | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 |  | 2014-12-03 |  | 2012-09-11 | 2016-12-03 |  | 2015-03-31 | 1 | 0.81676 |  | 0.18324 |  |  | 0.18324
0 | IDC | IDC | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 |  | 2014-12-03 |  | - | - |  | - | 1.9 | 0 |  | 1.9 |  |  | 1.9
14 | 3rd raising of Ash bund | DPR | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 |  | 2014-12-08 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
14.1 | 3rd raising of ash bund from TBL 581.50 to 586.50m in valley No. 4A at Nashik Thermal Power Station, Eklahare | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 |  | 2014-12-08 |  | 2017-04-06 | 2016-12-08 |  | 2022-03-01 | 12.3 | 10.2142 |  | 2.0858 |  |  | 2.0858
0 | IDC | IDC | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 |  | 2014-12-08 |  | - | - |  | - | 1.6 | 0 |  | 1.6 |  |  | 1.6
15 | System Rehabilitation & Upgradation at Nasik TPS | DPR | MERC/CAPEX/ 20172018/4153 | 2017-08-31 |  | 2017-08-31 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
15.1 | Shifting, Transportation & Replacement of Existing Generator Stator of Unit no.3 | Scheme | MERC/CAPEX/ 20172018/4153 | 2017-08-31 |  | 2017-08-31 |  | 2017-01-04 | 2019-03-01 |  | WIP | 7.98 | 0.8767 |  | 7.1033 |  |  | 7.1033
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0.26397 |  | -0.26397 |  |  | -0.26397
15.2 | Turbine Supervisory Instrumentation System for Unit no.5 | Scheme | MERC/CAPEX/ 20172018/4153 | 2017-08-31 |  | 2017-08-31 |  | 2016-10-14 | 2019-03-01 |  | 2019-01-30 | 0.5542 | 0.45436 |  | 0.099841 |  |  | 0.099841
15.3 | Supply of Air Compressors for NTPS | Scheme | MERC/CAPEX/ 20172018/4153 | 2017-08-31 |  | 2017-08-31 |  | 2017-12-11 | 2019-03-01 |  | 2020-03-31 | 3.398 | 3.8197 |  | -0.42166 |  |  | -0.42166
15.4 | Replacement of Old Brass Impellers of CTLP with SS Impellers. | Scheme | MERC/CAPEX/ 20172018/4153 | 2017-08-31 |  | 2017-08-31 |  | 2018-02-23 | 2019-03-01 |  | 2021-12-01 | 1.04 | 1.1331 |  | -0.093064 |  |  | -0.093064
0 | IDC | IDC | MERC/CAPEX/ 20172018/4153 | 2017-08-31 |  | 2017-08-31 |  | - | - |  | - | 0.4 | 0 |  | 0.4 |  |  | 0.4
16 | Up-gradation of DCS at U # 3 and New Rectiformers & ESP Refurbishment of U # 4 & 5 at Nasik TPS | DPR | MERC/CAPEX/ 20172018/4791 | 2017-11-28 |  | 2017-11-28 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
16.1 | Decommissioning & Shifting of M/s ABB make DCS system at BTPS Unit # 2 & Re-commissioning with Up gradation to Symphony Plus at NTPS Unit #3, Nasik. | Scheme | MERC/CAPEX/ 20172018/4791 | 2017-11-28 |  | 2017-11-28 |  | - | 2019-02-28 |  | WIP | 9.27 | 0 |  | 9.27 |  |  | 9.27
16.2 | Erection ,Testing & commissioning, Supply of rectiformer HVR 37/800 Hermatically sealed Rectiformer ( DC Peak voltage – 70 kV , Average voltage-45 KV ,DC Current – 800 milli amp , AC I/P – 1 Phase , 415 V ) | Scheme | MERC/CAPEX/ 20172018/4791 | 2017-11-28 |  | 2017-11-28 |  | - | 2018-11-29 |  | WIP | 10.34 | 0 |  | 10.34 |  |  | 10.34
16.3 | Refurbishment of ESP for Unit No. 4 & 5 at Nashik TPS, Eklahare | Scheme | MERC/CAPEX/ 20172018/4791 | 2017-11-28 |  | 2017-11-28 |  | 2018-06-11 | 2018-11-29 |  | 2020-03-31 | 12.5 | 12.8553 |  | -0.35526 |  |  | -0.35526
0 | IDC | IDC | MERC/CAPEX/ 20172018/4791 | 2017-11-28 |  | 2017-11-28 |  | - | - |  | - | 1.69 | 0 |  | 1.69 |  |  | 1.69
17 | Replacement of drum gate, augmentation of existing ash water recovery scheme and construction of concrete road for Nasik Thermal Power Station | DPR | MERC/CAPEX/ 20172018/4753 | 2017-11-22 |  | 2017-11-22 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
17.1 | Replacement of drum gate and restructuring of cofferdam, repairs to vertical sluice gate, Approach Bridge and allied civil works at Godavari barrage at Nashik TPS Eklahare. | Scheme | MERC/CAPEX/ 20172018/4753 | 2017-11-22 |  | 2017-11-22 |  | - | 2018-11-22 |  | WIP | 6.273 | 0 |  | 6.273 |  |  | 6.273
17.2 | Augmentation of existing ash water recovery scheme and connecting overflow of waste weir to existing toe drain of ash bund valley no.4 to WWR at NTPS Eklahare. | Scheme | MERC/CAPEX/ 20172018/4753 | 2017-11-22 |  | 2017-11-22 |  | 2020-10-10 | 2018-11-22 |  | 2022-04-25 | 2.5999 | 3.1676 |  | -0.56765 |  |  | -0.56765
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0.2441 |  | -0.2441 |  |  | -0.2441
17.3 | Up gradation of fly ash concrete road from Booster Pump house toward Hydrogen plant, Dirk India Company towards Hinganwedhe along ash bund valley No. 1 & 2, Ash bund approach road for ash transportation and abundant valley towards Kotamgaon road at NTPS Eklahare. | Scheme | MERC/CAPEX/ 20172018/4753 | 2017-11-22 |  | 2017-11-22 |  | 2018-09-04 | 2018-11-22 |  | 2023-03-01 | 5.3732 | 5.3752 |  | -0.0020321 |  |  | -0.0020321
0 | IDC | IDC | MERC/CAPEX/ 20172018/4753 | 2017-11-22 |  | 2017-11-22 |  | - | - |  | - | 0.27 | 0.38455 |  | -0.11455 |  |  | -0.11455
18 | Various DPR Schemes for Renovation of colony at NTPS Eklahare | DPR | MERC/CAPEX/ 20182019/0645 | 2018-05-18 |  | 2018-05-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
18.1 | Renovation of staff quarters, playground, Jogging track & Gymnasium at NTPS colony, Eklahare | Scheme | MERC/CAPEX/ 20182019/0645 | 2018-05-18 |  | 2018-05-18 |  | 2018-11-03 | 2019-05-18 |  | 2022-04-29 | 4.071 | 3.5306 |  | 0.54044 |  |  | 0.54044
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0.92832 |  | -0.92832 |  |  | -0.92832
18.2 | Road works in NTPS Colony Eklahare | Scheme | MERC/CAPEX/ 20182019/0645 | 2018-05-18 |  | 2018-05-18 |  | 2018-12-15 | 2019-05-18 |  | 2020-11-04 | 3.9766 | 3.8972 |  | 0.079424 |  |  | 0.079424
18.3 | Water supply and sanitation works at NTPS colony Eklahare | Scheme | MERC/CAPEX/ 20182019/0645 | 2018-05-18 |  | 2018-05-18 |  | 2019-02-05 | 2019-05-18 |  | 2022-09-01 | 2.8202 | 1.4586 |  | 1.3616 |  |  | 1.3616
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0.19994 |  | -0.19994 |  |  | -0.19994
18.4 | Renovation of Workers Recreation Club at Nashik TPS Eklahare | 0 | MERC/CAPEX/ 20182019/0645 | 2018-05-18 |  | 2018-05-18 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
19 | Life enhancement of stacker cum reclaimer machine in CHP & upgradation of SWAS laboratory at Nasik TPS | DPR | MERC/CAPEX/2019-2020/0505 | 2019-08-06 |  | 2019-08-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
19.1 | Supply, Erection & installation of sole plates, Rail track & Hydraulic cylinder of the Stacker cum Reclaimer machine at Coal Handling Plant-II Nashik TPS. | Scheme | MERC/CAPEX/2019-2020/0505 | 2019-08-06 |  | 2019-08-06 |  | - | 2021-02-06 |  | - | 6.58 | 0 |  | 6.58 |  |  | 6.58
19.2 | Procurement and replacement of 220 V, 1285 AH battery set for Unit No. 4 at Nasik Thermal Power Station. | Scheme | MERC/CAPEX/2019-2020/0505 | 2019-08-06 |  | 2019-08-06 |  | 2019-06-07 | 2021-02-06 |  | 2024-03-01 | 1.39 | 1.4116 |  | -0.021562 |  |  | -0.021562
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0.2227 |  | -0.2227 |  |  | -0.2227
19.3 | Supply of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers Ltd.) at Nasik TPS. | Scheme | MERC/CAPEX/2019-2020/0505 | 2019-08-06 |  | 2019-08-06 |  | 2019-04-22 | 2021-02-06 |  | 2020-02-18 | 3.11 | 3.0812 |  | 0.028756 |  |  | 0.028756
19.4 | Erection and commissioning of Steam and Water sampling system for SWAS Lab at WTP, NTPS. | Scheme | MERC/CAPEX/2019-2020/0505 | 2019-08-06 |  | 2019-08-06 |  | - | 2021-02-06 |  | WIP | 2.23 | 0 |  | 2.23 |  |  | 2.23
19.5 | Procurement of 3 nos. of Ash Slurry Disposal pump Type D - 85 for Ash Slurry Pump House of Unit no. 3, 4 & 5 at NTPSEklahare. | Scheme | MERC/CAPEX/2019-2020/0505 | 2019-08-06 |  | 2019-08-06 |  | 2019-10-02 | 2021-02-06 |  | WIP | 0.55 | 0.55578 |  | -0.00578 |  |  | -0.00578
0 | IDC | IDC | MERC/CAPEX/2019-2020/0505 | 2019-08-06 |  | 2019-08-06 |  | - | - |  | - | 0.34 | 0 |  | 0.34 |  |  | 0.34
20 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | DPR | Yet to be approved | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
20.1 | Flue Gas Desulphurization (FGD) System at Nasik TPS | Scheme | Yet to be approved | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
0 | IDC | IDC | Yet to be approved | - |  | - |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 2 | Ash Augmentation System at Nasik & Koradi Thermal Power Station | DPR | MERC/CAP/DPR/10/08/537 | 2008-03-04 |  | 2008-03-04 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 2.1 | Ash Augmentation System at Nasik Thermal Power Station | Scheme | MERC/CAP/DPR/10/08/537 | 2008-03-04 |  | 2008-03-04 |  | - | - |  | - | 18.03 | 5.71 |  | 12.32 |  |  | 12.32
0 | IDC | IDC | MERC/CAP/DPR/10/08/537 | 2008-03-04 |  | 2008-03-04 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 3 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | DPR | MERC/CAPEX/20112012/00424 | 2011-05-19 |  | 2011-05-19 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 3.1 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | Scheme | MERC/CAPEX/20112012/00424 | 2011-05-19 |  | 2011-05-19 |  | - | - |  | - | 11.4985 | 8.47 |  | 3.0285 |  |  | 3.0285
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 6.2 | NASIK TPS (U-3 to 5) (1 Nos.) | Scheme | MERC/CAPEX/20162017/00423 | 2016-08-03 |  | 2016-08-03 |  | 2018-05-30 | 2017-11-03 |  | 2022-11-01 | 2.6515 | 2.8842 |  | -0.23269 |  |  | -0.23269
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0.76776 |  | -0.76776 |  |  | -0.76776
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 7.2 | Nashik TPS | Scheme | MERC/CAPEX/20162017/00774 | 2016-09-30 |  | 2016-09-30 |  | - | - |  | - | 3.0414 | 0 |  | 3.0414 |  |  | 3.0414
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for Nashik | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | 2021-09-01 | 1.45 | 1.7765 |  | -0.3265 |  |  | -0.3265
HO DPR 8.2 | Normal Multipurpose Fire Tender Nashik | Scheme | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | 2023-03-01 | 1.25 | 2.2272 |  | -0.9772 |  |  | -0.9772
0 | IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 |  | 2017-11-13 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | DPR | MERC/CAPEX/20172018/0177 | 2018-02-06 |  | 2018-02-06 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 10.2a | TPS Nashik | Scheme | MERC/CAPEX/20172018/0177 | 2018-02-06 |  | 2018-02-06 |  | 2018-07-31 | 2020-08-02 |  | 2021-03-01 | 2.478 | 2.3118 |  | 0.1662 |  |  | 0.1662
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | DPR | MERC/CAPEX/2019-2020/643 | 2019-08-26 |  | 2019-08-26 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 15.1 | Procurement and Replacement of Complete sets of assembly of baskets for air preheater of type tri-sector APH 27 VI(T) 74” in NTPS unit no. 4 & 5 (210MW). (2 Sets Per Unit) | Scheme | MERC/CAPEX/2019-2020/643 | 2019-08-26 |  | 2019-08-26 |  | 2019-04-23 | 2021-01-26 |  | WIP | 4.22 | 5.1153 |  | -0.89529 |  |  | -0.89529
0 | IDC | 0 | 0 | - |  | - |  | - | - |  | - | 0 | 0.13531 |  | -0.13531 |  |  | -0.13531
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 54.24 | 0 |  | 54.24 |  |  | 54.24
0 | IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 |  | 2022-02-12 |  | - | - |  | - | 2.76 | 0 |  | 2.76 |  |  | 2.76
HO DPR 17 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 0 | 0 |  | 0 |  |  | 0
HO DPR 17.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 66.009 | 0 |  | 66.009 |  |  | 66.009
0 | IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 |  | 2023-11-02 |  | - | - |  | - | 3.3 | 0 |  | 3.3 |  |  | 3.3
Formulas:
Project Start Date = [MERC Approval Date]

## F4.2
|  |  | MSPGCL: Nashik TPS | [52 empty] | DPR | Not Initiated
|  |  | MTR Petition Formats - Generation | [52 empty] | Scheme | WIP
| Project Details |  | Form 4.2: Capitalisation Plan | [18 empty] | (Rs. Crore) | [24 empty] | (Rs. Crore) | [8 empty] | IDC | Partially Capitalised
Sr. No. | Project Code | DPR | MERC Approval No. | Date of Submission | MERC Approval Date | Cost as per DPR Crs. | MERC Approved Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [12 empty] | Physical Progress (%) | [11 empty] | Capitalisation | [12 empty] | Old Asset retired against capitalised item (in Rs. Cr) | Remarks | Current Status | Non-DPR | Capitalised
[15 empty] | Actual Capex till FY 2018-19 | Actual | Actual | Actual | Actual Capex till FY 2021-22 | Actual | Actual | Revised Estimated | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Actual Progress till FY 2018-19 | Actual | Actual | Actual | Actual | Actual | Revised Estimated | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Actual Capitalization till FY 2018-19 | Actual | Actual | Actual | Actual Capitalization till FY 2021-22 | Actual | Actual | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Revised Projected | Revised Projected |  |  |  |  | Cancelled
[16 empty] | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  | FY 2019-20 | FY 2020-21 | FY 2021-22 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 |  |  |  |  | To be cancelled
[55 empty] | N.A. |  | N.A.
| A) DPR Schemes | [53 empty] | N.A. |  | To be confirmed
| (i) Submitted to MERC | [53 empty] | N.A.
1 | Essential Works at Stage I | DPR | MERC/CAPEX /20112012/01181 | 2011-03-28 | 2011-08-03 | 30.32 | 30.32 |  |  | 2011-08-03 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | Cancelled
1.1 | Essential Works at Stage I | Scheme | MERC/CAPEX /20112012/01181 | 2011-03-28 | 2011-08-03 | 30.32 | 30.32 |  |  | 2011-08-03 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | Cancelled
2 | Measuring & Monitoring of Coal consumption | DPR | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 23.0165 | 23.0165 |  |  | 2010-12-24 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
2.1 | Belt Weighers | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 0.3295 | 0.3295 |  |  | 2010-12-24 | 2009-01-01 | 2012-06-24 | 2012-07-14 | Belt wieghers results in an accurate measurement/ estimation of available stock. | 0.3295 |  |  |  | 0.3295 | [8 empty] | 100% | [11 empty] | 0.3295 |  |  |  | 0.3295 | [9 empty] | Fully Capitalized & Closed | Capitalised
2.2 | Fully automatic pit-less in motion weigh bridges | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 0.793 | 0.793 |  |  | 2010-12-24 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
2.3 | Installation of inhaul outhaul betel chargers | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 6 | 6 |  |  | 2010-12-24 | 2014-06-26 | 2012-09-24 | 2018-03-09 | Reduction in Loco working Hrs , diesel consumption & Loco maintanance also. | 8.5943 |  |  |  | 8.5943 | [8 empty] | 100% | [11 empty] | 8.5943 |  |  |  | 8.5943 | [9 empty] | Fully Capitalized & Closed | Capitalised
2.4 | Dust Extraction System | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 1.65 | 1.65 |  |  | 2010-12-24 | 2012-09-26 | 2011-12-24 | 2016-05-09 | Reduction in spreading of fine coal dust and fatigue in the area. | 1.713 |  |  |  | 1.713 | [20 empty] | 1.713 |  |  |  | 1.713 | [9 empty] | Fully Capitalized & Closed | Capitalised
2.5 | Fogging system | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 2.44 | 2.44 |  |  | 2010-12-24 | 2015-02-18 | 2012-12-24 | 2020-07-22 | Reduction in air pollution at Wagon Tippler area and fulfilled MPCB requirement | 2.2756 | 0.22009 | 0.094227 |  | 2.59 | [9 empty] | 100% | [10 empty] | 2.2756 | 0.22009 | 0.094227 |  | 2.59 | [9 empty] | Cost Over run Justification: 1) DPR is initiated by 2010 2) Estimate was prepared in 2014 & Pos were finalized in 2015, 2019 3) At the time of estimation VAT was applicable whereas at the time of PO, GST was in force. Hence, there is cost overrun. Status - Fully Capitalized & Closed | Capitalised
2.6 | Bunker level montoring system | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 0.54 | 0.54 |  |  | 2010-12-24 | 2012-08-30 | 2012-03-24 | 2012-12-15 | Gives quantitative data on the bunker leve | 0.0694 |  |  |  | 0.0694 | [20 empty] | 0.0694 |  |  |  | 0.0694 | [10 empty] | Partially Capitalised
2.7 | Rotary pneumatic or electrical hammers | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 0.169 | 0.169 |  |  | 2010-12-24 | Deferred | 2011-09-24 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
2.8 | Operating the CHP near to its full capacity | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 7.3 | 7.3 |  |  | 2010-12-24 | Deferred | 2013-09-24 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
2.9 | Motor controller | Scheme | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 0.3732 | 0.3732 |  |  | 2010-12-24 | 2010-03-23 | 2011-12-24 | 2011-05-28 | Auxiliary consumption reduced | 0.3732 |  |  |  | 0.3732 | [8 empty] | 100% | [11 empty] | 0.3732 |  |  |  | 0.3732 | [9 empty] | Fully Capitalized & Closed | Capitalised
| IDC | IDC | MERC/CAPEX/ 20112012/01775 | 2010-11-01 | 2010-12-24 | 3.4218 | 3.4218 |  |  | 2010-12-24 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
3 | Renovation & Modernization of Nasik U-3 | DPR | MERC/CAPEX/ 20112012/07 | 2011-02-09 | 2011-04-01 | 481.46 | 481.46 |  |  | 2011-04-01 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | Cancelled
3.1 | Renovation & Modernization of Nasik U-3 | Scheme | MERC/CAPEX/ 20112012/07 | 2011-02-09 | 2011-04-01 | 481.46 | 481.46 |  |  | 2011-04-01 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | Cancelled
4 | Combustion optimization & Process improvement | DPR | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 58.7761 | 58.7761 |  |  | 2010-12-22 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
4.1 | Improvement in tooling techniques Power tools like cut off machines and surface grinders. | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 0.52821 | 0.52821 |  |  | 2010-12-22 | 2012-09-03 | 2012-06-22 | Aug-14 | Downtime reduced | 0.3388 |  |  |  | 0.3388 | [20 empty] | 0.3388 |  |  |  | 0.3388 | [9 empty] | Fully Capitalized & Closed | Capitalised
4.2 | Total replacement of boiler related skin insulation as well as skin cladding of furnace, Air pre heaters,air ducts and flue gas ducts Unit-4 &5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 4.5892 | 4.5892 |  |  | 2010-12-22 | 2017-03-03 | 2011-08-22 | 2019-12-01 | Reduction in heat loss | 3.5737 | 1.1451 |  |  | 4.7188 | [20 empty] | 3.5737 | 1.1451 |  |  | 4.7188 | [9 empty] | Cost Over run Justification: After approval of DPR, proposals were initiated according to CAPEX budget allotted but rate received were higher than estimated rates due to increase in the labour rate and the rate of the consumables. Hence, there is cost overrun. Status - Fully Capitalized & Closed | Capitalised
4.3 | Painting of Boiler ,bunker structure and other structure.Unit-3,4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 7.775 | 7.775 |  |  | 2010-12-22 | Deferred | 2016-12-22 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
4.4 | Dynamic coal flow measurement and control (balancing) system (one) | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 8.14 | 8.14 |  |  | 2010-12-22 | Deferred | 2011-12-22 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
4.5 | Retrofitting of Gas proportioning dampers, flue gas, primary and secondary air dampers. (SADC) for Unit-4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 2.456 | 2.456 |  |  | 2010-12-22 | 2017-01-04 | 2011-12-22 | 2024-03-01 | Proper control of air fuel mixture in the furnace for Complete combustion. | 0.6313 | 0.49654 |  |  | 1.1278 |  | 0.1288 | [11 empty] | 100% | [6 empty] | 0.6313 | 0.49654 |  |  | 1.1278 | 0 | 0.1288 | [7 empty] | Time Over run Justification: For Unit 3, PO placed on dtd 04.09.2017.Material received on dtd 05.01.2018. After receiving the material, installation is completed in next AOH of Unit 3 on dtd 15.01.2018 For Unit 5, PO placed on dtd 07.03.2019.Material received on dtd 12.04.2019. Since January 2019, Unit 5 overhaul was not carried out due to Covid 19 pandemic. In available opportunity of short shutdown, installation is completed in Unit 5 on dtd 19.11.2023 Status - Fully Capitalized & Closed | Capitalised
| IDC | [17 empty] | 0 | 0.33475 | 0.078806 | [22 empty] | 0 | 0.33475 | 0.078806
4.6 | Replacement of flue gas ducting zone prone to erosion with 6 to 8 mm high grade material & insulation of flue gas ducts. (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 4 and 5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 4 | 4 |  |  | 2010-12-22 | Deferred | 2011-12-22 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
4.7 | Replacement of boiler outlet valves and damaged valves of units 4 & 5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 2.349 | 2.349 |  |  | 2010-12-22 | 2012-03-31 | 2012-08-22 | 2014-08-01 | Life Enhanced | 1.4313 |  |  |  | 1.4313 | [8 empty] | 100% | [11 empty] | 1.4313 |  |  |  | 1.4313 | [9 empty] | Fully Capitalized & Closed | Capitalised
4.8 | Replacement of coal pipe at direction changing sections & flow curvature zone by upgraded material. Unit-4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 2.3292 | 2.3292 |  |  | 2010-12-22 | Deferred | 2012-08-22 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
4.9 | Installation of Smart soot blower system for Unit- 4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 5.6 | 5.6 |  |  | 2010-12-22 | Deferred | 2015-12-22 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
4.10 | Installation of Sonic soot blowers for second pass for Unit-4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 0.83184 | 0.83184 |  |  | 2010-12-22 | Deferred | 2012-08-22 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
4.11 | Air pre heater upgradation of heat exchanger matrix &regenerative dynamic sealing for Unit-4,5 | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 6 | 6 |  |  | 2010-12-22 | Deferred | 2014-12-22 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
4.12 | Replacement Platen water wall for Unit-3. | Scheme | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 0.60762 | 0.60762 |  |  | 2010-12-22 | 2011-04-30 | 2012-04-22 | 2014-08-01 | Process improved | 0.6964 |  |  |  | 0.6964 | [8 empty] | 100% | [11 empty] | 0.6964 |  |  |  | 0.6964 | [9 empty] | Fully Capitalized & Closed | Capitalised
| IDC | IDC | MERC/CAPEX/ 20102011/01756 | 2010-11-21 | 2010-12-22 | 13.57 | 13.57 |  |  | 2010-12-22 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
5 | Turbine Auxiliary Consumption Improvement | DPR | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 39.2903 | 39.2903 |  |  | 2011-04-05 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
5.1 | Installation of Turbo vaned fly wheeling eco ventilators to all Units 3, 4, 5. | Scheme | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 0.09 | 0.09 |  |  | 2011-04-05 | 2010-09-18 | 2012-10-05 | Partially Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | Partially completed and balance scheme deferred | Cancelled
5.2 | Replacement of selected old brass impellers of pumps with SS304 impellers. H.T. Auxiliary C.W. Pump and G.S. Water Pumps are selected. | Scheme | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 2.4 | 2.4 |  |  | 2011-04-05 | 2010-07-07 | 2013-04-05 | 2015-12-15 | Life Enhanced | 0.8251 |  |  |  | 0.8251 | [20 empty] | 0.8251 |  |  |  | 0.8251 | [9 empty] | Fully Capitalized & Closed | Capitalised
5.3 | Improving the BFP efficiency by replacing eroded internals of pump. | Scheme | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 0.75 | 0.75 |  |  | 2011-04-05 | 2010-09-13 | 2012-10-05 | 2016-07-08 | Efficiency improved | 0.48804 |  |  |  | 0.48804 | [20 empty] | 0.48804 |  |  |  | 0.48804 | [9 empty] | Fully Capitalized & Closed | Capitalised
5.4 | Replacement of BFP (200 KHI) cartridge with energy efficient cartridge. | Scheme | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 14.4456 | 14.4456 |  |  | 2011-04-05 | 2014-09-20 | 2014-04-05 | 2022-03-31 | Efficiency improved. Availability of the pumps increased. Operational reliability increased. | 12.0834 | 0.0021771 |  | 1.7644 | 13.85 | [20 empty] | 12.0834 | 0.0021771 |  | 1.7644 | 13.85 | [9 empty] | Fully Capitalized & Closed | Capitalised
5.5 | Improving the CEP efficiency by replacing eroded internals of pump. | Scheme | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 0.9 | 0.9 |  |  | 2011-04-05 | 2014-12-09 | 2012-10-05 | 2015-03-31 | Efficiency improved | 0.6018 |  |  |  | 0.6018 | [20 empty] | 0.6018 |  |  |  | 0.6018 | [9 empty] | Fully Capitalized & Closed | Capitalised
5.6 | Replacement of CEP with energy efficient pump. | Scheme | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 2.7 | 2.7 |  |  | 2011-04-05 | Deferred | 2013-04-05 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Cancelled
5.7 | Replacement of Pumps - GS Pumps, H2Cooler booster pump, DM/DM pumps, DM Makeup pumps, Emergency lift pumps, Drip pumps, BFP Booster pumps with energy efficient pumps. | Scheme | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 4.2733 | 4.2733 |  |  | 2011-04-05 | 2007-08-22 | 2013-04-05 | 2020-04-01 | Efficiency improved | 2.3608 |  |  |  | 2.3608 | [20 empty] | 2.3608 |  |  |  | 2.3608 | [9 empty] | Only Drip Pump scheme - Deferred and other scheme capitalized & closed | Capitalised
5.8 | Replacement of valves – MS - 3 to 8 , HD – 22,23,24 , MC- 36 , ES 3,4 and BFP Recirculation Valves. | Scheme | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 3.0852 | 3.0852 |  |  | 2011-04-05 | 2006-09-06 | 2013-07-05 | 2019-06-19 | Process improved | 1.1871 | 0.12765 |  |  | 1.3148 | [20 empty] | 1.1871 | 0.12765 |  |  | 1.3148 | [9 empty] | Fully Capitalized & Closed | Capitalised
5.9 | Replacement of tube nest of LP Heater no.3 of unit no.3, LP Heater no.4 of unit no.5, Main ejector 3B, GC2 of unit no.5, Seal oil coolers, H2 Coolers, BFP working and lub oil coolers, DM/GS plate type coolers. | Scheme | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 6.5962 | 6.5962 |  |  | 2011-04-05 | 2009-09-01 | 2013-04-05 | WIP | Enhance operation reliability, Reduction in maintenance cost, Overall performance will be increased | 1.4406 |  |  |  | 1.4406 | 0 | 0 | 0.51873 | [10 empty] | 90% | [6 empty] | 1.4406 |  |  |  | 1.4406 | 0 |  | 0.51873 | [6 empty] | 1) DM/GS plate type coolers scheme - Deferred 2) H2 Coolers scheme - WIP - Draft Order (4385000767) in process 3) Other schemes - Fully Capitalized & Closed For H2 Cooler- 1) PO Placed, Material awaited. 2) Scheme will be completed & capitalized by March-25 | WIP
| IDC | [17 empty] | 0 | 0.11461 | [23 empty] | 0 | 0.11461
5.10 | Steam path audit of Unit no,4,5 | Scheme | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 0.5 | 0.5 |  |  | 2011-04-05 | Deferred | 2013-01-05 | Deferred |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | Not Initiated (To be cancelled)
| IDC | IDC | MERC/CAPEX/ 20112012/00024 | 2010-12-03 | 2011-04-05 | 3.55 | 3.55 |  |  | 2011-04-05 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
6 | EMS, Numeric relays, Microprocessor DVR & VFD | DPR | MERC/TECH-1/CAPEX/ 20132014/02001 | 2013-06-19 | 2014-01-17 | 12.57 | 12.57 |  |  | 2014-01-17 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
6.1 | Design, manufacture, supply, erection, commissioning & testing of Variable Frequency Drives (VFD) with latest design and technology super premium efficiency motors for 415 V LT Auxiliaries (Total 50 No) of 210 MW Unit 3, 4 & 5. | Scheme | MERC/TECH-1/CAPEX/ 20132014/02001 | 2013-06-19 | 2014-01-17 | 6.3 | 6.3 |  |  | 2014-01-17 | 2013-08-22 | 2013-12-01 | WIP | The auxiliary consumption of LT motors was more earlier, hence, VFDs were proposed to be commissioned to reduce auxiliary consumption. Benefits of commissioning of the VFDs: 1) This system provides digital / programmable control / monitoring and protections. 2) Process improvement, reduced auxiliary consumption 3) Motor failure rate decreases, maintenance decreases. | 1.3714 | 0.79237 |  |  | 2.1638 | 2.5255 | 2.7428 | 1.3861 | [10 empty] | 90% | [6 empty] | 1.3714 | 0.79237 |  |  | 2.1638 |  | 2.7428 | 1.3861 | [6 empty] | 1) PO Placed, Material awaited. 2) Proposal is in process 3) Scheme will be completed & capitalized by March-25 | WIP
| IDC |  |  |  |  | 0.66 | 0.66 | [11 empty] | 0 |  | 0.74645 | [22 empty] | 0 |  | 0.74645
6.2 | Replacement of old EE make Generator Protection Relays with Numerical Generator Protection Relays for unit no. 3, 4 & 5 | Scheme | MERC/TECH-1/CAPEX/ 20132014/02001 | 2013-06-19 | 2014-01-17 | 1.7 | 1.7 |  |  | 2014-01-17 | 2012-02-28 | 2013-12-01 | 2014-08-10 | Process improved | 1.7029 |  |  |  | 1.7029 | [8 empty] | 100% | [11 empty] | 1.7029 |  |  |  | 1.7029 | [9 empty] | Fully Capitalized & Closed | Capitalised
6.3 | Replacement of old AVR with Microprocessor based Digital Voltage Regulator for unit no. 3 & 5 | Scheme | MERC/TECH-1/CAPEX/ 20132014/02001 | 2013-06-19 | 2014-01-17 | 2.44 | 2.44 |  |  | 2014-01-17 | 2012-01-20 | 2013-12-01 | 2014-08-10 | Process improved | 1.7055 |  |  |  | 1.7055 | [8 empty] | 100% | [11 empty] | 1.7055 |  |  |  | 1.7055 | [9 empty] | Fully Capitalized & Closed | Capitalised
6.4 | Installation and commissioning of Energy Management System for unit no. 3, 4 & 5 | Scheme | MERC/TECH-1/CAPEX/ 20132014/02001 | 2013-06-19 | 2014-01-17 | 0.81 | 0.81 |  |  | 2014-01-17 | 2015-07-13 | 2013-12-01 | 2022-03-31 | Process improved | 0.79442 |  |  | 0.036875 | 0.8313 | [20 empty] | 0.79442 |  |  | 0.036875 | 0.8313 | [9 empty] | Cost Over run Justification: This DPR scheme was approved on dtd. 27.01.2012 which was submitted by considering budgetary offer in the year 2009-2010. This order was palced in 2015. Because of time lapse about 5 years, cost is more than estimated cost. Hence, there is cost overrun. Status - Fully Capitalized & Closed | Capitalised
| IDC | IDC | MERC/TECH-1/CAPEX/ 20132014/02001 | 2013-06-19 | 2014-01-17 | 0.66 | 0.66 |  |  | 2014-01-17 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
7 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | DPR | MERC/CAPEX/ 20122013/00149 | 2011-11-08 | 2012-05-30 | 11.95 | 11.95 |  |  | 2012-05-30 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
7.1 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | Scheme | MERC/CAPEX/ 20122013/00149 | 2011-11-08 | 2012-05-30 | 11.95 | 11.95 |  |  | 2012-05-30 | 2013-04-01 | 2014-03-01 | 2016-09-30 | Better Transportation | 14.5069 |  |  |  | 14.5069 | [8 empty] | 100% | [11 empty] | 14.5069 |  |  |  | 14.5069 | [9 empty] | Fully Capitalized & Closed | Capitalised
8 | Renovation of Rail System | DPR | MERC/CAPEX/ 20112012/02118 | 2012-11-27 | 2012-12-21 | 57.915 | 57.915 |  |  | 2012-12-21 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | Capitalised
8.1 | Renovation of Rail System | Scheme | MERC/CAPEX/ 20112012/02118 | 2012-11-27 | 2012-12-21 | 57.915 | 57.915 |  |  | 2012-12-21 |  |  |  |  | 57.9147 |  |  |  | 57.9147 | [8 empty] | 100% | [11 empty] | 57.9147 |  |  |  | 57.9147 | [10 empty] | Capitalised
9 | Faster unloading of coal wagons by upgrading existing system (Post Facto) | DPR | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-04-08 | 2013-10-04 | 18.8481 | 18.8481 |  |  | 2013-10-04 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | Capitalised
9.1 | Re-design, Supply, Erection and commissioning of modified Apron Feeder. | Scheme | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-04-08 | 2013-10-04 | 5.7219 | 5.7219 |  |  | 2013-10-04 |  |  |  | Maximum utilization of unloading stream and faster unloading of coal wagons | 5.4 |  |  |  | 5.4 | [8 empty] | 100% | [11 empty] | 5.4 |  |  |  | 5.4 | [9 empty] | Fully Capitalized & Closed | Capitalised
9.2 | Design, manufacture, supply, erection and commissioning of modified bunker outlet cone of Unit 3, 4 and 5. | Scheme | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-04-08 | 2013-10-04 | 2.3295 | 2.3295 |  |  | 2013-10-04 |  |  |  | Bunker neck choke up minimized | 2.3196 |  |  |  | 2.3196 | [8 empty] | 100% | [11 empty] | 2.3196 |  |  |  | 2.3196 | [9 empty] | Fully Capitalized & Closed | Capitalised
9.3 | Design, manufacture, Supply & Erection Of Components Suitable For Modification Of Wagon Tipplers to Handle BOXNHL , BOX-H,BOX-NR,BOX-NJLSR1 & 25 T AXLE WAGONS | Scheme | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-04-08 | 2013-10-04 | 5.1298 | 5.1298 |  |  | 2013-10-04 | 2013-04-01 | 2013-04-01 | 2014-03-01 | Handle new type of coal wagons safely and ensure railway norms & continuous unloading of coal wagons | 4.413 |  |  |  | 4.413 | [8 empty] | 100% | [11 empty] | 4.413 |  |  |  | 4.413 | [9 empty] | Fully Capitalized & Closed | Capitalised
9.4 | Procurement of SAN Loco - 650-700 HP. | Scheme | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-04-08 | 2013-10-04 | 2.8627 | 2.8627 |  |  | 2013-10-04 | 2012-10-01 | 2012-10-01 | 2013-12-01 | Availability of resources increased for coal management | 2.81 |  |  |  | 2.81 | [8 empty] | 100% | [11 empty] | 2.81 |  |  |  | 2.81 | [9 empty] | Fully Capitalized & Closed | Capitalised
9.5 | Revamping of CHP II Wagon Tippler by replacing the Split Wheel Assembly, Pawl Lever, Pinion Shaft Assembly, Toe, Spur Gear Shaft, W.T Drive Assembly, Rack Segment, Rail Table Assembly Of Wagon Tippler and Dismantling & Replacement of above parts | Scheme | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-04-08 | 2013-10-04 | 2.8042 | 2.8042 |  |  | 2013-10-04 |  |  |  | Reduced breakdowns & Wagon unloading improved | 2.81 |  |  |  | 2.81 | [8 empty] | 100% | [11 empty] | 2.81 |  |  |  | 2.81 | [9 empty] | Fully Capitalized & Closed | Capitalised
10 | Procurement of 6.6 Kv HT motors as spare motors /for replacement | DPR | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 14.3563 | 14.3563 |  |  | 2016-08-03 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
10.1 | ID FAN MOTOR (1700 kW) | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 1.3125 | 1.3125 |  |  | 2016-08-03 |  |  |  | Old HT motors which are in continuous operation from last 40-45 years fequently fail and affect running of the unit causing generation loss. Motors while in service are subjected to electrical stresses and mechanical forces which have resulted in wearing out of the parts like bearing housings, cooling fans, grease covers etc and stator core and rotor have lost original electrical properties. 2) Now , fair life of almost all motors is over & rewinded more than twice. It is necessary to replace the HT motors on priority to reduce generation loss. | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.2 | ID FAN MOTOR (1700 kW) | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 1.1025 | 1.1025 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.3 | FD FAN MOTOR 650 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.7875 | 0.7875 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.4 | FD FAN MOTOR 750 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.8505 | 0.8505 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.5 | PA FAN MOTOR 1250 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 1.029 | 1.029 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.6 | BFP MOTOR 4000 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 4.5528 | 4.5528 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.7 | C/MILL MOTOR 320 kW (3 Nos) | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 1.3356 | 1.3356 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.8 | SOP MOTOR 200 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.2276 | 0.2276 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.9 | CWP MOTOR 950 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.8942 | 0.8942 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.10 | CTLP MOTOR 710 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.8081 | 0.8081 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.11 | RWP MOTOR 335 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.4861 | 0.4861 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.12 | HP PUMP MOTOR 258 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.3083 | 0.3083 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.13 | CEP MOTOR 220 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.2629 | 0.2629 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.14 | GS PUMP MOTOR 260 kW | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.3107 | 0.3107 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
10.15 | Testing charges | Scheme | MERC/CAPEX/20152016/00422 | 2015-09-08 | 2016-08-03 | 0.088 | 0.088 |  |  | 2016-08-03 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
11 | Replacement of complete LTSH coils at Unit-3 Boiler & Economiser coils at Unit-5 Boiler | DPR | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-08-26 | 2014-10-16 | 27.44 | 27.44 |  |  | 2014-10-16 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
11.1 | Complete Supply & Erection of LTSH coils at Unit-3 210 MW Boiler (67 nos. upper and lower modules each. 01 module = 02 coils) | Scheme | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-08-26 | 2014-10-16 | 16.43 | 16.43 |  |  | 2014-10-16 | 2016-11-01 | 2016-03-01 | 2017-09-01 | Reduction in BTL | 4.6378 |  |  |  | 4.6378 | [8 empty] | 100% | [11 empty] | 4.6378 |  |  |  | 4.6378 | [9 empty] | Fully Capitalized & Closed | Capitalised
11.2 | Complete Supply & Erection of 270 nos. Economizer coils in second pass of Unit-5 210 MW Boiler at Nasik TPS. | Scheme | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-08-26 | 2014-10-16 | 9.57 | 9.57 |  |  | 2014-10-16 | 2016-11-01 | 2017-03-01 | 2019-01-01 | Reduction in BTL | 3.0104 |  |  |  | 3.0104 | [8 empty] | 100% | [11 empty] | 3.0104 |  |  |  | 3.0104 | [9 empty] | Fully Capitalized & Closed | Capitalised
| IDC | IDC | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-08-26 | 2014-10-16 | 1.44 | 1.44 |  |  | 2014-10-16 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
12 | Enhancement of performance & life of Coal Handling plant | DPR | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-01-12 | 2015-02-23 | 17.52 | 17.52 |  |  | 2015-02-23 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
12.1 | Procurement of 02 nos of 320 hp bull dozers for Nasik TPS | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-01-12 | 2015-02-23 | 3.2 | 3.2 |  |  | 2015-02-23 | 2017-08-18 | 2016-11-23 | 2017-10-01 | Availability of resources increased for coal management | 4.2044 |  |  |  | 4.2044 | [8 empty] | 100% | [11 empty] | 4.2044 |  |  |  | 4.2044 | [9 empty] | Fully Capitalized & Closed | Capitalised
12.2 | Procurement of gear box for Apron Feeder in CHP III | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-01-12 | 2015-02-23 | 1.59 | 1.59 |  |  | 2015-02-23 | 2015-07-05 | 2016-11-23 | 2016-01-29 | Smooth & continuous bunkering achieved | 1.6043 |  |  |  | 1.6043 | [8 empty] | 100% | [11 empty] | 1.6043 |  |  |  | 1.6043 | [9 empty] | Fully Capitalized & Closed | Capitalised
12.3 | Procurement of gear box and 30 KW DC motor for Pedal Feeder in CHP III | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-01-12 | 2015-02-23 | 0.46 | 0.46 |  |  | 2015-02-23 | 2015-11-19 | 2016-11-23 | 2016-06-30 | Uninterupted & proper blending of indian & imported coal | 0.45847 |  |  |  | 0.45847 | [8 empty] | 100% | [11 empty] | 0.45847 |  |  |  | 0.45847 | [9 empty] | Fully Capitalized & Closed | Capitalised
12.4 | Procurement of Assembly of Impact Crusher Complete set, with Rotor Assembly and bearing Block. | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-01-12 | 2015-02-23 | 2.3 | 2.3 |  |  | 2015-02-23 | 2015-03-31 | 2016-11-23 | 2016-01-19 | Availability improved Crushing to required size is achieved | 2.3366 |  |  |  | 2.3366 | [8 empty] | 100% | [11 empty] | 2.3366 |  |  |  | 2.3366 | [9 empty] | Fully Capitalized & Closed | Capitalised
12.5 | Procurement of 10 KW Inline Magnetic Separator for CHP III | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-01-12 | 2015-02-23 | 0.4 | 0.4 |  |  | 2015-02-23 | 2015-03-07 | 2016-11-23 | 2016-11-30 | Secondary damges reduced | 0.54718 |  |  |  | 0.54718 | [8 empty] | 100% | [11 empty] | 0.54718 |  |  |  | 0.54718 | [9 empty] | Fully Capitalized & Closed | Capitalised
12.6 | Restoration of RBCR by replacing feed end Spider (Drg. No. 400-1428-01/A) & Discharge end Spider (400-1428-02) suitable to rotary Bradford breaker machine No.CR/634 along with support wheels. | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-01-12 | 2015-02-23 | 8.14 | 8.14 |  |  | 2015-02-23 | 2015-08-31 | 2016-11-23 | 2019-01-28 | Life of crushing elelment improved, required size crush coal ensured | 10.2287 |  |  |  | 10.2287 | [8 empty] | 100% | [11 empty] | 10.2287 |  |  |  | 10.2287 | [9 empty] | Fully Capitalized & Closed | Capitalised
12.7 | Procurement of 750 KW Impactor Motor for CHP III | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-01-12 | 2015-02-23 | 0.49 | 0.49 |  |  | 2015-02-23 | 2015-04-27 | 2016-11-23 | 2017-02-28 | Downtime reduced, availability increased | 0.22635 |  |  |  | 0.22635 | [8 empty] | 100% | [11 empty] | 0.22635 |  |  |  | 0.22635 | [9 empty] | Fully Capitalized & Closed | Capitalised
12.8 | Supply of Metal Detectors for CHP | Scheme | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-01-12 | 2015-02-23 | 0.14 | 0.14 |  |  | 2015-02-23 | 2015-03-07 | 2016-11-23 | 2016-11-30 |  | 0.09152 |  |  |  | 0.09152 | [8 empty] | 100% | [11 empty] | 0.09152 |  |  |  | 0.09152 | [9 empty] | Fully Capitalized & Closed | Capitalised
| IDC | IDC | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-01-12 | 2015-02-23 | 0.8 | 0.8 |  |  | 2015-02-23 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
13 | Retrofitting of 6.6 kV Breakers, Battery Replacement, System Improvement & MPCB Related schemes | DPR | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-11-26 | 2014-12-03 | 14.7811 | 14.7811 |  |  | 2014-12-03 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
13.1 | Retrofitting of 6.6 kV HT MOCB/SF6 Breakers by VCB | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-11-26 | 2014-12-03 | 3.57 | 3.57 |  |  | 2014-12-03 | 2016-05-20 | 2016-12-03 | 2016-10-05 | The normal life of MOCB/SF6 breakers was over & it was required to switching over to latest technology. Also, MOCB production was stopped. This scheme has resulted in ease of maintenance, improved availability and increased protection to motors and equipments. The latest breakers being technologically superior to old designed breakers are more user friendly and maintenance free. The cost of maintenance and time required to repair/recondition the vacuum circuit breakers is lesser compared to the older technology. Breaker OPEN/CLOSE timing reduced, flashover minimised. | 5.0621 |  |  |  | 5.0621 | [8 empty] | 100% | [11 empty] | 5.0621 |  |  |  | 5.0621 | [9 empty] | Fully Capitalized & Closed | Capitalised
13.2a | A) Procurement & Replacement of 220V/ 1285 AH Battery set for U#3 | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-11-26 | 2014-12-03 | 1.11 | 1.11 |  |  | 2014-12-03 | 2017-06-17 | 2016-06-03 | 2017-09-30 | 1) Battery Charger are continuously in service. Batteries life depends on the charging and discharging of batteries. These chargers are responsible for batteries boost charge if required and float charge in continous condition. 2) Also the 220V, 1285AH battery are in continuous service and due to ageing effect replacement was required. After the replacement of 220V, 1285AH battery set following benefits are observed: 1) Replacing the battery has proved beneficial in view of safety protections of plant & auxilliaries. 2) Healthiness of DC source duing AC failure. | 1.0493 |  |  |  | 1.0493 | [8 empty] | 100% | [11 empty] | 1.0493 |  |  |  | 1.0493 | [9 empty] | Fully Capitalized & Closed | Capitalised
13.2b | B) Procurement & Replacement of 220V/ 1285 AH Battery set for U#4 | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-11-26 | 2014-12-03 | 1.11 | 1.11 |  |  | 2014-12-03 | 2015-06-05 | 2016-06-03 | 2017-10-30 | 1) Battery Charger are continuously in service. Batteries life depends on the charging and discharging of batteries. These chargers are responsible for batteries boost charge if required and float charge in continous condition. 2) Also the 220V, 1285AH battery are in continuous service and due to ageing effect replacement was required. After the replacement of 220V, 1285AH battery set following benefits are observed: 1) Replacing the battery has proved beneficial in view of safety protections of plant & auxilliaries. 2) Healthiness of DC source duing AC failure. | 1.0047 |  |  |  | 1.0047 | [8 empty] | 100% | [11 empty] | 1.0047 |  |  |  | 1.0047 | [9 empty] | Fully Capitalized & Closed | Capitalised
13.3 | O2 Measurement System in the furnace & flue gas ducting | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-11-26 | 2014-12-03 | 2.17 | 2.17 |  |  | 2014-12-03 | 2016-08-04 | 2015-12-03 | 2022-01-27 | Proper monitoring of O2 to reduce in Boiler losses | 1.0764 |  |  | 0.22016 | 1.2966 | [11 empty] | 100% | [8 empty] | 1.0764 |  |  | 0.22016 | 1.2966 | [9 empty] | Fully Capitalized & Closed | Capitalised
13.4 | Supply, erection, commissioning & testing of online CO, SO2, NOX Analyser for U#3/4/5 | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-11-26 | 2014-12-03 | 1.6511 | 1.6511 |  |  | 2014-12-03 | 2017-01-01 | 2015-12-03 | 2019-02-28 | Proper monitoring of gases to reduce pollution as per MPCB norms | 1.6846 |  |  |  | 1.6846 | [8 empty] | 100% | [11 empty] | 1.6846 |  |  |  | 1.6846 | [9 empty] | Fully Capitalized & Closed | Capitalised
13.5 | A) Replacement of static Flame Monitoring System with Microprocessor based Flame Monitoring & Analyzing System | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-11-26 | 2014-12-03 | 2.27 | 2.27 |  |  | 2014-12-03 | 2013-06-25 | 2016-03-03 | 2019-01-31 | Proper monitoring of fuel burning for corrective measures to avoid fuel losses | 2.4267 |  |  |  | 2.4267 | [8 empty] | 100% | [11 empty] | 2.4267 |  |  |  | 2.4267 | [9 empty] | Fully Capitalized & Closed | Capitalised
13.6 | CAAQMS monitoring of ambient air quality around the NTPS. | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-11-26 | 2014-12-03 | 1 | 1 |  |  | 2014-12-03 | 2012-09-11 | 2016-12-03 | 2015-03-31 | Since it is a statutory requirement from the MPCB, its implementation is essential to achieve MPCB norms To comply to MPCB consent and restrict the emission of hazardous pollutants within limit | 0.81676 |  |  |  | 0.81676 | [8 empty] | 100% | [11 empty] | 0.81676 |  |  |  | 0.81676 | [9 empty] | Fully Capitalized & Closed | Capitalised
| IDC | IDC | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-11-26 | 2014-12-03 | 1.9 | 1.9 |  |  | 2014-12-03 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
14 | 3rd raising of Ash bund | DPR | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-11-03 | 2014-12-08 | 13.9 | 13.9 |  |  | 2014-12-08 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
14.1 | 3rd raising of ash bund from TBL 581.50 to 586.50m in valley No. 4A at Nashik Thermal Power Station, Eklahare | Scheme | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-11-03 | 2014-12-08 | 12.3 | 12.3 |  |  | 2014-12-08 | 2017-04-06 | 2016-12-08 | 2022-03-01 | Ash bund capacity increased by 2.242 MM3 | 7.2646 | 2.6548 | -0.056127 | 0.3509 | 10.2142 | [20 empty] | 7.2646 | 2.6548 | -0.056127 | 0.3509 | 10.2142 | [9 empty] | Time Over run Justification: 1. Actual Work period- 6.08.2015 to 05.02.2017 . 2. Orignial PO 4370000651, WO amount (without tax)- Rs. 6,84,13,108/- 3. PO due variation in work order value due to excess in quantities (PO 4370002236 Date 05.10.2019- amount Rs. 2,43,35,154/- (without tax)) 4. PO due revision of rates for quanties excuted more than 125 % claimed by agency (PO 4370002802 Dt. 24.01.2022- amoumt Rs. 29,74,168/- (without tax)) . 5. Actully work is technically completed on dt. 5/02/2017, bills for quntities revision & rate revision for quantities claimed after another PO's placement. Hence, delay during exceution- nil Fully Capitalized & Closed | Capitalised
| IDC | IDC | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-11-03 | 2014-12-08 | 1.6 | 1.6 |  |  | 2014-12-08 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
15 | System Rehabilitation & Upgradation at Nasik TPS | DPR | MERC/CAPEX/ 20172018/4153 | 2017-03-21 | 2017-08-31 | 13.3722 | 13.3722 |  |  | 2017-08-31 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
15.1 | Shifting, Transportation & Replacement of Existing Generator Stator of Unit no.3 | Scheme | MERC/CAPEX/ 20172018/4153 | 2017-03-21 | 2017-08-31 | 7.98 | 7.98 |  |  | 2017-08-31 | 2017-01-04 | 2019-03-01 | WIP | 1) Unit no.3 Generator Stator of 210MW having bituminous type insulation and running from last 35-40 years and during AOH & COH leakages found in stator bars and to prevent theses leakages stator bar made dummy time to time. It is experienced that, number of leaky conductors are increasing year by year. Due to increase in dummy coils heat on other adjacent coils is increasing. 2) Further it is to mention that, NTPS brought the spare Generator Stator of 210MW from Koradi TPS of Unit no.6 which is having epoxy class F insulation and kept at NTPS premises under preservation. | 0.8767 |  |  |  | 0.8767 | 0 | 0 | [18 empty] | 0.8767 |  |  |  | 0.8767 | 0 | 0 |  | 5 | [6 empty] | WIP
| IDC | [17 empty] | 0 | 0.20198 | 0.061987 | [22 empty] | 0 | 0.20198 | 0.061987
15.2 | Turbine Supervisory Instrumentation System for Unit no.5 | Scheme | MERC/CAPEX/ 20172018/4153 | 2017-03-21 | 2017-08-31 | 0.5542 | 0.5542 |  |  | 2017-08-31 | 2016-10-14 | 2019-03-01 | 2019-01-30 | Operational Efficiency improved & Accurate Measurement by reducing Calibration time | 0.45436 |  |  |  | 0.45436 | [8 empty] | 100% | [11 empty] | 0.45436 |  |  |  | 0.45436 | [9 empty] | Fully Capitalized & Closed | Capitalised
15.3 | Supply of Air Compressors for NTPS | Scheme | MERC/CAPEX/ 20172018/4153 | 2017-03-21 | 2017-08-31 | 3.398 | 3.398 |  |  | 2017-08-31 | 2017-12-11 | 2019-03-01 | 2020-03-31 | Improved Healthiness & reliability of Air Cycle | 1.1753 | 2.6444 |  |  | 3.8197 | [20 empty] | 1.1753 | 2.6444 |  |  | 3.8197 | [9 empty] | Cost Over run Justification: 1) Estimate of proposal was prepared on the basis of budgetary offers 2.-3 yrs. before finalization of purchase order. 2) GST was applied at the time of purchase order whereas VAT was applicable at the time of estimation. Hence, then was difference in rates which resulted in cost over run. Hence, there is cost overrun. Status - Fully Capitalized & Closed | Capitalised
15.4 | Replacement of Old Brass Impellers of CTLP with SS Impellers. | Scheme | MERC/CAPEX/ 20172018/4153 | 2017-03-21 | 2017-08-31 | 1.04 | 1.04 |  |  | 2017-08-31 | 2018-02-23 | 2019-03-01 | 2021-12-01 | Improved performance and healthiness of system. | 0.40993 | 0.40993 |  | 0.3132 | 1.1331 | [20 empty] | 0.40993 | 0.40993 |  | 0.3132 | 1.1331 | [9 empty] | Cost Over run Justification: 1) Estimate was prepared in 2016 & Pos were finalized in 2018,2019 & 2021. 2) At the tiome of estimation VAT was applicable whereas at the time of PO GST was in force. Hence, there is cost overrun. Status - Fully Capitalized & Closed | Capitalised
| IDC | IDC | MERC/CAPEX/ 20172018/4153 | 2017-03-21 | 2017-08-31 | 0.4 | 0.4 |  |  | 2017-08-31 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
16 | Up-gradation of DCS at U # 3 and New Rectiformers & ESP Refurbishment of U # 4 & 5 at Nasik TPS | DPR | MERC/CAPEX/ 20172018/4791 | 2017-09-13 | 2017-11-28 | 47 | 33.8 |  |  | 2017-11-28 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
16.1 | Decommissioning & Shifting of M/s ABB make DCS system at BTPS Unit # 2 & Re-commissioning with Up gradation to Symphony Plus at NTPS Unit #3, Nasik. | Scheme | MERC/CAPEX/ 20172018/4791 | 2017-09-13 | 2017-11-28 | 9.27 | 9.27 |  |  | 2017-11-28 |  | 2019-02-28 | WIP |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | Letter No. CE/NTPS/I&C-II/DCSU-3/No. 160 dtd. 05.02.2022 sent to HO regarding cancellation of Up-gradation of DCS of Unit No.3 1) As per Dir(O) instructions - With reference to Minutes of Nashik TPS 110th ORT meeting CE/EST/154 Dtd. 19.07.2021, Point No. 12, it is instructed by Dir (O) that "The scheme to be closed" 2) DCS cards, Controllers are not in running condition since last 7 years, so their electronic components are not reliable. 3) DCS controllers are of older version and would be difficult to maintain. | WIP
16.2 | Erection ,Testing & commissioning, Supply of rectiformer HVR 37/800 Hermatically sealed Rectiformer ( DC Peak voltage – 70 kV , Average voltage-45 KV ,DC Current – 800 milli amp , AC I/P – 1 Phase , 415 V ) | Scheme | MERC/CAPEX/ 20172018/4791 | 2017-09-13 | 2017-11-28 | 22.26 | 10.34 |  |  | 2017-11-28 |  | 2018-11-29 | WIP | Existing Rectiformers have completed fair service life and have been repaired / rewound several times during this period. The Rectiformers are in deteoriorated condition with increased internal losses, deterioration etc. ESP rectiformer to HFTR replacement of Unit- 4 & 5 in phase manner is to be done for the following benefits: 1) Increase in efficiency of ESP, reliability of ESP and fly ash collection. 2) Minimization of environmental degradation upto considerable level. | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 |  |  |  | 13 | [6 empty] | WIP
16.3 | Refurbishment of ESP for Unit No. 4 & 5 at Nashik TPS, Eklahare | Scheme | MERC/CAPEX/ 20172018/4791 | 2017-09-13 | 2017-11-28 | 12.51 | 12.5 |  |  | 2017-11-28 | 2018-06-11 | 2018-11-29 | 2020-03-31 | ESP performance improved & control in stack emmission | 6.0998 | 6.7555 |  |  | 12.8553 | [20 empty] | 6.0998 | 6.7555 |  |  | 12.8553 | [9 empty] | Cost Over run Justification: 1) After approval of DPR, proposals were initiated according to CAPEX budget allotted & Pos were finalised after 2-3 years. 2) As the rates received were higher than estimated rates due to increase in the labour rate and the rate of the supply itmes. Hence, there is cost overrun. Status - Fully Capitalized & Closed | Capitalised
| IDC | IDC | MERC/CAPEX/ 20172018/4791 | 2017-09-13 | 2017-11-28 | 2.96 | 1.69 |  |  | 2017-11-28 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
17 | Replacement of drum gate, augmentation of existing ash water recovery scheme and construction of concrete road for Nasik Thermal Power Station | DPR | MERC/CAPEX/ 20172018/4753 | 2017-10-03 | 2017-11-22 | 14.5161 | 14.5161 |  |  | 2017-11-22 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
17.1 | Replacement of drum gate and restructuring of cofferdam, repairs to vertical sluice gate, Approach Bridge and allied civil works at Godavari barrage at Nashik TPS Eklahare. | Scheme | MERC/CAPEX/ 20172018/4753 | 2017-10-03 | 2017-11-22 | 6.273 | 6.273 |  |  | 2017-11-22 |  | 2018-11-22 | WIP | Old barrage gate structure istotally corroded / beyond repaire. Hence it is necessary to carryout the replacement work for making arrangement of watert storage which is required for Nashi TPS. | 0 |  |  |  | 0 |  |  | 3 | [17 empty] | 0 |  |  |  | 0 | 0 |  | 3 | 3.27 | [5 empty] | After finalization of MoU, Agreement executed between MSPGCL & WRD on dtd. 15.09.2023. Tender will be prepared by WRD & PO will be place by NTPS As per Letter No. CGEU5Nsk/TPS-1/Eklahare/1 of 24/355 of 2024 DATE 05/03/2024 received from WRD – Technical work is in progress by WRD. | WIP
17.2 | Augmentation of existing ash water recovery scheme and connecting overflow of waste weir to existing toe drain of ash bund valley no.4 to WWR at NTPS Eklahare. | Scheme | MERC/CAPEX/ 20172018/4753 | 2017-10-03 | 2017-11-22 | 2.5999 | 2.5999 |  |  | 2017-11-22 | 2020-10-10 | 2018-11-22 | 2022-04-25 | Increased recovery of ash water | 0 |  | 1.5861 | 1.5815 | 3.1676 | 0 | [11 empty] | 100% | [7 empty] | 0 |  |  | 3.1676 | 3.1676 | 0 | [8 empty] | Time Overrun Justifications - Time laps between Tender process Cost Overrun Justifications - Vendor quoted 11% above estimated cost Status - Fully Capitalized & Closed | Capitalised
| IDC | [17 empty] | 0 | 0.2441 | [23 empty] | 0 | 0.2441
17.3 | Up gradation of fly ash concrete road from Booster Pump house toward Hydrogen plant, Dirk India Company towards Hinganwedhe along ash bund valley No. 1 & 2, Ash bund approach road for ash transportation and abundant valley towards Kotamgaon road at NTPS Eklahare. | Scheme | MERC/CAPEX/ 20172018/4753 | 2017-10-03 | 2017-11-22 | 5.3732 | 5.3732 |  |  | 2017-11-22 | 2018-09-04 | 2018-11-22 | 2023-03-01 | 01. Increase smootth movement of vehicles of colony residents and employees also decreases accidents. 02. Increases smooth movement of ash vehicles. | 0.72542 | 3.6205 | 1.0293 |  | 5.3752 | 0 | [11 empty] | 100% | [7 empty] | 0 | 4.3459 | 1.0293 |  | 5.3752 | 0 | [8 empty] | Time Overrun Justifications - 1.Time laps between Tender process 2. delay due to the half width of road was executed and the other half was utilized by the running traffic 3. The rainfall and cyclone situation during sept to oct -19 4.Election program of Loksabha in the month of March-2019 & State Assembly election in the month of Oct-2019 ( 80 days delay i.e. 20.01.2020 to 7.03.2020) Cost Overrun Justifications - Cost PV = Rs. 0.3845536 Cr. Status - Fully Capitalized & Closed Work period- 22.10.2018 to 07.03.2020 | Capitalised
| IDC | IDC | MERC/CAPEX/ 20172018/4753 | 2017-10-03 | 2017-11-22 | 0.27 | 0.27 |  |  | 2017-11-22 | [8 empty] | 0 | 0.38455 | [23 empty] | 0 | 0.38455 | [9 empty] | N.A.
18 | Various DPR Schemes for Renovation of colony at NTPS Eklahare | DPR | MERC/CAPEX/ 20182019/0645 | 2018-03-13 | 2018-05-18 | 12.1422 | 10.8678 |  |  | 2018-05-18 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
18.1 | Renovation of staff quarters, playground, Jogging track & Gymnasium at NTPS colony, Eklahare | Scheme | MERC/CAPEX/ 20182019/0645 | 2018-03-13 | 2018-05-18 | 4.4604 | 4.071 |  |  | 2018-05-18 | 2018-11-03 | 2019-05-18 | 2022-04-29 | 1) Asthetic view and safety of building increases. 2) Decrease of slab leakages of residential quarters and also inhance life of buildings. | 0.5521 | 2.6823 | 0.019018 | 0.27719 | 3.5306 | [20 empty] | 0 | 2.6823 |  | 0.84831 | 3.5306 | 0 | [8 empty] | Time Overrun Justifications - 1. PO 4370001685, 1685 Dt. 3.11.18 ( 26.12.19 to 25.06.19), 2. PO 4370002081 Dt. 22.04.19 ( 1.08.19 to 30.11.19 ), 3. PO 4370001688 Dt. 17.11.18 ( 26.12.19 to 25.06.19), 4. PO 4370002016 ( 24.02.20 to 2.12.21 ) { 4th PO delay period 466 days) Reson for delay- time to time lock down declared by central govt & state Govt Cost Overrun Justifications - Status - Fully Capitalized & Closed | Capitalised
| IDC | [17 empty] | 0 | 0.92832 | [23 empty] | 0 | 0.92832
18.2 | Road works in NTPS Colony Eklahare | Scheme | MERC/CAPEX/ 20182019/0645 | 2018-03-13 | 2018-05-18 | 3.9766 | 3.9766 |  |  | 2018-05-18 | 2018-12-15 | 2019-05-18 | 2020-11-04 | Avoided accidents and smooth movement of colony residents vehicles | 0 | 3.5679 | 0.32928 |  | 3.8972 | [20 empty] | 0 | 3.5679 | 0.32928 |  | 3.8972 | [9 empty] | Fully Capitalized & Closed | Capitalised
18.3 | Water supply and sanitation works at NTPS colony Eklahare | Scheme | MERC/CAPEX/ 20182019/0645 | 2018-03-13 | 2018-05-18 | 2.8202 | 2.8202 |  |  | 2018-05-18 | 2019-02-05 | 2019-05-18 | 2022-09-01 | 1) Provided potable drinking water to remaining residential quarter. 2) STP water recovery increase and avoid frequent chokeups through main line. | 0 | 1.1321 | 0.32648 |  | 1.4586 | [12 empty] | 100% | [7 empty] | 0 | 1.1321 | 0.32648 |  | 1.4586 | 0 | [8 empty] | Time Overrun Justifications - 1. 4370001819 Dt. 5.02.19 ( time period -20.03.19 to 19.09.19 ) 2. 4370002008 ( time -10.12.19 to 9.06.20 ) - 2nd PO about70 % excuted ( due to excessive detoriated bldg, work for said bldg not excuted) 3. PO 437 0001813 Dt. 11.02.2019 ( work cancelled during covid period only payment of 1.61 lac design charges paid, accordingly proposal sent to HO approval, no delay Status - Fully Capitalized & Closed | Capitalised
| IDC | [17 empty] | 0 | 0.19994 | [23 empty] | 0 | 0.19994
18.4 | Renovation of Workers Recreation Club at Nashik TPS Eklahare |  | MERC/CAPEX/ 20182019/0645 | 2018-03-13 | 2018-05-18 | 0.885 | 0 | [11 empty] | 0 | [24 empty] | 0 | [10 empty] | Cancelled
19 | Life enhancement of stacker cum reclaimer machine in CHP & upgradation of SWAS laboratory at Nasik TPS | DPR | MERC/CAPEX/2019-2020/0505 | 2019-05-02 | 2019-08-06 | 14.2 | 14.2 |  |  | 2019-08-06 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
19.1 | Supply, Erection & installation of sole plates, Rail track & Hydraulic cylinder of the Stacker cum Reclaimer machine at Coal Handling Plant-II Nashik TPS. | Scheme | MERC/CAPEX/2019-2020/0505 | 2017-01-10 | 2019-08-06 | 6.58 | 6.58 |  |  | 2019-08-06 |  | 2021-02-06 |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [9 empty] | NTPS Letter No.CE/NTPS/CHP/01368 dtd 24.11.2022 sent to HO regarding cancellation of this scheme. | Not Initiated
19.2 | Procurement and replacement of 220 V, 1285 AH battery set for Unit No. 4 at Nasik Thermal Power Station. | Scheme | MERC/CAPEX/2019-2020/0505 | 2017-01-11 | 2019-08-06 | 1.39 | 1.39 |  |  | 2019-08-06 | 2019-06-07 | 2021-02-06 | 2024-03-01 | Healthiness of DC source duing AC failure | 0 |  |  | 1.3596 | 1.3596 | 0 | 0.05192 | [11 empty] | 100% | [6 empty] | 0 |  |  | 1.3596 | 1.3596 | 0 | 0.05192 | [7 empty] | Time Overrun Justifications - Due to Covid-19, deviations and extension, the proposal was delayed. And, due to unavailability of Overhaul schedule installation of 220V battery set was delayed. Cost Overrun Justifications - The PR was prepared in 07.06.2019, and the PO was placed on 23.09.2021. Hence, the Vendor might have quoted 3.4% above estimated rates. Status - Fully Capitalized & Closed | Capitalised
| IDC | [17 empty] | 0 | 0.11272 | 0.10998 | [22 empty] | 0 | 0.11272 | 0.10998
19.3 | Supply of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers Ltd.) at Nasik TPS. | Scheme | MERC/CAPEX/2019-2020/0505 | 2017-01-12 | 2019-08-06 | 3.11 | 3.11 |  |  | 2019-08-06 | 2019-04-22 | 2021-02-06 | 2020-02-18 | 1) Improved Efficiency. 2) Better Reliability. 3) Less Maintenance. 4) Less Spares Consumption. | 0 | 3.0812 |  |  | 3.0812 | [20 empty] | 0 | 3.0812 |  |  | 3.0812 | [9 empty] | Fully Capitalized & Closed | Capitalised
19.4 | Erection and commissioning of Steam and Water sampling system for SWAS Lab at WTP, NTPS. | Scheme | MERC/CAPEX/2019-2020/0505 | 2017-01-13 | 2019-08-06 | 2.23 | 2.23 |  |  | 2019-08-06 |  | 2021-02-06 | WIP |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 |  |  |  | 3 | [5 empty] | Against this scheme, new scheme will be intiated by HO (Suptg. Chemist) | Not Initiated
19.5 | Procurement of 3 nos. of Ash Slurry Disposal pump Type D - 85 for Ash Slurry Pump House of Unit no. 3, 4 & 5 at NTPSEklahare. | Scheme | MERC/CAPEX/2019-2020/0505 | 2017-01-14 | 2019-08-06 | 0.55 | 0.55 |  |  | 2019-08-06 | 2019-10-02 | 2021-02-06 | WIP | 1. Improvement in ESP & Ash Evacuation system 2.Reduction in maintenece cost & time. | 0 |  |  |  | 0 | 0 | 0.55578 | [18 empty] | 0 |  |  |  | 0 |  |  | 0.51878 | [6 empty] | Scheme completed & capitalized | Capitalised
| IDC | IDC | MERC/CAPEX/2019-2020/0505 | 2017-01-15 | 2019-08-06 | 0.34 | 0.34 |  |  | 2019-08-06 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
20 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | DPR | Yet to be approved | 2021-02-26 |  | 113.32 | 0 |  |  | - | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
20.1 | Flue Gas Desulphurization (FGD) System at Nasik TPS | Scheme | Yet to be approved | 2021-02-26 | - | 108.19 |  |  |  | - | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | Not Initiated
| IDC | IDC | Yet to be approved | 2021-02-26 | - | 5.13 |  |  |  | - | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 2 | Ash Augmentation System at Nasik & Koradi Thermal Power Station | DPR | MERC/CAP/DPR/10/08/537 | 2007-07-31 | 2008-03-04 | 18.03 | 18.03 |  |  | 2008-03-04 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 2.1 | Ash Augmentation System at Nasik Thermal Power Station | Scheme | MERC/CAP/DPR/10/08/537 | 2007-07-31 | 2008-03-04 | 18.03 | 18.03 |  |  | 2008-03-04 |  |  |  |  | 5.71 |  |  |  | 5.71 | [8 empty] | 100% | [11 empty] | 5.71 |  |  |  | 5.71 | [10 empty] | Capitalised
| IDC | IDC | MERC/CAP/DPR/10/08/537 | 2007-07-31 | 2008-03-04 |  |  |  |  | 2008-03-04 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 3 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | DPR | MERC/CAPEX/20112012/00424 | 2007-09-28 | 2011-05-19 | 11.4985 | 11.4985 |  |  | 2011-05-19 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 3.1 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | Scheme | MERC/CAPEX/20112012/00424 | 2007-09-28 | 2011-05-19 | 11.4985 | 11.4985 |  |  | 2011-05-19 |  |  |  |  | 8.47 |  |  |  | 8.47 | [20 empty] | 8.47 |  |  |  | 8.47 | [10 empty] | Capitalised
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | DPR | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 2.6515 | 2.6515 |  |  | 2016-08-03 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 6.2 | NASIK TPS (U-3 to 5) (1 Nos.) | Scheme | MERC/CAPEX/20162017/00423 | 2016-02-03 | 2016-08-03 | 2.6515 | 2.6515 |  |  | 2016-08-03 | 2018-05-30 | 2017-11-03 | 2022-11-01 | As it is monitoring service benefits in quantified terms can not be given but CAAQMS monitoring is satutary requirement of MPCB & CPCB and its connectivity is compulsory to MPCB & CPCB server. As it is 24/7 online monitoring of AAQ corrective actions for the emmission can be taken immediately | 0 |  | 2.8152 |  | 2.8152 | 0.069 | [11 empty] | 100% | [7 empty] | 0 |  | 2.8152 |  | 2.8152 | 0.069 | [8 empty] | Fully Capitalized & Closed | Capitalised
| IDC | [17 empty] | 0 | 0.76776 | [23 empty] | 0 | 0.76776
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | DPR | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 3.0414 | 3.0414 |  |  | 2016-09-30 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 7.2 | Nashik TPS | Scheme | MERC/CAPEX/20162017/00774 | 2016-08-26 | 2016-09-30 | 3.0414 | 3.0414 |  |  | 2016-09-30 |  |  |  |  | 0 |  |  |  | 0 | [20 empty] | 0 |  |  |  | 0 | [10 empty] | WIP
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | DPR | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 2.7 | 2.7 |  |  | 2017-11-13 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 8.1 | Advance Multipurpose Fire Tender for Nashik | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 1.45 | 1.45 |  |  | 2017-11-13 |  |  | 2021-09-01 | 1) Speed of Fire Tende is good so crew reaching on Incident spot quicky 2) Automatic operated Sensors installed in both side hose reels sets so wound easily. 3) Multipurpose Water monitor installed on Fire Tender so getting perfect water spray jet at high rase. (Max. Ht 90 ft) 4)Multipurpose Hand operated foam guns installed on Fire Tender which tackle oil fire fastly with perfect concertration. 5) Equipped with modern and automatic fire fighting eqpuiments handling emergency situation very quickly | 0 |  |  | 1.7765 | 1.7765 | [20 empty] | 0 |  |  | 1.7765 | 1.7765 | [9 empty] | Fully Capitalized & Closed | Capitalised
HO DPR 8.2 | Normal Multipurpose Fire Tender Nashik | Scheme | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 | 1.25 | 1.25 |  |  | 2017-11-13 |  |  | 2023-03-01 | 1) Fie Tender equipped with automatic transmission gear box (no clutch) so getting high spped and crew reaching on incident site very quickly. 2) Equipped with 6000 ltr wtaer and 750 ltrfoam tank capacity so tackle with fire easily. 3) Multipurpose water monitor installed on Tender getting perfect water jet and spray. 4) LHS & RHS automatic operated hose reels with hand guns tackle any emergency situation quickly due to which less manpower is required. 5) 500 kg DCP tank installed on Fire Tener with hand operated DCP gun easily tackle any Trxn. Fire or oil fire. 6) Equipped with ultra Modern fire fighting equipments handling emergency situation quickly. | 0 | 0.042551 |  |  | 0.042551 | 2.1847 | [11 empty] | 100% | [7 empty] | 0 | 0.042551 |  |  | 0.042551 | 2.1847 | [8 empty] | Fully Capitalized & Closed | Capitalised
| IDC | IDC | MERC/CAPEX/20172018/4653 | 2017-04-19 | 2017-11-13 |  |  |  |  | 2017-11-13 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | DPR | MERC/CAPEX/20172018/0177 | 2018-01-12 | 2018-02-06 | 2.478 | 2.478 |  |  | 2018-02-06 | [8 empty] | 0 | [24 empty] | 0 | [10 empty] | N.A.
HO DPR 10.2a | TPS Nashik | Scheme | MERC/CAPEX/20172018/0177 | 2018-01-12 | 2018-02-06 | 2.478 | 2.478 |  |  | 2018-02-06 | 2018-07-31 | 2020-08-02 | 2021-03-01 | Work completed as per IB recommandations and increases safety and security. | 0.48185 | 1.4198 | 0.41013 |  | 2.3118 | [20 empty] | 0 | 1.9017 | 0.41013 |  | 2.3118 | [9 empty] | Fully Capitalized & Closed | Capitalised
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | DPR | MERC/CAPEX/2019-2020/643 | 2019-01-19 | 2019-08-26 | 4.22 | 4.22 |  |  | 2019-08-26 | [8 empty] | 0 | [24 empty] | 0
HO DPR 15.1 | Procurement and Replacement of Complete sets of assembly of baskets for air preheater of type tri-sector APH 27 VI(T) 74” in NTPS unit no. 4 & 5 (210MW). (2 Sets Per Unit) | Scheme | MERC/CAPEX/2019-2020/643 | 2019-01-19 | 2019-08-26 | 4.22 | 4.22 |  |  | 2019-08-26 | 2019-04-23 | 2021-01-26 | WIP | Air Heater Flue gas outlet temp. reduced to optimum level. so boiler efficency increased . | 0 | 1.9491 | 0.037711 |  | 1.9868 | 0.54994 | 2.5785 | 0.4776 | [17 empty] | 0 | 1.9491 | 0.037711 |  | 1.9868 | 0.54994 | 0 | 3.0561 | [6 empty] | 1) Installed during COH of Unit No.5 (Sept-Oct 2024) 2) Will by capitalized by March-25 | WIP
| IDC | [17 empty] | 0 |  | 0.13531 | [22 empty] | 0 |  | 0.13531
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | DPR | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 113.91 | 57 |  |  | 2022-02-12 | [8 empty] | 0 | [24 empty] | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | Scheme | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 108.48 | 54.24 |  |  | 2022-02-12 | [8 empty] | 0 | [24 empty] | 0
| IDC | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2018-08-31 | 2022-02-12 | 5.43 | 2.76 |  |  | 2022-02-12 | [8 empty] | 0 | [24 empty] | 0
HO DPR 17 | Centralized Monitoring Solution | DPR | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 69.309 | 69.309 |  |  | 2023-11-02 | [8 empty] | 0 | [24 empty] | 0
HO DPR 17.1 | Centralized Monitoring Solution | Scheme | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 66.009 | 66.009 |  |  | 2023-11-02 | [8 empty] | 0 | [24 empty] | 0
| IDC | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-03-28 | 2023-11-02 | 3.3 | 3.3 |  |  | 2023-11-02 | [8 empty] | 0 | [24 empty] | 0
| (ii) Yet to be submitted to MERC | [17 empty] | 0 | [24 empty] | 0
| <DPR Name> |  | N.A. |  | N.A. | [13 empty] | 0 | [24 empty] | 0
DPR 1 | Complete Replacement of HRH Coils, LTSH Coils, Economizer Coils at Unit No. 4 & Complete Replacement of Economizer coils at Unit No.3 Nashik TPS 210 MW Boilers |  |  |  |  | 31.11 | [12 empty] | 0 | [24 empty] | 0 | [9 empty] | BR approved as per Letter No. CE/Works/CAPEX/ NTPS/ DPR/U3&4/FY 23-24/ Coils/2300 dtd.27.02.2024
1 | Complete Replacement HRH Coils at NTPS Unit No. 4 Boiler |  |  |  |  | 8.83 | [7 empty] | Proposed coils are due for replacement. Coil erosion was observed in Overhaul. Also, BTL occured in this zone.Hence it is need to be replaced. |  |  |  |  | 0 |  |  |  | 6.84 | 1.711 | [19 empty] | 0 |  |  |  | 6.84 | 1.711
2 | Complete Replacement LTSH Coils at NTPS Unit No. 4 Boiler |  |  |  |  | 10.33 | [7 empty] | Proposed coils are due for replacement. Coil erosion was observed in Overhaul. Also, BTL occured in this zone.Hence it is need to be replaced. |  |  |  |  | 0 |  |  |  | 10.7498 | 1.911 | [19 empty] | 0 |  |  |  | 10.7498 | 1.911
3 | Complete Replacement Economiser Coils at NTPS Unit No. 3 & 4 Boilers |  |  |  |  | 10.17 | [7 empty] | Proposed coils are due for replacement. Coil erosion was observed in Overhaul. Also, BTL occured in this zone.Hence it is need to be replaced. |  |  |  |  | 0 |  |  |  | 13.66 | 1.2036 | 1.2036 | [18 empty] | 0 |  |  |  | 13.66 | 1.2036 | 1.2036
| IDC |  |  |  |  | 1.78 | [12 empty] | 0 | [24 empty] | 0
DPR 2 | Pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 and Commissioning of AFGC system for Unit No. 3, 4 & 5 and Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5 at Nashik TPS |  |  |  |  | 28.4239 | [12 empty] | 0 | [24 empty] | 0 | [9 empty] | DPR is submitted to HO vide Letter No. CE/NTPS/MPD/DPR/No. 01866 dtd 03.11.2023 Re-arranged DPR as per MERC Capex format sent to HO -Works on dtd.01.05.2024
1 | Supply of MSERW pipes for Replacement of various pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 at NTPS, Eklahare |  |  |  |  | 19.6769 | [7 empty] | Target of Zero leakage of water will be achieved.Work of Maintenance / repair / rotation of pipelines will be reduced. hence replacement cost, procurement cost & manpower charges will be saved. Environment pollution due to leakage of ash slurry through pipelines will be reduced. Due to structure strengthening, risk of accident will be reduced. |  |  |  |  | 0 |  |  |  | 16.1949 | 3.482 | [19 empty] | 0 |  |  |  | 16.1949 | 3.482
2 | Supply, erection, commissioning & testing of Ammonia Flue gas Conditioning system for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare |  |  |  |  | 3.9046 | [7 empty] | To improve working efficiency of ESP and to maintain emission levels within the limits stipulated by MPCB. |  |  |  |  | 0 |  |  |  | 3.9046 | [20 empty] | 0 |  |  |  | 3.9046
3 | Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5, 210 MW, NTPS, Eklahare, Nasik. |  |  |  |  | 2.9741 | [7 empty] | 1. Fast & precise operation 2. Low failure rate 3. Low operating cost 4. Low maintenance cost 5.Fails safe condition 6. Easy Manual / Auto operation at local |  |  |  |  | 0 |  |  |  | 2.9741 | [20 empty] | 0 |  |  |  | 2.9741
DPR 3 | Complete replacement of Platen Superheater coils at Unit No.3,4 & 5 ; Complete replacement of HRH coils at Unit No.3,& 5; Complete replacement of LTSH coils at Unit No. 5;Replacement of thermal insulation at Boiler for Nashik TPS 210 MW boilers |  |  |  |  | 57.2898 | [12 empty] | 0 | [24 empty] | 0
1 | Complete replacement of Platen Superheater coils at Unit No. 3,4 & 5 |  |  |  |  | 17.99 | [7 empty] | Proposed coils are due for replacement. Coil erosion & misalignment was observed in Overhaul. Also, BTL occured in this zone.Hence it is need to be replaced. |  |  |  |  | 0 |  |  |  | 13.82 | 1.39 | 1.39 | 1.39 | [17 empty] | 0 |  |  |  | 13.82 | 1.39 | 1.39 | 1.39
2 | Complete replacement of HRH coils at Unit No.3,& 5 |  |  |  |  | 17.102 | [7 empty] | Proposed coils are due for replacement. Coil erosion was observed in Overhaul. Also, BTL occured in this zone.Hence it is need to be replaced. |  |  |  |  | 0 |  |  |  | 13.68 | 1.711 |  | 1.711 | [17 empty] | 0 |  |  |  | 13.68 | 1.711 |  | 1.711
3 | Complete replacement of LTSH coils at Unit No.5 |  |  |  |  | 12.6608 | [7 empty] | Proposed coils are due for replacement. Coil erosion was observed in Overhaul. Also, BTL occured in this zone.Hence it is need to be replaced. |  |  |  |  | 0 |  |  |  | 10.7498 |  |  | 1.911 | [17 empty] | 0 |  |  |  | 10.7498 |  |  | 1.911
4 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines at Unit No.3,4 & 5 |  |  |  |  | 9.537 | [7 empty] | Reduction in heat loss |  |  |  |  | 0 |  |  |  | 1.617 | 2.64 | 2.64 | 2.64 | [17 empty] | 0 |  |  |  | 1.617 | 2.64 | 2.64 | 2.64
DPR 4 | Procurement of various pumps for TM & ODP |  |  |  |  | 42.39 | [12 empty] | 0 | [24 empty] | 0
1 | Procurement and Erection Commissioning of Condenser vacuum pump for Unit No. 3 ,4 & 5 at Nashik TPS, Eklahare |  |  |  |  | 29.24 | [7 empty] | 1. At present the performance of main ejectors are poor, after overhauling the same. 2. For vacuum pump, the steam required in the ejector will be eliminated. 3. Improvement in the heat rate gain. 4. Overall cycle efficiency will improve. 5. The rated condenser vacuum can be maintained. |  |  |  |  | 0 |  |  |  | 29.24 | [20 empty] | 0 |  |  |  | 29.24
2 | Procurement of Three Pump assemblies of SAM TURBO makes Type 150/500 N for Booster Pump house at NTPS Eklahare. |  |  |  |  | 0.8 | [7 empty] | To improve efficiency & availability of booster pumps & ash evacuation system. |  |  |  |  | 0 |  |  |  | 0.8 | [20 empty] | 0 |  |  |  | 0.8
3 | Procurement of 3 Nos Vertical Fly Ash Transfer Pump VO 150 /400 + ARS SAM make along with motor for ESP Hopper evacuation of Unit No.3,4 & 5 at NTPS Eklahare |  |  |  |  | 0.79 | [7 empty] | To improve efficiency & availability of ash evacuation system. |  |  |  |  | 0 |  |  |  | 0.79 | [20 empty] | 0 |  |  |  | 0.79
4 | Supply, erection, installation, civil foundation, commissioning, testing & trial of Rotating &casing assembly of pumps for WTP at Nashik TPS, Eklahare |  |  |  |  | 1.6 | [7 empty] | To improve efficiency of CWFW pumps, degasser pumps & prine injection pump system. |  |  |  |  | 0 |  |  |  |  | 1.6 | [19 empty] | 0 |  |  |  |  | 1.6
5 | Procurement (10 nos.) of CWFW pumps (with motor) at Stage-II (Beacon make) |  |  |  |  | 0.94 | [7 empty] | To improve efficiency & availability of CWFW pump system. |  |  |  |  | 0 |  |  |  |  | 0.94 | [19 empty] | 0 |  |  |  |  | 0.94
6 | Procurement of RWP Pump assembly at NTPS. |  |  |  |  | 1 | [7 empty] | To improve efficiency & availability of river water pump system. |  |  |  |  | 0 |  |  |  |  | 1 | [19 empty] | 0 |  |  |  |  | 1
7 | Procurement of Cooling Tower lift Pump Impeller for Jyoti make pump Type:-1200- VMI A 12 at NTPS Eklahare |  |  |  |  | 1.07 | [7 empty] | To improve efficiency & availability of Cooling Tower lift Pumps. |  |  |  |  | 0 |  |  |  |  | 1.07 | [19 empty] | 0 |  |  |  |  | 1.07
8 | Procurement of Degasser Pump assembly with motor (06 Nos.) |  |  |  |  | 0.354 | [7 empty] | To improve efficiency & availability of degasser Pumps. |  |  |  |  | 0 |  |  |  |  | 0.354 | [19 empty] | 0 |  |  |  |  | 0.354
9 | Procurement of 8 Nos. of Domestic water pumps (with motor) & Darna drinking water pump at Stage-I & II |  |  |  |  | 0.6 | [7 empty] | To improve efficiency & availability of Domestic water pumps & Darna drinking water pumps |  |  |  |  | 0 | [5 empty] | 0.6 | [18 empty] | 0 | [5 empty] | 0.6
10 | Procurement of 4 Nos. of DM backwash (2 Nos.) & CW backwash pump (2 Nos.)(with motor)at NTPS. |  |  |  |  | 0.36 | [7 empty] | To improve efficiency & availability of DM backwash & CW backwash pumps. |  |  |  |  | 0 | [5 empty] | 0.36 | [18 empty] | 0 | [5 empty] | 0.36
11 | Procurement of 4 Nos. of HP Pumps at NTPS. |  |  |  |  | 1.18 | [7 empty] | To improve efficiency & availability of HP pumps & ash evacuation system. |  |  |  |  | 0 | [5 empty] | 1.18 | [18 empty] | 0 | [5 empty] | 1.18
12 | Procurement of ETP pump assembly (06 Nos.) |  |  |  |  | 1.42 | [7 empty] | To improve efficiency & availability of ETP pumps. |  |  |  |  | 0 | [5 empty] | 1.42 | [18 empty] | 0 | [5 empty] | 1.42
13 | Procurement of RWP shaft with bearing, Impeller (02 Nos.) |  |  |  |  | 1.68 | [7 empty] | To improve efficiency & availability of RWP pumps. |  |  |  |  | 0 | [5 empty] | 1.68 | [18 empty] | 0 | [5 empty] | 1.68
14 | Procurement of AWR pump (02 Nos.) |  |  |  |  | 0.47 | [7 empty] | To improve efficiency & availability of AWR pumps. |  |  |  |  | 0 | [5 empty] | 0.47 | [18 empty] | 0 | [5 empty] | 0.47
15 | Procurement of Submersible Slurry Pumps for handling Ash water / Clear water for dewatering at various locations at NTPS (10 Nos.) |  |  |  |  | 0.885 | [7 empty] | To minimize water loss |  |  |  |  | 0 | [5 empty] | 0.885 | [18 empty] | 0 | [5 empty] | 0.885
DPR 5 | Renovation of Compressed Air Refrigerated Dryer System, Refurbishment of Centralized Air Conditioning system, Supply, erection & commissioning of Condensate Extraction Pump, Procurement of CW Pump and GS pump |  |  |  |  | 28.83 | [12 empty] | 0 | [24 empty] | 0
1 | Renovation of Compressed Air Refrigerated Dryer System for Nashik TPS, 210 MW Unit No. 3, 4 & 5 |  |  |  |  | 11.3737 | [7 empty] | 1. These equipments are in service since long time and are having frequent breakdowns. Their maint. Cost is more and having poor performance. 2. After renovation, there will be reduction in the power consumption 3. Implementation of Ozone friendly (eco-friendly) refrigerants 4. Reduction in the overall maintenance cost |  |  |  |  | 0 |  |  |  | 11.3737 | [20 empty] | 0 |  |  |  | 11.3737
2 | Refurbishment of Centralized Air Conditioning system of Unit No. 3, 4 & 5 at Nashik TPS, Eklahare. |  |  |  |  | 8.15 | [7 empty] | 1. Centralized Air Conditioning system of Unit No. 3, 4 & 5 are in service since installation of the unit and rendered service life of more than 44 years. They are having frequent breakdowns. Their maint. cost is more and having poor performance. This system uses fron 22 gas which is banned by statutory authority. 2. Main purpose of refurbishment of this system is to fulfil the statutory requirement, i.e. use of ecofriendly refrigerant 3. Reduction in the power consumption 4. To reduce the overall maintenance cost 5. To improve the operational reliability |  |  |  |  | 0 |  |  |  | 8.15 | [20 empty] | 0 |  |  |  | 8.15
3 | Supply, erection & commissioning of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers ltd. at Nasik TPS. Total Qty. 02 Nos. |  |  |  |  | 3.93 | [7 empty] | 1. These equipments are in service since commissioning of the unit and are having frequent breakdowns. Their maint. Cost is more and having poor performance. 2. Installation of new CEP's will enhance operational reliability 3.To reduce the overall maintenance cost 4.The efficiency of condensing as well as allied cycles gets improved |  |  |  |  | 0 |  |  |  | 3.93 | [20 empty] | 0 |  |  |  | 3.93
4 | Procurement of CW & CTLP Pump total 4 No.s |  |  |  |  | 4 | [7 empty] | 1. These equipments are in service since commissioning of the unit and are having frequent breakdowns. Their maint. Cost is more and having poor performance. 2. Installation of new CW pumps will improve pump availability. 3.Impeller life extension & process improvement. 4.Reduction in maintenance cost. 5.Reliability of Operation. |  |  |  |  | 0 |  |  |  |  | 4 | [19 empty] | 0 |  |  |  |  | 4
5 | Procurement of GS Pump assembly .Total qty- 3 No |  |  |  |  | 1.373 | [7 empty] | 1. These equipments are in service since commissioning of the unit and are having frequent breakdowns. Their maint. Cost is more and having poor performance. 2. Installation of new GS pumps will improve pump availability. 3.Reduction in maintenance cost. 4.Reliability of Operation. |  |  |  |  | 0 | [5 empty] | 1.373 | [18 empty] | 0 | [5 empty] | 1.373
DPR 6 | Procurement of oil free Rotary Screw Compressors and BFP cartridge |  |  |  |  | 28.66 | [12 empty] | 0 | [24 empty] | 0
1 | Procurement of BFP cartridge |  |  |  |  | 7 | [7 empty] | 1. Generally continuous service life of these cartridges is 5 years. Hence due for replacement. 2. New cartridges will enhance operational reliability 3.Pump performance will be improved 4.Reduction in maintenance cost |  |  |  |  | 0 |  |  |  |  | 7 | [19 empty] | 0 |  |  |  |  | 7
2 | Procurement of oil free rotary screw compressors |  |  |  |  | 21.6648 | [7 empty] | 1. Presently working compressors are of reciprocating type. Due to their typical layout & construction, wear & tear of the spares is more and vibration level is also high. 2. New oil free rotary screw compressors will have smooth & noise free operation 3. Enhance operation reliability 4.Reduction in maintenance cost 5.Overall performance will be increased |  |  |  |  | 0 |  |  |  |  | 21.6648 | [19 empty] | 0 |  |  |  |  | 21.6648
DPR 7 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets, Refurbishment of HPT rotor along with supply, Procurement of HP & IP control valve with cam shaft assemblies, Procurement of complete governing system assembly, Supply, Errection & Commissioning of COP assembly, Procurement of Condenser tubes & ODP related schemes |  |  |  |  | 37.83 | [12 empty] | 0 | [24 empty] | 0
1 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets at 3 x 210 MW, TM-II NTPS. |  |  |  |  | 0.63 | [7 empty] | 1. These equipments are in service since installation of the unit and rendered service life of more than 44 years. They are having frequent breakdowns. Their maint. cost is more and having poor performance 2. New DG sets will enhance operation reliability 3.Reduction in maintenance cost 4. Overall performance will be increased |  |  |  |  | 0 |  |  |  |  | 0.63 | [19 empty] | 0 |  |  |  |  | 0.63
2 | Refurbishment of HPT rotor along with supply. |  |  |  |  | 3.7908 | [7 empty] | 1. The exising rotor is in service since installation of the unit and rendered service life of more than 44 years. Due to wear & tear of the moving blades, its performace is lowered. 2. Refurbishment of the rotor will increase in HP Turbine Efficiency 3.Life extension 4.Decrease in Turbine heat rate 5.Increase in reliability of Turbine 6.Increase in equivalent PLF with same Input resource |  |  |  |  | 0 |  |  |  |  | 3.7908 | [19 empty] | 0 |  |  |  |  | 3.7908
3 | Procurement of HP & IP control valve with cam shaft assemblies.qty-1set |  |  |  |  | 0.81 | [7 empty] | 1. These are in service since installation of the unit and rendered service life of more than 44 years. They are having frequent breakdowns. Their maint. cost is more and having poor performance 2. New CV's will enhance operation reliability 3. Overall performance will be increased |  |  |  |  | 0 | [5 empty] | 0.81 | [18 empty] | 0 | [5 empty] | 0.81
4 | Procurement of complete governing system assembly. qty-1 set |  |  |  |  | 0.27563 | [7 empty] | 1. It is in service since installation of the unit and rendered service life of more than 44 years. They are having frequent breakdowns. Their maint. cost is more and having poor performance 2. New system will enhance operation reliability 3.Overall performance will be increased |  |  |  |  | 0 | [5 empty] | 0.27563 | [18 empty] | 0 | [5 empty] | 0.27563
5 | Supply, Errection & Commissioning of COP assembly.Total Qty.- 3 Nos. |  |  |  |  | 0.9642 | [7 empty] | 1. These are in service since installation of the unit and rendered service life of more than 44 years. They are having frequent breakdowns. Their maint. cost is more and having poor performance 2. New COP's will enhance operation reliability 3. Overall performance will be increased 4. To enhance the TG bearing life |  |  |  |  | 0 | [5 empty] | 0.9642 | [18 empty] | 0 | [5 empty] | 0.9642
6 | Procurement of Condenser tubes for Unit No.3, 4 & 5.Total Qty:15700 tubes |  |  |  |  | 20.27 | [7 empty] | 1. These are in service since installation of the unit and rendered service life of more than 44 years. They are maintaining poor vacuum due to tube leakages. Their maint. cost is more and having poor performance. 2. New tubes will enhance operation reliability 3. Overall performance will be increased |  |  |  |  | 0 | [5 empty] | 20.27 | [18 empty] | 0 | [5 empty] | 20.27
7 | Procurement of CT Fan Blade assembly & shaft- 36 nos for Unit No.3,4 & 5 at NTPS, Eklahare |  |  |  |  | 1.3 | [7 empty] | Due to ageing effect , CT fan blades are found damaged & needs replacement to improve efficiency & availability of CT fans system. It also leads to improvement in condenser vacuum. |  |  |  |  | 0 |  |  |  | 1.3 | [20 empty] | 0 |  |  |  | 1.3
8 | Procurement of Gearbox Assembly for Cooling Tower Fans type B-220 Premium make for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare (Qty-24) |  |  |  |  | 4.5 | [7 empty] | Due to ageing effect, Gear box spares are found damaged. After installation of new Gear Box, Vaccum will be improved. |  |  |  |  | 0 |  |  |  | 1.5 | 1.5 | 1.5 | [18 empty] | 0 |  |  |  | 1.5 | 1.5 | 1.5
9 | Procurement of 5 nos. of Air Blowers for Degasser system |  |  |  |  | 0.25 | [7 empty] | Degasser blowers installed to remove dissolved gases in DM water. Failure of these blowers resulted into frequent breakdown. Hence to improve efficiency & availability of air blower system its replacement is essential |  |  |  |  | 0 |  |  |  |  | 0.25 | [19 empty] | 0 |  |  |  |  | 0.25
10 | Procurement of Flocculator gearbox- 12 Nos. |  |  |  |  | 0.4 | [7 empty] | Replacement of Flocculator gearbox leads to reduced day to day chemical consumption. & improvement in water quality. Also it is essential to improve efficiency & availability of clarifier system. |  |  |  |  | 0 |  |  |  |  | 0.4 | [19 empty] | 0 |  |  |  |  | 0.4
11 | Procurement of 4 Nos. of Clinker grinder assembly at NTPS Eklahare |  |  |  |  | 0.65 | [7 empty] | Availability of clinker grinder leads to continuous ash evacuation. Due to continous erosion internal spares of clinker grinder are badly damaged hence needs replacement.To improve efficiency of the system. |  |  |  |  | 0 |  |  |  |  | 0.65 | [19 empty] | 0 |  |  |  |  | 0.65
12 | Procurement of 4 Nos. of Clinker grinder gearbox at NTPS Eklahare |  |  |  |  | 0.2 | [7 empty] | To improve efficiency & availability of clinker grinder & ash evacuation system. As due to continous erosion internal spares of clinker grinder gearbox are badly damaged hence needs replacement. |  |  |  |  | 0 |  |  |  |  | 0.2 | [19 empty] | 0 |  |  |  |  | 0.2
13 | Procurement of 5 Nos. of Air Blowers for Degasser system |  |  |  |  | 0.25 | [7 empty] | Degasser blowers installed to remove dissolved gases in DM water. Failure of these blowers resulted into frequent breakdown. Hence to improve efficiency & availability of air blower system its replacement is essential |  |  |  |  | 0 | [5 empty] | 0.25 | [18 empty] | 0 | [5 empty] | 0.25
14 | Augmentattion of existing Ash Water recovery Scheme(WWR,AWR, ETP-I,ETP-II & Phase-II pump assembly) |  |  |  |  | 2.97 | [7 empty] | To improve efficiency & availability of ETP-I, ETP-II & phase-II pumps. ETP pumps needs replacment due to wear & tear by ash slurry water. |  |  |  |  | 0 | [5 empty] | 2.97 | [18 empty] | 0 | [5 empty] | 2.97
15 | Procurement of Feed Gate Housing (08 Nos.) |  |  |  |  | 0.57 | [7 empty] | To improve efficiency & availability of feed gate & ash evacuation system. As due to continous erosion feed gate housings are badly damaged hence needs replacement |  |  |  |  | 0 | [5 empty] | 0.57 | [18 empty] | 0 | [5 empty] | 0.57
DPR 8 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area & Retrofitting of LT breakers at various LT boards at NTPS |  |  |  |  | 25 | [12 empty] | 0 | [24 empty] | 0
1 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area. |  |  |  |  | 20 | [7 empty] | Retrofitting of 6.6 KV Minimum Oil Circuit Breakers / SF6 Breakers of Unit No. 4 & 5 along with Outdoor plant boards by Vacuum Circuit Breakers at Nashik TPS. i)Retrofitting of obsolete technology 6.6 KV Minimum oil circuit breakers / SF6 Bkrs of Unit No.4 & 5 along with Outdoor plant boards by Vacuum circuit breakers. ii)These units were commissioned during the years 1979 to 1982 along with various important auxiliaries for efficient running of the units. These systems are in continuous service for over 37 to 40 years. iii)It is expected that all the difficulties encountered with the old breakers will be overcome and VCBs being of latest manufacture and of contemporary technology, no difficulties will be experienced in the procurement of spares or availing services from the manufacturer. This will ensure ease of maintenance, improved availability and increased protection to motors and equipments. The latest breakers being technologically superior to old designed breakers will be more user friendly and maintenance free. iv)The cost of maintenance and time required to repair/recondition the MOCB’s is more as compared to vacuum circuit breakers. |  |  |  |  | 0 |  |  |  | 20 | [20 empty] | 0 |  |  |  | 20
2 | Retrofitting of LT breakers at various LT boards at NTPS |  |  |  |  | 5 | [7 empty] | Breakers for LT board systems like Boiler board, Emergency Board, Turbine board, ESP Board of all units and SSB board & Standby board provide supply for all the LT Auxiliaries.These breakers are running since very long time and have degraded.Many breakers have to be mechanically operated leading to which they don't operate during electrical fault and carrying the fault to HT switchgear system, so needs replacement. |  |  |  |  | 0 | [5 empty] | 5 | [18 empty] | 0 | [5 empty] | 5
DPR 9 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS , Replacement of LT energy efficient motor |  |  |  |  | 25 | [12 empty] | 0 | [24 empty] | 0
1 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS. |  |  |  |  | 20 | [7 empty] | To improve the process and reduce auxiliary consumption catering the benefits of higher technology. |  |  |  |  | 0 |  |  |  | 20 | [20 empty] | 0 |  |  |  | 20
2 | Replacement of LT energy efficient motor |  |  |  |  | 5 | [7 empty] | 1) Existing LT motors in the plant are running since commissioning of the plant and rewinding of LT motors are done several times. 2) After replacement of LT motors by energy efficient motors will reduce the outages of motors and will reduce the auxiliary power consumption. |  |  |  |  | 0 |  |  |  |  | 5 | [19 empty] | 0 |  |  |  |  | 5
DPR 10 | Upgradation of various electrical related schemes |  |  |  |  | 47.5 | [12 empty] | 0 | [24 empty] | 0
1 | Procurement of 6.6KV HT motors and spares at Nashik TPS Unit No 3,4 & 5. |  |  |  |  | 10 | [7 empty] | Old HT motors which are in continuous operation from last 40-45 years fequently fail and affect running of the unit causing generation loss. Motors while in service are subjected to electrical stresses and mechanical forces which have resulted in wearing out of the parts like bearing housings, cooling fans, grease covers etc and stator core and rotor have lost original electrical properties. 2) Now , fair life of almost all motors is over & rewinded more than twice. It is necessary to replace the HT motors on priority to reduce generation loss. |  |  |  |  | 0 |  |  |  | 10 | [20 empty] | 0 |  |  |  | 10
2 | Replacement of Boiler and turbine house lighting of Unit No.3,4 & 5 along with removal of old wiring. |  |  |  |  | 5 | [7 empty] | 1) Energy conservation by LED as the existing lighting, cables and conduits are old and in service from 25-30 years. 2) It will minimise power consumption. |  |  |  |  | 0 |  |  |  |  | 5 | [19 empty] | 0 |  |  |  |  | 5
3 | Replacemet of IPH transformer 11KV/6.6 KV and lighting and welding transformer at NTPS. |  |  |  |  | 3 | [7 empty] | IPH transformer 132/6.6KV in NTPS is running since year 1970-71 i.e., before commissioning of the NTPS stage-II units, and due to ageing no load losses are also on higher side. This scheme shall benefit in the following: 1) Energy conservation by replacing old F4 transformer. 2) Energy conservation & losses will be reduced after replacement of F4 transformer 132/6.6KV by 11/6.6KV transformer. |  |  |  |  | 0 |  |  |  |  | 3 | [19 empty] | 0 |  |  |  |  | 3
4 | Excitation Transformer at Unit No. 3, 4 & 5 |  |  |  |  | 1.5 | [7 empty] | These transformers are continuously running and critical auxiliaries,these transformers are having ageing effect and showing signs of insulation ageing as operating temperatures are maintaining higher side and recent breakdown of Unit No.4 Excitation transformer has lead to requirement as there are no spare transformers available in case of breakdown . |  |  |  |  | 0 |  |  |  |  | 1.5 | [19 empty] | 0 |  |  |  |  | 1.5
5 | GTR /UAT/ station transformer spares LV bushings replacement, HV bushings (spare)-3nos, LV busbar, palm joint both station transformers bushings at Unit No.3, 4 & 5 |  |  |  |  | 2 | [7 empty] | Unit No.3, 4 & 5 GTR/UAT & Station Transformers have continuous operation since commissioning .The bushings and joints of these transformers are having ageing effect and may be subject to failure at any time which may lead to heavy generation losses and secondary damage to transformers. So the replacement of aged bushings and availability of spare bushings is essential. |  |  |  |  | 0 |  |  |  | 2 | [20 empty] | 0 |  |  |  | 2
6 | Replacement of overhead conductor HT/LT by underground HT/LT cable in Colony area. |  |  |  |  | 4 | [7 empty] | Existing conductor are in service from 20-25 years. Existing conductors are very old and need to be replaced. To reduce outage of supply in colony due to ageing and wear out due to atmospheric conditions, the existing overhead HT/LT cable needs to be replaced by underground HT/LT cable |  |  |  |  | 0 |  |  |  |  | 4 | [19 empty] | 0 |  |  |  |  | 4
7 | LT transformer procurement/ rewinding work at NTPS |  |  |  |  | 3 | [7 empty] | LT transformers in NTPS running since 40-45 years and no load losses are also on higher side and need to be rewind / procure for smooth running of plant. |  |  |  |  | 0 | [5 empty] | 3 | [18 empty] | 0 | [5 empty] | 3
8 | LT MCC panel modification at ODP area NTPS |  |  |  |  | 10 | [7 empty] | 1) The existing breakers installed MCC panel is working since last @40-45 years back i.e. since commissioning. the condition of its mechanical linkages , jaw contacts , auxiliary contacts etc. is deteriorated and not operated smoothly i.e. “ ON-OFF” operations of these breakers become lengthy. 2) To improve the reliability of system and isolate the faulty portion in case of fault condition, fastest operations of switchgears is expected to minimize the secondary damages to auxiliaries |  |  |  |  | 0 | [5 empty] | 10 | [18 empty] | 0 | [5 empty] | 10
9 | Battery Charger-220V,50V,380V UPS, 24V,DG set EMF panel with charger replacement, UPS battery replacement, Unit No. 5 station battery replacement,50 V battery set replacement at Unit No.3, 4 & 5 |  |  |  |  | 6 | [7 empty] | 1) Battery Charger are continuously in service. Batteries life depends on the charging and discharging of batteries. These chargers are responsible for batteries boost charge if required and float charge in continous condition.These charger's circuitory are deteriorated,leading to battery voltage unstability. 2) These Batteries are in continous service and are having ageing effect thus need replacement. |  |  |  |  | 0 |  |  |  | 1.5 | 1 | 2 | 1 | 0.5 | [16 empty] | 0 |  |  |  | 1.5 | 1 | 2 | 1 | 0.5
10 | Replacement of HT motor Cables. (Old PILC Cable replacement with XLPE Cable) at Unit No.3, 4 & 5 & ODP area |  |  |  |  | 2 | [7 empty] | The old Supply system for the HT motor have 6.6KV cable are of PILC type cable .These cables in comparison to XLPE cables are more susceptible to moisture ingress ,requiring regular maintenance and posing environmental concerns due to the lead content.The XLPE cables provide greater tensile strength,elongation and impact resistances.This cross linking nature provides material resistance to oil and chemicals even at elevated temperature. |  |  |  |  | 0 |  |  |  | 2 | [20 empty] | 0 |  |  |  | 2
11 | Unit No. 4 Field Breaker |  |  |  |  | 1 | [7 empty] | Field breaker of Unit No.4 has been in service since commissioning and is having ageing effect and is observed with increased degradation of breaker moving parts,spring tension etc and needs replacement. |  |  |  |  | 0 |  |  |  | 1 | [20 empty] | 0 |  |  |  | 1
DPR 11 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. |  |  |  |  | 40 | [12 empty] | 0 | [24 empty] | 0
1 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. |  |  |  |  | 40 | [7 empty] | Units 3 & 5 were commissioned in 1981 with ILK supplied by George Kent (G.K.) make Control system and IL Kota make Interlock system. This G.K. make control system is discrete analog card-based system. So, all the internet problems pertaining to system structure like Complex inter panel hardwiring, difficulties in control loop modifications, Difficulties in fine tuning and slow response are persisting. Due to these problems, it is very difficult to maintain the availability of all the control loops. The technology being outdated, and the availability of spares is also a problem. Faultfinding & maintenance is a tedious and time-consuming job. Therefore there is need for upgradation of system. |  |  |  |  | 0 |  |  |  | 20 | 20 | [19 empty] | 0 |  |  |  | 20 | 20
DPR 12 | Replacement/Upgradation of C&I old systems at Nashik TPS |  |  |  |  | 58.93 | [12 empty] | 0 | [24 empty] | 0
1 | Replacement/Upgradation of Unit No.4 DVR System. |  |  |  |  | 6 | [7 empty] | Present DVR system is commissioned in Nov.2008 therefore now it is old so maintainance is hard .Therefore for 1.Precise voltage control 2.Smooth operation 3.Fine tuning & stability. It is necessary to upgrade the system |  |  |  |  | 0 |  |  |  |  | 6 | [19 empty] | 0 |  |  |  |  | 6
2 | Replacement/Upgradation of Unit No.4 UPS System. |  |  |  |  | 1 | [7 empty] | Present UPS sytem is old commissioned , so spares of this system is not available,therefor breakdown maintainance is not possible .Also,OEM suggested the upgradation of current system as existing system is obsolute. So, to get following benefits it is needed to be upgraded: 1.Precise voltage control 2.Smooth operation |  |  |  |  | 0 |  |  |  |  | 1 | [19 empty] | 0 |  |  |  |  | 1
3 | Supply of Beck Rotory Electronic Control Drive for Burner Tilt and Auxiliary Air Damper at Unit No. 3, 4 & 5 210 MW, NTPS, Eklahare Nashik. |  |  |  |  | 7.93 | [7 empty] | Current system of auxillary air damper & burner tilt is pneumatic system that is instrument air based ,but now a days there is so much moisture in instrument air thats why failure rate &, maintainace is more.And accuracy & smoothness of operation is less. Also the new system is electrical i. e based on electrical signals which will give following benifits 1. fast and precise.operation 2.Low failure rate 3.Low operating cost 4.Low maintenance cost 5.Fails safe condition 6.Easy Manual /Auto operation at local. |  |  |  |  | 0 |  |  |  |  | 7.93 | [19 empty] | 0 |  |  |  |  | 7.93
4 | Modification/Upgradation of Turbovisory system of Unit No. 3,4 & 5. |  |  |  |  | 6 | [7 empty] | At present turbovisory systems are installed at unit 3,&5 is of ECIL for unit-4 it is of PHILIPS. Unit-3 & 5 ECIL sensors installed are of old versions therefore cards on which its operates is of old version so spares are not available. Unit-4 PHILLIPS sensors installed are of old versions therefore cards on which its operates is of old version so spares are not available.Now a days there are high maintainace issues evolving . As this system is very critical for plant operation new system need to be installed for the following benifits 1.More Accuracy. 2.Low failure rate . 3.Less maintainance cost. 4. fast and precise.operation |  |  |  |  | 0 |  |  |  |  | 6 | [19 empty] | 0 |  |  |  |  | 6
5 | Auxiliary air dampers & BT, HAD, feed gate replacement/modification work. |  |  |  |  | 1 | [7 empty] | Auxillary air damper ,BT,HAD & feed gate t is pneumatic system that is instrument air based ,but now a days there is so much moisture in instrument air thas why failure rate , maintainace is more.And accuracy & smoothness of operation is less. To sustain in these difficult conditions new versioned material that is positiners, cylinders ,I to P & smart sensors required to be installed . To get benifits as foolows. 1.More Accuracy. 2.Low failure rate . 3.Less maintainance cost. 4. fast and precise.operation |  |  |  |  | 0 |  |  |  |  | 1 | [19 empty] | 0 |  |  |  |  | 1
6 | Upgradation of Unit No.4 DCS-FCS 102 to FCS 106 (Total 5 Nos.) |  |  |  |  | 3 | [7 empty] | In U # 4, Yokogawa DCS is commissioned in Nov – 2003. In this DCS, FCS controllers (AFS30D) are working since commissioning. As service expiry of these controllers is due in 2025. These controllers are designed to monitor & control auto loops of plant parameters. One controller FCS101 AFS30D was upgraded to AFV30D last year and remaining 05 nos. of controllers are need to change in stepwise manner. Hence, it is proposed to upgrade centum FCS102 AFS30 D to AFV30D. For following benifitis:- 1. More I/Os avaialability. 2.Fast and precise.operation 3. Obsloete old system replacement. |  |  |  |  | 0 |  |  |  |  | 3 | [19 empty] | 0 |  |  |  |  | 3
7 | New sewage treatment plant required at NTPS. |  |  |  |  | 2 | [12 empty] | 0 |  |  |  |  | 2 | [19 empty] | 0 |  |  |  |  | 2
8 | Upgradation of Unit No.4 230 V UPS and new UPS, charger for Unit No. 3 & 5 DCS at NTPS. |  |  |  |  | 4 | [7 empty] | For unit-4 present UPS sytem is old commissioned , so spares of this system is not available,therefor breakdown maintainance is not possible .Also,OEM suggested the upgradation of current system as existing system is obsolute. So, to get following benefits it is needed to be upgraded: 1.Precise voltage control 2.Smooth operation For unit-3 &5 for precise & smooth voltage control for systems like turbovisiory DSM & other protection systems. |  |  |  |  | 0 |  |  |  |  | 4 | [19 empty] | 0 |  |  |  |  | 4
9 | ESP hopper high & low level indicator mounting in Unit No.3,4& 5. |  |  |  |  | 6 | [7 empty] | ESP hopper collects ash from ESP fields ,now a days field avilability of ESP field is very less . One of the reason over ash accumlation in hopper which makes field short affects on field availability.Currently there is no any high level or low level indication of ash hopper available. So to get following benifits upgradation is required 1.Instances of ESP filed outages will reduce 2.Early detection of ash bridging/built-up of rate holes |  |  |  |  | 0 |  |  |  |  | 6 | [19 empty] | 0 |  |  |  |  | 6
10 | OCEMS for Sox, Nox, opacity monitoring system upgradation work for Unit No.3, 4 & 5 at NTPS. |  |  |  |  | 3 | [7 empty] | Two Nos of Online Continuous Emission Monitoring (OCEMS) system is installed, at ID fan discharge duct of U # 5. NTPS, Eklahare, for monitoring Sox / Nox emission. Existing analyzers commissioned in July 2017 are very old and beyond maintenance. Existing system is out of service since a year. Spares & services for this system are not readily available in the market due to technology upgradation. As per norms of MPCB / CPCB, it is necessary to maintain this system in healthy condition for continuous stack emission. Therefore for better montitorong of continuous stack emission it is necessary to upgrade system. |  |  |  |  | 0 |  |  |  |  | 3 | [19 empty] | 0 |  |  |  |  | 3
11 | Supply, Erection, Commissioning & Testing of online H2 purity meter and Resistivity meter for Unit No. 5. |  |  |  |  | 1 | [7 empty] | There are total four nos. of ABB make H2 purity meters installed at Unit No. 5 and H2 plant at Stage –II, N.T.P.S.Nasik. As the H2 purity meters are installed since commissioning. Recently problem has been developed in H2 purity monitoring system in U#5.for, which M/S ABB has been asked to repair/supply the spares for existing system. However ABB replied showing their inability to repair or to provide spares for the system, as the system is obsolete. Therefore for above reason &More Accuracy,Low failure rate ,fast and precise.operation need to upgrade H2 purity meter |  |  |  |  | 0 |  |  |  |  | 1 | [19 empty] | 0 |  |  |  |  | 1
12 | Supply, Erection, commissioning of Hydra step system for Drum level control Unit No.3. |  |  |  |  | 2 | [7 empty] | Presently for unit -3 there is only one hydrastep installed that is at right side of boiler drum ,So for more accuracy low failure rate ,fast & precise operation & reliability there is need of erection of new hydrastep . |  |  |  |  | 0 |  |  |  |  | 2 | [19 empty] | 0 |  |  |  |  | 2
13 | HPLP - Servo Spares |  |  |  |  | 2 | [7 empty] | Sulzer makes HP/LP bypass / PRDS system supplied by BHEL is in service at all three units at NTPS. To maintain the system in healthy condition spares are required. At present spares (Servo valve and blocking element) are nil in stock.As this system is very important for smooth plant operation there is need of procuring of HPLP spares which gives following benifits 1.More Accuracy. 2.Low failure rate . 3.Less maintainance cost. 4. fast and precise.operation |  |  |  |  | 0 |  |  |  |  | 2 | [19 empty] | 0 |  |  |  |  | 2
14 | Replacement of Relays and Energy meter at NTPS, Nashik. |  |  |  |  | 3 | [7 empty] | The present relays used for various protection system are electromechanical also old commssioned thats why failure rate of these relays is more therefore there is need of upgradation of these relays. Also the Energy meter presently working is old & low accuracy class.Therefore there is need of upgradation of energy meter. |  |  |  |  | 0 |  |  |  |  | 3 | [19 empty] | 0 |  |  |  |  | 3
15 | ESP upgradation for Unit No. 3, 4 & 5. |  |  |  |  | 5 | [7 empty] | The ESP monitoring system has controller EPIC -II installed at unit-4&5. This controller monitors the operation of the ESP field. But as this system is very old the communication through RTUs is not working properly. Also, control from PCR is not working being software is of a very old version. For smooth operation of the ESP field & to avoid processor failure during automatic changeover to manual control, it is necessary to upgrade to sophisticated & advanced features such as intermittent optimization energization, and to enables energy saving. The ESP monitoring system has controller BAPCON installed at unit-3.The system installed is very old spares of this system is not available in market as this system is outdated .So to improve performance of ESP there is need of upgradation. |  |  |  |  | 0 |  |  |  |  | 5 | [19 empty] | 0 |  |  |  |  | 5
16 | Grounding Brush Monitoring System for Unit No. 3,4& 5. |  |  |  |  | 3 | [12 empty] | 0 |  |  |  |  | 3 | [19 empty] | 0 |  |  |  |  | 3
17 | Implementationof FGMO |  |  |  |  | 3 | [7 empty] | For maintaing the grid stability implementation of FGMO is necessary. Also as per MYT regulation of MERC,CERC & IEGC there is need of implementation of FGMO. |  |  |  |  | 0 |  |  |  | 3 | [20 empty] | 0 |  |  |  | 3
DPR 13 | Modification & replacement of various CHP schemes |  |  |  |  | 26.19 | [12 empty] | 0 | [24 empty] | 0
1 | Modification of single stream conveyor belt Gearboxes with new design Helical Bevel type Gearboxes at CHP-II NTPS |  |  |  |  | 1 | [7 empty] | 1.Improve coal unloading rate. 2.To improve unloading time. 3.To improve plant availability. 4.To reduce the maintenance cost. 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  |  | 1 | [20 empty] | 0 |  |  |  | 1
2 | Modification of Primary Vibrating screen at CHP-II, NTPS |  |  |  |  | 0.7 | [7 empty] | 1.Improve coal unloading rate. 2.To improve loadability. 3.To improve plant availability. 4.To reduce the maintenance cost. 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  |  | 0.7 | [20 empty] | 0 |  |  |  | 0.7
3 | Supply, erection & commissioning of Rail table alongwith weighment frame for rotaside Wagon Tippler at CHP-II, NTPS |  |  |  |  | 1.2 | [7 empty] | 1.Improve coal unloading rate. 2.To improve unloading time. 3.To improve plant availability. 4.To reduce the maintenance cost. 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  |  |  | 1.2 | [19 empty] | 0 |  |  |  |  | 1.2
4 | Modification of Conveyor Drive system with Motorised Pulley drive system at CHP-II, NTPS. |  |  |  |  | 2 | [7 empty] | 1.Improve coal unloading rate. 2.To improve unloading time. 3.To improve plant availability. 4.To reduce the breakdown hours & cost 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  |  |  | 2 | [19 empty] | 0 |  |  |  |  | 2
5 | Replacement of old damaged RBCR rail beam M/c No. CR/964 & screen to increase life of RBCR n reduced direct impact of raw coal on secondary impact crusher. |  |  |  |  | 5.09 | [7 empty] | 1.Improve coal unloading rate. 2.To improve unloading time. 3.To improve plant availability. 4.To reduce the maintenance cost of impact crusher & improvement in life of hammers. 5.Reduction in demurrage hours. |  |  |  |  | 0 | [5 empty] | 5.09 | [18 empty] | 0 | [5 empty] | 5.09
6 | Replacement of copmlete crusher unit as per Drg. No. P00304/0 CO/1050 CR635-636(impact crusher body & rotor shaft assembly) 2 Nos |  |  |  |  | 6.4 | [7 empty] | 1.Improve coal unloading rate. 2.To reduce maintenance cost. 3.To improve plant availability. 4. Improvement in life of hammers. 5.Reduction in demurrage hours. |  |  |  |  | 0 | [5 empty] | 6.4 | [18 empty] | 0 | [5 empty] | 6.4
7 | Replacement of appron feeder head shaft assembly-25/005 drg no.-M15076/2 & tail shaft assembly-25/006 Drg. No.- M15065/2 |  |  |  |  | 1 | [7 empty] | 1.Improve coal unloading rate. 2.To reduce maintenance cost. 3.To improve plant availability. 4.To reduce the breakdown hours & cost 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  |  | 1 | [20 empty] | 0 |  |  |  | 1
8 | Supply & erection of wagon tippler rail table Drg. No.12578/45-01 , tippler support roller & bogei Drg. No-12616/45-2M |  |  |  |  | 1.9 | [7 empty] | 1.Improve coal unloading rate. 2.To improve unloading time. 3.To improve plant availability. 4.To reduce the maintenance cost. 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  |  |  | 1.9 | [19 empty] | 0 |  |  |  |  | 1.9
9 | Supply of seondary crusher motors 6.6KV, 750KW & 220KW motor for CHP |  |  |  |  | 0.6 | [7 empty] | 1.Improve coal unloading rate. 2.To improve unloading time. 3.To improve plant availability. 4.To reduce the maintenance cost. 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  |  | 0.6 | [20 empty] | 0 |  |  |  | 0.6
10 | Supply of LT motors for various conveyor belts of CHP |  |  |  |  | 0.5 | [7 empty] | 1.Improve coal unloading rate. 2.To improve unloading time. 3.To improve plant availability. 4.To reduce the maintenance cost. 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  |  | 0.5 | [20 empty] | 0 |  |  |  | 0.5
11 | Up-gradation of existing DC drive system of Wagon Tippler & Paddle feeder with new version DIGICON make system along with supply, installtion, commissioning & testing of DC drives at CHP-III. |  |  |  |  | 0.8 | [7 empty] | 1.Improve coal unloading rate. 2.To improve unloading time. 3.To improve plant availability. 4.To reduce the maintenance cost. 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  |  |  | 0.8 | [19 empty] | 0 |  |  |  |  | 0.8
12 | Supply of Variable Frequency drives for Conv.16C2 at CHP-III. |  |  |  |  | 0.5 | [7 empty] | 1.Improve coal unloading rate. 2.To improve unloading time. 3.To improve plant availability. 4.To reduce the maintenance cost. 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  |  | 0.5 | [20 empty] | 0 |  |  |  | 0.5
13 | Up-gradation of existing relay panel of control room with microprocessor based PLC logic system along with supply, installtion, commissioning & testing of relay panel at CHP. |  |  |  |  | 1.5 | [7 empty] | 1.Improve coal unloading rate. 2.To improve unloading time. 3.To improve plant availability. 4.To reduce the maintenance cost. 5.Reduction in demurrage hours. |  |  |  |  | 0 | [5 empty] | 1.5 | [18 empty] | 0 | [5 empty] | 1.5
14 | Supply of Magnetic seperators & Metal detectors at CHP |  |  |  |  | 3 | [7 empty] | 1.To improve plant availability. 2.To reduce the maintenance cost. 3.Reduction in demurrage hours. |  |  |  |  | 0 | [5 empty] | 3 | [18 empty] | 0 | [5 empty] | 3
| Civil Yet to be submitted DPR | [17 empty] | 0 | [24 empty] | 0
DPR 1 | Repair & renovation of NTPS colony ,Repairing work of ash bund side & Eklahare barrage |  |  |  |  | 30.35 | [12 empty] | 0 | [24 empty] | 0
1 | Work of renovation of various residential quarters by providing and fixing kitchen sink, kitchen trolley & granite otta at NTPS Colony Eklahare. |  |  |  |  | 1.5 | [7 empty] | To provide pleasant and healthy environment in quarters, Better appearance of colony premises. Also it will be easy in maintenance point of view. |  |  |  |  | 0 |  |  |  | 0.9 | 0.6 | [19 empty] | 0 |  |  |  | 0.9 | 0.6
2 | Providing and applying external painting to various types residential buildings at NTPS colony Eklahare. |  |  |  |  | 1.81 | [7 empty] | To increase life of residential quarters. Better appearance of quarter. To maintain hygienic conditions by preventing dampness during rains. To provide pleasant and healthy environment in quarters. |  |  |  |  | 0 |  |  |  | 1.09 | 0.72 | [19 empty] | 0 |  |  |  | 1.09 | 0.72
3 | Providing and applying internal painting to various types of residential quarters at NTPS Colony Eklahare. |  |  |  |  | 1.61 | [7 empty] | To increase life of residential quarters. Better appearance of quarter. To provide pleasant and healthy environment in quarters. |  |  |  |  | 0 |  |  |  |  | 0.97 | 0.64 | [18 empty] | 0 |  |  |  |  | 0.97 | 0.64
4 | Providing and fixing vitrified tiles to various types of residnetial buildings at NTPS Colony Eklahare. |  |  |  |  | 5.4 | [7 empty] | Better appearance of colony premises. To increase life of residential quarters. For proper flooring to avoid ponding. To increase life of structure resulting in low maintenance cost. |  |  |  |  | 0 |  |  |  |  | 3.24 | 2.16 | [18 empty] | 0 |  |  |  |  | 3.24 | 2.16
5 | Structural strengthening works to various residential quarters at NTPS colony Eklahare. |  |  |  |  | 5.9 | [7 empty] | To increase life of residential quarters. To restrict water entry to inside quarters. To reduce the excessive damages due to aging of buildings. |  |  |  |  | 0 |  |  |  |  | 3.54 | 2.36 | [18 empty] | 0 |  |  |  |  | 3.54 | 2.36
6 | Providing and fixing colour coated galvanised iron sheets for roofing at various residential buildings at NTPS Colony Eklahare. |  |  |  |  | 7.48 | [7 empty] | Provide protection to terrace slab due to rains. To arrest the water leakages of terrace slab. To avoid further deacy of terrace slab. To reduce stuctral decay due to rain water. |  |  |  |  | 0 |  |  |  |  | 4.5 | 2.98 | [18 empty] | 0 |  |  |  |  | 4.5 | 2.98
7 | Sewer line repair of various quarters at NTPS Eklahare |  |  |  |  | 4.25 | [7 empty] | Smooth flow of sewage water by laying new sanitary lines. To prevent frequent chock-up by laying new sanitary lines. To maintain hygienic environment by laying new sanitary lines. To reduce mosquito breeding by laying new sanitary line |  |  |  |  | 0 |  |  |  |  | 0.5 | 3.3 | 0.45 | [17 empty] | 0 |  |  |  |  | 0.5 | 3.3 | 0.45
8 | Stair case repairing of various building at NTPS Eklahare |  |  |  |  | 0.65 | [7 empty] | For smooth movement of residents to avoid the accidents & to avoid the futher damages to staircase. |  |  |  |  | 0 |  |  |  |  | 0.15 | 0.5 | [18 empty] | 0 |  |  |  |  | 0.15 | 0.5
9 | Construction of WBM road over/at the top of ash bund at NTPS Eklahare. |  |  |  |  | 0.59 | [7 empty] | For safe and economical transportationof ash bulkers To prevent accidents and ensure safety . To avoid inconvenience and insecurity while moving on this roads |  |  |  |  | 0 |  |  |  |  | 0.45 | 0.14 | [18 empty] | 0 |  |  |  |  | 0.45 | 0.14
10 | Repairs to filters of drain well No.4 and other allied works at ash bund valley No.4A at NTPS Eklahare. |  |  |  |  | 0.57 | [7 empty] | To avoid the ash content into to toe drain, which is lifted again from WWR for futher ash mixing. Its act as filter meduim . Which reduces water pollution & land pollution, by reducing seepage of ash mixed water in the toe drain. |  |  |  |  | 0 |  |  |  |  | 0.4 | 0.17 | [18 empty] | 0 |  |  |  |  | 0.4 | 0.17
11 | Repairs to Godavari river barrage gates and allied works at NTPS, Eklahare. |  |  |  |  | 0.59 | [7 empty] | Due to polluted water of Godvari, gates are mostly rusted to needs to repair to avoid failure of barrage gates working. |  |  |  |  | 0 |  |  |  |  | 0.4 | 0.19 | [18 empty] | 0 |  |  |  |  | 0.4 | 0.19
DPR 2 | Structural repairs of Cooling Tower |  |  |  |  | 38.54 | [12 empty] | 0 | [24 empty] | 0
1 | Structural repairs of cooling tower components at Unit No. 3A, 3B, 4A, 4B,5A & 5B, Stage-II NTPS Eklahare. |  |  |  |  | 38.54 | [7 empty] | 1. Due to execution of above scheme there will be saving of about 2.16 Cr. per annum on chemical treatment in WT Plant on Godawari river water. 2. To prevent any fatal accident in future and also to safe guard the remaining structures. 3. For smooth and easy functioning of cooling tower. |  |  |  |  | 0 |  |  |  | 26.98 | 11.56 | [19 empty] | 0 |  |  |  | 26.98 | 11.56
DPR 3 | Structural repair & rehabilitation and Renovation and modification work at NTPS Plant |  |  |  |  | 30.96 | [12 empty] | 0 | [24 empty] | 0
1 | Structural repair & rehabilitation of various machine foundations of ID, FD & PA fans for Unit No. 3, 4, 5 at Stage-II, NTPS, Eklahare. |  |  |  |  | 0.36 | [7 empty] | 1.Increase life of structure of buildings. 2. Avoid serious accident for structure and man power. 3. Avoid generation losses due to emergency shut down. |  |  |  |  | 0 |  |  |  | 0.25 | 0.11 | [19 empty] | 0 |  |  |  | 0.25 | 0.11
2 | Work of removing and providing 24 B.W.G.for pent house side & roof at Unit No. 3,4 & 5 Stage-II NTPS, Eklahare. |  |  |  |  | 2.48 | [7 empty] | 1. Increase life of structure of buildings. 2. Avoid serious accident for structure and man power. 3.Avoid generation losses due to emergency shutdown. |  |  |  |  | 0 |  |  |  | 1.74 | 0.74 | [19 empty] | 0 |  |  |  | 1.74 | 0.74
3 | Work of removing and providing old damaged siporex wall and poly coated sheet for 28 mtr. height at Unit No. 3, 4 & 5 Stage-II NTPS, Eklahare. |  |  |  |  | 1.8 | [7 empty] | 1. Increase life of structure of buildings. 2. Avoid serious accident for structure and man power. 3. Avoid generation losses due to emergency shut down. |  |  |  |  | 0 |  |  |  | 1.26 | 0.54 | [19 empty] | 0 |  |  |  | 1.26 | 0.54
4 | Structural repairs of chimney at Unit No. 3,4 & 5 Stage-II, NTPS, Eklahare. |  |  |  |  | 4.32 | [7 empty] | 1. Safe and economical transportation, avoid accidents will be achieved and Maintenance of company vehicles reduced. 2. Will maintain environment in hygienic condition. |  |  |  |  | 0 |  |  |  | 3.02 | 1.3 | [19 empty] | 0 |  |  |  | 3.02 | 1.3
5 | Renovation of sump No. 2,3,4,5,6 and 7 at WTP Stage-II, NTPS Eklahare. |  |  |  |  | 2.36 | [7 empty] | 1. Increase life of structure of buildings. 2. Avoid serious accident for structure and man power. 3. Avoid generation losses due to emergency shut down. |  |  |  |  | 0 |  |  |  | 1.65 | 0.71 | [19 empty] | 0 |  |  |  | 1.65 | 0.71
6 | Work of structural repairing at CHP-I,II & III area at NTPS, Eklahare. |  |  |  |  | 1.09 | [7 empty] | 1. Structural repairs of CHP I, II & III buildings shall ensure structural stability for running of 3 x 210 MW plant. 2. Structural strengthening ensures accident proof atmosphere. |  |  |  |  | 0 |  |  |  | 0.76 | 0.33 | [19 empty] | 0 |  |  |  | 0.76 | 0.33
7 | Work of structural repairing at WTP, Stage-II, NTPS, Eklahare. |  |  |  |  | 8.1 | [7 empty] | 1.Thus, to keep the plant in running conditions it is must to repair and strengthening the WTP structures 2. As the WTP plays vital role in maintaining plant in running condition. It becomes part and parcel of running unit. 3. Therefore, key key benefits of WTP are to be considered for effective and economical generation of energy and to prevent generation loss. |  |  |  |  | 0 |  |  |  | 5.67 | 2.43 | [19 empty] | 0 |  |  |  | 5.67 | 2.43
8 | Work of structural repair of GS pump Unit No. 3,4,& 5 and fire fighting pump house at Stage-II,NTPS, Eklahare. |  |  |  |  | 0.83 | [7 empty] | 1.Thus, to keep the plant in running conditions it is must to keep structural healthy ness of G.S. pump unit no. 3, 4, 5 & firefighting pump house. 2. As these structures plays vital role in maintaining plant in running condition. It becomes part & parcel of running unit. 3. Therefore, key benefit of these structures are to be considered for effective & economical generation of energy & to prevent generation loss. |  |  |  |  | 0 |  |  |  | 0.58 | 0.25 | [19 empty] | 0 |  |  |  | 0.58 | 0.25
9 | Work of repairs to doors & windows of various building at WTP, Stage-II, NTPS, Eklahare. |  |  |  |  | 0.34 | [7 empty] | 1. Good doors and windows are required to protect inner man and machineries in safe working condition. 2. Good doors and windows give more aesthetic look to all structures. |  |  |  |  | 0 |  |  |  | 0.24 | 0.1 | [19 empty] | 0 |  |  |  | 0.24 | 0.1
10 | Providing and fixing powder coated colored Zincalume profiled sheet for various building at CHP,AWR building, Time office & ODP EM at NTPS, Eklahare. |  |  |  |  | 3.89 | [7 empty] | 1. For ensuring of perfect waterproofing powder coated sheets are to be provided to CHP, AWR building etc. 2. Therefore, key benefit of these buildings are to be considered for effective & economical generation of energy & to prevent generation loss. 3. The life of above buildings shall be enhanced. |  |  |  |  | 0 |  |  |  | 2.72 | 1.17 | [19 empty] | 0 |  |  |  | 2.72 | 1.17
11 | Work of external painting & internal painting at WTP, Stage-II NTPS, Eklahare. |  |  |  |  | 1.33 | [7 empty] | 1. For protecting the building walls from weathering effect its painting is must. 2. It gives more aesthetic look and graced the work areas. |  |  |  |  | 0 |  |  |  | 0.93 | 0.4 | [19 empty] | 0 |  |  |  | 0.93 | 0.4
12 | Work of external painting & internal painting at CHP area NTPS, Eklahare. |  |  |  |  | 0.67 | [7 empty] | 1.For protecting the building walls from weathering effect its painting is must. 2. It gives more aesthetic look and graced the work areas. |  |  |  |  | 0 |  |  |  | 0.47 | 0.2 | [19 empty] | 0 |  |  |  | 0.47 | 0.2
13 | Renovation and restructuring of shed No. 1, 2, 5, 6, 9 & 11 of major store custody of NTPS, Eklahare. |  |  |  |  | 3.39 | [7 empty] | The soundness and structural stability will ensure, safeness of stored materials and consumables required for running of 3 x 210 MW units. |  |  |  |  | 0 |  |  |  | 2.37 | 1.02 | [19 empty] | 0 |  |  |  | 2.37 | 1.02
DPR 4 | As per I.B.Recommondation |  |  |  |  | 59.48 | [12 empty] | 0 | [24 empty] | 0
1 | Work of construction compound wall with concertina coil at various locations at Nashik TPS. |  |  |  |  | 58.87 | [7 empty] | With the schemes being implemented at NTPS plant Eklahare, safety & security of NTPS power house will be increased. |  |  |  |  | 0 |  |  |  | 41.21 | 17.66 | [19 empty] | 0 |  |  |  | 41.21 | 17.66
2 | Providing & renovating security watch tower at NTPS Premises Eklahare. |  |  |  |  | 0.61 | [7 empty] | With the schemes being implemented at NTPS plant Eklahare, safety & security of NTPS power house will be increased. |  |  |  |  | 0 |  |  |  | 0.43 | 0.18 | [19 empty] | 0 |  |  |  | 0.43 | 0.18
| HO Yet to be submitted DPR | [17 empty] | 0 | [24 empty] | 0
DPR 1 | R&M/LE for Identified Thermal units of MSPGCL of (3 x 210 MW) |  |  |  |  | 600 | [12 empty] | 0 | [24 empty] | 0
| R&M/LE for Identified Thermal units of MSPGCL (3 x 210 MW) units of MSPGCL |  |  |  |  | 1180.14 | [12 empty] | 0 |  |  |  | 384.04 | 796.1 | [19 empty] | 0 |  |  |  | 384.04 | 796.1
DPR 2 | CHP Improvcement Schemes at 3 x 210 MW units |  |  |  |  | 30 | [12 empty] | 0 | [24 empty] | 0
| CHP Improvement Schemes at 3 x 210 MW units |  |  |  |  | 30 | [12 empty] | 0 |  |  |  |  | 30 | [19 empty] | 0 |  |  |  |  | 30
| B) Non-DPR Schemes | [17 empty] | 0 | [24 empty] | 0
1 | TATA Mini Truck SFC 709 EX No.MH-15-JV-3992 | Non-DPR | N.A. | [11 empty] | 0.22635 | 0.09464 |  |  | 0.32099 | [20 empty] | 0.22635 | 0.09464 |  |  | 0.32099
2 | Executive chair(10),S Type Arm chai(20) | Non-DPR | N.A. | [11 empty] | 0.09152 | 0.016317 |  |  | 0.10784 | [20 empty] | 0.09152 | 0.016317 |  |  | 0.10784
3 | Office Table and S-Type Chair with Arm | Non-DPR | N.A. | [11 empty] | 0 | 0.030968 |  |  | 0.030968 | [20 empty] | 0 | 0.030968 |  |  | 0.030968
4 | Windows Slot in PC VPC 10-Intel Core 13 4th -NTC | Non-DPR | N.A. | [11 empty] | 0 | 0.010561 |  |  | 0.010561 | [20 empty] | 0 | 0.010561 |  |  | 0.010561
5 | LG Screen wall mounted computer-LED display65"-NTC | Non-DPR | N.A. | [11 empty] | 5.0621 | 0.034798 |  |  | 5.0969 | [20 empty] | 5.0621 | 0.034798 |  |  | 5.0969
6 | 20 Ton Split AC for Audtiorium -NTC | Non-DPR | N.A. | [11 empty] | 1.0493 | 0.038016 |  |  | 1.0873 | [20 empty] | 1.0493 | 0.038016 |  |  | 1.0873
7 | Colour Laser Printer, All in one A3 LaserJet Print | Non-DPR | N.A. | [11 empty] | 1.0047 | 0.05415 |  |  | 1.0589 | [20 empty] | 1.0047 | 0.05415 |  |  | 1.0589
8 | Digital DSLR Camera | Non-DPR | N.A. | [11 empty] | 1.0764 | 0.00295 |  |  | 1.0793 | [20 empty] | 1.0764 | 0.00295 |  |  | 1.0793
9 | Indoor Gymnasium Equipments at NTC, Eklahare | Non-DPR | N.A. | [12 empty] | 0.02853 |  |  | 0.02853 | [21 empty] | 0.02853 |  |  | 0.02853
10 | CLASS ROOM CHAIR WITH DESKLET | Non-DPR | N.A. | [12 empty] | 0.023576 |  |  | 0.023576 | [21 empty] | 0.023576 |  |  | 0.023576
11 | PA System and Sport Material,Table Tannis for | Non-DPR | N.A. | [12 empty] | 0.01687 |  |  | 0.01687 | [21 empty] | 0.01687 |  |  | 0.01687
12 | EXECUTIVE CHAIR WITH 5 SUPRT & S-TYPE CHAIR | Non-DPR | N.A. | [12 empty] | 0.01003 |  |  | 0.01003 | [21 empty] | 0.01003 |  |  | 0.01003
13 | APPLN COOLER AIR SEMIEXH AIR COOLER ASSY | Non-DPR | N.A. | [12 empty] | 0.033896 |  |  | 0.033896 | [21 empty] | 0.033896 |  |  | 0.033896
14 | FULL PAD CHAIRS WITH SIDE ARM | Non-DPR | N.A. | [12 empty] | 0.029637 |  |  | 0.029637 | [21 empty] | 0.029637 |  |  | 0.029637
15 | Industrial Cabinet with 12 Lockers | Non-DPR | N.A. | [12 empty] | 0.0070163 |  |  | 0.0070163 | [21 empty] | 0.0070163 |  |  | 0.0070163
16 | UV Water Purifier Filter | Non-DPR | N.A. | [12 empty] | 0.019116 |  |  | 0.019116 | [21 empty] | 0.019116 |  |  | 0.019116
17 | FILTER RO+UV+UF+TDS WATER PURIFIER | Non-DPR | N.A. | [12 empty] | 0.032906 |  |  | 0.032906 | [21 empty] | 0.032906 |  |  | 0.032906
18 | 2 Tone SPLIT AC INDOOR UNIT | Non-DPR | N.A. | [12 empty] | 0.008064 |  |  | 0.008064 | [21 empty] | 0.008064 |  |  | 0.008064
19 | 1.5 TON CAPACITY SPLIT AC | Non-DPR | N.A. | [12 empty] | 0.006688 |  |  | 0.006688 | [21 empty] | 0.006688 |  |  | 0.006688
20 | FILTER RO+UV+UF+TDS WATER PURIFIER | [13 empty] | 1.6846 | 0.013405 |  |  | 1.698 | [20 empty] | 1.6846 | 0.013405 |  |  | 1.698
21 | Logitech PTZ Group Camera 960-001054 | Non-DPR | N.A. | [11 empty] | 2.4267 | 0.010792 |  |  | 2.4375 | [20 empty] | 2.4267 | 0.010792 |  |  | 2.4375
22 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | [15 empty] | 0.011564 |  | 0.011564 | [22 empty] | 0.011564 |  | 0.011564
23 | WORK BENCH WITHOUT DRAWER | [15 empty] | 0.011647 |  | 0.011647 | [22 empty] | 0.011647 |  | 0.011647
24 | WALL MOUNTED FAN 18" 230V 1440RPM | [15 empty] | 0.030075 |  | 0.030075 | [22 empty] | 0.030075 |  | 0.030075
25 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | [15 empty] | 0.011788 |  | 0.011788 | [22 empty] | 0.011788 |  | 0.011788
26 | EXECUTIVE CHAIR, S-TYPE CH-7 CHAIR WITH ARM | [15 empty] | 0.035229 |  | 0.035229 | [22 empty] | 0.035229 |  | 0.035229
27 | SAMSUNG GALAXY TAB S3, 32GB 9.7 INCH | [15 empty] | 0.003845 |  | 0.003845 | [22 empty] | 0.003845 |  | 0.003845
28 | i5 Laptop - 2 Nos & i7 Laptop - 3 Nos | [15 empty] | 0.037636 |  | 0.037636 | [22 empty] | 0.037636 |  | 0.037636
29 | Godrej make 1.5 Ton High Wall Split AC | [15 empty] | 0.020975 |  | 0.020975 | [22 empty] | 0.020975 |  | 0.020975
30 | Complete Multimedia Projector with Std Accessories | [15 empty] | 0.0109 |  | 0.0109 | [22 empty] | 0.0109 |  | 0.0109
31 | LED 40 INCH SMART TV | [15 empty] | 0.0092016 |  | 0.0092016 | [22 empty] | 0.0092016 |  | 0.0092016
32 | FULL PAD CHAIRS, EXECUTIVE CHAIR, | [15 empty] | 0.068995 |  | 0.068995 | [22 empty] | 0.068995 |  | 0.068995
33 | Cash Counting Machine | [15 empty] | 0.001888 |  | 0.001888 | [22 empty] | 0.001888 |  | 0.001888
34 | 230 V AC DIGITAL SINE WAVE INVERTER 1 No. | [15 empty] | 0.010175 |  | 0.010175 | [22 empty] | 0.010175 |  | 0.010175
35 | HPCV no.3 &4 Stem | [16 empty] | 0.025694 | 0.025694 | [23 empty] | 0.025694 | 0.025694
36 | HEAVY DUTY AIR PURIFIURE 230V,50HZ | [16 empty] | 0.0105 | 0.0105 | [23 empty] | 0.0105 | 0.0105
37 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | [16 empty] | 0.0048144 | 0.0048144 | [23 empty] | 0.0048144 | 0.0048144
38 | WALL MOUNTED FAN 18" 230V 1440RPM | [16 empty] | 0.025939 | 0.025939 | [23 empty] | 0.025939 | 0.025939
39 | APPLN COOLER WTR CAP CAP: 60 LITERS | [16 empty] | 0.0053799 | 0.0053799 | [23 empty] | 0.0053799 | 0.0053799
40 | LASER LASERJET PRINTER FOR A4 PAPER | [16 empty] | 0.0057 | 0.0057 | [23 empty] | 0.0057 | 0.0057
41 | 40 Inch Smart LED TV 3.00 | [16 empty] | 0.010178 | 0.010178 | [23 empty] | 0.010178 | 0.010178
42 | DESKTOP INTEL CORE I5 2300 PROCESSOR | [16 empty] | 0.021459 | 0.021459 | [23 empty] | 0.021459 | 0.021459
43 | ONLINE WATER HEATER, 3KW,3LTR. | [16 empty] | 0.029683 | 0.029683 | [23 empty] | 0.029683 | 0.029683
44 | CAMERA FOR VC, MICROPHONE WITH SPEAKER | [16 empty] | 0.023889 | 0.023889 | [23 empty] | 0.023889 | 0.023889
45 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | [16 empty] | 0.0082836 | 0.0082836 | [23 empty] | 0.0082836 | 0.0082836
46 | FILTER RO+UV+UF+TDS WATER PURIFIER | [16 empty] | 0.01873 | 0.01873 | [23 empty] | 0.01873 | 0.01873
47 | Water Cooler | [16 empty] | 0.005 | 0.005 | [23 empty] | 0.005 | 0.005
48 | PORTABLE HARD DISK USB 1TB | [16 empty] | 0.0017388 | 0.0017388 | [23 empty] | 0.0017388 | 0.0017388
49 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | [16 empty] | 0.00095 | 0.00095 | [23 empty] | 0.00095 | 0.00095
50 | Garbox assembly for premium make type B-220 of | [17 empty] | 0 | 0.44095 | [23 empty] | 0 | 0.44095
51 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | [17 empty] | 0 | 0.006726 | [23 empty] | 0 | 0.006726
52 | RO+UV+UF+TDS CAP 50 LITRE PER HOUR | [17 empty] | 0 | 0.002731 | [23 empty] | 0 | 0.002731
53 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | [17 empty] | 0 | 0.0025995 | [23 empty] | 0 | 0.0025995
54 | WEIGHING SCALE 500KG CAPACITY | [17 empty] | 0 | 0.002183 | [23 empty] | 0 | 0.002183
55 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | [17 empty] | 0 | 0.0061808 | [23 empty] | 0 | 0.0061808
56 | REGULAR CHAIR WITHOUT CUSHION | [17 empty] | 0 | 0.0082836 | [23 empty] | 0 | 0.0082836
57 | BLDC Fans through GeM Portal and GA -2022-23 at | [17 empty] | 0 | 0.0049556 | [23 empty] | 0 | 0.0049556
58 | ALL IN ONE PC, CORE I5, 4 GB RAM, 500 GB | [17 empty] | 0 | 0.02973 | [23 empty] | 0 | 0.02973
59 | PRINTER LASER LASERJET NETWORK PRINTER | [17 empty] | 0 | 0.0020024 | [23 empty] | 0 | 0.0020024
60 | APPLN FAN AIR CEIL SIZE 1200 MM SWEEP | [17 empty] | 0 | 0.033918 | [23 empty] | 0 | 0.033918
61 | WALL MOUNTED FAN 18" 230V 1440RPM | [17 empty] | 0 | 0.014828 | [23 empty] | 0 | 0.014828
62 | 400 MM, 230V, 3 BLADE DOMESTIC FAN | [17 empty] | 0 | 0.0024532 | [23 empty] | 0 | 0.0024532
63 | APPLN FAN AIR EXHAUST SIZE15"1400RPM-15 Nos | [17 empty] | 0 | 0.01781 | [23 empty] | 0 | 0.01781
64 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | [17 empty] | 0 | 0.013559 | [23 empty] | 0 | 0.013559
65 | MICROWAVE OVEN CAPACITY 27 / 28 LITERS-1 Nos | [17 empty] | 0 | 0.0048362 | [23 empty] | 0 | 0.0048362
66 | REFRIGERATOR SINGLE DOOR CAPCITY 190 LTR | [17 empty] | 0 | 0.0067225 | [23 empty] | 0 | 0.0067225
67 | Supply of Thinclients on Buyback for NTPS | [17 empty] | 0 | 0.23166 | [23 empty] | 0 | 0.23166
68 | ABC Powder type DCP Composite Fire Extinguisher | [17 empty] | 0 |  | 0.357 | [22 empty] | 0 |  | 0.357
69 | CLASS ROOM CHAIR WITH DESKLET | [17 empty] | 0 |  | 0.024631 | [22 empty] | 0 |  | 0.024631
70 | CLASS ROOM CHAIR WITH DESKLET | [17 empty] | 0 |  | 0.024213 | [22 empty] | 0 |  | 0.024213
71 | Furniture Dining Table for Main Mess Hall and Cus | [17 empty] | 0 |  | 0.019803 | [22 empty] | 0 |  | 0.019803
72 | Servers for DSM at Nashik Thermal Power Station | [17 empty] | 0 |  | 0.43559 | [22 empty] | 0 |  | 0.43559
73 | DESKTOP INTEL CORE I5 2300 PROCESSOR - 5 Nos | [17 empty] | 0 |  | 0.05632 | [22 empty] | 0 |  | 0.05632
74 | SPLIT AC 3 TON COMPLETE UNIT | [17 empty] | 0 |  | 0.041064 | [22 empty] | 0 |  | 0.041064
75 | SPLIT AC 3 TON COMPLETE UNIT | [17 empty] | 0 |  | 0.038246 | [22 empty] | 0 |  | 0.038246
76 | APPLN TV STD ULSLIM 42" - 4 Nos | [17 empty] | 0 |  | 0.037376 | [22 empty] | 0 |  | 0.037376
77 | 1 T SPLIT AC COMPL UNIT WITH ACCESSORIES | [17 empty] | 0 |  | 0.011682 | [22 empty] | 0 |  | 0.011682
78 | MULTIMEDIA PROJECTOR EPSON EB-U05-1 No | [17 empty] | 0 |  | 0.0081606 | [22 empty] | 0 |  | 0.0081606
79 | WEIGHING SCALE 500KG CAPACITY | [17 empty] | 0 |  | 0.0023246 | [22 empty] | 0 |  | 0.0023246
80 | Procurement of Complete Vibrating Screen Assembly at CHP-II | [12 empty] | 1.Improve coal unloading rate. 2.To reduce unloading time. 3.To improve plant availability. 4.To reduce the maintenance cost. 5.Reduction in demurrage hours. |  |  |  |  | 0 |  |  | 0.61 | [21 empty] | 0 |  |  | 0.61 | [6 empty] | 1) Non-DPR Scheme 2) Will be completed & capitalized by March-25 | WIP
| General Asset | [17 empty] | 0 |  |  | 0.575 | [21 empty] | 0 |  |  | 0.575 | [6 empty] | General Asset Schemes | WIP
| Total | [13 empty] | 220.0698 | 33.2669 | 6.8552 | 7.8783 | 268.0703 | 9.45 | 8.2467 | 6.5675 | 711.384 | 1040.6982 | 89.2414 | 9.102 | 0.5 | [12 empty] | 218.3105 | 34.4742 | 5.2501 | 10.0355 | 268.0703 | 6.9245 | 5.1124 | 9.6648 | 735.654 | 1040.6982 | 89.2414 | 9.102 | 0.5
[45 empty] | 0.83213 | 1.0564 | 1.185
0
Formulas:
Date of Submission = [Date of Submission, row above]
MERC Approval Date = IF([MERC Approval Date, row above]=0,"-",[MERC Approval Date, row above])
Note on M4: SSP-RCD As per the implementation plan submitted in the DPR/ Approved by MERC
Note on P63: SSP-RCD: FY 2010-11
Note on AO63: SSP-RCD: FY 2010-11
Note on P65: SSP-RCD: FY 2011-12
Note on AO65: SSP-RCD: FY 2011-12
Note on P66: SSP-RCD: FY 2012-13 & 2014-15
Note on AO66: SSP-RCD: FY 2012-13 & 2014-15
Note on P67: SSP-RCD: FY 2013-14 & 2014-15
Note on AO67: SSP-RCD: FY 2013-14 & 2014-15
Note on P69: SSP-RCD: FY 2013-14
Note on AO69: SSP-RCD: FY 2013-14
Note on P149: SSP-RCD: FY 2009-10
Note on AO149: SSP-RCD: FY 2009-10
Note on P152: SSP-RCD: FY 2008-09
Note on AO152: SSP-RCD: FY 2008-09

## F4.3
MSPGCL: Nashik TPS
MTR Petition Formats - Generation
| Project Details | Form 4.3: Capital Work-in-progress - Project-wise details | [9 empty] | (Rs. Crore)
Sr. No. | Project Code | MERC Approval No. | MERC Approval Date | Approved Project Cost | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Opening CWIP | Investment during the year | Capitalization |  |  |  | Closing CWIP
[9 empty] | Works Capitalised | Interest Capitalised | Expenses Capitalised | Total Capitalisation |  | Allowable Capitalisation | Probable Disallowance
FY 2022-23
a) DPR Schemes
(i) Submitted to MERC
1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Measuring & Monitoring of Coal consumption | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 23.0165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Belt Weighers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3295 | 0.3295 | 0.3295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.793 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of inhaul outhaul betel chargers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 6 | 8.5943 | 8.5943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Dust Extraction System | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 1.65 | 1.713 | 1.713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Fogging system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 2.44 | 2.59 | 2.59 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Bunker level montoring system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.54 | 0.0694 | 0.0694 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.169 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Operating the CHP near to its full capacity | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 7.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Motor controller | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3732 | 0.3732 | 0.3732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 3.4218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Combustion optimization & Process improvement | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 58.7761 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Improvement in tooling techniques Power tools like cut off machines and surface grinders. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.52821 | 0.3388 | 0.3388 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Total replacement of boiler related skin insulation as well as skin cladding of furnace, Air pre heaters,air ducts and flue gas ducts Unit-4 &5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4.5892 | 4.7188 | 4.7188 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Painting of Boiler ,bunker structure and other structure.Unit-3,4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 7.775 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 8.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Retrofitting of Gas proportioning dampers, flue gas, primary and secondary air dampers. (SADC) for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.456 | 1.1278 | 1.1278 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.33475 | 0.33475 |  |  | 0.33475 | 0
4.6 | Replacement of flue gas ducting zone prone to erosion with 6 to 8 mm high grade material & insulation of flue gas ducts. (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 4 and 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Replacement of boiler outlet valves and damaged valves of units 4 & 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.349 | 1.4313 | 1.4313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Replacement of coal pipe at direction changing sections & flow curvature zone by upgraded material. Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.3292 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.9 | Installation of Smart soot blower system for Unit- 4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 5.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.10 | Installation of Sonic soot blowers for second pass for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.83184 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.11 | Air pre heater upgradation of heat exchanger matrix &regenerative dynamic sealing for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.12 | Replacement Platen water wall for Unit-3. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.60762 | 0.6964 | 0.6964 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 13.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Turbine Auxiliary Consumption Improvement | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 39.2903 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Installation of Turbo vaned fly wheeling eco ventilators to all Units 3, 4, 5. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Replacement of selected old brass impellers of pumps with SS304 impellers. H.T. Auxiliary C.W. Pump and G.S. Water Pumps are selected. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.4 | 0.8251 | 0.8251 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Improving the BFP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.75 | 0.48804 | 0.48804 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Replacement of BFP (200 KHI) cartridge with energy efficient cartridge. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 14.4456 | 13.85 | 13.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Improving the CEP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.9 | 0.6018 | 0.6018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Replacement of CEP with energy efficient pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Replacement of Pumps - GS Pumps, H2Cooler booster pump, DM/DM pumps, DM Makeup pumps, Emergency lift pumps, Drip pumps, BFP Booster pumps with energy efficient pumps. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 4.2733 | 2.3608 | 2.3608 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.8 | Replacement of valves – MS - 3 to 8 , HD – 22,23,24 , MC- 36 , ES 3,4 and BFP Recirculation Valves. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.0852 | 1.3148 | 1.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.9 | Replacement of tube nest of LP Heater no.3 of unit no.3, LP Heater no.4 of unit no.5, Main ejector 3B, GC2 of unit no.5, Seal oil coolers, H2 Coolers, BFP working and lub oil coolers, DM/GS plate type coolers. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 6.5962 | 1.4406 | 1.4406 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.11461 | 0.11461 |  |  | 0.11461 | 0
5.10 | Steam path audit of Unit no,4,5 | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | EMS, Numeric relays, Microprocessor DVR & VFD | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 12.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Design, manufacture, supply, erection, commissioning & testing of Variable Frequency Drives (VFD) with latest design and technology super premium efficiency motors for 415 V LT Auxiliaries (Total 50 No) of 210 MW Unit 3, 4 & 5. | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 6.3 | 2.1638 | 2.1638 | 0 | 2.5255 | 0 |  |  | 0 | 2.5255 | 0 | 0
0 | IDC | 0 | - | 0.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Replacement of old EE make Generator Protection Relays with Numerical Generator Protection Relays for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 1.7 | 1.7029 | 1.7029 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Replacement of old AVR with Microprocessor based Digital Voltage Regulator for unit no. 3 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 2.44 | 1.7055 | 1.7055 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Installation and commissioning of Energy Management System for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.81 | 0.8313 | 0.8313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 14.5069 | 14.5069 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 57.9147 | 57.9147 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Faster unloading of coal wagons by upgrading existing system (Post Facto) | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 18.8481 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Re-design, Supply, Erection and commissioning of modified Apron Feeder. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.7219 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Design, manufacture, supply, erection and commissioning of modified bunker outlet cone of Unit 3, 4 and 5. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.3295 | 2.3196 | 2.3196 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Design, manufacture, Supply & Erection Of Components Suitable For Modification Of Wagon Tipplers to Handle BOXNHL , BOX-H,BOX-NR,BOX-NJLSR1 & 25 T AXLE WAGONS | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.1298 | 4.413 | 4.413 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Procurement of SAN Loco - 650-700 HP. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8627 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.5 | Revamping of CHP II Wagon Tippler by replacing the Split Wheel Assembly, Pawl Lever, Pinion Shaft Assembly, Toe, Spur Gear Shaft, W.T Drive Assembly, Rack Segment, Rail Table Assembly Of Wagon Tippler and Dismantling & Replacement of above parts | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8042 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement of 6.6 Kv HT motors as spare motors /for replacement | MERC/CAPEX/20152016/00422 | 2016-08-03 | 14.3563 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3125 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1025 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | FD FAN MOTOR 650 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | FD FAN MOTOR 750 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8505 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | PA FAN MOTOR 1250 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.029 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | BFP MOTOR 4000 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 4.5528 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | C/MILL MOTOR 320 kW (3 Nos) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3356 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.8 | SOP MOTOR 200 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.9 | CWP MOTOR 950 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8942 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.10 | CTLP MOTOR 710 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8081 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.11 | RWP MOTOR 335 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.4861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.12 | HP PUMP MOTOR 258 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3083 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.13 | CEP MOTOR 220 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2629 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.14 | GS PUMP MOTOR 260 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3107 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.15 | Testing charges | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.088 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Replacement of complete LTSH coils at Unit-3 Boiler & Economiser coils at Unit-5 Boiler | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 27.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Complete Supply & Erection of LTSH coils at Unit-3 210 MW Boiler (67 nos. upper and lower modules each. 01 module = 02 coils) | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 16.43 | 4.6378 | 4.6378 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Complete Supply & Erection of 270 nos. Economizer coils in second pass of Unit-5 210 MW Boiler at Nasik TPS. | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 9.57 | 3.0104 | 3.0104 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 1.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Enhancement of performance & life of Coal Handling plant | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 17.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Procurement of 02 nos of 320 hp bull dozers for Nasik TPS | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 3.2 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Procurement of gear box for Apron Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 1.59 | 1.6043 | 1.6043 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Procurement of gear box and 30 KW DC motor for Pedal Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.46 | 0.45847 | 0.45847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.4 | Procurement of Assembly of Impact Crusher Complete set, with Rotor Assembly and bearing Block. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 2.3 | 2.3366 | 2.3366 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.5 | Procurement of 10 KW Inline Magnetic Separator for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.4 | 0.54718 | 0.54718 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.6 | Restoration of RBCR by replacing feed end Spider (Drg. No. 400-1428-01/A) & Discharge end Spider (400-1428-02) suitable to rotary Bradford breaker machine No.CR/634 along with support wheels. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 8.14 | 10.2287 | 10.2287 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.7 | Procurement of 750 KW Impactor Motor for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.49 | 0.22635 | 0.22635 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.8 | Supply of Metal Detectors for CHP | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.14 | 0.09152 | 0.09152 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Retrofitting of 6.6 kV Breakers, Battery Replacement, System Improvement & MPCB Related schemes | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 14.7811 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Retrofitting of 6.6 kV HT MOCB/SF6 Breakers by VCB | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 3.57 | 5.0621 | 5.0621 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2a | A) Procurement & Replacement of 220V/ 1285 AH Battery set for U#3 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0493 | 1.0493 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2b | B) Procurement & Replacement of 220V/ 1285 AH Battery set for U#4 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0047 | 1.0047 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | O2 Measurement System in the furnace & flue gas ducting | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.17 | 1.2966 | 1.2966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Supply, erection, commissioning & testing of online CO, SO2, NOX Analyser for U#3/4/5 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.6511 | 1.6846 | 1.6846 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | A) Replacement of static Flame Monitoring System with Microprocessor based Flame Monitoring & Analyzing System | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.27 | 2.4267 | 2.4267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | CAAQMS monitoring of ambient air quality around the NTPS. | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1 | 0.81676 | 0.81676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | 3rd raising of Ash bund | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | 3rd raising of ash bund from TBL 581.50 to 586.50m in valley No. 4A at Nashik Thermal Power Station, Eklahare | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 12.3 | 10.2142 | 10.2142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | System Rehabilitation & Upgradation at Nasik TPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 13.3722 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Shifting, Transportation & Replacement of Existing Generator Stator of Unit no.3 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 7.98 | 0.8767 | 0.8767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.20198 | 0.20198 |  |  | 0.20198 | 0
15.2 | Turbine Supervisory Instrumentation System for Unit no.5 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.5542 | 0.45436 | 0.45436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Supply of Air Compressors for NTPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 3.398 | 3.8197 | 3.8197 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Replacement of Old Brass Impellers of CTLP with SS Impellers. | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 1.04 | 1.1331 | 1.1331 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up-gradation of DCS at U # 3 and New Rectiformers & ESP Refurbishment of U # 4 & 5 at Nasik TPS | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 33.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Decommissioning & Shifting of M/s ABB make DCS system at BTPS Unit # 2 & Re-commissioning with Up gradation to Symphony Plus at NTPS Unit #3, Nasik. | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 9.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Erection ,Testing & commissioning, Supply of rectiformer HVR 37/800 Hermatically sealed Rectiformer ( DC Peak voltage – 70 kV , Average voltage-45 KV ,DC Current – 800 milli amp , AC I/P – 1 Phase , 415 V ) | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 10.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.3 | Refurbishment of ESP for Unit No. 4 & 5 at Nashik TPS, Eklahare | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 12.5 | 12.8553 | 12.8553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 1.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Replacement of drum gate, augmentation of existing ash water recovery scheme and construction of concrete road for Nasik Thermal Power Station | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 14.5161 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Replacement of drum gate and restructuring of cofferdam, repairs to vertical sluice gate, Approach Bridge and allied civil works at Godavari barrage at Nashik TPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 6.273 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | Augmentation of existing ash water recovery scheme and connecting overflow of waste weir to existing toe drain of ash bund valley no.4 to WWR at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 2.5999 | 3.1676 | 3.1676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.2441 | 0.2441 |  |  | 0.2441 | 0
17.3 | Up gradation of fly ash concrete road from Booster Pump house toward Hydrogen plant, Dirk India Company towards Hinganwedhe along ash bund valley No. 1 & 2, Ash bund approach road for ash transportation and abundant valley towards Kotamgaon road at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 5.3732 | 5.3752 | 5.3752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 0.27 | 0 | 0 | 0 | 0.38455 | 0.38455 |  |  | 0.38455 | 0 | 0.27 | 0.11455
18 | Various DPR Schemes for Renovation of colony at NTPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 10.8678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Renovation of staff quarters, playground, Jogging track & Gymnasium at NTPS colony, Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 4.071 | 3.5306 | 3.5306 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.92832 | 0.92832 |  |  | 0.92832 | 0
18.2 | Road works in NTPS Colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 3.9766 | 3.8972 | 3.8972 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Water supply and sanitation works at NTPS colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 2.8202 | 1.4586 | 1.4586 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.19994 | 0.19994 |  |  | 0.19994 | 0
18.4 | Renovation of Workers Recreation Club at Nashik TPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Life enhancement of stacker cum reclaimer machine in CHP & upgradation of SWAS laboratory at Nasik TPS | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 14.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Supply, Erection & installation of sole plates, Rail track & Hydraulic cylinder of the Stacker cum Reclaimer machine at Coal Handling Plant-II Nashik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 6.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement and replacement of 220 V, 1285 AH battery set for Unit No. 4 at Nasik Thermal Power Station. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 1.39 | 1.3596 | 1.3596 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.11272 | 0.11272 |  |  | 0.11272 | 0
19.3 | Supply of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers Ltd.) at Nasik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 3.11 | 3.0812 | 3.0812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Erection and commissioning of Steam and Water sampling system for SWAS Lab at WTP, NTPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 2.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.5 | Procurement of 3 nos. of Ash Slurry Disposal pump Type D - 85 for Ash Slurry Pump House of Unit no. 3, 4 & 5 at NTPSEklahare. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Flue Gas Desulphurization (FGD) System at Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Ash Augmentation System at Nasik & Koradi Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Ash Augmentation System at Nasik Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 5.71 | 5.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3.1 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 8.47 | 8.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | NASIK TPS (U-3 to 5) (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 2.8152 | 2.8152 | 0 | 0.069 | 0.069 |  |  | 0.069 | 0 | 0 | 0.069
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.76776 | 0.76776 |  |  | 0.76776 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Nashik TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 0.042551 | 0.042551 | 0 | 2.1847 | 2.1847 |  |  | 2.1847 | 0 | 1.2074 | 0.9772
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | TPS Nashik | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 2.3118 | 2.3118 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.1 | Procurement and Replacement of Complete sets of assembly of baskets for air preheater of type tri-sector APH 27 VI(T) 74” in NTPS unit no. 4 & 5 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 1.9868 | 1.9868 | 0 | 0.54994 | 0.54994 |  |  | 0.54994 | 0 | 0.54994 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | <DPR Name> | N.A. | N.A. | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Complete Replacement of HRH Coils, LTSH Coils, Economizer Coils at Unit No. 4 & Complete Replacement of Economizer coils at Unit No.3 Nashik TPS 210 MW Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Replacement HRH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete Replacement LTSH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete Replacement Economiser Coils at NTPS Unit No. 3 & 4 Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 and Commissioning of AFGC system for Unit No. 3, 4 & 5 and Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5 at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of MSERW pipes for Replacement of various pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 at NTPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, erection, commissioning & testing of Ammonia Flue gas Conditioning system for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5, 210 MW, NTPS, Eklahare, Nasik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Complete replacement of Platen Superheater coils at Unit No.3,4 & 5 ; Complete replacement of HRH coils at Unit No.3,& 5; Complete replacement of LTSH coils at Unit No. 5;Replacement of thermal insulation at Boiler for Nashik TPS 210 MW boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete replacement of Platen Superheater coils at Unit No. 3,4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete replacement of HRH coils at Unit No.3,& 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete replacement of LTSH coils at Unit No.5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines at Unit No.3,4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | Procurement of various pumps for TM & ODP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement and Erection Commissioning of Condenser vacuum pump for Unit No. 3 ,4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Three Pump assemblies of SAM TURBO makes Type 150/500 N for Booster Pump house at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 3 Nos Vertical Fly Ash Transfer Pump VO 150 /400 + ARS SAM make along with motor for ESP Hopper evacuation of Unit No.3,4 & 5 at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection, installation, civil foundation, commissioning, testing & trial of Rotating &casing assembly of pumps for WTP at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement (10 nos.) of CWFW pumps (with motor) at Stage-II (Beacon make) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of RWP Pump assembly at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Cooling Tower lift Pump Impeller for Jyoti make pump Type:-1200- VMI A 12 at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Degasser Pump assembly with motor (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 8 Nos. of Domestic water pumps (with motor) & Darna drinking water pump at Stage-I & II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of 4 Nos. of DM backwash (2 Nos.) & CW backwash pump (2 Nos.)(with motor)at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of HP Pumps at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of ETP pump assembly (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of RWP shaft with bearing, Impeller (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Procurement of AWR pump (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Submersible Slurry Pumps for handling Ash water / Clear water for dewatering at various locations at NTPS (10 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 5 | Renovation of Compressed Air Refrigerated Dryer System, Refurbishment of Centralized Air Conditioning system, Supply, erection & commissioning of Condensate Extraction Pump, Procurement of CW Pump and GS pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Compressed Air Refrigerated Dryer System for Nashik TPS, 210 MW Unit No. 3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of Centralized Air Conditioning system of Unit No. 3, 4 & 5 at Nashik TPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers ltd. at Nasik TPS. Total Qty. 02 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of CW & CTLP Pump total 4 No.s | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of GS Pump assembly .Total qty- 3 No | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 6 | Procurement of oil free Rotary Screw Compressors and BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of oil free rotary screw compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 7 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets, Refurbishment of HPT rotor along with supply, Procurement of HP & IP control valve with cam shaft assemblies, Procurement of complete governing system assembly, Supply, Errection & Commissioning of COP assembly, Procurement of Condenser tubes & ODP related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets at 3 x 210 MW, TM-II NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of HPT rotor along with supply. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of HP & IP control valve with cam shaft assemblies.qty-1set | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of complete governing system assembly. qty-1 set | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, Errection & Commissioning of COP assembly.Total Qty.- 3 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Condenser tubes for Unit No.3, 4 & 5.Total Qty:15700 tubes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of CT Fan Blade assembly & shaft- 36 nos for Unit No.3,4 & 5 at NTPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Gearbox Assembly for Cooling Tower Fans type B-220 Premium make for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare (Qty-24) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 5 nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Flocculator gearbox- 12 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of Clinker grinder assembly at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of 4 Nos. of Clinker grinder gearbox at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of 5 Nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Augmentattion of existing Ash Water recovery Scheme(WWR,AWR, ETP-I,ETP-II & Phase-II pump assembly) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Feed Gate Housing (08 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 8 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area & Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 9 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS , Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 10 | Upgradation of various electrical related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of 6.6KV HT motors and spares at Nashik TPS Unit No 3,4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Boiler and turbine house lighting of Unit No.3,4 & 5 along with removal of old wiring. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacemet of IPH transformer 11KV/6.6 KV and lighting and welding transformer at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Excitation Transformer at Unit No. 3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | GTR /UAT/ station transformer spares LV bushings replacement, HV bushings (spare)-3nos, LV busbar, palm joint both station transformers bushings at Unit No.3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of overhead conductor HT/LT by underground HT/LT cable in Colony area. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | LT transformer procurement/ rewinding work at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | LT MCC panel modification at ODP area NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Battery Charger-220V,50V,380V UPS, 24V,DG set EMF panel with charger replacement, UPS battery replacement, Unit No. 5 station battery replacement,50 V battery set replacement at Unit No.3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Replacement of HT motor Cables. (Old PILC Cable replacement with XLPE Cable) at Unit No.3, 4 & 5 & ODP area | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Unit No. 4 Field Breaker | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 11 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 12 | Replacement/Upgradation of C&I old systems at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement/Upgradation of Unit No.4 DVR System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement/Upgradation of Unit No.4 UPS System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotory Electronic Control Drive for Burner Tilt and Auxiliary Air Damper at Unit No. 3, 4 & 5 210 MW, NTPS, Eklahare Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification/Upgradation of Turbovisory system of Unit No. 3,4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Auxiliary air dampers & BT, HAD, feed gate replacement/modification work. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Unit No.4 DCS-FCS 102 to FCS 106 (Total 5 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | New sewage treatment plant required at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Upgradation of Unit No.4 230 V UPS and new UPS, charger for Unit No. 3 & 5 DCS at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | ESP hopper high & low level indicator mounting in Unit No.3,4& 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | OCEMS for Sox, Nox, opacity monitoring system upgradation work for Unit No.3, 4 & 5 at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Supply, Erection, Commissioning & Testing of online H2 purity meter and Resistivity meter for Unit No. 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, Erection, commissioning of Hydra step system for Drum level control Unit No.3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | HPLP - Servo Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Replacement of Relays and Energy meter at NTPS, Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | ESP upgradation for Unit No. 3, 4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Grounding Brush Monitoring System for Unit No. 3,4& 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Implementationof FGMO | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 13 | Modification & replacement of various CHP schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Modification of single stream conveyor belt Gearboxes with new design Helical Bevel type Gearboxes at CHP-II NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Modification of Primary Vibrating screen at CHP-II, NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Rail table alongwith weighment frame for rotaside Wagon Tippler at CHP-II, NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification of Conveyor Drive system with Motorised Pulley drive system at CHP-II, NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Replacement of old damaged RBCR rail beam M/c No. CR/964 & screen to increase life of RBCR n reduced direct impact of raw coal on secondary impact crusher. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of copmlete crusher unit as per Drg. No. P00304/0 CO/1050 CR635-636(impact crusher body & rotor shaft assembly) 2 Nos | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of appron feeder head shaft assembly-25/005 drg no.-M15076/2 & tail shaft assembly-25/006 Drg. No.- M15065/2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply & erection of wagon tippler rail table Drg. No.12578/45-01 , tippler support roller & bogei Drg. No-12616/45-2M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of seondary crusher motors 6.6KV, 750KW & 220KW motor for CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Supply of LT motors for various conveyor belts of CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Up-gradation of existing DC drive system of Wagon Tippler & Paddle feeder with new version DIGICON make system along with supply, installtion, commissioning & testing of DC drives at CHP-III. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply of Variable Frequency drives for Conv.16C2 at CHP-III. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Up-gradation of existing relay panel of control room with microprocessor based PLC logic system along with supply, installtion, commissioning & testing of relay panel at CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Supply of Magnetic seperators & Metal detectors at CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Repair & renovation of NTPS colony ,Repairing work of ash bund side & Eklahare barrage | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of renovation of various residential quarters by providing and fixing kitchen sink, kitchen trolley & granite otta at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing and applying external painting to various types residential buildings at NTPS colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Providing and applying internal painting to various types of residential quarters at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Providing and fixing vitrified tiles to various types of residnetial buildings at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening works to various residential quarters at NTPS colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing and fixing colour coated galvanised iron sheets for roofing at various residential buildings at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Sewer line repair of various quarters at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Stair case repairing of various building at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Construction of WBM road over/at the top of ash bund at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Repairs to filters of drain well No.4 and other allied works at ash bund valley No.4A at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Repairs to Godavari river barrage gates and allied works at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Structural repairs of Cooling Tower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repairs of cooling tower components at Unit No. 3A, 3B, 4A, 4B,5A & 5B, Stage-II NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Structural repair & rehabilitation and Renovation and modification work at NTPS Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repair & rehabilitation of various machine foundations of ID, FD & PA fans for Unit No. 3, 4, 5 at Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of removing and providing 24 B.W.G.for pent house side & roof at Unit No. 3,4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of removing and providing old damaged siporex wall and poly coated sheet for 28 mtr. height at Unit No. 3, 4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Structural repairs of chimney at Unit No. 3,4 & 5 Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Renovation of sump No. 2,3,4,5,6 and 7 at WTP Stage-II, NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Work of structural repairing at CHP-I,II & III area at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work of structural repairing at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Work of structural repair of GS pump Unit No. 3,4,& 5 and fire fighting pump house at Stage-II,NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Work of repairs to doors & windows of various building at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Providing and fixing powder coated colored Zincalume profiled sheet for various building at CHP,AWR building, Time office & ODP EM at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of external painting & internal painting at WTP, Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of external painting & internal painting at CHP area NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Renovation and restructuring of shed No. 1, 2, 5, 6, 9 & 11 of major store custody of NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | As per I.B.Recommondation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of construction compound wall with concertina coil at various locations at Nashik TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing & renovating security watch tower at NTPS Premises Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | R&M/LE for Identified Thermal units of MSPGCL of (3 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL (3 x 210 MW) units of MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | CHP Improvcement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | TATA Mini Truck SFC 709 EX No.MH-15-JV-3992 | N.A. | - | 0 | 0.32099 | 0.32099 | 0 | 0 | 0 |  |  | 0 | 0
2 | Executive chair(10),S Type Arm chai(20) | N.A. | - | 0 | 0.10784 | 0.10784 | 0 | 0 | 0 |  |  | 0 | 0
3 | Office Table and S-Type Chair with Arm | N.A. | - | 0 | 0.030968 | 0.030968 | 0 | 0 | 0 |  |  | 0 | 0
4 | Windows Slot in PC VPC 10-Intel Core 13 4th -NTC | N.A. | - | 0 | 0.010561 | 0.010561 | 0 | 0 | 0 |  |  | 0 | 0
5 | LG Screen wall mounted computer-LED display65"-NTC | N.A. | - | 0 | 5.0969 | 5.0969 | 0 | 0 | 0 |  |  | 0 | 0
6 | 20 Ton Split AC for Audtiorium -NTC | N.A. | - | 0 | 1.0873 | 1.0873 | 0 | 0 | 0 |  |  | 0 | 0
7 | Colour Laser Printer, All in one A3 LaserJet Print | N.A. | - | 0 | 1.0589 | 1.0589 | 0 | 0 | 0 |  |  | 0 | 0
8 | Digital DSLR Camera | N.A. | - | 0 | 1.0793 | 1.0793 | 0 | 0 | 0 |  |  | 0 | 0
9 | Indoor Gymnasium Equipments at NTC, Eklahare | N.A. | - | 0 | 0.02853 | 0.02853 | 0 | 0 | 0 |  |  | 0 | 0
10 | CLASS ROOM CHAIR WITH DESKLET | N.A. | - | 0 | 0.023576 | 0.023576 | 0 | 0 | 0 |  |  | 0 | 0
11 | PA System and Sport Material,Table Tannis for | N.A. | - | 0 | 0.01687 | 0.01687 | 0 | 0 | 0 |  |  | 0 | 0
12 | EXECUTIVE CHAIR WITH 5 SUPRT & S-TYPE CHAIR | N.A. | - | 0 | 0.01003 | 0.01003 | 0 | 0 | 0 |  |  | 0 | 0
13 | APPLN COOLER AIR SEMIEXH AIR COOLER ASSY | N.A. | - | 0 | 0.033896 | 0.033896 | 0 | 0 | 0 |  |  | 0 | 0
14 | FULL PAD CHAIRS WITH SIDE ARM | N.A. | - | 0 | 0.029637 | 0.029637 | 0 | 0 | 0 |  |  | 0 | 0
15 | Industrial Cabinet with 12 Lockers | N.A. | - | 0 | 0.0070163 | 0.0070163 | 0 | 0 | 0 |  |  | 0 | 0
16 | UV Water Purifier Filter | N.A. | - | 0 | 0.019116 | 0.019116 | 0 | 0 | 0 |  |  | 0 | 0
17 | FILTER RO+UV+UF+TDS WATER PURIFIER | N.A. | - | 0 | 0.032906 | 0.032906 | 0 | 0 | 0 |  |  | 0 | 0
18 | 2 Tone SPLIT AC INDOOR UNIT | N.A. | - | 0 | 0.008064 | 0.008064 | 0 | 0 | 0 |  |  | 0 | 0
19 | 1.5 TON CAPACITY SPLIT AC | N.A. | - | 0 | 0.006688 | 0.006688 | 0 | 0 | 0 |  |  | 0 | 0
20 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 1.698 | 1.698 | 0 | 0 | 0 |  |  | 0 | 0
21 | Logitech PTZ Group Camera 960-001054 | N.A. | - | 0 | 2.4375 | 2.4375 | 0 | 0 | 0 |  |  | 0 | 0
22 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011564 | 0.011564 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK BENCH WITHOUT DRAWER | 0 | - | 0 | 0.011647 | 0.011647 | 0 | 0 | 0 |  |  | 0 | 0
24 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.030075 | 0.030075 | 0 | 0 | 0 |  |  | 0 | 0
25 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011788 | 0.011788 | 0 | 0 | 0 |  |  | 0 | 0
26 | EXECUTIVE CHAIR, S-TYPE CH-7 CHAIR WITH ARM | 0 | - | 0 | 0.035229 | 0.035229 | 0 | 0 | 0 |  |  | 0 | 0
27 | SAMSUNG GALAXY TAB S3, 32GB 9.7 INCH | 0 | - | 0 | 0.003845 | 0.003845 | 0 | 0 | 0 |  |  | 0 | 0
28 | i5 Laptop - 2 Nos & i7 Laptop - 3 Nos | 0 | - | 0 | 0.037636 | 0.037636 | 0 | 0 | 0 |  |  | 0 | 0
29 | Godrej make 1.5 Ton High Wall Split AC | 0 | - | 0 | 0.020975 | 0.020975 | 0 | 0 | 0 |  |  | 0 | 0
30 | Complete Multimedia Projector with Std Accessories | 0 | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
31 | LED 40 INCH SMART TV | 0 | - | 0 | 0.0092016 | 0.0092016 | 0 | 0 | 0 |  |  | 0 | 0
32 | FULL PAD CHAIRS, EXECUTIVE CHAIR, | 0 | - | 0 | 0.068995 | 0.068995 | 0 | 0 | 0 |  |  | 0 | 0
33 | Cash Counting Machine | 0 | - | 0 | 0.001888 | 0.001888 | 0 | 0 | 0 |  |  | 0 | 0
34 | 230 V AC DIGITAL SINE WAVE INVERTER 1 No. | 0 | - | 0 | 0.010175 | 0.010175 | 0 | 0 | 0 |  |  | 0 | 0
35 | HPCV no.3 &4 Stem | 0 | - | 0 | 0.025694 | 0.025694 | 0 | 0 | 0 |  |  | 0 | 0
36 | HEAVY DUTY AIR PURIFIURE 230V,50HZ | 0 | - | 0 | 0.0105 | 0.0105 | 0 | 0 | 0 |  |  | 0 | 0
37 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.0048144 | 0.0048144 | 0 | 0 | 0 |  |  | 0 | 0
38 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.025939 | 0.025939 | 0 | 0 | 0 |  |  | 0 | 0
39 | APPLN COOLER WTR CAP CAP: 60 LITERS | 0 | - | 0 | 0.0053799 | 0.0053799 | 0 | 0 | 0 |  |  | 0 | 0
40 | LASER LASERJET PRINTER FOR A4 PAPER | 0 | - | 0 | 0.0057 | 0.0057 | 0 | 0 | 0 |  |  | 0 | 0
41 | 40 Inch Smart LED TV 3.00 | 0 | - | 0 | 0.010178 | 0.010178 | 0 | 0 | 0 |  |  | 0 | 0
42 | DESKTOP INTEL CORE I5 2300 PROCESSOR | 0 | - | 0 | 0.021459 | 0.021459 | 0 | 0 | 0 |  |  | 0 | 0
43 | ONLINE WATER HEATER, 3KW,3LTR. | 0 | - | 0 | 0.029683 | 0.029683 | 0 | 0 | 0 |  |  | 0 | 0
44 | CAMERA FOR VC, MICROPHONE WITH SPEAKER | 0 | - | 0 | 0.023889 | 0.023889 | 0 | 0 | 0 |  |  | 0 | 0
45 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
46 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 0.01873 | 0.01873 | 0 | 0 | 0 |  |  | 0 | 0
47 | Water Cooler | 0 | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
48 | PORTABLE HARD DISK USB 1TB | 0 | - | 0 | 0.0017388 | 0.0017388 | 0 | 0 | 0 |  |  | 0 | 0
49 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.00095 | 0.00095 | 0 | 0 | 0 |  |  | 0 | 0
50 | Garbox assembly for premium make type B-220 of | 0 | - | 0 | 0 | 0 | 0 | 0.44095 | 0.44095 |  |  | 0.44095 | 0
51 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0 | 0 | 0 | 0.006726 | 0.006726 |  |  | 0.006726 | 0
52 | RO+UV+UF+TDS CAP 50 LITRE PER HOUR | 0 | - | 0 | 0 | 0 | 0 | 0.002731 | 0.002731 |  |  | 0.002731 | 0
53 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0 | 0 | 0 | 0.0025995 | 0.0025995 |  |  | 0.0025995 | 0
54 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0 | 0 | 0 | 0.002183 | 0.002183 |  |  | 0.002183 | 0
55 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0 | 0 | 0 | 0.0061808 | 0.0061808 |  |  | 0.0061808 | 0
56 | REGULAR CHAIR WITHOUT CUSHION | 0 | - | 0 | 0 | 0 | 0 | 0.0082836 | 0.0082836 |  |  | 0.0082836 | 0
57 | BLDC Fans through GeM Portal and GA -2022-23 at | 0 | - | 0 | 0 | 0 | 0 | 0.0049556 | 0.0049556 |  |  | 0.0049556 | 0
58 | ALL IN ONE PC, CORE I5, 4 GB RAM, 500 GB | 0 | - | 0 | 0 | 0 | 0 | 0.02973 | 0.02973 |  |  | 0.02973 | 0
59 | PRINTER LASER LASERJET NETWORK PRINTER | 0 | - | 0 | 0 | 0 | 0 | 0.0020024 | 0.0020024 |  |  | 0.0020024 | 0
60 | APPLN FAN AIR CEIL SIZE 1200 MM SWEEP | 0 | - | 0 | 0 | 0 | 0 | 0.033918 | 0.033918 |  |  | 0.033918 | 0
61 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0 | 0 | 0 | 0.014828 | 0.014828 |  |  | 0.014828 | 0
62 | 400 MM, 230V, 3 BLADE DOMESTIC FAN | 0 | - | 0 | 0 | 0 | 0 | 0.0024532 | 0.0024532 |  |  | 0.0024532 | 0
63 | APPLN FAN AIR EXHAUST SIZE15"1400RPM-15 Nos | 0 | - | 0 | 0 | 0 | 0 | 0.01781 | 0.01781 |  |  | 0.01781 | 0
64 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0 | 0 | 0 | 0.013559 | 0.013559 |  |  | 0.013559 | 0
65 | MICROWAVE OVEN CAPACITY 27 / 28 LITERS-1 Nos | 0 | - | 0 | 0 | 0 | 0 | 0.0048362 | 0.0048362 |  |  | 0.0048362 | 0
66 | REFRIGERATOR SINGLE DOOR CAPCITY 190 LTR | 0 | - | 0 | 0 | 0 | 0 | 0.0067225 | 0.0067225 |  |  | 0.0067225 | 0
67 | Supply of Thinclients on Buyback for NTPS | 0 | - | 0 | 0 | 0 | 0 | 0.23166 | 0.23166 |  |  | 0.23166 | 0
68 | ABC Powder type DCP Composite Fire Extinguisher | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
69 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
70 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
71 | Furniture Dining Table for Main Mess Hall and Cus | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
72 | Servers for DSM at Nashik Thermal Power Station | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
73 | DESKTOP INTEL CORE I5 2300 PROCESSOR - 5 Nos | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
74 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
75 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
76 | APPLN TV STD ULSLIM 42" - 4 Nos | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
77 | 1 T SPLIT AC COMPL UNIT WITH ACCESSORIES | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
78 | MULTIMEDIA PROJECTOR EPSON EB-U05-1 No | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
79 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
80 | Procurement of Complete Vibrating Screen Assembly at CHP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Asset | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 268.0703 | 268.0703 | 0 | 9.45 | 6.9245 | 0 | 0 | 6.9245 | 2.5255
FY 2023-24
a) DPR Schemes
(i) Submitted to MERC
1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Measuring & Monitoring of Coal consumption | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 23.0165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Belt Weighers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3295 | 0.3295 | 0.3295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.793 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of inhaul outhaul betel chargers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 6 | 8.5943 | 8.5943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Dust Extraction System | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 1.65 | 1.713 | 1.713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Fogging system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 2.44 | 2.59 | 2.59 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Bunker level montoring system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.54 | 0.0694 | 0.0694 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.169 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Operating the CHP near to its full capacity | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 7.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Motor controller | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3732 | 0.3732 | 0.3732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 3.4218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Combustion optimization & Process improvement | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 58.7761 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Improvement in tooling techniques Power tools like cut off machines and surface grinders. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.52821 | 0.3388 | 0.3388 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Total replacement of boiler related skin insulation as well as skin cladding of furnace, Air pre heaters,air ducts and flue gas ducts Unit-4 &5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4.5892 | 4.7188 | 4.7188 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Painting of Boiler ,bunker structure and other structure.Unit-3,4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 7.775 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 8.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Retrofitting of Gas proportioning dampers, flue gas, primary and secondary air dampers. (SADC) for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.456 | 1.1278 | 1.1278 | 0 | 0.1288 | 0.1288 |  |  | 0.1288 | 0 | 0.1288 | 0
0 | IDC | 0 | - | 0 | 0.33475 | 0.33475 | 0 | 0.078806 | 0.078806 |  |  | 0.078806 | 0
4.6 | Replacement of flue gas ducting zone prone to erosion with 6 to 8 mm high grade material & insulation of flue gas ducts. (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 4 and 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Replacement of boiler outlet valves and damaged valves of units 4 & 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.349 | 1.4313 | 1.4313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Replacement of coal pipe at direction changing sections & flow curvature zone by upgraded material. Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.3292 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.9 | Installation of Smart soot blower system for Unit- 4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 5.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.10 | Installation of Sonic soot blowers for second pass for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.83184 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.11 | Air pre heater upgradation of heat exchanger matrix &regenerative dynamic sealing for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.12 | Replacement Platen water wall for Unit-3. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.60762 | 0.6964 | 0.6964 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 13.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Turbine Auxiliary Consumption Improvement | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 39.2903 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Installation of Turbo vaned fly wheeling eco ventilators to all Units 3, 4, 5. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Replacement of selected old brass impellers of pumps with SS304 impellers. H.T. Auxiliary C.W. Pump and G.S. Water Pumps are selected. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.4 | 0.8251 | 0.8251 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Improving the BFP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.75 | 0.48804 | 0.48804 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Replacement of BFP (200 KHI) cartridge with energy efficient cartridge. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 14.4456 | 13.85 | 13.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Improving the CEP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.9 | 0.6018 | 0.6018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Replacement of CEP with energy efficient pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Replacement of Pumps - GS Pumps, H2Cooler booster pump, DM/DM pumps, DM Makeup pumps, Emergency lift pumps, Drip pumps, BFP Booster pumps with energy efficient pumps. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 4.2733 | 2.3608 | 2.3608 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.8 | Replacement of valves – MS - 3 to 8 , HD – 22,23,24 , MC- 36 , ES 3,4 and BFP Recirculation Valves. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.0852 | 1.3148 | 1.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.9 | Replacement of tube nest of LP Heater no.3 of unit no.3, LP Heater no.4 of unit no.5, Main ejector 3B, GC2 of unit no.5, Seal oil coolers, H2 Coolers, BFP working and lub oil coolers, DM/GS plate type coolers. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 6.5962 | 1.4406 | 1.4406 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.11461 | 0.11461 | 0 | 0 | 0 |  |  | 0 | 0
5.10 | Steam path audit of Unit no,4,5 | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | EMS, Numeric relays, Microprocessor DVR & VFD | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 12.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Design, manufacture, supply, erection, commissioning & testing of Variable Frequency Drives (VFD) with latest design and technology super premium efficiency motors for 415 V LT Auxiliaries (Total 50 No) of 210 MW Unit 3, 4 & 5. | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 6.3 | 4.6893 | 2.1638 | 2.5255 | 2.7428 | 2.7428 |  |  | 2.7428 | 2.5255 | 2.7428 | 0
0 | IDC | 0 | - | 0.66 | 0 | 0 | 0 | 0.74645 | 0.74645 |  |  | 0.74645 | 0
6.2 | Replacement of old EE make Generator Protection Relays with Numerical Generator Protection Relays for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 1.7 | 1.7029 | 1.7029 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Replacement of old AVR with Microprocessor based Digital Voltage Regulator for unit no. 3 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 2.44 | 1.7055 | 1.7055 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Installation and commissioning of Energy Management System for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.81 | 0.8313 | 0.8313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 14.5069 | 14.5069 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 57.9147 | 57.9147 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Faster unloading of coal wagons by upgrading existing system (Post Facto) | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 18.8481 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Re-design, Supply, Erection and commissioning of modified Apron Feeder. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.7219 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Design, manufacture, supply, erection and commissioning of modified bunker outlet cone of Unit 3, 4 and 5. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.3295 | 2.3196 | 2.3196 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Design, manufacture, Supply & Erection Of Components Suitable For Modification Of Wagon Tipplers to Handle BOXNHL , BOX-H,BOX-NR,BOX-NJLSR1 & 25 T AXLE WAGONS | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.1298 | 4.413 | 4.413 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Procurement of SAN Loco - 650-700 HP. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8627 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.5 | Revamping of CHP II Wagon Tippler by replacing the Split Wheel Assembly, Pawl Lever, Pinion Shaft Assembly, Toe, Spur Gear Shaft, W.T Drive Assembly, Rack Segment, Rail Table Assembly Of Wagon Tippler and Dismantling & Replacement of above parts | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8042 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement of 6.6 Kv HT motors as spare motors /for replacement | MERC/CAPEX/20152016/00422 | 2016-08-03 | 14.3563 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3125 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1025 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | FD FAN MOTOR 650 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | FD FAN MOTOR 750 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8505 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | PA FAN MOTOR 1250 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.029 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | BFP MOTOR 4000 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 4.5528 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | C/MILL MOTOR 320 kW (3 Nos) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3356 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.8 | SOP MOTOR 200 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.9 | CWP MOTOR 950 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8942 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.10 | CTLP MOTOR 710 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8081 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.11 | RWP MOTOR 335 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.4861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.12 | HP PUMP MOTOR 258 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3083 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.13 | CEP MOTOR 220 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2629 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.14 | GS PUMP MOTOR 260 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3107 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.15 | Testing charges | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.088 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Replacement of complete LTSH coils at Unit-3 Boiler & Economiser coils at Unit-5 Boiler | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 27.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Complete Supply & Erection of LTSH coils at Unit-3 210 MW Boiler (67 nos. upper and lower modules each. 01 module = 02 coils) | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 16.43 | 4.6378 | 4.6378 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Complete Supply & Erection of 270 nos. Economizer coils in second pass of Unit-5 210 MW Boiler at Nasik TPS. | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 9.57 | 3.0104 | 3.0104 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 1.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Enhancement of performance & life of Coal Handling plant | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 17.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Procurement of 02 nos of 320 hp bull dozers for Nasik TPS | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 3.2 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Procurement of gear box for Apron Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 1.59 | 1.6043 | 1.6043 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Procurement of gear box and 30 KW DC motor for Pedal Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.46 | 0.45847 | 0.45847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.4 | Procurement of Assembly of Impact Crusher Complete set, with Rotor Assembly and bearing Block. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 2.3 | 2.3366 | 2.3366 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.5 | Procurement of 10 KW Inline Magnetic Separator for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.4 | 0.54718 | 0.54718 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.6 | Restoration of RBCR by replacing feed end Spider (Drg. No. 400-1428-01/A) & Discharge end Spider (400-1428-02) suitable to rotary Bradford breaker machine No.CR/634 along with support wheels. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 8.14 | 10.2287 | 10.2287 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.7 | Procurement of 750 KW Impactor Motor for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.49 | 0.22635 | 0.22635 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.8 | Supply of Metal Detectors for CHP | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.14 | 0.09152 | 0.09152 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Retrofitting of 6.6 kV Breakers, Battery Replacement, System Improvement & MPCB Related schemes | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 14.7811 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Retrofitting of 6.6 kV HT MOCB/SF6 Breakers by VCB | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 3.57 | 5.0621 | 5.0621 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2a | A) Procurement & Replacement of 220V/ 1285 AH Battery set for U#3 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0493 | 1.0493 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2b | B) Procurement & Replacement of 220V/ 1285 AH Battery set for U#4 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0047 | 1.0047 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | O2 Measurement System in the furnace & flue gas ducting | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.17 | 1.2966 | 1.2966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Supply, erection, commissioning & testing of online CO, SO2, NOX Analyser for U#3/4/5 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.6511 | 1.6846 | 1.6846 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | A) Replacement of static Flame Monitoring System with Microprocessor based Flame Monitoring & Analyzing System | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.27 | 2.4267 | 2.4267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | CAAQMS monitoring of ambient air quality around the NTPS. | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1 | 0.81676 | 0.81676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | 3rd raising of Ash bund | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | 3rd raising of ash bund from TBL 581.50 to 586.50m in valley No. 4A at Nashik Thermal Power Station, Eklahare | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 12.3 | 10.2142 | 10.2142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | System Rehabilitation & Upgradation at Nasik TPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 13.3722 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Shifting, Transportation & Replacement of Existing Generator Stator of Unit no.3 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 7.98 | 0.8767 | 0.8767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.20198 | 0.20198 | 0 | 0.061987 | 0.061987 |  |  | 0.061987 | 0
15.2 | Turbine Supervisory Instrumentation System for Unit no.5 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.5542 | 0.45436 | 0.45436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Supply of Air Compressors for NTPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 3.398 | 3.8197 | 3.8197 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Replacement of Old Brass Impellers of CTLP with SS Impellers. | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 1.04 | 1.1331 | 1.1331 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up-gradation of DCS at U # 3 and New Rectiformers & ESP Refurbishment of U # 4 & 5 at Nasik TPS | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 33.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Decommissioning & Shifting of M/s ABB make DCS system at BTPS Unit # 2 & Re-commissioning with Up gradation to Symphony Plus at NTPS Unit #3, Nasik. | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 9.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Erection ,Testing & commissioning, Supply of rectiformer HVR 37/800 Hermatically sealed Rectiformer ( DC Peak voltage – 70 kV , Average voltage-45 KV ,DC Current – 800 milli amp , AC I/P – 1 Phase , 415 V ) | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 10.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.3 | Refurbishment of ESP for Unit No. 4 & 5 at Nashik TPS, Eklahare | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 12.5 | 12.8553 | 12.8553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 1.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Replacement of drum gate, augmentation of existing ash water recovery scheme and construction of concrete road for Nasik Thermal Power Station | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 14.5161 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Replacement of drum gate and restructuring of cofferdam, repairs to vertical sluice gate, Approach Bridge and allied civil works at Godavari barrage at Nashik TPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 6.273 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.2 | Augmentation of existing ash water recovery scheme and connecting overflow of waste weir to existing toe drain of ash bund valley no.4 to WWR at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 2.5999 | 3.1676 | 3.1676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2441 | 0.2441 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Up gradation of fly ash concrete road from Booster Pump house toward Hydrogen plant, Dirk India Company towards Hinganwedhe along ash bund valley No. 1 & 2, Ash bund approach road for ash transportation and abundant valley towards Kotamgaon road at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 5.3732 | 5.3752 | 5.3752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 0.27 | 0.38455 | 0.38455 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Various DPR Schemes for Renovation of colony at NTPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 10.8678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Renovation of staff quarters, playground, Jogging track & Gymnasium at NTPS colony, Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 4.071 | 3.5306 | 3.5306 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.92832 | 0.92832 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Road works in NTPS Colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 3.9766 | 3.8972 | 3.8972 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Water supply and sanitation works at NTPS colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 2.8202 | 1.4586 | 1.4586 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.19994 | 0.19994 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Renovation of Workers Recreation Club at Nashik TPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Life enhancement of stacker cum reclaimer machine in CHP & upgradation of SWAS laboratory at Nasik TPS | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 14.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Supply, Erection & installation of sole plates, Rail track & Hydraulic cylinder of the Stacker cum Reclaimer machine at Coal Handling Plant-II Nashik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 6.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement and replacement of 220 V, 1285 AH battery set for Unit No. 4 at Nasik Thermal Power Station. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 1.39 | 1.3596 | 1.3596 | 0 | 0.05192 | 0.05192 |  |  | 0.05192 | 0 | 0.030358 | 0.021562
0 | IDC | 0 | - | 0 | 0.11272 | 0.11272 | 0 | 0.10998 | 0.10998 |  |  | 0.10998 | 0
19.3 | Supply of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers Ltd.) at Nasik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 3.11 | 3.0812 | 3.0812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Erection and commissioning of Steam and Water sampling system for SWAS Lab at WTP, NTPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 2.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.5 | Procurement of 3 nos. of Ash Slurry Disposal pump Type D - 85 for Ash Slurry Pump House of Unit no. 3, 4 & 5 at NTPSEklahare. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.55 | 0 | 0 | 0 | 0.55578 | 0 |  |  | 0 | 0.55578 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Flue Gas Desulphurization (FGD) System at Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Ash Augmentation System at Nasik & Koradi Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Ash Augmentation System at Nasik Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 5.71 | 5.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3.1 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 8.47 | 8.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | NASIK TPS (U-3 to 5) (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 2.8842 | 2.8842 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.76776 | 0.76776 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Nashik TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.2272 | 2.2272 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | TPS Nashik | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 2.3118 | 2.3118 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.1 | Procurement and Replacement of Complete sets of assembly of baskets for air preheater of type tri-sector APH 27 VI(T) 74” in NTPS unit no. 4 & 5 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 2.5368 | 2.5368 | 0 | 2.5785 | 0 |  |  | 0 | 2.5785 | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0.13531 | 0.13531 |  |  | 0.13531 | 0 | 0 | 0.13531
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | <DPR Name> | N.A. | N.A. | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Complete Replacement of HRH Coils, LTSH Coils, Economizer Coils at Unit No. 4 & Complete Replacement of Economizer coils at Unit No.3 Nashik TPS 210 MW Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Replacement HRH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete Replacement LTSH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete Replacement Economiser Coils at NTPS Unit No. 3 & 4 Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 and Commissioning of AFGC system for Unit No. 3, 4 & 5 and Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5 at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of MSERW pipes for Replacement of various pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 at NTPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, erection, commissioning & testing of Ammonia Flue gas Conditioning system for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5, 210 MW, NTPS, Eklahare, Nasik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Complete replacement of Platen Superheater coils at Unit No.3,4 & 5 ; Complete replacement of HRH coils at Unit No.3,& 5; Complete replacement of LTSH coils at Unit No. 5;Replacement of thermal insulation at Boiler for Nashik TPS 210 MW boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete replacement of Platen Superheater coils at Unit No. 3,4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete replacement of HRH coils at Unit No.3,& 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete replacement of LTSH coils at Unit No.5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines at Unit No.3,4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | Procurement of various pumps for TM & ODP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement and Erection Commissioning of Condenser vacuum pump for Unit No. 3 ,4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Three Pump assemblies of SAM TURBO makes Type 150/500 N for Booster Pump house at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 3 Nos Vertical Fly Ash Transfer Pump VO 150 /400 + ARS SAM make along with motor for ESP Hopper evacuation of Unit No.3,4 & 5 at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection, installation, civil foundation, commissioning, testing & trial of Rotating &casing assembly of pumps for WTP at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement (10 nos.) of CWFW pumps (with motor) at Stage-II (Beacon make) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of RWP Pump assembly at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Cooling Tower lift Pump Impeller for Jyoti make pump Type:-1200- VMI A 12 at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Degasser Pump assembly with motor (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 8 Nos. of Domestic water pumps (with motor) & Darna drinking water pump at Stage-I & II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of 4 Nos. of DM backwash (2 Nos.) & CW backwash pump (2 Nos.)(with motor)at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of HP Pumps at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of ETP pump assembly (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of RWP shaft with bearing, Impeller (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Procurement of AWR pump (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Submersible Slurry Pumps for handling Ash water / Clear water for dewatering at various locations at NTPS (10 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 5 | Renovation of Compressed Air Refrigerated Dryer System, Refurbishment of Centralized Air Conditioning system, Supply, erection & commissioning of Condensate Extraction Pump, Procurement of CW Pump and GS pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Compressed Air Refrigerated Dryer System for Nashik TPS, 210 MW Unit No. 3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of Centralized Air Conditioning system of Unit No. 3, 4 & 5 at Nashik TPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers ltd. at Nasik TPS. Total Qty. 02 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of CW & CTLP Pump total 4 No.s | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of GS Pump assembly .Total qty- 3 No | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 6 | Procurement of oil free Rotary Screw Compressors and BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of oil free rotary screw compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 7 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets, Refurbishment of HPT rotor along with supply, Procurement of HP & IP control valve with cam shaft assemblies, Procurement of complete governing system assembly, Supply, Errection & Commissioning of COP assembly, Procurement of Condenser tubes & ODP related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets at 3 x 210 MW, TM-II NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of HPT rotor along with supply. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of HP & IP control valve with cam shaft assemblies.qty-1set | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of complete governing system assembly. qty-1 set | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, Errection & Commissioning of COP assembly.Total Qty.- 3 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Condenser tubes for Unit No.3, 4 & 5.Total Qty:15700 tubes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of CT Fan Blade assembly & shaft- 36 nos for Unit No.3,4 & 5 at NTPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Gearbox Assembly for Cooling Tower Fans type B-220 Premium make for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare (Qty-24) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 5 nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Flocculator gearbox- 12 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of Clinker grinder assembly at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of 4 Nos. of Clinker grinder gearbox at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of 5 Nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Augmentattion of existing Ash Water recovery Scheme(WWR,AWR, ETP-I,ETP-II & Phase-II pump assembly) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Feed Gate Housing (08 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 8 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area & Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 9 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS , Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 10 | Upgradation of various electrical related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of 6.6KV HT motors and spares at Nashik TPS Unit No 3,4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Boiler and turbine house lighting of Unit No.3,4 & 5 along with removal of old wiring. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacemet of IPH transformer 11KV/6.6 KV and lighting and welding transformer at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Excitation Transformer at Unit No. 3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | GTR /UAT/ station transformer spares LV bushings replacement, HV bushings (spare)-3nos, LV busbar, palm joint both station transformers bushings at Unit No.3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of overhead conductor HT/LT by underground HT/LT cable in Colony area. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | LT transformer procurement/ rewinding work at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | LT MCC panel modification at ODP area NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Battery Charger-220V,50V,380V UPS, 24V,DG set EMF panel with charger replacement, UPS battery replacement, Unit No. 5 station battery replacement,50 V battery set replacement at Unit No.3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Replacement of HT motor Cables. (Old PILC Cable replacement with XLPE Cable) at Unit No.3, 4 & 5 & ODP area | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Unit No. 4 Field Breaker | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 11 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 12 | Replacement/Upgradation of C&I old systems at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement/Upgradation of Unit No.4 DVR System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement/Upgradation of Unit No.4 UPS System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotory Electronic Control Drive for Burner Tilt and Auxiliary Air Damper at Unit No. 3, 4 & 5 210 MW, NTPS, Eklahare Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification/Upgradation of Turbovisory system of Unit No. 3,4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Auxiliary air dampers & BT, HAD, feed gate replacement/modification work. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Unit No.4 DCS-FCS 102 to FCS 106 (Total 5 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | New sewage treatment plant required at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Upgradation of Unit No.4 230 V UPS and new UPS, charger for Unit No. 3 & 5 DCS at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | ESP hopper high & low level indicator mounting in Unit No.3,4& 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | OCEMS for Sox, Nox, opacity monitoring system upgradation work for Unit No.3, 4 & 5 at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Supply, Erection, Commissioning & Testing of online H2 purity meter and Resistivity meter for Unit No. 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, Erection, commissioning of Hydra step system for Drum level control Unit No.3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | HPLP - Servo Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Replacement of Relays and Energy meter at NTPS, Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | ESP upgradation for Unit No. 3, 4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Grounding Brush Monitoring System for Unit No. 3,4& 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Implementationof FGMO | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 13 | Modification & replacement of various CHP schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Modification of single stream conveyor belt Gearboxes with new design Helical Bevel type Gearboxes at CHP-II NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Modification of Primary Vibrating screen at CHP-II, NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Rail table alongwith weighment frame for rotaside Wagon Tippler at CHP-II, NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification of Conveyor Drive system with Motorised Pulley drive system at CHP-II, NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Replacement of old damaged RBCR rail beam M/c No. CR/964 & screen to increase life of RBCR n reduced direct impact of raw coal on secondary impact crusher. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of copmlete crusher unit as per Drg. No. P00304/0 CO/1050 CR635-636(impact crusher body & rotor shaft assembly) 2 Nos | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of appron feeder head shaft assembly-25/005 drg no.-M15076/2 & tail shaft assembly-25/006 Drg. No.- M15065/2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply & erection of wagon tippler rail table Drg. No.12578/45-01 , tippler support roller & bogei Drg. No-12616/45-2M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of seondary crusher motors 6.6KV, 750KW & 220KW motor for CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Supply of LT motors for various conveyor belts of CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Up-gradation of existing DC drive system of Wagon Tippler & Paddle feeder with new version DIGICON make system along with supply, installtion, commissioning & testing of DC drives at CHP-III. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply of Variable Frequency drives for Conv.16C2 at CHP-III. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Up-gradation of existing relay panel of control room with microprocessor based PLC logic system along with supply, installtion, commissioning & testing of relay panel at CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Supply of Magnetic seperators & Metal detectors at CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Repair & renovation of NTPS colony ,Repairing work of ash bund side & Eklahare barrage | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of renovation of various residential quarters by providing and fixing kitchen sink, kitchen trolley & granite otta at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing and applying external painting to various types residential buildings at NTPS colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Providing and applying internal painting to various types of residential quarters at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Providing and fixing vitrified tiles to various types of residnetial buildings at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening works to various residential quarters at NTPS colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing and fixing colour coated galvanised iron sheets for roofing at various residential buildings at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Sewer line repair of various quarters at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Stair case repairing of various building at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Construction of WBM road over/at the top of ash bund at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Repairs to filters of drain well No.4 and other allied works at ash bund valley No.4A at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Repairs to Godavari river barrage gates and allied works at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Structural repairs of Cooling Tower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repairs of cooling tower components at Unit No. 3A, 3B, 4A, 4B,5A & 5B, Stage-II NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Structural repair & rehabilitation and Renovation and modification work at NTPS Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repair & rehabilitation of various machine foundations of ID, FD & PA fans for Unit No. 3, 4, 5 at Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of removing and providing 24 B.W.G.for pent house side & roof at Unit No. 3,4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of removing and providing old damaged siporex wall and poly coated sheet for 28 mtr. height at Unit No. 3, 4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Structural repairs of chimney at Unit No. 3,4 & 5 Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Renovation of sump No. 2,3,4,5,6 and 7 at WTP Stage-II, NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Work of structural repairing at CHP-I,II & III area at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work of structural repairing at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Work of structural repair of GS pump Unit No. 3,4,& 5 and fire fighting pump house at Stage-II,NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Work of repairs to doors & windows of various building at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Providing and fixing powder coated colored Zincalume profiled sheet for various building at CHP,AWR building, Time office & ODP EM at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of external painting & internal painting at WTP, Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of external painting & internal painting at CHP area NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Renovation and restructuring of shed No. 1, 2, 5, 6, 9 & 11 of major store custody of NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | As per I.B.Recommondation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of construction compound wall with concertina coil at various locations at Nashik TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing & renovating security watch tower at NTPS Premises Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | R&M/LE for Identified Thermal units of MSPGCL of (3 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL (3 x 210 MW) units of MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | CHP Improvcement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | TATA Mini Truck SFC 709 EX No.MH-15-JV-3992 | N.A. | - | 0 | 0.32099 | 0.32099 | 0 | 0 | 0 |  |  | 0 | 0
2 | Executive chair(10),S Type Arm chai(20) | N.A. | - | 0 | 0.10784 | 0.10784 | 0 | 0 | 0 |  |  | 0 | 0
3 | Office Table and S-Type Chair with Arm | N.A. | - | 0 | 0.030968 | 0.030968 | 0 | 0 | 0 |  |  | 0 | 0
4 | Windows Slot in PC VPC 10-Intel Core 13 4th -NTC | N.A. | - | 0 | 0.010561 | 0.010561 | 0 | 0 | 0 |  |  | 0 | 0
5 | LG Screen wall mounted computer-LED display65"-NTC | N.A. | - | 0 | 5.0969 | 5.0969 | 0 | 0 | 0 |  |  | 0 | 0
6 | 20 Ton Split AC for Audtiorium -NTC | N.A. | - | 0 | 1.0873 | 1.0873 | 0 | 0 | 0 |  |  | 0 | 0
7 | Colour Laser Printer, All in one A3 LaserJet Print | N.A. | - | 0 | 1.0589 | 1.0589 | 0 | 0 | 0 |  |  | 0 | 0
8 | Digital DSLR Camera | N.A. | - | 0 | 1.0793 | 1.0793 | 0 | 0 | 0 |  |  | 0 | 0
9 | Indoor Gymnasium Equipments at NTC, Eklahare | N.A. | - | 0 | 0.02853 | 0.02853 | 0 | 0 | 0 |  |  | 0 | 0
10 | CLASS ROOM CHAIR WITH DESKLET | N.A. | - | 0 | 0.023576 | 0.023576 | 0 | 0 | 0 |  |  | 0 | 0
11 | PA System and Sport Material,Table Tannis for | N.A. | - | 0 | 0.01687 | 0.01687 | 0 | 0 | 0 |  |  | 0 | 0
12 | EXECUTIVE CHAIR WITH 5 SUPRT & S-TYPE CHAIR | N.A. | - | 0 | 0.01003 | 0.01003 | 0 | 0 | 0 |  |  | 0 | 0
13 | APPLN COOLER AIR SEMIEXH AIR COOLER ASSY | N.A. | - | 0 | 0.033896 | 0.033896 | 0 | 0 | 0 |  |  | 0 | 0
14 | FULL PAD CHAIRS WITH SIDE ARM | N.A. | - | 0 | 0.029637 | 0.029637 | 0 | 0 | 0 |  |  | 0 | 0
15 | Industrial Cabinet with 12 Lockers | N.A. | - | 0 | 0.0070163 | 0.0070163 | 0 | 0 | 0 |  |  | 0 | 0
16 | UV Water Purifier Filter | N.A. | - | 0 | 0.019116 | 0.019116 | 0 | 0 | 0 |  |  | 0 | 0
17 | FILTER RO+UV+UF+TDS WATER PURIFIER | N.A. | - | 0 | 0.032906 | 0.032906 | 0 | 0 | 0 |  |  | 0 | 0
18 | 2 Tone SPLIT AC INDOOR UNIT | N.A. | - | 0 | 0.008064 | 0.008064 | 0 | 0 | 0 |  |  | 0 | 0
19 | 1.5 TON CAPACITY SPLIT AC | N.A. | - | 0 | 0.006688 | 0.006688 | 0 | 0 | 0 |  |  | 0 | 0
20 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 1.698 | 1.698 | 0 | 0 | 0 |  |  | 0 | 0
21 | Logitech PTZ Group Camera 960-001054 | N.A. | - | 0 | 2.4375 | 2.4375 | 0 | 0 | 0 |  |  | 0 | 0
22 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011564 | 0.011564 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK BENCH WITHOUT DRAWER | 0 | - | 0 | 0.011647 | 0.011647 | 0 | 0 | 0 |  |  | 0 | 0
24 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.030075 | 0.030075 | 0 | 0 | 0 |  |  | 0 | 0
25 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011788 | 0.011788 | 0 | 0 | 0 |  |  | 0 | 0
26 | EXECUTIVE CHAIR, S-TYPE CH-7 CHAIR WITH ARM | 0 | - | 0 | 0.035229 | 0.035229 | 0 | 0 | 0 |  |  | 0 | 0
27 | SAMSUNG GALAXY TAB S3, 32GB 9.7 INCH | 0 | - | 0 | 0.003845 | 0.003845 | 0 | 0 | 0 |  |  | 0 | 0
28 | i5 Laptop - 2 Nos & i7 Laptop - 3 Nos | 0 | - | 0 | 0.037636 | 0.037636 | 0 | 0 | 0 |  |  | 0 | 0
29 | Godrej make 1.5 Ton High Wall Split AC | 0 | - | 0 | 0.020975 | 0.020975 | 0 | 0 | 0 |  |  | 0 | 0
30 | Complete Multimedia Projector with Std Accessories | 0 | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
31 | LED 40 INCH SMART TV | 0 | - | 0 | 0.0092016 | 0.0092016 | 0 | 0 | 0 |  |  | 0 | 0
32 | FULL PAD CHAIRS, EXECUTIVE CHAIR, | 0 | - | 0 | 0.068995 | 0.068995 | 0 | 0 | 0 |  |  | 0 | 0
33 | Cash Counting Machine | 0 | - | 0 | 0.001888 | 0.001888 | 0 | 0 | 0 |  |  | 0 | 0
34 | 230 V AC DIGITAL SINE WAVE INVERTER 1 No. | 0 | - | 0 | 0.010175 | 0.010175 | 0 | 0 | 0 |  |  | 0 | 0
35 | HPCV no.3 &4 Stem | 0 | - | 0 | 0.025694 | 0.025694 | 0 | 0 | 0 |  |  | 0 | 0
36 | HEAVY DUTY AIR PURIFIURE 230V,50HZ | 0 | - | 0 | 0.0105 | 0.0105 | 0 | 0 | 0 |  |  | 0 | 0
37 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.0048144 | 0.0048144 | 0 | 0 | 0 |  |  | 0 | 0
38 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.025939 | 0.025939 | 0 | 0 | 0 |  |  | 0 | 0
39 | APPLN COOLER WTR CAP CAP: 60 LITERS | 0 | - | 0 | 0.0053799 | 0.0053799 | 0 | 0 | 0 |  |  | 0 | 0
40 | LASER LASERJET PRINTER FOR A4 PAPER | 0 | - | 0 | 0.0057 | 0.0057 | 0 | 0 | 0 |  |  | 0 | 0
41 | 40 Inch Smart LED TV 3.00 | 0 | - | 0 | 0.010178 | 0.010178 | 0 | 0 | 0 |  |  | 0 | 0
42 | DESKTOP INTEL CORE I5 2300 PROCESSOR | 0 | - | 0 | 0.021459 | 0.021459 | 0 | 0 | 0 |  |  | 0 | 0
43 | ONLINE WATER HEATER, 3KW,3LTR. | 0 | - | 0 | 0.029683 | 0.029683 | 0 | 0 | 0 |  |  | 0 | 0
44 | CAMERA FOR VC, MICROPHONE WITH SPEAKER | 0 | - | 0 | 0.023889 | 0.023889 | 0 | 0 | 0 |  |  | 0 | 0
45 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
46 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 0.01873 | 0.01873 | 0 | 0 | 0 |  |  | 0 | 0
47 | Water Cooler | 0 | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
48 | PORTABLE HARD DISK USB 1TB | 0 | - | 0 | 0.0017388 | 0.0017388 | 0 | 0 | 0 |  |  | 0 | 0
49 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.00095 | 0.00095 | 0 | 0 | 0 |  |  | 0 | 0
50 | Garbox assembly for premium make type B-220 of | 0 | - | 0 | 0.44095 | 0.44095 | 0 | 0 | 0 |  |  | 0 | 0
51 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.006726 | 0.006726 | 0 | 0 | 0 |  |  | 0 | 0
52 | RO+UV+UF+TDS CAP 50 LITRE PER HOUR | 0 | - | 0 | 0.002731 | 0.002731 | 0 | 0 | 0 |  |  | 0 | 0
53 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.0025995 | 0.0025995 | 0 | 0 | 0 |  |  | 0 | 0
54 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.002183 | 0.002183 | 0 | 0 | 0 |  |  | 0 | 0
55 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0061808 | 0.0061808 | 0 | 0 | 0 |  |  | 0 | 0
56 | REGULAR CHAIR WITHOUT CUSHION | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
57 | BLDC Fans through GeM Portal and GA -2022-23 at | 0 | - | 0 | 0.0049556 | 0.0049556 | 0 | 0 | 0 |  |  | 0 | 0
58 | ALL IN ONE PC, CORE I5, 4 GB RAM, 500 GB | 0 | - | 0 | 0.02973 | 0.02973 | 0 | 0 | 0 |  |  | 0 | 0
59 | PRINTER LASER LASERJET NETWORK PRINTER | 0 | - | 0 | 0.0020024 | 0.0020024 | 0 | 0 | 0 |  |  | 0 | 0
60 | APPLN FAN AIR CEIL SIZE 1200 MM SWEEP | 0 | - | 0 | 0.033918 | 0.033918 | 0 | 0 | 0 |  |  | 0 | 0
61 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.014828 | 0.014828 | 0 | 0 | 0 |  |  | 0 | 0
62 | 400 MM, 230V, 3 BLADE DOMESTIC FAN | 0 | - | 0 | 0.0024532 | 0.0024532 | 0 | 0 | 0 |  |  | 0 | 0
63 | APPLN FAN AIR EXHAUST SIZE15"1400RPM-15 Nos | 0 | - | 0 | 0.01781 | 0.01781 | 0 | 0 | 0 |  |  | 0 | 0
64 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.013559 | 0.013559 | 0 | 0 | 0 |  |  | 0 | 0
65 | MICROWAVE OVEN CAPACITY 27 / 28 LITERS-1 Nos | 0 | - | 0 | 0.0048362 | 0.0048362 | 0 | 0 | 0 |  |  | 0 | 0
66 | REFRIGERATOR SINGLE DOOR CAPCITY 190 LTR | 0 | - | 0 | 0.0067225 | 0.0067225 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Thinclients on Buyback for NTPS | 0 | - | 0 | 0.23166 | 0.23166 | 0 | 0 | 0 |  |  | 0 | 0
68 | ABC Powder type DCP Composite Fire Extinguisher | 0 | - | 0 | 0 | 0 | 0 | 0.357 | 0.357 |  |  | 0.357 | 0
69 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0 | 0 | 0 | 0.024631 | 0.024631 |  |  | 0.024631 | 0
70 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0 | 0 | 0 | 0.024213 | 0.024213 |  |  | 0.024213 | 0
71 | Furniture Dining Table for Main Mess Hall and Cus | 0 | - | 0 | 0 | 0 | 0 | 0.019803 | 0.019803 |  |  | 0.019803 | 0
72 | Servers for DSM at Nashik Thermal Power Station | 0 | - | 0 | 0 | 0 | 0 | 0.43559 | 0.43559 |  |  | 0.43559 | 0
73 | DESKTOP INTEL CORE I5 2300 PROCESSOR - 5 Nos | 0 | - | 0 | 0 | 0 | 0 | 0.05632 | 0.05632 |  |  | 0.05632 | 0
74 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0 | 0 | 0 | 0.041064 | 0.041064 |  |  | 0.041064 | 0
75 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0 | 0 | 0 | 0.038246 | 0.038246 |  |  | 0.038246 | 0
76 | APPLN TV STD ULSLIM 42" - 4 Nos | 0 | - | 0 | 0 | 0 | 0 | 0.037376 | 0.037376 |  |  | 0.037376 | 0
77 | 1 T SPLIT AC COMPL UNIT WITH ACCESSORIES | 0 | - | 0 | 0 | 0 | 0 | 0.011682 | 0.011682 |  |  | 0.011682 | 0
78 | MULTIMEDIA PROJECTOR EPSON EB-U05-1 No | 0 | - | 0 | 0 | 0 | 0 | 0.0081606 | 0.0081606 |  |  | 0.0081606 | 0
79 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0 | 0 | 0 | 0.0023246 | 0.0023246 |  |  | 0.0023246 | 0
80 | Procurement of Complete Vibrating Screen Assembly at CHP-II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Asset | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 277.5203 | 274.9947 | 2.5255 | 8.2467 | 5.1124 | 0 | 0 | 5.1124 | 5.6598
FY 2024-25
a) DPR Schemes
(i) Submitted to MERC
1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Measuring & Monitoring of Coal consumption | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 23.0165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Belt Weighers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3295 | 0.3295 | 0.3295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.793 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of inhaul outhaul betel chargers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 6 | 8.5943 | 8.5943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Dust Extraction System | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 1.65 | 1.713 | 1.713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Fogging system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 2.44 | 2.59 | 2.59 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Bunker level montoring system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.54 | 0.0694 | 0.0694 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.169 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Operating the CHP near to its full capacity | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 7.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Motor controller | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3732 | 0.3732 | 0.3732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 3.4218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Combustion optimization & Process improvement | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 58.7761 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Improvement in tooling techniques Power tools like cut off machines and surface grinders. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.52821 | 0.3388 | 0.3388 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Total replacement of boiler related skin insulation as well as skin cladding of furnace, Air pre heaters,air ducts and flue gas ducts Unit-4 &5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4.5892 | 4.7188 | 4.7188 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Painting of Boiler ,bunker structure and other structure.Unit-3,4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 7.775 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 8.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Retrofitting of Gas proportioning dampers, flue gas, primary and secondary air dampers. (SADC) for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.456 | 1.2566 | 1.2566 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.41356 | 0.41356 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Replacement of flue gas ducting zone prone to erosion with 6 to 8 mm high grade material & insulation of flue gas ducts. (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 4 and 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Replacement of boiler outlet valves and damaged valves of units 4 & 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.349 | 1.4313 | 1.4313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Replacement of coal pipe at direction changing sections & flow curvature zone by upgraded material. Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.3292 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.9 | Installation of Smart soot blower system for Unit- 4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 5.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.10 | Installation of Sonic soot blowers for second pass for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.83184 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.11 | Air pre heater upgradation of heat exchanger matrix &regenerative dynamic sealing for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.12 | Replacement Platen water wall for Unit-3. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.60762 | 0.6964 | 0.6964 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 13.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Turbine Auxiliary Consumption Improvement | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 39.2903 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Installation of Turbo vaned fly wheeling eco ventilators to all Units 3, 4, 5. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Replacement of selected old brass impellers of pumps with SS304 impellers. H.T. Auxiliary C.W. Pump and G.S. Water Pumps are selected. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.4 | 0.8251 | 0.8251 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Improving the BFP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.75 | 0.48804 | 0.48804 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Replacement of BFP (200 KHI) cartridge with energy efficient cartridge. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 14.4456 | 13.85 | 13.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Improving the CEP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.9 | 0.6018 | 0.6018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Replacement of CEP with energy efficient pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Replacement of Pumps - GS Pumps, H2Cooler booster pump, DM/DM pumps, DM Makeup pumps, Emergency lift pumps, Drip pumps, BFP Booster pumps with energy efficient pumps. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 4.2733 | 2.3608 | 2.3608 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.8 | Replacement of valves – MS - 3 to 8 , HD – 22,23,24 , MC- 36 , ES 3,4 and BFP Recirculation Valves. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.0852 | 1.3148 | 1.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.9 | Replacement of tube nest of LP Heater no.3 of unit no.3, LP Heater no.4 of unit no.5, Main ejector 3B, GC2 of unit no.5, Seal oil coolers, H2 Coolers, BFP working and lub oil coolers, DM/GS plate type coolers. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 6.5962 | 1.4406 | 1.4406 | 0 | 0.51873 | 0.51873 |  |  | 0.51873 | 0 | 0.51873 | 0
0 | IDC | 0 | - | 0 | 0.11461 | 0.11461 | 0 | 0 | 0 |  |  | 0 | 0
5.10 | Steam path audit of Unit no,4,5 | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | EMS, Numeric relays, Microprocessor DVR & VFD | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 12.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Design, manufacture, supply, erection, commissioning & testing of Variable Frequency Drives (VFD) with latest design and technology super premium efficiency motors for 415 V LT Auxiliaries (Total 50 No) of 210 MW Unit 3, 4 & 5. | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 6.3 | 7.4321 | 4.9066 | 2.5255 | 1.3861 | 1.3861 |  |  | 1.3861 | 2.5255 | 1.3861 | 0
0 | IDC | 0 | - | 0.66 | 0.74645 | 0.74645 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Replacement of old EE make Generator Protection Relays with Numerical Generator Protection Relays for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 1.7 | 1.7029 | 1.7029 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Replacement of old AVR with Microprocessor based Digital Voltage Regulator for unit no. 3 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 2.44 | 1.7055 | 1.7055 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Installation and commissioning of Energy Management System for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.81 | 0.8313 | 0.8313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 14.5069 | 14.5069 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 57.9147 | 57.9147 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Faster unloading of coal wagons by upgrading existing system (Post Facto) | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 18.8481 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Re-design, Supply, Erection and commissioning of modified Apron Feeder. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.7219 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Design, manufacture, supply, erection and commissioning of modified bunker outlet cone of Unit 3, 4 and 5. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.3295 | 2.3196 | 2.3196 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Design, manufacture, Supply & Erection Of Components Suitable For Modification Of Wagon Tipplers to Handle BOXNHL , BOX-H,BOX-NR,BOX-NJLSR1 & 25 T AXLE WAGONS | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.1298 | 4.413 | 4.413 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Procurement of SAN Loco - 650-700 HP. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8627 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.5 | Revamping of CHP II Wagon Tippler by replacing the Split Wheel Assembly, Pawl Lever, Pinion Shaft Assembly, Toe, Spur Gear Shaft, W.T Drive Assembly, Rack Segment, Rail Table Assembly Of Wagon Tippler and Dismantling & Replacement of above parts | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8042 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement of 6.6 Kv HT motors as spare motors /for replacement | MERC/CAPEX/20152016/00422 | 2016-08-03 | 14.3563 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3125 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1025 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | FD FAN MOTOR 650 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | FD FAN MOTOR 750 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8505 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | PA FAN MOTOR 1250 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.029 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | BFP MOTOR 4000 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 4.5528 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | C/MILL MOTOR 320 kW (3 Nos) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3356 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.8 | SOP MOTOR 200 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.9 | CWP MOTOR 950 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8942 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.10 | CTLP MOTOR 710 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8081 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.11 | RWP MOTOR 335 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.4861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.12 | HP PUMP MOTOR 258 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3083 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.13 | CEP MOTOR 220 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2629 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.14 | GS PUMP MOTOR 260 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3107 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.15 | Testing charges | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.088 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Replacement of complete LTSH coils at Unit-3 Boiler & Economiser coils at Unit-5 Boiler | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 27.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Complete Supply & Erection of LTSH coils at Unit-3 210 MW Boiler (67 nos. upper and lower modules each. 01 module = 02 coils) | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 16.43 | 4.6378 | 4.6378 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Complete Supply & Erection of 270 nos. Economizer coils in second pass of Unit-5 210 MW Boiler at Nasik TPS. | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 9.57 | 3.0104 | 3.0104 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 1.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Enhancement of performance & life of Coal Handling plant | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 17.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Procurement of 02 nos of 320 hp bull dozers for Nasik TPS | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 3.2 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Procurement of gear box for Apron Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 1.59 | 1.6043 | 1.6043 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Procurement of gear box and 30 KW DC motor for Pedal Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.46 | 0.45847 | 0.45847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.4 | Procurement of Assembly of Impact Crusher Complete set, with Rotor Assembly and bearing Block. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 2.3 | 2.3366 | 2.3366 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.5 | Procurement of 10 KW Inline Magnetic Separator for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.4 | 0.54718 | 0.54718 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.6 | Restoration of RBCR by replacing feed end Spider (Drg. No. 400-1428-01/A) & Discharge end Spider (400-1428-02) suitable to rotary Bradford breaker machine No.CR/634 along with support wheels. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 8.14 | 10.2287 | 10.2287 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.7 | Procurement of 750 KW Impactor Motor for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.49 | 0.22635 | 0.22635 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.8 | Supply of Metal Detectors for CHP | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.14 | 0.09152 | 0.09152 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Retrofitting of 6.6 kV Breakers, Battery Replacement, System Improvement & MPCB Related schemes | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 14.7811 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Retrofitting of 6.6 kV HT MOCB/SF6 Breakers by VCB | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 3.57 | 5.0621 | 5.0621 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2a | A) Procurement & Replacement of 220V/ 1285 AH Battery set for U#3 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0493 | 1.0493 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2b | B) Procurement & Replacement of 220V/ 1285 AH Battery set for U#4 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0047 | 1.0047 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | O2 Measurement System in the furnace & flue gas ducting | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.17 | 1.2966 | 1.2966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Supply, erection, commissioning & testing of online CO, SO2, NOX Analyser for U#3/4/5 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.6511 | 1.6846 | 1.6846 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | A) Replacement of static Flame Monitoring System with Microprocessor based Flame Monitoring & Analyzing System | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.27 | 2.4267 | 2.4267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | CAAQMS monitoring of ambient air quality around the NTPS. | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1 | 0.81676 | 0.81676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | 3rd raising of Ash bund | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | 3rd raising of ash bund from TBL 581.50 to 586.50m in valley No. 4A at Nashik Thermal Power Station, Eklahare | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 12.3 | 10.2142 | 10.2142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | System Rehabilitation & Upgradation at Nasik TPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 13.3722 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Shifting, Transportation & Replacement of Existing Generator Stator of Unit no.3 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 7.98 | 0.8767 | 0.8767 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.26397 | 0.26397 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Turbine Supervisory Instrumentation System for Unit no.5 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.5542 | 0.45436 | 0.45436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Supply of Air Compressors for NTPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 3.398 | 3.8197 | 3.8197 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Replacement of Old Brass Impellers of CTLP with SS Impellers. | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 1.04 | 1.1331 | 1.1331 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up-gradation of DCS at U # 3 and New Rectiformers & ESP Refurbishment of U # 4 & 5 at Nasik TPS | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 33.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Decommissioning & Shifting of M/s ABB make DCS system at BTPS Unit # 2 & Re-commissioning with Up gradation to Symphony Plus at NTPS Unit #3, Nasik. | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 9.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Erection ,Testing & commissioning, Supply of rectiformer HVR 37/800 Hermatically sealed Rectiformer ( DC Peak voltage – 70 kV , Average voltage-45 KV ,DC Current – 800 milli amp , AC I/P – 1 Phase , 415 V ) | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 10.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.3 | Refurbishment of ESP for Unit No. 4 & 5 at Nashik TPS, Eklahare | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 12.5 | 12.8553 | 12.8553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 1.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Replacement of drum gate, augmentation of existing ash water recovery scheme and construction of concrete road for Nasik Thermal Power Station | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 14.5161 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Replacement of drum gate and restructuring of cofferdam, repairs to vertical sluice gate, Approach Bridge and allied civil works at Godavari barrage at Nashik TPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 6.273 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0 | 3 | 0
17.2 | Augmentation of existing ash water recovery scheme and connecting overflow of waste weir to existing toe drain of ash bund valley no.4 to WWR at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 2.5999 | 3.1676 | 3.1676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2441 | 0.2441 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Up gradation of fly ash concrete road from Booster Pump house toward Hydrogen plant, Dirk India Company towards Hinganwedhe along ash bund valley No. 1 & 2, Ash bund approach road for ash transportation and abundant valley towards Kotamgaon road at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 5.3732 | 5.3752 | 5.3752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 0.27 | 0.38455 | 0.38455 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Various DPR Schemes for Renovation of colony at NTPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 10.8678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Renovation of staff quarters, playground, Jogging track & Gymnasium at NTPS colony, Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 4.071 | 3.5306 | 3.5306 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.92832 | 0.92832 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Road works in NTPS Colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 3.9766 | 3.8972 | 3.8972 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Water supply and sanitation works at NTPS colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 2.8202 | 1.4586 | 1.4586 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.19994 | 0.19994 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Renovation of Workers Recreation Club at Nashik TPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Life enhancement of stacker cum reclaimer machine in CHP & upgradation of SWAS laboratory at Nasik TPS | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 14.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Supply, Erection & installation of sole plates, Rail track & Hydraulic cylinder of the Stacker cum Reclaimer machine at Coal Handling Plant-II Nashik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 6.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement and replacement of 220 V, 1285 AH battery set for Unit No. 4 at Nasik Thermal Power Station. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 1.39 | 1.4116 | 1.4116 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2227 | 0.2227 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Supply of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers Ltd.) at Nasik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 3.11 | 3.0812 | 3.0812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Erection and commissioning of Steam and Water sampling system for SWAS Lab at WTP, NTPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 2.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.5 | Procurement of 3 nos. of Ash Slurry Disposal pump Type D - 85 for Ash Slurry Pump House of Unit no. 3, 4 & 5 at NTPSEklahare. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.55 | 0.55578 | 0 | 0.55578 | 0 | 0.51878 |  |  | 0.51878 | 0.037 | 0.51878 | 0
0 | IDC | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Flue Gas Desulphurization (FGD) System at Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Ash Augmentation System at Nasik & Koradi Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Ash Augmentation System at Nasik Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 5.71 | 5.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3.1 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 8.47 | 8.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | NASIK TPS (U-3 to 5) (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 2.8842 | 2.8842 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.76776 | 0.76776 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Nashik TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.2272 | 2.2272 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | TPS Nashik | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 2.3118 | 2.3118 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.1 | Procurement and Replacement of Complete sets of assembly of baskets for air preheater of type tri-sector APH 27 VI(T) 74” in NTPS unit no. 4 & 5 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 5.1153 | 2.5368 | 2.5785 | 0.4776 | 3.0561 |  |  | 3.0561 | 0 | 1.6832 | 1.3729
0 | IDC | 0 | - | 0 | 0.13531 | 0.13531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | <DPR Name> | N.A. | N.A. | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Complete Replacement of HRH Coils, LTSH Coils, Economizer Coils at Unit No. 4 & Complete Replacement of Economizer coils at Unit No.3 Nashik TPS 210 MW Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Replacement HRH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete Replacement LTSH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete Replacement Economiser Coils at NTPS Unit No. 3 & 4 Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 and Commissioning of AFGC system for Unit No. 3, 4 & 5 and Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5 at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of MSERW pipes for Replacement of various pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 at NTPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, erection, commissioning & testing of Ammonia Flue gas Conditioning system for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5, 210 MW, NTPS, Eklahare, Nasik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Complete replacement of Platen Superheater coils at Unit No.3,4 & 5 ; Complete replacement of HRH coils at Unit No.3,& 5; Complete replacement of LTSH coils at Unit No. 5;Replacement of thermal insulation at Boiler for Nashik TPS 210 MW boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete replacement of Platen Superheater coils at Unit No. 3,4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete replacement of HRH coils at Unit No.3,& 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete replacement of LTSH coils at Unit No.5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines at Unit No.3,4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | Procurement of various pumps for TM & ODP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement and Erection Commissioning of Condenser vacuum pump for Unit No. 3 ,4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Three Pump assemblies of SAM TURBO makes Type 150/500 N for Booster Pump house at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 3 Nos Vertical Fly Ash Transfer Pump VO 150 /400 + ARS SAM make along with motor for ESP Hopper evacuation of Unit No.3,4 & 5 at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection, installation, civil foundation, commissioning, testing & trial of Rotating &casing assembly of pumps for WTP at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement (10 nos.) of CWFW pumps (with motor) at Stage-II (Beacon make) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of RWP Pump assembly at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Cooling Tower lift Pump Impeller for Jyoti make pump Type:-1200- VMI A 12 at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Degasser Pump assembly with motor (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 8 Nos. of Domestic water pumps (with motor) & Darna drinking water pump at Stage-I & II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of 4 Nos. of DM backwash (2 Nos.) & CW backwash pump (2 Nos.)(with motor)at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of HP Pumps at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of ETP pump assembly (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of RWP shaft with bearing, Impeller (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Procurement of AWR pump (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Submersible Slurry Pumps for handling Ash water / Clear water for dewatering at various locations at NTPS (10 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 5 | Renovation of Compressed Air Refrigerated Dryer System, Refurbishment of Centralized Air Conditioning system, Supply, erection & commissioning of Condensate Extraction Pump, Procurement of CW Pump and GS pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Compressed Air Refrigerated Dryer System for Nashik TPS, 210 MW Unit No. 3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of Centralized Air Conditioning system of Unit No. 3, 4 & 5 at Nashik TPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers ltd. at Nasik TPS. Total Qty. 02 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of CW & CTLP Pump total 4 No.s | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of GS Pump assembly .Total qty- 3 No | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 6 | Procurement of oil free Rotary Screw Compressors and BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of oil free rotary screw compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 7 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets, Refurbishment of HPT rotor along with supply, Procurement of HP & IP control valve with cam shaft assemblies, Procurement of complete governing system assembly, Supply, Errection & Commissioning of COP assembly, Procurement of Condenser tubes & ODP related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets at 3 x 210 MW, TM-II NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of HPT rotor along with supply. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of HP & IP control valve with cam shaft assemblies.qty-1set | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of complete governing system assembly. qty-1 set | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, Errection & Commissioning of COP assembly.Total Qty.- 3 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Condenser tubes for Unit No.3, 4 & 5.Total Qty:15700 tubes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of CT Fan Blade assembly & shaft- 36 nos for Unit No.3,4 & 5 at NTPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Gearbox Assembly for Cooling Tower Fans type B-220 Premium make for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare (Qty-24) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 5 nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Flocculator gearbox- 12 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of Clinker grinder assembly at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of 4 Nos. of Clinker grinder gearbox at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of 5 Nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Augmentattion of existing Ash Water recovery Scheme(WWR,AWR, ETP-I,ETP-II & Phase-II pump assembly) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Feed Gate Housing (08 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 8 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area & Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 9 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS , Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 10 | Upgradation of various electrical related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of 6.6KV HT motors and spares at Nashik TPS Unit No 3,4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Boiler and turbine house lighting of Unit No.3,4 & 5 along with removal of old wiring. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacemet of IPH transformer 11KV/6.6 KV and lighting and welding transformer at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Excitation Transformer at Unit No. 3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | GTR /UAT/ station transformer spares LV bushings replacement, HV bushings (spare)-3nos, LV busbar, palm joint both station transformers bushings at Unit No.3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of overhead conductor HT/LT by underground HT/LT cable in Colony area. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | LT transformer procurement/ rewinding work at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | LT MCC panel modification at ODP area NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Battery Charger-220V,50V,380V UPS, 24V,DG set EMF panel with charger replacement, UPS battery replacement, Unit No. 5 station battery replacement,50 V battery set replacement at Unit No.3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Replacement of HT motor Cables. (Old PILC Cable replacement with XLPE Cable) at Unit No.3, 4 & 5 & ODP area | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Unit No. 4 Field Breaker | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 11 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 12 | Replacement/Upgradation of C&I old systems at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement/Upgradation of Unit No.4 DVR System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement/Upgradation of Unit No.4 UPS System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotory Electronic Control Drive for Burner Tilt and Auxiliary Air Damper at Unit No. 3, 4 & 5 210 MW, NTPS, Eklahare Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification/Upgradation of Turbovisory system of Unit No. 3,4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Auxiliary air dampers & BT, HAD, feed gate replacement/modification work. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Unit No.4 DCS-FCS 102 to FCS 106 (Total 5 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | New sewage treatment plant required at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Upgradation of Unit No.4 230 V UPS and new UPS, charger for Unit No. 3 & 5 DCS at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | ESP hopper high & low level indicator mounting in Unit No.3,4& 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | OCEMS for Sox, Nox, opacity monitoring system upgradation work for Unit No.3, 4 & 5 at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Supply, Erection, Commissioning & Testing of online H2 purity meter and Resistivity meter for Unit No. 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, Erection, commissioning of Hydra step system for Drum level control Unit No.3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | HPLP - Servo Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Replacement of Relays and Energy meter at NTPS, Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | ESP upgradation for Unit No. 3, 4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Grounding Brush Monitoring System for Unit No. 3,4& 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Implementationof FGMO | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 13 | Modification & replacement of various CHP schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Modification of single stream conveyor belt Gearboxes with new design Helical Bevel type Gearboxes at CHP-II NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Modification of Primary Vibrating screen at CHP-II, NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Rail table alongwith weighment frame for rotaside Wagon Tippler at CHP-II, NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification of Conveyor Drive system with Motorised Pulley drive system at CHP-II, NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Replacement of old damaged RBCR rail beam M/c No. CR/964 & screen to increase life of RBCR n reduced direct impact of raw coal on secondary impact crusher. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of copmlete crusher unit as per Drg. No. P00304/0 CO/1050 CR635-636(impact crusher body & rotor shaft assembly) 2 Nos | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of appron feeder head shaft assembly-25/005 drg no.-M15076/2 & tail shaft assembly-25/006 Drg. No.- M15065/2 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply & erection of wagon tippler rail table Drg. No.12578/45-01 , tippler support roller & bogei Drg. No-12616/45-2M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of seondary crusher motors 6.6KV, 750KW & 220KW motor for CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Supply of LT motors for various conveyor belts of CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Up-gradation of existing DC drive system of Wagon Tippler & Paddle feeder with new version DIGICON make system along with supply, installtion, commissioning & testing of DC drives at CHP-III. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply of Variable Frequency drives for Conv.16C2 at CHP-III. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Up-gradation of existing relay panel of control room with microprocessor based PLC logic system along with supply, installtion, commissioning & testing of relay panel at CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Supply of Magnetic seperators & Metal detectors at CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Repair & renovation of NTPS colony ,Repairing work of ash bund side & Eklahare barrage | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of renovation of various residential quarters by providing and fixing kitchen sink, kitchen trolley & granite otta at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing and applying external painting to various types residential buildings at NTPS colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Providing and applying internal painting to various types of residential quarters at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Providing and fixing vitrified tiles to various types of residnetial buildings at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening works to various residential quarters at NTPS colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing and fixing colour coated galvanised iron sheets for roofing at various residential buildings at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Sewer line repair of various quarters at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Stair case repairing of various building at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Construction of WBM road over/at the top of ash bund at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Repairs to filters of drain well No.4 and other allied works at ash bund valley No.4A at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Repairs to Godavari river barrage gates and allied works at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Structural repairs of Cooling Tower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repairs of cooling tower components at Unit No. 3A, 3B, 4A, 4B,5A & 5B, Stage-II NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Structural repair & rehabilitation and Renovation and modification work at NTPS Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repair & rehabilitation of various machine foundations of ID, FD & PA fans for Unit No. 3, 4, 5 at Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of removing and providing 24 B.W.G.for pent house side & roof at Unit No. 3,4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of removing and providing old damaged siporex wall and poly coated sheet for 28 mtr. height at Unit No. 3, 4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Structural repairs of chimney at Unit No. 3,4 & 5 Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Renovation of sump No. 2,3,4,5,6 and 7 at WTP Stage-II, NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Work of structural repairing at CHP-I,II & III area at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work of structural repairing at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Work of structural repair of GS pump Unit No. 3,4,& 5 and fire fighting pump house at Stage-II,NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Work of repairs to doors & windows of various building at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Providing and fixing powder coated colored Zincalume profiled sheet for various building at CHP,AWR building, Time office & ODP EM at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of external painting & internal painting at WTP, Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of external painting & internal painting at CHP area NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Renovation and restructuring of shed No. 1, 2, 5, 6, 9 & 11 of major store custody of NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | As per I.B.Recommondation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of construction compound wall with concertina coil at various locations at Nashik TPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing & renovating security watch tower at NTPS Premises Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | R&M/LE for Identified Thermal units of MSPGCL of (3 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL (3 x 210 MW) units of MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | CHP Improvcement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | TATA Mini Truck SFC 709 EX No.MH-15-JV-3992 | N.A. | - | 0 | 0.32099 | 0.32099 | 0 | 0 | 0 |  |  | 0 | 0
2 | Executive chair(10),S Type Arm chai(20) | N.A. | - | 0 | 0.10784 | 0.10784 | 0 | 0 | 0 |  |  | 0 | 0
3 | Office Table and S-Type Chair with Arm | N.A. | - | 0 | 0.030968 | 0.030968 | 0 | 0 | 0 |  |  | 0 | 0
4 | Windows Slot in PC VPC 10-Intel Core 13 4th -NTC | N.A. | - | 0 | 0.010561 | 0.010561 | 0 | 0 | 0 |  |  | 0 | 0
5 | LG Screen wall mounted computer-LED display65"-NTC | N.A. | - | 0 | 5.0969 | 5.0969 | 0 | 0 | 0 |  |  | 0 | 0
6 | 20 Ton Split AC for Audtiorium -NTC | N.A. | - | 0 | 1.0873 | 1.0873 | 0 | 0 | 0 |  |  | 0 | 0
7 | Colour Laser Printer, All in one A3 LaserJet Print | N.A. | - | 0 | 1.0589 | 1.0589 | 0 | 0 | 0 |  |  | 0 | 0
8 | Digital DSLR Camera | N.A. | - | 0 | 1.0793 | 1.0793 | 0 | 0 | 0 |  |  | 0 | 0
9 | Indoor Gymnasium Equipments at NTC, Eklahare | N.A. | - | 0 | 0.02853 | 0.02853 | 0 | 0 | 0 |  |  | 0 | 0
10 | CLASS ROOM CHAIR WITH DESKLET | N.A. | - | 0 | 0.023576 | 0.023576 | 0 | 0 | 0 |  |  | 0 | 0
11 | PA System and Sport Material,Table Tannis for | N.A. | - | 0 | 0.01687 | 0.01687 | 0 | 0 | 0 |  |  | 0 | 0
12 | EXECUTIVE CHAIR WITH 5 SUPRT & S-TYPE CHAIR | N.A. | - | 0 | 0.01003 | 0.01003 | 0 | 0 | 0 |  |  | 0 | 0
13 | APPLN COOLER AIR SEMIEXH AIR COOLER ASSY | N.A. | - | 0 | 0.033896 | 0.033896 | 0 | 0 | 0 |  |  | 0 | 0
14 | FULL PAD CHAIRS WITH SIDE ARM | N.A. | - | 0 | 0.029637 | 0.029637 | 0 | 0 | 0 |  |  | 0 | 0
15 | Industrial Cabinet with 12 Lockers | N.A. | - | 0 | 0.0070163 | 0.0070163 | 0 | 0 | 0 |  |  | 0 | 0
16 | UV Water Purifier Filter | N.A. | - | 0 | 0.019116 | 0.019116 | 0 | 0 | 0 |  |  | 0 | 0
17 | FILTER RO+UV+UF+TDS WATER PURIFIER | N.A. | - | 0 | 0.032906 | 0.032906 | 0 | 0 | 0 |  |  | 0 | 0
18 | 2 Tone SPLIT AC INDOOR UNIT | N.A. | - | 0 | 0.008064 | 0.008064 | 0 | 0 | 0 |  |  | 0 | 0
19 | 1.5 TON CAPACITY SPLIT AC | N.A. | - | 0 | 0.006688 | 0.006688 | 0 | 0 | 0 |  |  | 0 | 0
20 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 1.698 | 1.698 | 0 | 0 | 0 |  |  | 0 | 0
21 | Logitech PTZ Group Camera 960-001054 | N.A. | - | 0 | 2.4375 | 2.4375 | 0 | 0 | 0 |  |  | 0 | 0
22 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011564 | 0.011564 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK BENCH WITHOUT DRAWER | 0 | - | 0 | 0.011647 | 0.011647 | 0 | 0 | 0 |  |  | 0 | 0
24 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.030075 | 0.030075 | 0 | 0 | 0 |  |  | 0 | 0
25 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011788 | 0.011788 | 0 | 0 | 0 |  |  | 0 | 0
26 | EXECUTIVE CHAIR, S-TYPE CH-7 CHAIR WITH ARM | 0 | - | 0 | 0.035229 | 0.035229 | 0 | 0 | 0 |  |  | 0 | 0
27 | SAMSUNG GALAXY TAB S3, 32GB 9.7 INCH | 0 | - | 0 | 0.003845 | 0.003845 | 0 | 0 | 0 |  |  | 0 | 0
28 | i5 Laptop - 2 Nos & i7 Laptop - 3 Nos | 0 | - | 0 | 0.037636 | 0.037636 | 0 | 0 | 0 |  |  | 0 | 0
29 | Godrej make 1.5 Ton High Wall Split AC | 0 | - | 0 | 0.020975 | 0.020975 | 0 | 0 | 0 |  |  | 0 | 0
30 | Complete Multimedia Projector with Std Accessories | 0 | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
31 | LED 40 INCH SMART TV | 0 | - | 0 | 0.0092016 | 0.0092016 | 0 | 0 | 0 |  |  | 0 | 0
32 | FULL PAD CHAIRS, EXECUTIVE CHAIR, | 0 | - | 0 | 0.068995 | 0.068995 | 0 | 0 | 0 |  |  | 0 | 0
33 | Cash Counting Machine | 0 | - | 0 | 0.001888 | 0.001888 | 0 | 0 | 0 |  |  | 0 | 0
34 | 230 V AC DIGITAL SINE WAVE INVERTER 1 No. | 0 | - | 0 | 0.010175 | 0.010175 | 0 | 0 | 0 |  |  | 0 | 0
35 | HPCV no.3 &4 Stem | 0 | - | 0 | 0.025694 | 0.025694 | 0 | 0 | 0 |  |  | 0 | 0
36 | HEAVY DUTY AIR PURIFIURE 230V,50HZ | 0 | - | 0 | 0.0105 | 0.0105 | 0 | 0 | 0 |  |  | 0 | 0
37 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.0048144 | 0.0048144 | 0 | 0 | 0 |  |  | 0 | 0
38 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.025939 | 0.025939 | 0 | 0 | 0 |  |  | 0 | 0
39 | APPLN COOLER WTR CAP CAP: 60 LITERS | 0 | - | 0 | 0.0053799 | 0.0053799 | 0 | 0 | 0 |  |  | 0 | 0
40 | LASER LASERJET PRINTER FOR A4 PAPER | 0 | - | 0 | 0.0057 | 0.0057 | 0 | 0 | 0 |  |  | 0 | 0
41 | 40 Inch Smart LED TV 3.00 | 0 | - | 0 | 0.010178 | 0.010178 | 0 | 0 | 0 |  |  | 0 | 0
42 | DESKTOP INTEL CORE I5 2300 PROCESSOR | 0 | - | 0 | 0.021459 | 0.021459 | 0 | 0 | 0 |  |  | 0 | 0
43 | ONLINE WATER HEATER, 3KW,3LTR. | 0 | - | 0 | 0.029683 | 0.029683 | 0 | 0 | 0 |  |  | 0 | 0
44 | CAMERA FOR VC, MICROPHONE WITH SPEAKER | 0 | - | 0 | 0.023889 | 0.023889 | 0 | 0 | 0 |  |  | 0 | 0
45 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
46 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 0.01873 | 0.01873 | 0 | 0 | 0 |  |  | 0 | 0
47 | Water Cooler | 0 | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
48 | PORTABLE HARD DISK USB 1TB | 0 | - | 0 | 0.0017388 | 0.0017388 | 0 | 0 | 0 |  |  | 0 | 0
49 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.00095 | 0.00095 | 0 | 0 | 0 |  |  | 0 | 0
50 | Garbox assembly for premium make type B-220 of | 0 | - | 0 | 0.44095 | 0.44095 | 0 | 0 | 0 |  |  | 0 | 0
51 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.006726 | 0.006726 | 0 | 0 | 0 |  |  | 0 | 0
52 | RO+UV+UF+TDS CAP 50 LITRE PER HOUR | 0 | - | 0 | 0.002731 | 0.002731 | 0 | 0 | 0 |  |  | 0 | 0
53 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.0025995 | 0.0025995 | 0 | 0 | 0 |  |  | 0 | 0
54 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.002183 | 0.002183 | 0 | 0 | 0 |  |  | 0 | 0
55 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0061808 | 0.0061808 | 0 | 0 | 0 |  |  | 0 | 0
56 | REGULAR CHAIR WITHOUT CUSHION | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
57 | BLDC Fans through GeM Portal and GA -2022-23 at | 0 | - | 0 | 0.0049556 | 0.0049556 | 0 | 0 | 0 |  |  | 0 | 0
58 | ALL IN ONE PC, CORE I5, 4 GB RAM, 500 GB | 0 | - | 0 | 0.02973 | 0.02973 | 0 | 0 | 0 |  |  | 0 | 0
59 | PRINTER LASER LASERJET NETWORK PRINTER | 0 | - | 0 | 0.0020024 | 0.0020024 | 0 | 0 | 0 |  |  | 0 | 0
60 | APPLN FAN AIR CEIL SIZE 1200 MM SWEEP | 0 | - | 0 | 0.033918 | 0.033918 | 0 | 0 | 0 |  |  | 0 | 0
61 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.014828 | 0.014828 | 0 | 0 | 0 |  |  | 0 | 0
62 | 400 MM, 230V, 3 BLADE DOMESTIC FAN | 0 | - | 0 | 0.0024532 | 0.0024532 | 0 | 0 | 0 |  |  | 0 | 0
63 | APPLN FAN AIR EXHAUST SIZE15"1400RPM-15 Nos | 0 | - | 0 | 0.01781 | 0.01781 | 0 | 0 | 0 |  |  | 0 | 0
64 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.013559 | 0.013559 | 0 | 0 | 0 |  |  | 0 | 0
65 | MICROWAVE OVEN CAPACITY 27 / 28 LITERS-1 Nos | 0 | - | 0 | 0.0048362 | 0.0048362 | 0 | 0 | 0 |  |  | 0 | 0
66 | REFRIGERATOR SINGLE DOOR CAPCITY 190 LTR | 0 | - | 0 | 0.0067225 | 0.0067225 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Thinclients on Buyback for NTPS | 0 | - | 0 | 0.23166 | 0.23166 | 0 | 0 | 0 |  |  | 0 | 0
68 | ABC Powder type DCP Composite Fire Extinguisher | 0 | - | 0 | 0.357 | 0.357 | 0 | 0 | 0 |  |  | 0 | 0
69 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024631 | 0.024631 | 0 | 0 | 0 |  |  | 0 | 0
70 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024213 | 0.024213 | 0 | 0 | 0 |  |  | 0 | 0
71 | Furniture Dining Table for Main Mess Hall and Cus | 0 | - | 0 | 0.019803 | 0.019803 | 0 | 0 | 0 |  |  | 0 | 0
72 | Servers for DSM at Nashik Thermal Power Station | 0 | - | 0 | 0.43559 | 0.43559 | 0 | 0 | 0 |  |  | 0 | 0
73 | DESKTOP INTEL CORE I5 2300 PROCESSOR - 5 Nos | 0 | - | 0 | 0.05632 | 0.05632 | 0 | 0 | 0 |  |  | 0 | 0
74 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.041064 | 0.041064 | 0 | 0 | 0 |  |  | 0 | 0
75 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.038246 | 0.038246 | 0 | 0 | 0 |  |  | 0 | 0
76 | APPLN TV STD ULSLIM 42" - 4 Nos | 0 | - | 0 | 0.037376 | 0.037376 | 0 | 0 | 0 |  |  | 0 | 0
77 | 1 T SPLIT AC COMPL UNIT WITH ACCESSORIES | 0 | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
78 | MULTIMEDIA PROJECTOR EPSON EB-U05-1 No | 0 | - | 0 | 0.0081606 | 0.0081606 | 0 | 0 | 0 |  |  | 0 | 0
79 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.0023246 | 0.0023246 | 0 | 0 | 0 |  |  | 0 | 0
80 | Procurement of Complete Vibrating Screen Assembly at CHP-II | 0 | - | 0 | 0 | 0 | 0 | 0.61 | 0.61 |  |  | 0.61 | 0
0 | General Asset | 0 | - | 0 | 0 | 0 | 0 | 0.575 | 0.575 |  |  | 0.575 | 0
| Total |  |  |  | 285.767 | 280.1072 | 5.6598 | 6.5675 | 9.6648 | 0 | 0 | 9.6648 | 2.5625
FY 2025-26
a) DPR Schemes
(i) Submitted to MERC
1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Measuring & Monitoring of Coal consumption | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 23.0165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Belt Weighers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3295 | 0.3295 | 0.3295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.793 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of inhaul outhaul betel chargers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 6 | 8.5943 | 8.5943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Dust Extraction System | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 1.65 | 1.713 | 1.713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Fogging system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 2.44 | 2.59 | 2.59 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Bunker level montoring system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.54 | 0.0694 | 0.0694 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.169 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Operating the CHP near to its full capacity | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 7.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Motor controller | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3732 | 0.3732 | 0.3732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 3.4218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Combustion optimization & Process improvement | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 58.7761 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Improvement in tooling techniques Power tools like cut off machines and surface grinders. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.52821 | 0.3388 | 0.3388 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Total replacement of boiler related skin insulation as well as skin cladding of furnace, Air pre heaters,air ducts and flue gas ducts Unit-4 &5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4.5892 | 4.7188 | 4.7188 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Painting of Boiler ,bunker structure and other structure.Unit-3,4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 7.775 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 8.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Retrofitting of Gas proportioning dampers, flue gas, primary and secondary air dampers. (SADC) for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.456 | 1.2566 | 1.2566 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.41356 | 0.41356 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Replacement of flue gas ducting zone prone to erosion with 6 to 8 mm high grade material & insulation of flue gas ducts. (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 4 and 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Replacement of boiler outlet valves and damaged valves of units 4 & 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.349 | 1.4313 | 1.4313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Replacement of coal pipe at direction changing sections & flow curvature zone by upgraded material. Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.3292 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.9 | Installation of Smart soot blower system for Unit- 4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 5.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.10 | Installation of Sonic soot blowers for second pass for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.83184 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.11 | Air pre heater upgradation of heat exchanger matrix &regenerative dynamic sealing for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.12 | Replacement Platen water wall for Unit-3. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.60762 | 0.6964 | 0.6964 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 13.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Turbine Auxiliary Consumption Improvement | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 39.2903 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Installation of Turbo vaned fly wheeling eco ventilators to all Units 3, 4, 5. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Replacement of selected old brass impellers of pumps with SS304 impellers. H.T. Auxiliary C.W. Pump and G.S. Water Pumps are selected. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.4 | 0.8251 | 0.8251 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Improving the BFP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.75 | 0.48804 | 0.48804 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Replacement of BFP (200 KHI) cartridge with energy efficient cartridge. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 14.4456 | 13.85 | 13.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Improving the CEP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.9 | 0.6018 | 0.6018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Replacement of CEP with energy efficient pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Replacement of Pumps - GS Pumps, H2Cooler booster pump, DM/DM pumps, DM Makeup pumps, Emergency lift pumps, Drip pumps, BFP Booster pumps with energy efficient pumps. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 4.2733 | 2.3608 | 2.3608 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.8 | Replacement of valves – MS - 3 to 8 , HD – 22,23,24 , MC- 36 , ES 3,4 and BFP Recirculation Valves. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.0852 | 1.3148 | 1.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.9 | Replacement of tube nest of LP Heater no.3 of unit no.3, LP Heater no.4 of unit no.5, Main ejector 3B, GC2 of unit no.5, Seal oil coolers, H2 Coolers, BFP working and lub oil coolers, DM/GS plate type coolers. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 6.5962 | 1.9594 | 1.9594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.11461 | 0.11461 | 0 | 0 | 0 |  |  | 0 | 0
5.10 | Steam path audit of Unit no,4,5 | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | EMS, Numeric relays, Microprocessor DVR & VFD | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 12.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Design, manufacture, supply, erection, commissioning & testing of Variable Frequency Drives (VFD) with latest design and technology super premium efficiency motors for 415 V LT Auxiliaries (Total 50 No) of 210 MW Unit 3, 4 & 5. | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 6.3 | 8.8183 | 6.2927 | 2.5255 | 0 | 0 |  |  | 0 | 2.5255 | 0 | 0
0 | IDC | 0 | - | 0.66 | 0.74645 | 0.74645 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Replacement of old EE make Generator Protection Relays with Numerical Generator Protection Relays for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 1.7 | 1.7029 | 1.7029 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Replacement of old AVR with Microprocessor based Digital Voltage Regulator for unit no. 3 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 2.44 | 1.7055 | 1.7055 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Installation and commissioning of Energy Management System for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.81 | 0.8313 | 0.8313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 14.5069 | 14.5069 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 57.9147 | 57.9147 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Faster unloading of coal wagons by upgrading existing system (Post Facto) | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 18.8481 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Re-design, Supply, Erection and commissioning of modified Apron Feeder. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.7219 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Design, manufacture, supply, erection and commissioning of modified bunker outlet cone of Unit 3, 4 and 5. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.3295 | 2.3196 | 2.3196 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Design, manufacture, Supply & Erection Of Components Suitable For Modification Of Wagon Tipplers to Handle BOXNHL , BOX-H,BOX-NR,BOX-NJLSR1 & 25 T AXLE WAGONS | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.1298 | 4.413 | 4.413 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Procurement of SAN Loco - 650-700 HP. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8627 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.5 | Revamping of CHP II Wagon Tippler by replacing the Split Wheel Assembly, Pawl Lever, Pinion Shaft Assembly, Toe, Spur Gear Shaft, W.T Drive Assembly, Rack Segment, Rail Table Assembly Of Wagon Tippler and Dismantling & Replacement of above parts | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8042 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement of 6.6 Kv HT motors as spare motors /for replacement | MERC/CAPEX/20152016/00422 | 2016-08-03 | 14.3563 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3125 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1025 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | FD FAN MOTOR 650 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | FD FAN MOTOR 750 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8505 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | PA FAN MOTOR 1250 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.029 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | BFP MOTOR 4000 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 4.5528 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | C/MILL MOTOR 320 kW (3 Nos) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3356 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.8 | SOP MOTOR 200 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.9 | CWP MOTOR 950 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8942 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.10 | CTLP MOTOR 710 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8081 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.11 | RWP MOTOR 335 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.4861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.12 | HP PUMP MOTOR 258 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3083 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.13 | CEP MOTOR 220 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2629 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.14 | GS PUMP MOTOR 260 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3107 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.15 | Testing charges | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.088 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Replacement of complete LTSH coils at Unit-3 Boiler & Economiser coils at Unit-5 Boiler | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 27.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Complete Supply & Erection of LTSH coils at Unit-3 210 MW Boiler (67 nos. upper and lower modules each. 01 module = 02 coils) | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 16.43 | 4.6378 | 4.6378 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Complete Supply & Erection of 270 nos. Economizer coils in second pass of Unit-5 210 MW Boiler at Nasik TPS. | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 9.57 | 3.0104 | 3.0104 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 1.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Enhancement of performance & life of Coal Handling plant | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 17.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Procurement of 02 nos of 320 hp bull dozers for Nasik TPS | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 3.2 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Procurement of gear box for Apron Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 1.59 | 1.6043 | 1.6043 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Procurement of gear box and 30 KW DC motor for Pedal Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.46 | 0.45847 | 0.45847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.4 | Procurement of Assembly of Impact Crusher Complete set, with Rotor Assembly and bearing Block. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 2.3 | 2.3366 | 2.3366 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.5 | Procurement of 10 KW Inline Magnetic Separator for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.4 | 0.54718 | 0.54718 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.6 | Restoration of RBCR by replacing feed end Spider (Drg. No. 400-1428-01/A) & Discharge end Spider (400-1428-02) suitable to rotary Bradford breaker machine No.CR/634 along with support wheels. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 8.14 | 10.2287 | 10.2287 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.7 | Procurement of 750 KW Impactor Motor for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.49 | 0.22635 | 0.22635 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.8 | Supply of Metal Detectors for CHP | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.14 | 0.09152 | 0.09152 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Retrofitting of 6.6 kV Breakers, Battery Replacement, System Improvement & MPCB Related schemes | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 14.7811 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Retrofitting of 6.6 kV HT MOCB/SF6 Breakers by VCB | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 3.57 | 5.0621 | 5.0621 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2a | A) Procurement & Replacement of 220V/ 1285 AH Battery set for U#3 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0493 | 1.0493 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2b | B) Procurement & Replacement of 220V/ 1285 AH Battery set for U#4 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0047 | 1.0047 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | O2 Measurement System in the furnace & flue gas ducting | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.17 | 1.2966 | 1.2966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Supply, erection, commissioning & testing of online CO, SO2, NOX Analyser for U#3/4/5 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.6511 | 1.6846 | 1.6846 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | A) Replacement of static Flame Monitoring System with Microprocessor based Flame Monitoring & Analyzing System | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.27 | 2.4267 | 2.4267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | CAAQMS monitoring of ambient air quality around the NTPS. | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1 | 0.81676 | 0.81676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | 3rd raising of Ash bund | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | 3rd raising of ash bund from TBL 581.50 to 586.50m in valley No. 4A at Nashik Thermal Power Station, Eklahare | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 12.3 | 10.2142 | 10.2142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | System Rehabilitation & Upgradation at Nasik TPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 13.3722 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Shifting, Transportation & Replacement of Existing Generator Stator of Unit no.3 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 7.98 | 0.8767 | 0.8767 | 0 | 0 | 5 |  |  | 5 | -5 | 5 | 0
0 | IDC | 0 | - | 0 | 0.26397 | 0.26397 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Turbine Supervisory Instrumentation System for Unit no.5 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.5542 | 0.45436 | 0.45436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Supply of Air Compressors for NTPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 3.398 | 3.8197 | 3.8197 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Replacement of Old Brass Impellers of CTLP with SS Impellers. | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 1.04 | 1.1331 | 1.1331 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up-gradation of DCS at U # 3 and New Rectiformers & ESP Refurbishment of U # 4 & 5 at Nasik TPS | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 33.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Decommissioning & Shifting of M/s ABB make DCS system at BTPS Unit # 2 & Re-commissioning with Up gradation to Symphony Plus at NTPS Unit #3, Nasik. | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 9.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Erection ,Testing & commissioning, Supply of rectiformer HVR 37/800 Hermatically sealed Rectiformer ( DC Peak voltage – 70 kV , Average voltage-45 KV ,DC Current – 800 milli amp , AC I/P – 1 Phase , 415 V ) | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 10.34 | 0 | 0 | 0 | 0 | 13 |  |  | 13 | -13 | 10.34 | 2.66
16.3 | Refurbishment of ESP for Unit No. 4 & 5 at Nashik TPS, Eklahare | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 12.5 | 12.8553 | 12.8553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 1.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Replacement of drum gate, augmentation of existing ash water recovery scheme and construction of concrete road for Nasik Thermal Power Station | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 14.5161 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Replacement of drum gate and restructuring of cofferdam, repairs to vertical sluice gate, Approach Bridge and allied civil works at Godavari barrage at Nashik TPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 6.273 | 3 | 3 | 0 | 0 | 3.27 |  |  | 3.27 | -3.27 | 3.27 | 0
17.2 | Augmentation of existing ash water recovery scheme and connecting overflow of waste weir to existing toe drain of ash bund valley no.4 to WWR at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 2.5999 | 3.1676 | 3.1676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2441 | 0.2441 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Up gradation of fly ash concrete road from Booster Pump house toward Hydrogen plant, Dirk India Company towards Hinganwedhe along ash bund valley No. 1 & 2, Ash bund approach road for ash transportation and abundant valley towards Kotamgaon road at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 5.3732 | 5.3752 | 5.3752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 0.27 | 0.38455 | 0.38455 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Various DPR Schemes for Renovation of colony at NTPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 10.8678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Renovation of staff quarters, playground, Jogging track & Gymnasium at NTPS colony, Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 4.071 | 3.5306 | 3.5306 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.92832 | 0.92832 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Road works in NTPS Colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 3.9766 | 3.8972 | 3.8972 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Water supply and sanitation works at NTPS colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 2.8202 | 1.4586 | 1.4586 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.19994 | 0.19994 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Renovation of Workers Recreation Club at Nashik TPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Life enhancement of stacker cum reclaimer machine in CHP & upgradation of SWAS laboratory at Nasik TPS | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 14.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Supply, Erection & installation of sole plates, Rail track & Hydraulic cylinder of the Stacker cum Reclaimer machine at Coal Handling Plant-II Nashik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 6.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement and replacement of 220 V, 1285 AH battery set for Unit No. 4 at Nasik Thermal Power Station. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 1.39 | 1.4116 | 1.4116 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2227 | 0.2227 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Supply of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers Ltd.) at Nasik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 3.11 | 3.0812 | 3.0812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Erection and commissioning of Steam and Water sampling system for SWAS Lab at WTP, NTPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 2.23 | 0 | 0 | 0 | 0 | 3 |  |  | 3 | -3 | 2.23 | 0.77
19.5 | Procurement of 3 nos. of Ash Slurry Disposal pump Type D - 85 for Ash Slurry Pump House of Unit no. 3, 4 & 5 at NTPSEklahare. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.55 | 0.55578 | 0.51878 | 0.037 | 0 | 0 |  |  | 0 | 0.037 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Flue Gas Desulphurization (FGD) System at Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Ash Augmentation System at Nasik & Koradi Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Ash Augmentation System at Nasik Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 5.71 | 5.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3.1 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 8.47 | 8.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | NASIK TPS (U-3 to 5) (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 2.8842 | 2.8842 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.76776 | 0.76776 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Nashik TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.2272 | 2.2272 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | TPS Nashik | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 2.3118 | 2.3118 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.1 | Procurement and Replacement of Complete sets of assembly of baskets for air preheater of type tri-sector APH 27 VI(T) 74” in NTPS unit no. 4 & 5 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 5.5929 | 5.5929 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.13531 | 0.13531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | <DPR Name> | N.A. | N.A. | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Complete Replacement of HRH Coils, LTSH Coils, Economizer Coils at Unit No. 4 & Complete Replacement of Economizer coils at Unit No.3 Nashik TPS 210 MW Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Replacement HRH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 0 | 0 | 0 | 6.84 | 6.84 |  |  | 6.84 | 0
2 | Complete Replacement LTSH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 0 | 0 | 0 | 10.7498 | 10.7498 |  |  | 10.7498 | 0
3 | Complete Replacement Economiser Coils at NTPS Unit No. 3 & 4 Boilers | 0 | - | 0 | 0 | 0 | 0 | 13.66 | 13.66 |  |  | 13.66 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 and Commissioning of AFGC system for Unit No. 3, 4 & 5 and Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5 at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of MSERW pipes for Replacement of various pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 at NTPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 16.1949 | 16.1949 |  |  | 16.1949 | 0
2 | Supply, erection, commissioning & testing of Ammonia Flue gas Conditioning system for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 3.9046 | 3.9046 |  |  | 3.9046 | 0
3 | Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5, 210 MW, NTPS, Eklahare, Nasik. | 0 | - | 0 | 0 | 0 | 0 | 2.9741 | 2.9741 |  |  | 2.9741 | 0
DPR 3 | Complete replacement of Platen Superheater coils at Unit No.3,4 & 5 ; Complete replacement of HRH coils at Unit No.3,& 5; Complete replacement of LTSH coils at Unit No. 5;Replacement of thermal insulation at Boiler for Nashik TPS 210 MW boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete replacement of Platen Superheater coils at Unit No. 3,4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 13.82 | 13.82 |  |  | 13.82 | 0
2 | Complete replacement of HRH coils at Unit No.3,& 5 | 0 | - | 0 | 0 | 0 | 0 | 13.68 | 13.68 |  |  | 13.68 | 0
3 | Complete replacement of LTSH coils at Unit No.5 | 0 | - | 0 | 0 | 0 | 0 | 10.7498 | 10.7498 |  |  | 10.7498 | 0
4 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines at Unit No.3,4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 1.617 | 1.617 |  |  | 1.617 | 0
DPR 4 | Procurement of various pumps for TM & ODP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement and Erection Commissioning of Condenser vacuum pump for Unit No. 3 ,4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 29.24 | 29.24 |  |  | 29.24 | 0
2 | Procurement of Three Pump assemblies of SAM TURBO makes Type 150/500 N for Booster Pump house at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0
3 | Procurement of 3 Nos Vertical Fly Ash Transfer Pump VO 150 /400 + ARS SAM make along with motor for ESP Hopper evacuation of Unit No.3,4 & 5 at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0.79 | 0.79 |  |  | 0.79 | 0
4 | Supply, erection, installation, civil foundation, commissioning, testing & trial of Rotating &casing assembly of pumps for WTP at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement (10 nos.) of CWFW pumps (with motor) at Stage-II (Beacon make) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of RWP Pump assembly at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Cooling Tower lift Pump Impeller for Jyoti make pump Type:-1200- VMI A 12 at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Degasser Pump assembly with motor (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 8 Nos. of Domestic water pumps (with motor) & Darna drinking water pump at Stage-I & II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of 4 Nos. of DM backwash (2 Nos.) & CW backwash pump (2 Nos.)(with motor)at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of HP Pumps at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of ETP pump assembly (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of RWP shaft with bearing, Impeller (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Procurement of AWR pump (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Submersible Slurry Pumps for handling Ash water / Clear water for dewatering at various locations at NTPS (10 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 5 | Renovation of Compressed Air Refrigerated Dryer System, Refurbishment of Centralized Air Conditioning system, Supply, erection & commissioning of Condensate Extraction Pump, Procurement of CW Pump and GS pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Compressed Air Refrigerated Dryer System for Nashik TPS, 210 MW Unit No. 3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 11.3737 | 11.3737 |  |  | 11.3737 | 0
2 | Refurbishment of Centralized Air Conditioning system of Unit No. 3, 4 & 5 at Nashik TPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 8.15 | 8.15 |  |  | 8.15 | 0
3 | Supply, erection & commissioning of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers ltd. at Nasik TPS. Total Qty. 02 Nos. | 0 | - | 0 | 0 | 0 | 0 | 3.93 | 3.93 |  |  | 3.93 | 0
4 | Procurement of CW & CTLP Pump total 4 No.s | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of GS Pump assembly .Total qty- 3 No | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 6 | Procurement of oil free Rotary Screw Compressors and BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of oil free rotary screw compressors | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 7 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets, Refurbishment of HPT rotor along with supply, Procurement of HP & IP control valve with cam shaft assemblies, Procurement of complete governing system assembly, Supply, Errection & Commissioning of COP assembly, Procurement of Condenser tubes & ODP related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets at 3 x 210 MW, TM-II NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of HPT rotor along with supply. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of HP & IP control valve with cam shaft assemblies.qty-1set | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of complete governing system assembly. qty-1 set | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, Errection & Commissioning of COP assembly.Total Qty.- 3 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Condenser tubes for Unit No.3, 4 & 5.Total Qty:15700 tubes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of CT Fan Blade assembly & shaft- 36 nos for Unit No.3,4 & 5 at NTPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 1.3 | 1.3 |  |  | 1.3 | 0
8 | Procurement of Gearbox Assembly for Cooling Tower Fans type B-220 Premium make for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare (Qty-24) | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
9 | Procurement of 5 nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Flocculator gearbox- 12 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of Clinker grinder assembly at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of 4 Nos. of Clinker grinder gearbox at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of 5 Nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Augmentattion of existing Ash Water recovery Scheme(WWR,AWR, ETP-I,ETP-II & Phase-II pump assembly) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Feed Gate Housing (08 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 8 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area & Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area. | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
2 | Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 9 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS , Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
2 | Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 10 | Upgradation of various electrical related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of 6.6KV HT motors and spares at Nashik TPS Unit No 3,4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
2 | Replacement of Boiler and turbine house lighting of Unit No.3,4 & 5 along with removal of old wiring. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacemet of IPH transformer 11KV/6.6 KV and lighting and welding transformer at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Excitation Transformer at Unit No. 3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | GTR /UAT/ station transformer spares LV bushings replacement, HV bushings (spare)-3nos, LV busbar, palm joint both station transformers bushings at Unit No.3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
6 | Replacement of overhead conductor HT/LT by underground HT/LT cable in Colony area. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | LT transformer procurement/ rewinding work at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | LT MCC panel modification at ODP area NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Battery Charger-220V,50V,380V UPS, 24V,DG set EMF panel with charger replacement, UPS battery replacement, Unit No. 5 station battery replacement,50 V battery set replacement at Unit No.3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
10 | Replacement of HT motor Cables. (Old PILC Cable replacement with XLPE Cable) at Unit No.3, 4 & 5 & ODP area | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
11 | Unit No. 4 Field Breaker | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
DPR 11 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 20 | 20 |  |  | 20 | 0
DPR 12 | Replacement/Upgradation of C&I old systems at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement/Upgradation of Unit No.4 DVR System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement/Upgradation of Unit No.4 UPS System. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotory Electronic Control Drive for Burner Tilt and Auxiliary Air Damper at Unit No. 3, 4 & 5 210 MW, NTPS, Eklahare Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification/Upgradation of Turbovisory system of Unit No. 3,4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Auxiliary air dampers & BT, HAD, feed gate replacement/modification work. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Unit No.4 DCS-FCS 102 to FCS 106 (Total 5 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | New sewage treatment plant required at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Upgradation of Unit No.4 230 V UPS and new UPS, charger for Unit No. 3 & 5 DCS at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | ESP hopper high & low level indicator mounting in Unit No.3,4& 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | OCEMS for Sox, Nox, opacity monitoring system upgradation work for Unit No.3, 4 & 5 at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Supply, Erection, Commissioning & Testing of online H2 purity meter and Resistivity meter for Unit No. 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, Erection, commissioning of Hydra step system for Drum level control Unit No.3. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | HPLP - Servo Spares | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Replacement of Relays and Energy meter at NTPS, Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | ESP upgradation for Unit No. 3, 4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
16 | Grounding Brush Monitoring System for Unit No. 3,4& 5. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
17 | Implementationof FGMO | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
DPR 13 | Modification & replacement of various CHP schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Modification of single stream conveyor belt Gearboxes with new design Helical Bevel type Gearboxes at CHP-II NTPS | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
2 | Modification of Primary Vibrating screen at CHP-II, NTPS | 0 | - | 0 | 0 | 0 | 0 | 0.7 | 0.7 |  |  | 0.7 | 0
3 | Supply, erection & commissioning of Rail table alongwith weighment frame for rotaside Wagon Tippler at CHP-II, NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification of Conveyor Drive system with Motorised Pulley drive system at CHP-II, NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Replacement of old damaged RBCR rail beam M/c No. CR/964 & screen to increase life of RBCR n reduced direct impact of raw coal on secondary impact crusher. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of copmlete crusher unit as per Drg. No. P00304/0 CO/1050 CR635-636(impact crusher body & rotor shaft assembly) 2 Nos | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of appron feeder head shaft assembly-25/005 drg no.-M15076/2 & tail shaft assembly-25/006 Drg. No.- M15065/2 | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
8 | Supply & erection of wagon tippler rail table Drg. No.12578/45-01 , tippler support roller & bogei Drg. No-12616/45-2M | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of seondary crusher motors 6.6KV, 750KW & 220KW motor for CHP | 0 | - | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  |  | 0.6 | 0
10 | Supply of LT motors for various conveyor belts of CHP | 0 | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
11 | Up-gradation of existing DC drive system of Wagon Tippler & Paddle feeder with new version DIGICON make system along with supply, installtion, commissioning & testing of DC drives at CHP-III. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply of Variable Frequency drives for Conv.16C2 at CHP-III. | 0 | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
13 | Up-gradation of existing relay panel of control room with microprocessor based PLC logic system along with supply, installtion, commissioning & testing of relay panel at CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Supply of Magnetic seperators & Metal detectors at CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Repair & renovation of NTPS colony ,Repairing work of ash bund side & Eklahare barrage | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of renovation of various residential quarters by providing and fixing kitchen sink, kitchen trolley & granite otta at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.9 | 0.9 |  |  | 0.9 | 0
2 | Providing and applying external painting to various types residential buildings at NTPS colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 1.09 | 1.09 |  |  | 1.09 | 0
3 | Providing and applying internal painting to various types of residential quarters at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Providing and fixing vitrified tiles to various types of residnetial buildings at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening works to various residential quarters at NTPS colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing and fixing colour coated galvanised iron sheets for roofing at various residential buildings at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Sewer line repair of various quarters at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | Stair case repairing of various building at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Construction of WBM road over/at the top of ash bund at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Repairs to filters of drain well No.4 and other allied works at ash bund valley No.4A at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Repairs to Godavari river barrage gates and allied works at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Structural repairs of Cooling Tower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repairs of cooling tower components at Unit No. 3A, 3B, 4A, 4B,5A & 5B, Stage-II NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 26.98 | 26.98 |  |  | 26.98 | 0
DPR 3 | Structural repair & rehabilitation and Renovation and modification work at NTPS Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repair & rehabilitation of various machine foundations of ID, FD & PA fans for Unit No. 3, 4, 5 at Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.25 | 0.25 |  |  | 0.25 | 0
2 | Work of removing and providing 24 B.W.G.for pent house side & roof at Unit No. 3,4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 1.74 | 1.74 |  |  | 1.74 | 0
3 | Work of removing and providing old damaged siporex wall and poly coated sheet for 28 mtr. height at Unit No. 3, 4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 1.26 | 1.26 |  |  | 1.26 | 0
4 | Structural repairs of chimney at Unit No. 3,4 & 5 Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 3.02 | 3.02 |  |  | 3.02 | 0
5 | Renovation of sump No. 2,3,4,5,6 and 7 at WTP Stage-II, NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 1.65 | 1.65 |  |  | 1.65 | 0
6 | Work of structural repairing at CHP-I,II & III area at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.76 | 0.76 |  |  | 0.76 | 0
7 | Work of structural repairing at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 5.67 | 5.67 |  |  | 5.67 | 0
8 | Work of structural repair of GS pump Unit No. 3,4,& 5 and fire fighting pump house at Stage-II,NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.58 | 0.58 |  |  | 0.58 | 0
9 | Work of repairs to doors & windows of various building at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.24 | 0.24 |  |  | 0.24 | 0
10 | Providing and fixing powder coated colored Zincalume profiled sheet for various building at CHP,AWR building, Time office & ODP EM at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 2.72 | 2.72 |  |  | 2.72 | 0
11 | Work of external painting & internal painting at WTP, Stage-II NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.93 | 0.93 |  |  | 0.93 | 0
12 | Work of external painting & internal painting at CHP area NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.47 | 0.47 |  |  | 0.47 | 0
13 | Renovation and restructuring of shed No. 1, 2, 5, 6, 9 & 11 of major store custody of NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 2.37 | 2.37 |  |  | 2.37 | 0
DPR 4 | As per I.B.Recommondation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of construction compound wall with concertina coil at various locations at Nashik TPS. | 0 | - | 0 | 0 | 0 | 0 | 41.21 | 41.21 |  |  | 41.21 | 0
2 | Providing & renovating security watch tower at NTPS Premises Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.43 | 0.43 |  |  | 0.43 | 0
0 | HO Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | R&M/LE for Identified Thermal units of MSPGCL of (3 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL (3 x 210 MW) units of MSPGCL | 0 | - | 0 | 0 | 0 | 0 | 384.04 | 384.04 |  |  | 384.04 | 0
DPR 2 | CHP Improvcement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | TATA Mini Truck SFC 709 EX No.MH-15-JV-3992 | N.A. | - | 0 | 0.32099 | 0.32099 | 0 | 0 | 0 |  |  | 0 | 0
2 | Executive chair(10),S Type Arm chai(20) | N.A. | - | 0 | 0.10784 | 0.10784 | 0 | 0 | 0 |  |  | 0 | 0
3 | Office Table and S-Type Chair with Arm | N.A. | - | 0 | 0.030968 | 0.030968 | 0 | 0 | 0 |  |  | 0 | 0
4 | Windows Slot in PC VPC 10-Intel Core 13 4th -NTC | N.A. | - | 0 | 0.010561 | 0.010561 | 0 | 0 | 0 |  |  | 0 | 0
5 | LG Screen wall mounted computer-LED display65"-NTC | N.A. | - | 0 | 5.0969 | 5.0969 | 0 | 0 | 0 |  |  | 0 | 0
6 | 20 Ton Split AC for Audtiorium -NTC | N.A. | - | 0 | 1.0873 | 1.0873 | 0 | 0 | 0 |  |  | 0 | 0
7 | Colour Laser Printer, All in one A3 LaserJet Print | N.A. | - | 0 | 1.0589 | 1.0589 | 0 | 0 | 0 |  |  | 0 | 0
8 | Digital DSLR Camera | N.A. | - | 0 | 1.0793 | 1.0793 | 0 | 0 | 0 |  |  | 0 | 0
9 | Indoor Gymnasium Equipments at NTC, Eklahare | N.A. | - | 0 | 0.02853 | 0.02853 | 0 | 0 | 0 |  |  | 0 | 0
10 | CLASS ROOM CHAIR WITH DESKLET | N.A. | - | 0 | 0.023576 | 0.023576 | 0 | 0 | 0 |  |  | 0 | 0
11 | PA System and Sport Material,Table Tannis for | N.A. | - | 0 | 0.01687 | 0.01687 | 0 | 0 | 0 |  |  | 0 | 0
12 | EXECUTIVE CHAIR WITH 5 SUPRT & S-TYPE CHAIR | N.A. | - | 0 | 0.01003 | 0.01003 | 0 | 0 | 0 |  |  | 0 | 0
13 | APPLN COOLER AIR SEMIEXH AIR COOLER ASSY | N.A. | - | 0 | 0.033896 | 0.033896 | 0 | 0 | 0 |  |  | 0 | 0
14 | FULL PAD CHAIRS WITH SIDE ARM | N.A. | - | 0 | 0.029637 | 0.029637 | 0 | 0 | 0 |  |  | 0 | 0
15 | Industrial Cabinet with 12 Lockers | N.A. | - | 0 | 0.0070163 | 0.0070163 | 0 | 0 | 0 |  |  | 0 | 0
16 | UV Water Purifier Filter | N.A. | - | 0 | 0.019116 | 0.019116 | 0 | 0 | 0 |  |  | 0 | 0
17 | FILTER RO+UV+UF+TDS WATER PURIFIER | N.A. | - | 0 | 0.032906 | 0.032906 | 0 | 0 | 0 |  |  | 0 | 0
18 | 2 Tone SPLIT AC INDOOR UNIT | N.A. | - | 0 | 0.008064 | 0.008064 | 0 | 0 | 0 |  |  | 0 | 0
19 | 1.5 TON CAPACITY SPLIT AC | N.A. | - | 0 | 0.006688 | 0.006688 | 0 | 0 | 0 |  |  | 0 | 0
20 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 1.698 | 1.698 | 0 | 0 | 0 |  |  | 0 | 0
21 | Logitech PTZ Group Camera 960-001054 | N.A. | - | 0 | 2.4375 | 2.4375 | 0 | 0 | 0 |  |  | 0 | 0
22 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011564 | 0.011564 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK BENCH WITHOUT DRAWER | 0 | - | 0 | 0.011647 | 0.011647 | 0 | 0 | 0 |  |  | 0 | 0
24 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.030075 | 0.030075 | 0 | 0 | 0 |  |  | 0 | 0
25 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011788 | 0.011788 | 0 | 0 | 0 |  |  | 0 | 0
26 | EXECUTIVE CHAIR, S-TYPE CH-7 CHAIR WITH ARM | 0 | - | 0 | 0.035229 | 0.035229 | 0 | 0 | 0 |  |  | 0 | 0
27 | SAMSUNG GALAXY TAB S3, 32GB 9.7 INCH | 0 | - | 0 | 0.003845 | 0.003845 | 0 | 0 | 0 |  |  | 0 | 0
28 | i5 Laptop - 2 Nos & i7 Laptop - 3 Nos | 0 | - | 0 | 0.037636 | 0.037636 | 0 | 0 | 0 |  |  | 0 | 0
29 | Godrej make 1.5 Ton High Wall Split AC | 0 | - | 0 | 0.020975 | 0.020975 | 0 | 0 | 0 |  |  | 0 | 0
30 | Complete Multimedia Projector with Std Accessories | 0 | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
31 | LED 40 INCH SMART TV | 0 | - | 0 | 0.0092016 | 0.0092016 | 0 | 0 | 0 |  |  | 0 | 0
32 | FULL PAD CHAIRS, EXECUTIVE CHAIR, | 0 | - | 0 | 0.068995 | 0.068995 | 0 | 0 | 0 |  |  | 0 | 0
33 | Cash Counting Machine | 0 | - | 0 | 0.001888 | 0.001888 | 0 | 0 | 0 |  |  | 0 | 0
34 | 230 V AC DIGITAL SINE WAVE INVERTER 1 No. | 0 | - | 0 | 0.010175 | 0.010175 | 0 | 0 | 0 |  |  | 0 | 0
35 | HPCV no.3 &4 Stem | 0 | - | 0 | 0.025694 | 0.025694 | 0 | 0 | 0 |  |  | 0 | 0
36 | HEAVY DUTY AIR PURIFIURE 230V,50HZ | 0 | - | 0 | 0.0105 | 0.0105 | 0 | 0 | 0 |  |  | 0 | 0
37 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.0048144 | 0.0048144 | 0 | 0 | 0 |  |  | 0 | 0
38 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.025939 | 0.025939 | 0 | 0 | 0 |  |  | 0 | 0
39 | APPLN COOLER WTR CAP CAP: 60 LITERS | 0 | - | 0 | 0.0053799 | 0.0053799 | 0 | 0 | 0 |  |  | 0 | 0
40 | LASER LASERJET PRINTER FOR A4 PAPER | 0 | - | 0 | 0.0057 | 0.0057 | 0 | 0 | 0 |  |  | 0 | 0
41 | 40 Inch Smart LED TV 3.00 | 0 | - | 0 | 0.010178 | 0.010178 | 0 | 0 | 0 |  |  | 0 | 0
42 | DESKTOP INTEL CORE I5 2300 PROCESSOR | 0 | - | 0 | 0.021459 | 0.021459 | 0 | 0 | 0 |  |  | 0 | 0
43 | ONLINE WATER HEATER, 3KW,3LTR. | 0 | - | 0 | 0.029683 | 0.029683 | 0 | 0 | 0 |  |  | 0 | 0
44 | CAMERA FOR VC, MICROPHONE WITH SPEAKER | 0 | - | 0 | 0.023889 | 0.023889 | 0 | 0 | 0 |  |  | 0 | 0
45 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
46 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 0.01873 | 0.01873 | 0 | 0 | 0 |  |  | 0 | 0
47 | Water Cooler | 0 | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
48 | PORTABLE HARD DISK USB 1TB | 0 | - | 0 | 0.0017388 | 0.0017388 | 0 | 0 | 0 |  |  | 0 | 0
49 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.00095 | 0.00095 | 0 | 0 | 0 |  |  | 0 | 0
50 | Garbox assembly for premium make type B-220 of | 0 | - | 0 | 0.44095 | 0.44095 | 0 | 0 | 0 |  |  | 0 | 0
51 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.006726 | 0.006726 | 0 | 0 | 0 |  |  | 0 | 0
52 | RO+UV+UF+TDS CAP 50 LITRE PER HOUR | 0 | - | 0 | 0.002731 | 0.002731 | 0 | 0 | 0 |  |  | 0 | 0
53 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.0025995 | 0.0025995 | 0 | 0 | 0 |  |  | 0 | 0
54 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.002183 | 0.002183 | 0 | 0 | 0 |  |  | 0 | 0
55 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0061808 | 0.0061808 | 0 | 0 | 0 |  |  | 0 | 0
56 | REGULAR CHAIR WITHOUT CUSHION | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
57 | BLDC Fans through GeM Portal and GA -2022-23 at | 0 | - | 0 | 0.0049556 | 0.0049556 | 0 | 0 | 0 |  |  | 0 | 0
58 | ALL IN ONE PC, CORE I5, 4 GB RAM, 500 GB | 0 | - | 0 | 0.02973 | 0.02973 | 0 | 0 | 0 |  |  | 0 | 0
59 | PRINTER LASER LASERJET NETWORK PRINTER | 0 | - | 0 | 0.0020024 | 0.0020024 | 0 | 0 | 0 |  |  | 0 | 0
60 | APPLN FAN AIR CEIL SIZE 1200 MM SWEEP | 0 | - | 0 | 0.033918 | 0.033918 | 0 | 0 | 0 |  |  | 0 | 0
61 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.014828 | 0.014828 | 0 | 0 | 0 |  |  | 0 | 0
62 | 400 MM, 230V, 3 BLADE DOMESTIC FAN | 0 | - | 0 | 0.0024532 | 0.0024532 | 0 | 0 | 0 |  |  | 0 | 0
63 | APPLN FAN AIR EXHAUST SIZE15"1400RPM-15 Nos | 0 | - | 0 | 0.01781 | 0.01781 | 0 | 0 | 0 |  |  | 0 | 0
64 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.013559 | 0.013559 | 0 | 0 | 0 |  |  | 0 | 0
65 | MICROWAVE OVEN CAPACITY 27 / 28 LITERS-1 Nos | 0 | - | 0 | 0.0048362 | 0.0048362 | 0 | 0 | 0 |  |  | 0 | 0
66 | REFRIGERATOR SINGLE DOOR CAPCITY 190 LTR | 0 | - | 0 | 0.0067225 | 0.0067225 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Thinclients on Buyback for NTPS | 0 | - | 0 | 0.23166 | 0.23166 | 0 | 0 | 0 |  |  | 0 | 0
68 | ABC Powder type DCP Composite Fire Extinguisher | 0 | - | 0 | 0.357 | 0.357 | 0 | 0 | 0 |  |  | 0 | 0
69 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024631 | 0.024631 | 0 | 0 | 0 |  |  | 0 | 0
70 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024213 | 0.024213 | 0 | 0 | 0 |  |  | 0 | 0
71 | Furniture Dining Table for Main Mess Hall and Cus | 0 | - | 0 | 0.019803 | 0.019803 | 0 | 0 | 0 |  |  | 0 | 0
72 | Servers for DSM at Nashik Thermal Power Station | 0 | - | 0 | 0.43559 | 0.43559 | 0 | 0 | 0 |  |  | 0 | 0
73 | DESKTOP INTEL CORE I5 2300 PROCESSOR - 5 Nos | 0 | - | 0 | 0.05632 | 0.05632 | 0 | 0 | 0 |  |  | 0 | 0
74 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.041064 | 0.041064 | 0 | 0 | 0 |  |  | 0 | 0
75 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.038246 | 0.038246 | 0 | 0 | 0 |  |  | 0 | 0
76 | APPLN TV STD ULSLIM 42" - 4 Nos | 0 | - | 0 | 0.037376 | 0.037376 | 0 | 0 | 0 |  |  | 0 | 0
77 | 1 T SPLIT AC COMPL UNIT WITH ACCESSORIES | 0 | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
78 | MULTIMEDIA PROJECTOR EPSON EB-U05-1 No | 0 | - | 0 | 0.0081606 | 0.0081606 | 0 | 0 | 0 |  |  | 0 | 0
79 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.0023246 | 0.0023246 | 0 | 0 | 0 |  |  | 0 | 0
80 | Procurement of Complete Vibrating Screen Assembly at CHP-II | 0 | - | 0 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Asset | 0 | - | 0 | 0.575 | 0.575 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 292.3345 | 289.7719 | 2.5625 | 711.384 | 735.654 | 0 | 0 | 735.654 | -21.7075
FY 2026-27
a) DPR Schemes
(i) Submitted to MERC
1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Measuring & Monitoring of Coal consumption | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 23.0165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Belt Weighers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3295 | 0.3295 | 0.3295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.793 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of inhaul outhaul betel chargers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 6 | 8.5943 | 8.5943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Dust Extraction System | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 1.65 | 1.713 | 1.713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Fogging system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 2.44 | 2.59 | 2.59 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Bunker level montoring system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.54 | 0.0694 | 0.0694 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.169 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Operating the CHP near to its full capacity | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 7.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Motor controller | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3732 | 0.3732 | 0.3732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 3.4218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Combustion optimization & Process improvement | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 58.7761 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Improvement in tooling techniques Power tools like cut off machines and surface grinders. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.52821 | 0.3388 | 0.3388 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Total replacement of boiler related skin insulation as well as skin cladding of furnace, Air pre heaters,air ducts and flue gas ducts Unit-4 &5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4.5892 | 4.7188 | 4.7188 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Painting of Boiler ,bunker structure and other structure.Unit-3,4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 7.775 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 8.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Retrofitting of Gas proportioning dampers, flue gas, primary and secondary air dampers. (SADC) for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.456 | 1.2566 | 1.2566 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.41356 | 0.41356 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Replacement of flue gas ducting zone prone to erosion with 6 to 8 mm high grade material & insulation of flue gas ducts. (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 4 and 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Replacement of boiler outlet valves and damaged valves of units 4 & 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.349 | 1.4313 | 1.4313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Replacement of coal pipe at direction changing sections & flow curvature zone by upgraded material. Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.3292 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.9 | Installation of Smart soot blower system for Unit- 4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 5.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.10 | Installation of Sonic soot blowers for second pass for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.83184 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.11 | Air pre heater upgradation of heat exchanger matrix &regenerative dynamic sealing for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.12 | Replacement Platen water wall for Unit-3. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.60762 | 0.6964 | 0.6964 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 13.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Turbine Auxiliary Consumption Improvement | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 39.2903 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Installation of Turbo vaned fly wheeling eco ventilators to all Units 3, 4, 5. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Replacement of selected old brass impellers of pumps with SS304 impellers. H.T. Auxiliary C.W. Pump and G.S. Water Pumps are selected. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.4 | 0.8251 | 0.8251 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Improving the BFP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.75 | 0.48804 | 0.48804 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Replacement of BFP (200 KHI) cartridge with energy efficient cartridge. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 14.4456 | 13.85 | 13.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Improving the CEP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.9 | 0.6018 | 0.6018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Replacement of CEP with energy efficient pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Replacement of Pumps - GS Pumps, H2Cooler booster pump, DM/DM pumps, DM Makeup pumps, Emergency lift pumps, Drip pumps, BFP Booster pumps with energy efficient pumps. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 4.2733 | 2.3608 | 2.3608 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.8 | Replacement of valves – MS - 3 to 8 , HD – 22,23,24 , MC- 36 , ES 3,4 and BFP Recirculation Valves. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.0852 | 1.3148 | 1.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.9 | Replacement of tube nest of LP Heater no.3 of unit no.3, LP Heater no.4 of unit no.5, Main ejector 3B, GC2 of unit no.5, Seal oil coolers, H2 Coolers, BFP working and lub oil coolers, DM/GS plate type coolers. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 6.5962 | 1.9594 | 1.9594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.11461 | 0.11461 | 0 | 0 | 0 |  |  | 0 | 0
5.10 | Steam path audit of Unit no,4,5 | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | EMS, Numeric relays, Microprocessor DVR & VFD | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 12.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Design, manufacture, supply, erection, commissioning & testing of Variable Frequency Drives (VFD) with latest design and technology super premium efficiency motors for 415 V LT Auxiliaries (Total 50 No) of 210 MW Unit 3, 4 & 5. | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 6.3 | 8.8183 | 6.2927 | 2.5255 | 0 | 0 |  |  | 0 | 2.5255 | 0 | 0
0 | IDC | 0 | - | 0.66 | 0.74645 | 0.74645 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Replacement of old EE make Generator Protection Relays with Numerical Generator Protection Relays for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 1.7 | 1.7029 | 1.7029 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Replacement of old AVR with Microprocessor based Digital Voltage Regulator for unit no. 3 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 2.44 | 1.7055 | 1.7055 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Installation and commissioning of Energy Management System for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.81 | 0.8313 | 0.8313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 14.5069 | 14.5069 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 57.9147 | 57.9147 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Faster unloading of coal wagons by upgrading existing system (Post Facto) | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 18.8481 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Re-design, Supply, Erection and commissioning of modified Apron Feeder. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.7219 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Design, manufacture, supply, erection and commissioning of modified bunker outlet cone of Unit 3, 4 and 5. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.3295 | 2.3196 | 2.3196 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Design, manufacture, Supply & Erection Of Components Suitable For Modification Of Wagon Tipplers to Handle BOXNHL , BOX-H,BOX-NR,BOX-NJLSR1 & 25 T AXLE WAGONS | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.1298 | 4.413 | 4.413 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Procurement of SAN Loco - 650-700 HP. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8627 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.5 | Revamping of CHP II Wagon Tippler by replacing the Split Wheel Assembly, Pawl Lever, Pinion Shaft Assembly, Toe, Spur Gear Shaft, W.T Drive Assembly, Rack Segment, Rail Table Assembly Of Wagon Tippler and Dismantling & Replacement of above parts | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8042 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement of 6.6 Kv HT motors as spare motors /for replacement | MERC/CAPEX/20152016/00422 | 2016-08-03 | 14.3563 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3125 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1025 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | FD FAN MOTOR 650 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | FD FAN MOTOR 750 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8505 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | PA FAN MOTOR 1250 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.029 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | BFP MOTOR 4000 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 4.5528 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | C/MILL MOTOR 320 kW (3 Nos) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3356 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.8 | SOP MOTOR 200 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.9 | CWP MOTOR 950 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8942 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.10 | CTLP MOTOR 710 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8081 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.11 | RWP MOTOR 335 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.4861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.12 | HP PUMP MOTOR 258 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3083 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.13 | CEP MOTOR 220 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2629 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.14 | GS PUMP MOTOR 260 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3107 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.15 | Testing charges | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.088 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Replacement of complete LTSH coils at Unit-3 Boiler & Economiser coils at Unit-5 Boiler | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 27.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Complete Supply & Erection of LTSH coils at Unit-3 210 MW Boiler (67 nos. upper and lower modules each. 01 module = 02 coils) | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 16.43 | 4.6378 | 4.6378 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Complete Supply & Erection of 270 nos. Economizer coils in second pass of Unit-5 210 MW Boiler at Nasik TPS. | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 9.57 | 3.0104 | 3.0104 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 1.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Enhancement of performance & life of Coal Handling plant | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 17.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Procurement of 02 nos of 320 hp bull dozers for Nasik TPS | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 3.2 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Procurement of gear box for Apron Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 1.59 | 1.6043 | 1.6043 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Procurement of gear box and 30 KW DC motor for Pedal Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.46 | 0.45847 | 0.45847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.4 | Procurement of Assembly of Impact Crusher Complete set, with Rotor Assembly and bearing Block. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 2.3 | 2.3366 | 2.3366 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.5 | Procurement of 10 KW Inline Magnetic Separator for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.4 | 0.54718 | 0.54718 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.6 | Restoration of RBCR by replacing feed end Spider (Drg. No. 400-1428-01/A) & Discharge end Spider (400-1428-02) suitable to rotary Bradford breaker machine No.CR/634 along with support wheels. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 8.14 | 10.2287 | 10.2287 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.7 | Procurement of 750 KW Impactor Motor for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.49 | 0.22635 | 0.22635 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.8 | Supply of Metal Detectors for CHP | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.14 | 0.09152 | 0.09152 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Retrofitting of 6.6 kV Breakers, Battery Replacement, System Improvement & MPCB Related schemes | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 14.7811 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Retrofitting of 6.6 kV HT MOCB/SF6 Breakers by VCB | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 3.57 | 5.0621 | 5.0621 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2a | A) Procurement & Replacement of 220V/ 1285 AH Battery set for U#3 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0493 | 1.0493 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2b | B) Procurement & Replacement of 220V/ 1285 AH Battery set for U#4 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0047 | 1.0047 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | O2 Measurement System in the furnace & flue gas ducting | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.17 | 1.2966 | 1.2966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Supply, erection, commissioning & testing of online CO, SO2, NOX Analyser for U#3/4/5 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.6511 | 1.6846 | 1.6846 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | A) Replacement of static Flame Monitoring System with Microprocessor based Flame Monitoring & Analyzing System | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.27 | 2.4267 | 2.4267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | CAAQMS monitoring of ambient air quality around the NTPS. | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1 | 0.81676 | 0.81676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | 3rd raising of Ash bund | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | 3rd raising of ash bund from TBL 581.50 to 586.50m in valley No. 4A at Nashik Thermal Power Station, Eklahare | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 12.3 | 10.2142 | 10.2142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | System Rehabilitation & Upgradation at Nasik TPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 13.3722 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Shifting, Transportation & Replacement of Existing Generator Stator of Unit no.3 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 7.98 | 0.8767 | 5.8767 | -5 | 0 | 0 |  |  | 0 | -5 | 0 | 0
0 | IDC | 0 | - | 0 | 0.26397 | 0.26397 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Turbine Supervisory Instrumentation System for Unit no.5 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.5542 | 0.45436 | 0.45436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Supply of Air Compressors for NTPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 3.398 | 3.8197 | 3.8197 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Replacement of Old Brass Impellers of CTLP with SS Impellers. | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 1.04 | 1.1331 | 1.1331 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up-gradation of DCS at U # 3 and New Rectiformers & ESP Refurbishment of U # 4 & 5 at Nasik TPS | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 33.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Decommissioning & Shifting of M/s ABB make DCS system at BTPS Unit # 2 & Re-commissioning with Up gradation to Symphony Plus at NTPS Unit #3, Nasik. | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 9.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Erection ,Testing & commissioning, Supply of rectiformer HVR 37/800 Hermatically sealed Rectiformer ( DC Peak voltage – 70 kV , Average voltage-45 KV ,DC Current – 800 milli amp , AC I/P – 1 Phase , 415 V ) | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 10.34 | 0 | 13 | -13 | 0 | 0 |  |  | 0 | -13 | 0 | 0
16.3 | Refurbishment of ESP for Unit No. 4 & 5 at Nashik TPS, Eklahare | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 12.5 | 12.8553 | 12.8553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 1.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Replacement of drum gate, augmentation of existing ash water recovery scheme and construction of concrete road for Nasik Thermal Power Station | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 14.5161 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Replacement of drum gate and restructuring of cofferdam, repairs to vertical sluice gate, Approach Bridge and allied civil works at Godavari barrage at Nashik TPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 6.273 | 3 | 6.27 | -3.27 | 0 | 0 |  |  | 0 | -3.27 | 0 | 0
17.2 | Augmentation of existing ash water recovery scheme and connecting overflow of waste weir to existing toe drain of ash bund valley no.4 to WWR at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 2.5999 | 3.1676 | 3.1676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2441 | 0.2441 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Up gradation of fly ash concrete road from Booster Pump house toward Hydrogen plant, Dirk India Company towards Hinganwedhe along ash bund valley No. 1 & 2, Ash bund approach road for ash transportation and abundant valley towards Kotamgaon road at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 5.3732 | 5.3752 | 5.3752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 0.27 | 0.38455 | 0.38455 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Various DPR Schemes for Renovation of colony at NTPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 10.8678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Renovation of staff quarters, playground, Jogging track & Gymnasium at NTPS colony, Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 4.071 | 3.5306 | 3.5306 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.92832 | 0.92832 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Road works in NTPS Colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 3.9766 | 3.8972 | 3.8972 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Water supply and sanitation works at NTPS colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 2.8202 | 1.4586 | 1.4586 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.19994 | 0.19994 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Renovation of Workers Recreation Club at Nashik TPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Life enhancement of stacker cum reclaimer machine in CHP & upgradation of SWAS laboratory at Nasik TPS | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 14.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Supply, Erection & installation of sole plates, Rail track & Hydraulic cylinder of the Stacker cum Reclaimer machine at Coal Handling Plant-II Nashik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 6.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement and replacement of 220 V, 1285 AH battery set for Unit No. 4 at Nasik Thermal Power Station. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 1.39 | 1.4116 | 1.4116 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2227 | 0.2227 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Supply of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers Ltd.) at Nasik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 3.11 | 3.0812 | 3.0812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Erection and commissioning of Steam and Water sampling system for SWAS Lab at WTP, NTPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 2.23 | 0 | 3 | -3 | 0 | 0 |  |  | 0 | -3 | 0 | 0
19.5 | Procurement of 3 nos. of Ash Slurry Disposal pump Type D - 85 for Ash Slurry Pump House of Unit no. 3, 4 & 5 at NTPSEklahare. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.55 | 0.55578 | 0.51878 | 0.037 | 0 | 0 |  |  | 0 | 0.037 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Flue Gas Desulphurization (FGD) System at Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Ash Augmentation System at Nasik & Koradi Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Ash Augmentation System at Nasik Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 5.71 | 5.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3.1 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 8.47 | 8.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | NASIK TPS (U-3 to 5) (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 2.8842 | 2.8842 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.76776 | 0.76776 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Nashik TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.2272 | 2.2272 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | TPS Nashik | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 2.3118 | 2.3118 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.1 | Procurement and Replacement of Complete sets of assembly of baskets for air preheater of type tri-sector APH 27 VI(T) 74” in NTPS unit no. 4 & 5 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 5.5929 | 5.5929 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.13531 | 0.13531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | <DPR Name> | N.A. | N.A. | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Complete Replacement of HRH Coils, LTSH Coils, Economizer Coils at Unit No. 4 & Complete Replacement of Economizer coils at Unit No.3 Nashik TPS 210 MW Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Replacement HRH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 6.84 | 6.84 | 0 | 1.711 | 1.711 |  |  | 1.711 | 0
2 | Complete Replacement LTSH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 10.7498 | 10.7498 | 0 | 1.911 | 1.911 |  |  | 1.911 | 0
3 | Complete Replacement Economiser Coils at NTPS Unit No. 3 & 4 Boilers | 0 | - | 0 | 13.66 | 13.66 | 0 | 1.2036 | 1.2036 |  |  | 1.2036 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 and Commissioning of AFGC system for Unit No. 3, 4 & 5 and Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5 at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of MSERW pipes for Replacement of various pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 at NTPS, Eklahare | 0 | - | 0 | 16.1949 | 16.1949 | 0 | 3.482 | 3.482 |  |  | 3.482 | 0
2 | Supply, erection, commissioning & testing of Ammonia Flue gas Conditioning system for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 3.9046 | 3.9046 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5, 210 MW, NTPS, Eklahare, Nasik. | 0 | - | 0 | 2.9741 | 2.9741 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Complete replacement of Platen Superheater coils at Unit No.3,4 & 5 ; Complete replacement of HRH coils at Unit No.3,& 5; Complete replacement of LTSH coils at Unit No. 5;Replacement of thermal insulation at Boiler for Nashik TPS 210 MW boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete replacement of Platen Superheater coils at Unit No. 3,4 & 5 | 0 | - | 0 | 13.82 | 13.82 | 0 | 1.39 | 1.39 |  |  | 1.39 | 0
2 | Complete replacement of HRH coils at Unit No.3,& 5 | 0 | - | 0 | 13.68 | 13.68 | 0 | 1.711 | 1.711 |  |  | 1.711 | 0
3 | Complete replacement of LTSH coils at Unit No.5 | 0 | - | 0 | 10.7498 | 10.7498 | 0 | 0 | 0 |  |  | 0 | 0
4 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines at Unit No.3,4 & 5 | 0 | - | 0 | 1.617 | 1.617 | 0 | 2.64 | 2.64 |  |  | 2.64 | 0
DPR 4 | Procurement of various pumps for TM & ODP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement and Erection Commissioning of Condenser vacuum pump for Unit No. 3 ,4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 29.24 | 29.24 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Three Pump assemblies of SAM TURBO makes Type 150/500 N for Booster Pump house at NTPS Eklahare. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 3 Nos Vertical Fly Ash Transfer Pump VO 150 /400 + ARS SAM make along with motor for ESP Hopper evacuation of Unit No.3,4 & 5 at NTPS Eklahare | 0 | - | 0 | 0.79 | 0.79 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection, installation, civil foundation, commissioning, testing & trial of Rotating &casing assembly of pumps for WTP at Nashik TPS, Eklahare | 0 | - | 0 | 0 | 0 | 0 | 1.6 | 1.6 |  |  | 1.6 | 0
5 | Procurement (10 nos.) of CWFW pumps (with motor) at Stage-II (Beacon make) | 0 | - | 0 | 0 | 0 | 0 | 0.94 | 0.94 |  |  | 0.94 | 0
6 | Procurement of RWP Pump assembly at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
7 | Procurement of Cooling Tower lift Pump Impeller for Jyoti make pump Type:-1200- VMI A 12 at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 1.07 | 1.07 |  |  | 1.07 | 0
8 | Procurement of Degasser Pump assembly with motor (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0.354 | 0.354 |  |  | 0.354 | 0
9 | Procurement of 8 Nos. of Domestic water pumps (with motor) & Darna drinking water pump at Stage-I & II | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of 4 Nos. of DM backwash (2 Nos.) & CW backwash pump (2 Nos.)(with motor)at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of HP Pumps at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of ETP pump assembly (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of RWP shaft with bearing, Impeller (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Procurement of AWR pump (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Submersible Slurry Pumps for handling Ash water / Clear water for dewatering at various locations at NTPS (10 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 5 | Renovation of Compressed Air Refrigerated Dryer System, Refurbishment of Centralized Air Conditioning system, Supply, erection & commissioning of Condensate Extraction Pump, Procurement of CW Pump and GS pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Compressed Air Refrigerated Dryer System for Nashik TPS, 210 MW Unit No. 3, 4 & 5 | 0 | - | 0 | 11.3737 | 11.3737 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of Centralized Air Conditioning system of Unit No. 3, 4 & 5 at Nashik TPS, Eklahare. | 0 | - | 0 | 8.15 | 8.15 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers ltd. at Nasik TPS. Total Qty. 02 Nos. | 0 | - | 0 | 3.93 | 3.93 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of CW & CTLP Pump total 4 No.s | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
5 | Procurement of GS Pump assembly .Total qty- 3 No | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 6 | Procurement of oil free Rotary Screw Compressors and BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 7 | 0
2 | Procurement of oil free rotary screw compressors | 0 | - | 0 | 0 | 0 | 0 | 21.6648 | 21.6648 |  |  | 21.6648 | 0
DPR 7 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets, Refurbishment of HPT rotor along with supply, Procurement of HP & IP control valve with cam shaft assemblies, Procurement of complete governing system assembly, Supply, Errection & Commissioning of COP assembly, Procurement of Condenser tubes & ODP related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets at 3 x 210 MW, TM-II NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0.63 | 0.63 |  |  | 0.63 | 0
2 | Refurbishment of HPT rotor along with supply. | 0 | - | 0 | 0 | 0 | 0 | 3.7908 | 3.7908 |  |  | 3.7908 | 0
3 | Procurement of HP & IP control valve with cam shaft assemblies.qty-1set | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of complete governing system assembly. qty-1 set | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, Errection & Commissioning of COP assembly.Total Qty.- 3 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Condenser tubes for Unit No.3, 4 & 5.Total Qty:15700 tubes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of CT Fan Blade assembly & shaft- 36 nos for Unit No.3,4 & 5 at NTPS, Eklahare | 0 | - | 0 | 1.3 | 1.3 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Gearbox Assembly for Cooling Tower Fans type B-220 Premium make for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare (Qty-24) | 0 | - | 0 | 1.5 | 1.5 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
9 | Procurement of 5 nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0.25 | 0.25 |  |  | 0.25 | 0
10 | Procurement of Flocculator gearbox- 12 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0.4 | 0.4 |  |  | 0.4 | 0
11 | Procurement of 4 Nos. of Clinker grinder assembly at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0.65 | 0.65 |  |  | 0.65 | 0
12 | Procurement of 4 Nos. of Clinker grinder gearbox at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0.2 | 0.2 |  |  | 0.2 | 0
13 | Procurement of 5 Nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Augmentattion of existing Ash Water recovery Scheme(WWR,AWR, ETP-I,ETP-II & Phase-II pump assembly) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Feed Gate Housing (08 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 8 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area & Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 9 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS , Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
DPR 10 | Upgradation of various electrical related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of 6.6KV HT motors and spares at Nashik TPS Unit No 3,4 & 5. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Boiler and turbine house lighting of Unit No.3,4 & 5 along with removal of old wiring. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
3 | Replacemet of IPH transformer 11KV/6.6 KV and lighting and welding transformer at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
4 | Excitation Transformer at Unit No. 3, 4 & 5 | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
5 | GTR /UAT/ station transformer spares LV bushings replacement, HV bushings (spare)-3nos, LV busbar, palm joint both station transformers bushings at Unit No.3, 4 & 5 | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of overhead conductor HT/LT by underground HT/LT cable in Colony area. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
7 | LT transformer procurement/ rewinding work at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8 | LT MCC panel modification at ODP area NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
9 | Battery Charger-220V,50V,380V UPS, 24V,DG set EMF panel with charger replacement, UPS battery replacement, Unit No. 5 station battery replacement,50 V battery set replacement at Unit No.3, 4 & 5 | 0 | - | 0 | 1.5 | 1.5 | 0 | 1 | 1 |  |  | 1 | 0
10 | Replacement of HT motor Cables. (Old PILC Cable replacement with XLPE Cable) at Unit No.3, 4 & 5 & ODP area | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
11 | Unit No. 4 Field Breaker | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
DPR 11 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 20 | 20 | 0 | 20 | 20 |  |  | 20 | 0
DPR 12 | Replacement/Upgradation of C&I old systems at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement/Upgradation of Unit No.4 DVR System. | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
2 | Replacement/Upgradation of Unit No.4 UPS System. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
3 | Supply of Beck Rotory Electronic Control Drive for Burner Tilt and Auxiliary Air Damper at Unit No. 3, 4 & 5 210 MW, NTPS, Eklahare Nashik. | 0 | - | 0 | 0 | 0 | 0 | 7.93 | 7.93 |  |  | 7.93 | 0
4 | Modification/Upgradation of Turbovisory system of Unit No. 3,4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
5 | Auxiliary air dampers & BT, HAD, feed gate replacement/modification work. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
6 | Upgradation of Unit No.4 DCS-FCS 102 to FCS 106 (Total 5 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
7 | New sewage treatment plant required at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
8 | Upgradation of Unit No.4 230 V UPS and new UPS, charger for Unit No. 3 & 5 DCS at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 4 | 4 |  |  | 4 | 0
9 | ESP hopper high & low level indicator mounting in Unit No.3,4& 5. | 0 | - | 0 | 0 | 0 | 0 | 6 | 6 |  |  | 6 | 0
10 | OCEMS for Sox, Nox, opacity monitoring system upgradation work for Unit No.3, 4 & 5 at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
11 | Supply, Erection, Commissioning & Testing of online H2 purity meter and Resistivity meter for Unit No. 5. | 0 | - | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0
12 | Supply, Erection, commissioning of Hydra step system for Drum level control Unit No.3. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
13 | HPLP - Servo Spares | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
14 | Replacement of Relays and Energy meter at NTPS, Nashik. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
15 | ESP upgradation for Unit No. 3, 4 & 5. | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
16 | Grounding Brush Monitoring System for Unit No. 3,4& 5. | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
17 | Implementationof FGMO | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
DPR 13 | Modification & replacement of various CHP schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Modification of single stream conveyor belt Gearboxes with new design Helical Bevel type Gearboxes at CHP-II NTPS | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
2 | Modification of Primary Vibrating screen at CHP-II, NTPS | 0 | - | 0 | 0.7 | 0.7 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Rail table alongwith weighment frame for rotaside Wagon Tippler at CHP-II, NTPS | 0 | - | 0 | 0 | 0 | 0 | 1.2 | 1.2 |  |  | 1.2 | 0
4 | Modification of Conveyor Drive system with Motorised Pulley drive system at CHP-II, NTPS. | 0 | - | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 0
5 | Replacement of old damaged RBCR rail beam M/c No. CR/964 & screen to increase life of RBCR n reduced direct impact of raw coal on secondary impact crusher. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of copmlete crusher unit as per Drg. No. P00304/0 CO/1050 CR635-636(impact crusher body & rotor shaft assembly) 2 Nos | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of appron feeder head shaft assembly-25/005 drg no.-M15076/2 & tail shaft assembly-25/006 Drg. No.- M15065/2 | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply & erection of wagon tippler rail table Drg. No.12578/45-01 , tippler support roller & bogei Drg. No-12616/45-2M | 0 | - | 0 | 0 | 0 | 0 | 1.9 | 1.9 |  |  | 1.9 | 0
9 | Supply of seondary crusher motors 6.6KV, 750KW & 220KW motor for CHP | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
10 | Supply of LT motors for various conveyor belts of CHP | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
11 | Up-gradation of existing DC drive system of Wagon Tippler & Paddle feeder with new version DIGICON make system along with supply, installtion, commissioning & testing of DC drives at CHP-III. | 0 | - | 0 | 0 | 0 | 0 | 0.8 | 0.8 |  |  | 0.8 | 0
12 | Supply of Variable Frequency drives for Conv.16C2 at CHP-III. | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
13 | Up-gradation of existing relay panel of control room with microprocessor based PLC logic system along with supply, installtion, commissioning & testing of relay panel at CHP. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
14 | Supply of Magnetic seperators & Metal detectors at CHP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Repair & renovation of NTPS colony ,Repairing work of ash bund side & Eklahare barrage | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of renovation of various residential quarters by providing and fixing kitchen sink, kitchen trolley & granite otta at NTPS Colony Eklahare. | 0 | - | 0 | 0.9 | 0.9 | 0 | 0.6 | 0.6 |  |  | 0.6 | 0
2 | Providing and applying external painting to various types residential buildings at NTPS colony Eklahare. | 0 | - | 0 | 1.09 | 1.09 | 0 | 0.72 | 0.72 |  |  | 0.72 | 0
3 | Providing and applying internal painting to various types of residential quarters at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.97 | 0.97 |  |  | 0.97 | 0
4 | Providing and fixing vitrified tiles to various types of residnetial buildings at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 3.24 | 3.24 |  |  | 3.24 | 0
5 | Structural strengthening works to various residential quarters at NTPS colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 3.54 | 3.54 |  |  | 3.54 | 0
6 | Providing and fixing colour coated galvanised iron sheets for roofing at various residential buildings at NTPS Colony Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 4.5 | 4.5 |  |  | 4.5 | 0
7 | Sewer line repair of various quarters at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
8 | Stair case repairing of various building at NTPS Eklahare | 0 | - | 0 | 0 | 0 | 0 | 0.15 | 0.15 |  |  | 0.15 | 0
9 | Construction of WBM road over/at the top of ash bund at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.45 | 0.45 |  |  | 0.45 | 0
10 | Repairs to filters of drain well No.4 and other allied works at ash bund valley No.4A at NTPS Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.4 | 0.4 |  |  | 0.4 | 0
11 | Repairs to Godavari river barrage gates and allied works at NTPS, Eklahare. | 0 | - | 0 | 0 | 0 | 0 | 0.4 | 0.4 |  |  | 0.4 | 0
DPR 2 | Structural repairs of Cooling Tower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repairs of cooling tower components at Unit No. 3A, 3B, 4A, 4B,5A & 5B, Stage-II NTPS Eklahare. | 0 | - | 0 | 26.98 | 26.98 | 0 | 11.56 | 11.56 |  |  | 11.56 | 0
DPR 3 | Structural repair & rehabilitation and Renovation and modification work at NTPS Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repair & rehabilitation of various machine foundations of ID, FD & PA fans for Unit No. 3, 4, 5 at Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0.25 | 0.25 | 0 | 0.11 | 0.11 |  |  | 0.11 | 0
2 | Work of removing and providing 24 B.W.G.for pent house side & roof at Unit No. 3,4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 1.74 | 1.74 | 0 | 0.74 | 0.74 |  |  | 0.74 | 0
3 | Work of removing and providing old damaged siporex wall and poly coated sheet for 28 mtr. height at Unit No. 3, 4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 1.26 | 1.26 | 0 | 0.54 | 0.54 |  |  | 0.54 | 0
4 | Structural repairs of chimney at Unit No. 3,4 & 5 Stage-II, NTPS, Eklahare. | 0 | - | 0 | 3.02 | 3.02 | 0 | 1.3 | 1.3 |  |  | 1.3 | 0
5 | Renovation of sump No. 2,3,4,5,6 and 7 at WTP Stage-II, NTPS Eklahare. | 0 | - | 0 | 1.65 | 1.65 | 0 | 0.71 | 0.71 |  |  | 0.71 | 0
6 | Work of structural repairing at CHP-I,II & III area at NTPS, Eklahare. | 0 | - | 0 | 0.76 | 0.76 | 0 | 0.33 | 0.33 |  |  | 0.33 | 0
7 | Work of structural repairing at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 5.67 | 5.67 | 0 | 2.43 | 2.43 |  |  | 2.43 | 0
8 | Work of structural repair of GS pump Unit No. 3,4,& 5 and fire fighting pump house at Stage-II,NTPS, Eklahare. | 0 | - | 0 | 0.58 | 0.58 | 0 | 0.25 | 0.25 |  |  | 0.25 | 0
9 | Work of repairs to doors & windows of various building at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0.24 | 0.24 | 0 | 0.1 | 0.1 |  |  | 0.1 | 0
10 | Providing and fixing powder coated colored Zincalume profiled sheet for various building at CHP,AWR building, Time office & ODP EM at NTPS, Eklahare. | 0 | - | 0 | 2.72 | 2.72 | 0 | 1.17 | 1.17 |  |  | 1.17 | 0
11 | Work of external painting & internal painting at WTP, Stage-II NTPS, Eklahare. | 0 | - | 0 | 0.93 | 0.93 | 0 | 0.4 | 0.4 |  |  | 0.4 | 0
12 | Work of external painting & internal painting at CHP area NTPS, Eklahare. | 0 | - | 0 | 0.47 | 0.47 | 0 | 0.2 | 0.2 |  |  | 0.2 | 0
13 | Renovation and restructuring of shed No. 1, 2, 5, 6, 9 & 11 of major store custody of NTPS, Eklahare. | 0 | - | 0 | 2.37 | 2.37 | 0 | 1.02 | 1.02 |  |  | 1.02 | 0
DPR 4 | As per I.B.Recommondation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of construction compound wall with concertina coil at various locations at Nashik TPS. | 0 | - | 0 | 41.21 | 41.21 | 0 | 17.66 | 17.66 |  |  | 17.66 | 0
2 | Providing & renovating security watch tower at NTPS Premises Eklahare. | 0 | - | 0 | 0.43 | 0.43 | 0 | 0.18 | 0.18 |  |  | 0.18 | 0
0 | HO Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | R&M/LE for Identified Thermal units of MSPGCL of (3 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL (3 x 210 MW) units of MSPGCL | 0 | - | 0 | 384.04 | 384.04 | 0 | 796.1 | 796.1 |  |  | 796.1 | 0
DPR 2 | CHP Improvcement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 30 | 30 |  |  | 30 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | TATA Mini Truck SFC 709 EX No.MH-15-JV-3992 | N.A. | - | 0 | 0.32099 | 0.32099 | 0 | 0 | 0 |  |  | 0 | 0
2 | Executive chair(10),S Type Arm chai(20) | N.A. | - | 0 | 0.10784 | 0.10784 | 0 | 0 | 0 |  |  | 0 | 0
3 | Office Table and S-Type Chair with Arm | N.A. | - | 0 | 0.030968 | 0.030968 | 0 | 0 | 0 |  |  | 0 | 0
4 | Windows Slot in PC VPC 10-Intel Core 13 4th -NTC | N.A. | - | 0 | 0.010561 | 0.010561 | 0 | 0 | 0 |  |  | 0 | 0
5 | LG Screen wall mounted computer-LED display65"-NTC | N.A. | - | 0 | 5.0969 | 5.0969 | 0 | 0 | 0 |  |  | 0 | 0
6 | 20 Ton Split AC for Audtiorium -NTC | N.A. | - | 0 | 1.0873 | 1.0873 | 0 | 0 | 0 |  |  | 0 | 0
7 | Colour Laser Printer, All in one A3 LaserJet Print | N.A. | - | 0 | 1.0589 | 1.0589 | 0 | 0 | 0 |  |  | 0 | 0
8 | Digital DSLR Camera | N.A. | - | 0 | 1.0793 | 1.0793 | 0 | 0 | 0 |  |  | 0 | 0
9 | Indoor Gymnasium Equipments at NTC, Eklahare | N.A. | - | 0 | 0.02853 | 0.02853 | 0 | 0 | 0 |  |  | 0 | 0
10 | CLASS ROOM CHAIR WITH DESKLET | N.A. | - | 0 | 0.023576 | 0.023576 | 0 | 0 | 0 |  |  | 0 | 0
11 | PA System and Sport Material,Table Tannis for | N.A. | - | 0 | 0.01687 | 0.01687 | 0 | 0 | 0 |  |  | 0 | 0
12 | EXECUTIVE CHAIR WITH 5 SUPRT & S-TYPE CHAIR | N.A. | - | 0 | 0.01003 | 0.01003 | 0 | 0 | 0 |  |  | 0 | 0
13 | APPLN COOLER AIR SEMIEXH AIR COOLER ASSY | N.A. | - | 0 | 0.033896 | 0.033896 | 0 | 0 | 0 |  |  | 0 | 0
14 | FULL PAD CHAIRS WITH SIDE ARM | N.A. | - | 0 | 0.029637 | 0.029637 | 0 | 0 | 0 |  |  | 0 | 0
15 | Industrial Cabinet with 12 Lockers | N.A. | - | 0 | 0.0070163 | 0.0070163 | 0 | 0 | 0 |  |  | 0 | 0
16 | UV Water Purifier Filter | N.A. | - | 0 | 0.019116 | 0.019116 | 0 | 0 | 0 |  |  | 0 | 0
17 | FILTER RO+UV+UF+TDS WATER PURIFIER | N.A. | - | 0 | 0.032906 | 0.032906 | 0 | 0 | 0 |  |  | 0 | 0
18 | 2 Tone SPLIT AC INDOOR UNIT | N.A. | - | 0 | 0.008064 | 0.008064 | 0 | 0 | 0 |  |  | 0 | 0
19 | 1.5 TON CAPACITY SPLIT AC | N.A. | - | 0 | 0.006688 | 0.006688 | 0 | 0 | 0 |  |  | 0 | 0
20 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 1.698 | 1.698 | 0 | 0 | 0 |  |  | 0 | 0
21 | Logitech PTZ Group Camera 960-001054 | N.A. | - | 0 | 2.4375 | 2.4375 | 0 | 0 | 0 |  |  | 0 | 0
22 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011564 | 0.011564 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK BENCH WITHOUT DRAWER | 0 | - | 0 | 0.011647 | 0.011647 | 0 | 0 | 0 |  |  | 0 | 0
24 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.030075 | 0.030075 | 0 | 0 | 0 |  |  | 0 | 0
25 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011788 | 0.011788 | 0 | 0 | 0 |  |  | 0 | 0
26 | EXECUTIVE CHAIR, S-TYPE CH-7 CHAIR WITH ARM | 0 | - | 0 | 0.035229 | 0.035229 | 0 | 0 | 0 |  |  | 0 | 0
27 | SAMSUNG GALAXY TAB S3, 32GB 9.7 INCH | 0 | - | 0 | 0.003845 | 0.003845 | 0 | 0 | 0 |  |  | 0 | 0
28 | i5 Laptop - 2 Nos & i7 Laptop - 3 Nos | 0 | - | 0 | 0.037636 | 0.037636 | 0 | 0 | 0 |  |  | 0 | 0
29 | Godrej make 1.5 Ton High Wall Split AC | 0 | - | 0 | 0.020975 | 0.020975 | 0 | 0 | 0 |  |  | 0 | 0
30 | Complete Multimedia Projector with Std Accessories | 0 | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
31 | LED 40 INCH SMART TV | 0 | - | 0 | 0.0092016 | 0.0092016 | 0 | 0 | 0 |  |  | 0 | 0
32 | FULL PAD CHAIRS, EXECUTIVE CHAIR, | 0 | - | 0 | 0.068995 | 0.068995 | 0 | 0 | 0 |  |  | 0 | 0
33 | Cash Counting Machine | 0 | - | 0 | 0.001888 | 0.001888 | 0 | 0 | 0 |  |  | 0 | 0
34 | 230 V AC DIGITAL SINE WAVE INVERTER 1 No. | 0 | - | 0 | 0.010175 | 0.010175 | 0 | 0 | 0 |  |  | 0 | 0
35 | HPCV no.3 &4 Stem | 0 | - | 0 | 0.025694 | 0.025694 | 0 | 0 | 0 |  |  | 0 | 0
36 | HEAVY DUTY AIR PURIFIURE 230V,50HZ | 0 | - | 0 | 0.0105 | 0.0105 | 0 | 0 | 0 |  |  | 0 | 0
37 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.0048144 | 0.0048144 | 0 | 0 | 0 |  |  | 0 | 0
38 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.025939 | 0.025939 | 0 | 0 | 0 |  |  | 0 | 0
39 | APPLN COOLER WTR CAP CAP: 60 LITERS | 0 | - | 0 | 0.0053799 | 0.0053799 | 0 | 0 | 0 |  |  | 0 | 0
40 | LASER LASERJET PRINTER FOR A4 PAPER | 0 | - | 0 | 0.0057 | 0.0057 | 0 | 0 | 0 |  |  | 0 | 0
41 | 40 Inch Smart LED TV 3.00 | 0 | - | 0 | 0.010178 | 0.010178 | 0 | 0 | 0 |  |  | 0 | 0
42 | DESKTOP INTEL CORE I5 2300 PROCESSOR | 0 | - | 0 | 0.021459 | 0.021459 | 0 | 0 | 0 |  |  | 0 | 0
43 | ONLINE WATER HEATER, 3KW,3LTR. | 0 | - | 0 | 0.029683 | 0.029683 | 0 | 0 | 0 |  |  | 0 | 0
44 | CAMERA FOR VC, MICROPHONE WITH SPEAKER | 0 | - | 0 | 0.023889 | 0.023889 | 0 | 0 | 0 |  |  | 0 | 0
45 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
46 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 0.01873 | 0.01873 | 0 | 0 | 0 |  |  | 0 | 0
47 | Water Cooler | 0 | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
48 | PORTABLE HARD DISK USB 1TB | 0 | - | 0 | 0.0017388 | 0.0017388 | 0 | 0 | 0 |  |  | 0 | 0
49 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.00095 | 0.00095 | 0 | 0 | 0 |  |  | 0 | 0
50 | Garbox assembly for premium make type B-220 of | 0 | - | 0 | 0.44095 | 0.44095 | 0 | 0 | 0 |  |  | 0 | 0
51 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.006726 | 0.006726 | 0 | 0 | 0 |  |  | 0 | 0
52 | RO+UV+UF+TDS CAP 50 LITRE PER HOUR | 0 | - | 0 | 0.002731 | 0.002731 | 0 | 0 | 0 |  |  | 0 | 0
53 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.0025995 | 0.0025995 | 0 | 0 | 0 |  |  | 0 | 0
54 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.002183 | 0.002183 | 0 | 0 | 0 |  |  | 0 | 0
55 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0061808 | 0.0061808 | 0 | 0 | 0 |  |  | 0 | 0
56 | REGULAR CHAIR WITHOUT CUSHION | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
57 | BLDC Fans through GeM Portal and GA -2022-23 at | 0 | - | 0 | 0.0049556 | 0.0049556 | 0 | 0 | 0 |  |  | 0 | 0
58 | ALL IN ONE PC, CORE I5, 4 GB RAM, 500 GB | 0 | - | 0 | 0.02973 | 0.02973 | 0 | 0 | 0 |  |  | 0 | 0
59 | PRINTER LASER LASERJET NETWORK PRINTER | 0 | - | 0 | 0.0020024 | 0.0020024 | 0 | 0 | 0 |  |  | 0 | 0
60 | APPLN FAN AIR CEIL SIZE 1200 MM SWEEP | 0 | - | 0 | 0.033918 | 0.033918 | 0 | 0 | 0 |  |  | 0 | 0
61 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.014828 | 0.014828 | 0 | 0 | 0 |  |  | 0 | 0
62 | 400 MM, 230V, 3 BLADE DOMESTIC FAN | 0 | - | 0 | 0.0024532 | 0.0024532 | 0 | 0 | 0 |  |  | 0 | 0
63 | APPLN FAN AIR EXHAUST SIZE15"1400RPM-15 Nos | 0 | - | 0 | 0.01781 | 0.01781 | 0 | 0 | 0 |  |  | 0 | 0
64 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.013559 | 0.013559 | 0 | 0 | 0 |  |  | 0 | 0
65 | MICROWAVE OVEN CAPACITY 27 / 28 LITERS-1 Nos | 0 | - | 0 | 0.0048362 | 0.0048362 | 0 | 0 | 0 |  |  | 0 | 0
66 | REFRIGERATOR SINGLE DOOR CAPCITY 190 LTR | 0 | - | 0 | 0.0067225 | 0.0067225 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Thinclients on Buyback for NTPS | 0 | - | 0 | 0.23166 | 0.23166 | 0 | 0 | 0 |  |  | 0 | 0
68 | ABC Powder type DCP Composite Fire Extinguisher | 0 | - | 0 | 0.357 | 0.357 | 0 | 0 | 0 |  |  | 0 | 0
69 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024631 | 0.024631 | 0 | 0 | 0 |  |  | 0 | 0
70 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024213 | 0.024213 | 0 | 0 | 0 |  |  | 0 | 0
71 | Furniture Dining Table for Main Mess Hall and Cus | 0 | - | 0 | 0.019803 | 0.019803 | 0 | 0 | 0 |  |  | 0 | 0
72 | Servers for DSM at Nashik Thermal Power Station | 0 | - | 0 | 0.43559 | 0.43559 | 0 | 0 | 0 |  |  | 0 | 0
73 | DESKTOP INTEL CORE I5 2300 PROCESSOR - 5 Nos | 0 | - | 0 | 0.05632 | 0.05632 | 0 | 0 | 0 |  |  | 0 | 0
74 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.041064 | 0.041064 | 0 | 0 | 0 |  |  | 0 | 0
75 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.038246 | 0.038246 | 0 | 0 | 0 |  |  | 0 | 0
76 | APPLN TV STD ULSLIM 42" - 4 Nos | 0 | - | 0 | 0.037376 | 0.037376 | 0 | 0 | 0 |  |  | 0 | 0
77 | 1 T SPLIT AC COMPL UNIT WITH ACCESSORIES | 0 | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
78 | MULTIMEDIA PROJECTOR EPSON EB-U05-1 No | 0 | - | 0 | 0.0081606 | 0.0081606 | 0 | 0 | 0 |  |  | 0 | 0
79 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.0023246 | 0.0023246 | 0 | 0 | 0 |  |  | 0 | 0
80 | Procurement of Complete Vibrating Screen Assembly at CHP-II | 0 | - | 0 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Asset | 0 | - | 0 | 0.575 | 0.575 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 1003.7184 | 1025.4259 | -21.7075 | 1040.6982 | 1040.6982 | 0 | 0 | 1040.6982 | -21.7075
FY 2027-28
a) DPR Schemes
(i) Submitted to MERC
1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Measuring & Monitoring of Coal consumption | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 23.0165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Belt Weighers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3295 | 0.3295 | 0.3295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.793 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of inhaul outhaul betel chargers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 6 | 8.5943 | 8.5943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Dust Extraction System | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 1.65 | 1.713 | 1.713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Fogging system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 2.44 | 2.59 | 2.59 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Bunker level montoring system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.54 | 0.0694 | 0.0694 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.169 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Operating the CHP near to its full capacity | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 7.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Motor controller | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3732 | 0.3732 | 0.3732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 3.4218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Combustion optimization & Process improvement | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 58.7761 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Improvement in tooling techniques Power tools like cut off machines and surface grinders. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.52821 | 0.3388 | 0.3388 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Total replacement of boiler related skin insulation as well as skin cladding of furnace, Air pre heaters,air ducts and flue gas ducts Unit-4 &5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4.5892 | 4.7188 | 4.7188 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Painting of Boiler ,bunker structure and other structure.Unit-3,4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 7.775 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 8.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Retrofitting of Gas proportioning dampers, flue gas, primary and secondary air dampers. (SADC) for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.456 | 1.2566 | 1.2566 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.41356 | 0.41356 | 0 | 0 | 0 |  |  | 0 | 0
4.6 | Replacement of flue gas ducting zone prone to erosion with 6 to 8 mm high grade material & insulation of flue gas ducts. (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 4 and 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Replacement of boiler outlet valves and damaged valves of units 4 & 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.349 | 1.4313 | 1.4313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Replacement of coal pipe at direction changing sections & flow curvature zone by upgraded material. Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.3292 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.9 | Installation of Smart soot blower system for Unit- 4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 5.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.10 | Installation of Sonic soot blowers for second pass for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.83184 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.11 | Air pre heater upgradation of heat exchanger matrix &regenerative dynamic sealing for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.12 | Replacement Platen water wall for Unit-3. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.60762 | 0.6964 | 0.6964 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 13.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Turbine Auxiliary Consumption Improvement | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 39.2903 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Installation of Turbo vaned fly wheeling eco ventilators to all Units 3, 4, 5. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Replacement of selected old brass impellers of pumps with SS304 impellers. H.T. Auxiliary C.W. Pump and G.S. Water Pumps are selected. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.4 | 0.8251 | 0.8251 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Improving the BFP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.75 | 0.48804 | 0.48804 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Replacement of BFP (200 KHI) cartridge with energy efficient cartridge. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 14.4456 | 13.85 | 13.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Improving the CEP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.9 | 0.6018 | 0.6018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Replacement of CEP with energy efficient pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Replacement of Pumps - GS Pumps, H2Cooler booster pump, DM/DM pumps, DM Makeup pumps, Emergency lift pumps, Drip pumps, BFP Booster pumps with energy efficient pumps. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 4.2733 | 2.3608 | 2.3608 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.8 | Replacement of valves – MS - 3 to 8 , HD – 22,23,24 , MC- 36 , ES 3,4 and BFP Recirculation Valves. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.0852 | 1.3148 | 1.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.9 | Replacement of tube nest of LP Heater no.3 of unit no.3, LP Heater no.4 of unit no.5, Main ejector 3B, GC2 of unit no.5, Seal oil coolers, H2 Coolers, BFP working and lub oil coolers, DM/GS plate type coolers. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 6.5962 | 1.9594 | 1.9594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.11461 | 0.11461 | 0 | 0 | 0 |  |  | 0 | 0
5.10 | Steam path audit of Unit no,4,5 | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | EMS, Numeric relays, Microprocessor DVR & VFD | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 12.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Design, manufacture, supply, erection, commissioning & testing of Variable Frequency Drives (VFD) with latest design and technology super premium efficiency motors for 415 V LT Auxiliaries (Total 50 No) of 210 MW Unit 3, 4 & 5. | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 6.3 | 8.8183 | 6.2927 | 2.5255 | 0 | 0 |  |  | 0 | 2.5255 | 0 | 0
0 | IDC | 0 | - | 0.66 | 0.74645 | 0.74645 | 0 | 0 | 0 |  |  | 0 | 0
6.2 | Replacement of old EE make Generator Protection Relays with Numerical Generator Protection Relays for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 1.7 | 1.7029 | 1.7029 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Replacement of old AVR with Microprocessor based Digital Voltage Regulator for unit no. 3 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 2.44 | 1.7055 | 1.7055 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Installation and commissioning of Energy Management System for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.81 | 0.8313 | 0.8313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 14.5069 | 14.5069 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 57.9147 | 57.9147 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Faster unloading of coal wagons by upgrading existing system (Post Facto) | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 18.8481 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Re-design, Supply, Erection and commissioning of modified Apron Feeder. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.7219 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Design, manufacture, supply, erection and commissioning of modified bunker outlet cone of Unit 3, 4 and 5. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.3295 | 2.3196 | 2.3196 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Design, manufacture, Supply & Erection Of Components Suitable For Modification Of Wagon Tipplers to Handle BOXNHL , BOX-H,BOX-NR,BOX-NJLSR1 & 25 T AXLE WAGONS | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.1298 | 4.413 | 4.413 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Procurement of SAN Loco - 650-700 HP. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8627 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.5 | Revamping of CHP II Wagon Tippler by replacing the Split Wheel Assembly, Pawl Lever, Pinion Shaft Assembly, Toe, Spur Gear Shaft, W.T Drive Assembly, Rack Segment, Rail Table Assembly Of Wagon Tippler and Dismantling & Replacement of above parts | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8042 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement of 6.6 Kv HT motors as spare motors /for replacement | MERC/CAPEX/20152016/00422 | 2016-08-03 | 14.3563 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3125 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1025 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | FD FAN MOTOR 650 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | FD FAN MOTOR 750 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8505 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | PA FAN MOTOR 1250 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.029 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | BFP MOTOR 4000 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 4.5528 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | C/MILL MOTOR 320 kW (3 Nos) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3356 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.8 | SOP MOTOR 200 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.9 | CWP MOTOR 950 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8942 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.10 | CTLP MOTOR 710 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8081 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.11 | RWP MOTOR 335 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.4861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.12 | HP PUMP MOTOR 258 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3083 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.13 | CEP MOTOR 220 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2629 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.14 | GS PUMP MOTOR 260 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3107 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.15 | Testing charges | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.088 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Replacement of complete LTSH coils at Unit-3 Boiler & Economiser coils at Unit-5 Boiler | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 27.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Complete Supply & Erection of LTSH coils at Unit-3 210 MW Boiler (67 nos. upper and lower modules each. 01 module = 02 coils) | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 16.43 | 4.6378 | 4.6378 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Complete Supply & Erection of 270 nos. Economizer coils in second pass of Unit-5 210 MW Boiler at Nasik TPS. | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 9.57 | 3.0104 | 3.0104 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 1.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Enhancement of performance & life of Coal Handling plant | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 17.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Procurement of 02 nos of 320 hp bull dozers for Nasik TPS | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 3.2 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Procurement of gear box for Apron Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 1.59 | 1.6043 | 1.6043 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Procurement of gear box and 30 KW DC motor for Pedal Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.46 | 0.45847 | 0.45847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.4 | Procurement of Assembly of Impact Crusher Complete set, with Rotor Assembly and bearing Block. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 2.3 | 2.3366 | 2.3366 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.5 | Procurement of 10 KW Inline Magnetic Separator for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.4 | 0.54718 | 0.54718 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.6 | Restoration of RBCR by replacing feed end Spider (Drg. No. 400-1428-01/A) & Discharge end Spider (400-1428-02) suitable to rotary Bradford breaker machine No.CR/634 along with support wheels. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 8.14 | 10.2287 | 10.2287 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.7 | Procurement of 750 KW Impactor Motor for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.49 | 0.22635 | 0.22635 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.8 | Supply of Metal Detectors for CHP | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.14 | 0.09152 | 0.09152 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Retrofitting of 6.6 kV Breakers, Battery Replacement, System Improvement & MPCB Related schemes | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 14.7811 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Retrofitting of 6.6 kV HT MOCB/SF6 Breakers by VCB | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 3.57 | 5.0621 | 5.0621 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2a | A) Procurement & Replacement of 220V/ 1285 AH Battery set for U#3 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0493 | 1.0493 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2b | B) Procurement & Replacement of 220V/ 1285 AH Battery set for U#4 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0047 | 1.0047 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | O2 Measurement System in the furnace & flue gas ducting | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.17 | 1.2966 | 1.2966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Supply, erection, commissioning & testing of online CO, SO2, NOX Analyser for U#3/4/5 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.6511 | 1.6846 | 1.6846 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | A) Replacement of static Flame Monitoring System with Microprocessor based Flame Monitoring & Analyzing System | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.27 | 2.4267 | 2.4267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | CAAQMS monitoring of ambient air quality around the NTPS. | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1 | 0.81676 | 0.81676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | 3rd raising of Ash bund | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | 3rd raising of ash bund from TBL 581.50 to 586.50m in valley No. 4A at Nashik Thermal Power Station, Eklahare | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 12.3 | 10.2142 | 10.2142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | System Rehabilitation & Upgradation at Nasik TPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 13.3722 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Shifting, Transportation & Replacement of Existing Generator Stator of Unit no.3 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 7.98 | 0.8767 | 5.8767 | -5 | 0 | 0 |  |  | 0 | -5 | 0 | 0
0 | IDC | 0 | - | 0 | 0.26397 | 0.26397 | 0 | 0 | 0 |  |  | 0 | 0
15.2 | Turbine Supervisory Instrumentation System for Unit no.5 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.5542 | 0.45436 | 0.45436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Supply of Air Compressors for NTPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 3.398 | 3.8197 | 3.8197 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Replacement of Old Brass Impellers of CTLP with SS Impellers. | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 1.04 | 1.1331 | 1.1331 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up-gradation of DCS at U # 3 and New Rectiformers & ESP Refurbishment of U # 4 & 5 at Nasik TPS | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 33.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Decommissioning & Shifting of M/s ABB make DCS system at BTPS Unit # 2 & Re-commissioning with Up gradation to Symphony Plus at NTPS Unit #3, Nasik. | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 9.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Erection ,Testing & commissioning, Supply of rectiformer HVR 37/800 Hermatically sealed Rectiformer ( DC Peak voltage – 70 kV , Average voltage-45 KV ,DC Current – 800 milli amp , AC I/P – 1 Phase , 415 V ) | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 10.34 | 0 | 13 | -13 | 0 | 0 |  |  | 0 | -13 | 0 | 0
16.3 | Refurbishment of ESP for Unit No. 4 & 5 at Nashik TPS, Eklahare | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 12.5 | 12.8553 | 12.8553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 1.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Replacement of drum gate, augmentation of existing ash water recovery scheme and construction of concrete road for Nasik Thermal Power Station | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 14.5161 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Replacement of drum gate and restructuring of cofferdam, repairs to vertical sluice gate, Approach Bridge and allied civil works at Godavari barrage at Nashik TPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 6.273 | 3 | 6.27 | -3.27 | 0 | 0 |  |  | 0 | -3.27 | 0 | 0
17.2 | Augmentation of existing ash water recovery scheme and connecting overflow of waste weir to existing toe drain of ash bund valley no.4 to WWR at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 2.5999 | 3.1676 | 3.1676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2441 | 0.2441 | 0 | 0 | 0 |  |  | 0 | 0
17.3 | Up gradation of fly ash concrete road from Booster Pump house toward Hydrogen plant, Dirk India Company towards Hinganwedhe along ash bund valley No. 1 & 2, Ash bund approach road for ash transportation and abundant valley towards Kotamgaon road at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 5.3732 | 5.3752 | 5.3752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 0.27 | 0.38455 | 0.38455 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Various DPR Schemes for Renovation of colony at NTPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 10.8678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Renovation of staff quarters, playground, Jogging track & Gymnasium at NTPS colony, Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 4.071 | 3.5306 | 3.5306 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.92832 | 0.92832 | 0 | 0 | 0 |  |  | 0 | 0
18.2 | Road works in NTPS Colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 3.9766 | 3.8972 | 3.8972 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Water supply and sanitation works at NTPS colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 2.8202 | 1.4586 | 1.4586 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.19994 | 0.19994 | 0 | 0 | 0 |  |  | 0 | 0
18.4 | Renovation of Workers Recreation Club at Nashik TPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Life enhancement of stacker cum reclaimer machine in CHP & upgradation of SWAS laboratory at Nasik TPS | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 14.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Supply, Erection & installation of sole plates, Rail track & Hydraulic cylinder of the Stacker cum Reclaimer machine at Coal Handling Plant-II Nashik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 6.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement and replacement of 220 V, 1285 AH battery set for Unit No. 4 at Nasik Thermal Power Station. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 1.39 | 1.4116 | 1.4116 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2227 | 0.2227 | 0 | 0 | 0 |  |  | 0 | 0
19.3 | Supply of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers Ltd.) at Nasik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 3.11 | 3.0812 | 3.0812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Erection and commissioning of Steam and Water sampling system for SWAS Lab at WTP, NTPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 2.23 | 0 | 3 | -3 | 0 | 0 |  |  | 0 | -3 | 0 | 0
19.5 | Procurement of 3 nos. of Ash Slurry Disposal pump Type D - 85 for Ash Slurry Pump House of Unit no. 3, 4 & 5 at NTPSEklahare. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.55 | 0.55578 | 0.51878 | 0.037 | 0 | 0 |  |  | 0 | 0.037 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Flue Gas Desulphurization (FGD) System at Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Ash Augmentation System at Nasik & Koradi Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Ash Augmentation System at Nasik Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 5.71 | 5.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3.1 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 8.47 | 8.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | NASIK TPS (U-3 to 5) (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 2.8842 | 2.8842 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.76776 | 0.76776 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Nashik TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.2272 | 2.2272 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | TPS Nashik | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 2.3118 | 2.3118 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.1 | Procurement and Replacement of Complete sets of assembly of baskets for air preheater of type tri-sector APH 27 VI(T) 74” in NTPS unit no. 4 & 5 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 5.5929 | 5.5929 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.13531 | 0.13531 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | <DPR Name> | N.A. | N.A. | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Complete Replacement of HRH Coils, LTSH Coils, Economizer Coils at Unit No. 4 & Complete Replacement of Economizer coils at Unit No.3 Nashik TPS 210 MW Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Replacement HRH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 8.551 | 8.551 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete Replacement LTSH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 12.6608 | 12.6608 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete Replacement Economiser Coils at NTPS Unit No. 3 & 4 Boilers | 0 | - | 0 | 14.8636 | 14.8636 | 0 | 1.2036 | 1.2036 |  |  | 1.2036 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 and Commissioning of AFGC system for Unit No. 3, 4 & 5 and Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5 at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of MSERW pipes for Replacement of various pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 at NTPS, Eklahare | 0 | - | 0 | 19.6769 | 19.6769 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, erection, commissioning & testing of Ammonia Flue gas Conditioning system for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 3.9046 | 3.9046 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5, 210 MW, NTPS, Eklahare, Nasik. | 0 | - | 0 | 2.9741 | 2.9741 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Complete replacement of Platen Superheater coils at Unit No.3,4 & 5 ; Complete replacement of HRH coils at Unit No.3,& 5; Complete replacement of LTSH coils at Unit No. 5;Replacement of thermal insulation at Boiler for Nashik TPS 210 MW boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete replacement of Platen Superheater coils at Unit No. 3,4 & 5 | 0 | - | 0 | 15.21 | 15.21 | 0 | 1.39 | 1.39 |  |  | 1.39 | 0
2 | Complete replacement of HRH coils at Unit No.3,& 5 | 0 | - | 0 | 15.391 | 15.391 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete replacement of LTSH coils at Unit No.5 | 0 | - | 0 | 10.7498 | 10.7498 | 0 | 0 | 0 |  |  | 0 | 0
4 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines at Unit No.3,4 & 5 | 0 | - | 0 | 4.257 | 4.257 | 0 | 2.64 | 2.64 |  |  | 2.64 | 0
DPR 4 | Procurement of various pumps for TM & ODP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement and Erection Commissioning of Condenser vacuum pump for Unit No. 3 ,4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 29.24 | 29.24 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Three Pump assemblies of SAM TURBO makes Type 150/500 N for Booster Pump house at NTPS Eklahare. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 3 Nos Vertical Fly Ash Transfer Pump VO 150 /400 + ARS SAM make along with motor for ESP Hopper evacuation of Unit No.3,4 & 5 at NTPS Eklahare | 0 | - | 0 | 0.79 | 0.79 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection, installation, civil foundation, commissioning, testing & trial of Rotating &casing assembly of pumps for WTP at Nashik TPS, Eklahare | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement (10 nos.) of CWFW pumps (with motor) at Stage-II (Beacon make) | 0 | - | 0 | 0.94 | 0.94 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of RWP Pump assembly at NTPS. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Cooling Tower lift Pump Impeller for Jyoti make pump Type:-1200- VMI A 12 at NTPS Eklahare | 0 | - | 0 | 1.07 | 1.07 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Degasser Pump assembly with motor (06 Nos.) | 0 | - | 0 | 0.354 | 0.354 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 8 Nos. of Domestic water pumps (with motor) & Darna drinking water pump at Stage-I & II | 0 | - | 0 | 0 | 0 | 0 | 0.6 | 0.6 |  |  | 0.6 | 0
10 | Procurement of 4 Nos. of DM backwash (2 Nos.) & CW backwash pump (2 Nos.)(with motor)at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 0.36 | 0.36 |  |  | 0.36 | 0
11 | Procurement of 4 Nos. of HP Pumps at NTPS. | 0 | - | 0 | 0 | 0 | 0 | 1.18 | 1.18 |  |  | 1.18 | 0
12 | Procurement of ETP pump assembly (06 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 1.42 | 1.42 |  |  | 1.42 | 0
13 | Procurement of RWP shaft with bearing, Impeller (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 1.68 | 1.68 |  |  | 1.68 | 0
14 | Procurement of AWR pump (02 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0.47 | 0.47 |  |  | 0.47 | 0
15 | Procurement of Submersible Slurry Pumps for handling Ash water / Clear water for dewatering at various locations at NTPS (10 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0.885 | 0.885 |  |  | 0.885 | 0
DPR 5 | Renovation of Compressed Air Refrigerated Dryer System, Refurbishment of Centralized Air Conditioning system, Supply, erection & commissioning of Condensate Extraction Pump, Procurement of CW Pump and GS pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Compressed Air Refrigerated Dryer System for Nashik TPS, 210 MW Unit No. 3, 4 & 5 | 0 | - | 0 | 11.3737 | 11.3737 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of Centralized Air Conditioning system of Unit No. 3, 4 & 5 at Nashik TPS, Eklahare. | 0 | - | 0 | 8.15 | 8.15 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers ltd. at Nasik TPS. Total Qty. 02 Nos. | 0 | - | 0 | 3.93 | 3.93 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of CW & CTLP Pump total 4 No.s | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of GS Pump assembly .Total qty- 3 No | 0 | - | 0 | 0 | 0 | 0 | 1.373 | 1.373 |  |  | 1.373 | 0
DPR 6 | Procurement of oil free Rotary Screw Compressors and BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of BFP cartridge | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of oil free rotary screw compressors | 0 | - | 0 | 21.6648 | 21.6648 | 0 | 0 | 0 |  |  | 0 | 0
DPR 7 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets, Refurbishment of HPT rotor along with supply, Procurement of HP & IP control valve with cam shaft assemblies, Procurement of complete governing system assembly, Supply, Errection & Commissioning of COP assembly, Procurement of Condenser tubes & ODP related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets at 3 x 210 MW, TM-II NTPS. | 0 | - | 0 | 0.63 | 0.63 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of HPT rotor along with supply. | 0 | - | 0 | 3.7908 | 3.7908 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of HP & IP control valve with cam shaft assemblies.qty-1set | 0 | - | 0 | 0 | 0 | 0 | 0.81 | 0.81 |  |  | 0.81 | 0
4 | Procurement of complete governing system assembly. qty-1 set | 0 | - | 0 | 0 | 0 | 0 | 0.27563 | 0.27563 |  |  | 0.27563 | 0
5 | Supply, Errection & Commissioning of COP assembly.Total Qty.- 3 Nos. | 0 | - | 0 | 0 | 0 | 0 | 0.9642 | 0.9642 |  |  | 0.9642 | 0
6 | Procurement of Condenser tubes for Unit No.3, 4 & 5.Total Qty:15700 tubes | 0 | - | 0 | 0 | 0 | 0 | 20.27 | 20.27 |  |  | 20.27 | 0
7 | Procurement of CT Fan Blade assembly & shaft- 36 nos for Unit No.3,4 & 5 at NTPS, Eklahare | 0 | - | 0 | 1.3 | 1.3 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Gearbox Assembly for Cooling Tower Fans type B-220 Premium make for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare (Qty-24) | 0 | - | 0 | 3 | 3 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
9 | Procurement of 5 nos. of Air Blowers for Degasser system | 0 | - | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Flocculator gearbox- 12 Nos. | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of Clinker grinder assembly at NTPS Eklahare | 0 | - | 0 | 0.65 | 0.65 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of 4 Nos. of Clinker grinder gearbox at NTPS Eklahare | 0 | - | 0 | 0.2 | 0.2 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of 5 Nos. of Air Blowers for Degasser system | 0 | - | 0 | 0 | 0 | 0 | 0.25 | 0.25 |  |  | 0.25 | 0
14 | Augmentattion of existing Ash Water recovery Scheme(WWR,AWR, ETP-I,ETP-II & Phase-II pump assembly) | 0 | - | 0 | 0 | 0 | 0 | 2.97 | 2.97 |  |  | 2.97 | 0
15 | Procurement of Feed Gate Housing (08 Nos.) | 0 | - | 0 | 0 | 0 | 0 | 0.57 | 0.57 |  |  | 0.57 | 0
DPR 8 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area & Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 5 | 0
DPR 9 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS , Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of LT energy efficient motor | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
DPR 10 | Upgradation of various electrical related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of 6.6KV HT motors and spares at Nashik TPS Unit No 3,4 & 5. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Boiler and turbine house lighting of Unit No.3,4 & 5 along with removal of old wiring. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacemet of IPH transformer 11KV/6.6 KV and lighting and welding transformer at NTPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
4 | Excitation Transformer at Unit No. 3, 4 & 5 | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
5 | GTR /UAT/ station transformer spares LV bushings replacement, HV bushings (spare)-3nos, LV busbar, palm joint both station transformers bushings at Unit No.3, 4 & 5 | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of overhead conductor HT/LT by underground HT/LT cable in Colony area. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
7 | LT transformer procurement/ rewinding work at NTPS | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
8 | LT MCC panel modification at ODP area NTPS | 0 | - | 0 | 0 | 0 | 0 | 10 | 10 |  |  | 10 | 0
9 | Battery Charger-220V,50V,380V UPS, 24V,DG set EMF panel with charger replacement, UPS battery replacement, Unit No. 5 station battery replacement,50 V battery set replacement at Unit No.3, 4 & 5 | 0 | - | 0 | 2.5 | 2.5 | 0 | 2 | 2 |  |  | 2 | 0
10 | Replacement of HT motor Cables. (Old PILC Cable replacement with XLPE Cable) at Unit No.3, 4 & 5 & ODP area | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
11 | Unit No. 4 Field Breaker | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
DPR 11 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
DPR 12 | Replacement/Upgradation of C&I old systems at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement/Upgradation of Unit No.4 DVR System. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement/Upgradation of Unit No.4 UPS System. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotory Electronic Control Drive for Burner Tilt and Auxiliary Air Damper at Unit No. 3, 4 & 5 210 MW, NTPS, Eklahare Nashik. | 0 | - | 0 | 7.93 | 7.93 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification/Upgradation of Turbovisory system of Unit No. 3,4 & 5. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
5 | Auxiliary air dampers & BT, HAD, feed gate replacement/modification work. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Unit No.4 DCS-FCS 102 to FCS 106 (Total 5 Nos.) | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
7 | New sewage treatment plant required at NTPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
8 | Upgradation of Unit No.4 230 V UPS and new UPS, charger for Unit No. 3 & 5 DCS at NTPS. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
9 | ESP hopper high & low level indicator mounting in Unit No.3,4& 5. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
10 | OCEMS for Sox, Nox, opacity monitoring system upgradation work for Unit No.3, 4 & 5 at NTPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
11 | Supply, Erection, Commissioning & Testing of online H2 purity meter and Resistivity meter for Unit No. 5. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, Erection, commissioning of Hydra step system for Drum level control Unit No.3. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
13 | HPLP - Servo Spares | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
14 | Replacement of Relays and Energy meter at NTPS, Nashik. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
15 | ESP upgradation for Unit No. 3, 4 & 5. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
16 | Grounding Brush Monitoring System for Unit No. 3,4& 5. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
17 | Implementationof FGMO | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
DPR 13 | Modification & replacement of various CHP schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Modification of single stream conveyor belt Gearboxes with new design Helical Bevel type Gearboxes at CHP-II NTPS | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
2 | Modification of Primary Vibrating screen at CHP-II, NTPS | 0 | - | 0 | 0.7 | 0.7 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Rail table alongwith weighment frame for rotaside Wagon Tippler at CHP-II, NTPS | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification of Conveyor Drive system with Motorised Pulley drive system at CHP-II, NTPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
5 | Replacement of old damaged RBCR rail beam M/c No. CR/964 & screen to increase life of RBCR n reduced direct impact of raw coal on secondary impact crusher. | 0 | - | 0 | 0 | 0 | 0 | 5.09 | 5.09 |  |  | 5.09 | 0
6 | Replacement of copmlete crusher unit as per Drg. No. P00304/0 CO/1050 CR635-636(impact crusher body & rotor shaft assembly) 2 Nos | 0 | - | 0 | 0 | 0 | 0 | 6.4 | 6.4 |  |  | 6.4 | 0
7 | Replacement of appron feeder head shaft assembly-25/005 drg no.-M15076/2 & tail shaft assembly-25/006 Drg. No.- M15065/2 | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply & erection of wagon tippler rail table Drg. No.12578/45-01 , tippler support roller & bogei Drg. No-12616/45-2M | 0 | - | 0 | 1.9 | 1.9 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of seondary crusher motors 6.6KV, 750KW & 220KW motor for CHP | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
10 | Supply of LT motors for various conveyor belts of CHP | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
11 | Up-gradation of existing DC drive system of Wagon Tippler & Paddle feeder with new version DIGICON make system along with supply, installtion, commissioning & testing of DC drives at CHP-III. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply of Variable Frequency drives for Conv.16C2 at CHP-III. | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
13 | Up-gradation of existing relay panel of control room with microprocessor based PLC logic system along with supply, installtion, commissioning & testing of relay panel at CHP. | 0 | - | 0 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | 1.5 | 0
14 | Supply of Magnetic seperators & Metal detectors at CHP | 0 | - | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 3 | 0
0 | Civil Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Repair & renovation of NTPS colony ,Repairing work of ash bund side & Eklahare barrage | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of renovation of various residential quarters by providing and fixing kitchen sink, kitchen trolley & granite otta at NTPS Colony Eklahare. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing and applying external painting to various types residential buildings at NTPS colony Eklahare. | 0 | - | 0 | 1.81 | 1.81 | 0 | 0 | 0 |  |  | 0 | 0
3 | Providing and applying internal painting to various types of residential quarters at NTPS Colony Eklahare. | 0 | - | 0 | 0.97 | 0.97 | 0 | 0.64 | 0.64 |  |  | 0.64 | 0
4 | Providing and fixing vitrified tiles to various types of residnetial buildings at NTPS Colony Eklahare. | 0 | - | 0 | 3.24 | 3.24 | 0 | 2.16 | 2.16 |  |  | 2.16 | 0
5 | Structural strengthening works to various residential quarters at NTPS colony Eklahare. | 0 | - | 0 | 3.54 | 3.54 | 0 | 2.36 | 2.36 |  |  | 2.36 | 0
6 | Providing and fixing colour coated galvanised iron sheets for roofing at various residential buildings at NTPS Colony Eklahare. | 0 | - | 0 | 4.5 | 4.5 | 0 | 2.98 | 2.98 |  |  | 2.98 | 0
7 | Sewer line repair of various quarters at NTPS Eklahare | 0 | - | 0 | 0.5 | 0.5 | 0 | 3.3 | 3.3 |  |  | 3.3 | 0
8 | Stair case repairing of various building at NTPS Eklahare | 0 | - | 0 | 0.15 | 0.15 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
9 | Construction of WBM road over/at the top of ash bund at NTPS Eklahare. | 0 | - | 0 | 0.45 | 0.45 | 0 | 0.14 | 0.14 |  |  | 0.14 | 0
10 | Repairs to filters of drain well No.4 and other allied works at ash bund valley No.4A at NTPS Eklahare. | 0 | - | 0 | 0.4 | 0.4 | 0 | 0.17 | 0.17 |  |  | 0.17 | 0
11 | Repairs to Godavari river barrage gates and allied works at NTPS, Eklahare. | 0 | - | 0 | 0.4 | 0.4 | 0 | 0.19 | 0.19 |  |  | 0.19 | 0
DPR 2 | Structural repairs of Cooling Tower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repairs of cooling tower components at Unit No. 3A, 3B, 4A, 4B,5A & 5B, Stage-II NTPS Eklahare. | 0 | - | 0 | 38.54 | 38.54 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Structural repair & rehabilitation and Renovation and modification work at NTPS Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repair & rehabilitation of various machine foundations of ID, FD & PA fans for Unit No. 3, 4, 5 at Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0.36 | 0.36 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of removing and providing 24 B.W.G.for pent house side & roof at Unit No. 3,4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 2.48 | 2.48 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of removing and providing old damaged siporex wall and poly coated sheet for 28 mtr. height at Unit No. 3, 4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 1.8 | 1.8 | 0 | 0 | 0 |  |  | 0 | 0
4 | Structural repairs of chimney at Unit No. 3,4 & 5 Stage-II, NTPS, Eklahare. | 0 | - | 0 | 4.32 | 4.32 | 0 | 0 | 0 |  |  | 0 | 0
5 | Renovation of sump No. 2,3,4,5,6 and 7 at WTP Stage-II, NTPS Eklahare. | 0 | - | 0 | 2.36 | 2.36 | 0 | 0 | 0 |  |  | 0 | 0
6 | Work of structural repairing at CHP-I,II & III area at NTPS, Eklahare. | 0 | - | 0 | 1.09 | 1.09 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work of structural repairing at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 8.1 | 8.1 | 0 | 0 | 0 |  |  | 0 | 0
8 | Work of structural repair of GS pump Unit No. 3,4,& 5 and fire fighting pump house at Stage-II,NTPS, Eklahare. | 0 | - | 0 | 0.83 | 0.83 | 0 | 0 | 0 |  |  | 0 | 0
9 | Work of repairs to doors & windows of various building at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0.34 | 0.34 | 0 | 0 | 0 |  |  | 0 | 0
10 | Providing and fixing powder coated colored Zincalume profiled sheet for various building at CHP,AWR building, Time office & ODP EM at NTPS, Eklahare. | 0 | - | 0 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of external painting & internal painting at WTP, Stage-II NTPS, Eklahare. | 0 | - | 0 | 1.33 | 1.33 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of external painting & internal painting at CHP area NTPS, Eklahare. | 0 | - | 0 | 0.67 | 0.67 | 0 | 0 | 0 |  |  | 0 | 0
13 | Renovation and restructuring of shed No. 1, 2, 5, 6, 9 & 11 of major store custody of NTPS, Eklahare. | 0 | - | 0 | 3.39 | 3.39 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | As per I.B.Recommondation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of construction compound wall with concertina coil at various locations at Nashik TPS. | 0 | - | 0 | 58.87 | 58.87 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing & renovating security watch tower at NTPS Premises Eklahare. | 0 | - | 0 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | R&M/LE for Identified Thermal units of MSPGCL of (3 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL (3 x 210 MW) units of MSPGCL | 0 | - | 0 | 1180.14 | 1180.14 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | CHP Improvcement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 3 x 210 MW units | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | TATA Mini Truck SFC 709 EX No.MH-15-JV-3992 | N.A. | - | 0 | 0.32099 | 0.32099 | 0 | 0 | 0 |  |  | 0 | 0
2 | Executive chair(10),S Type Arm chai(20) | N.A. | - | 0 | 0.10784 | 0.10784 | 0 | 0 | 0 |  |  | 0 | 0
3 | Office Table and S-Type Chair with Arm | N.A. | - | 0 | 0.030968 | 0.030968 | 0 | 0 | 0 |  |  | 0 | 0
4 | Windows Slot in PC VPC 10-Intel Core 13 4th -NTC | N.A. | - | 0 | 0.010561 | 0.010561 | 0 | 0 | 0 |  |  | 0 | 0
5 | LG Screen wall mounted computer-LED display65"-NTC | N.A. | - | 0 | 5.0969 | 5.0969 | 0 | 0 | 0 |  |  | 0 | 0
6 | 20 Ton Split AC for Audtiorium -NTC | N.A. | - | 0 | 1.0873 | 1.0873 | 0 | 0 | 0 |  |  | 0 | 0
7 | Colour Laser Printer, All in one A3 LaserJet Print | N.A. | - | 0 | 1.0589 | 1.0589 | 0 | 0 | 0 |  |  | 0 | 0
8 | Digital DSLR Camera | N.A. | - | 0 | 1.0793 | 1.0793 | 0 | 0 | 0 |  |  | 0 | 0
9 | Indoor Gymnasium Equipments at NTC, Eklahare | N.A. | - | 0 | 0.02853 | 0.02853 | 0 | 0 | 0 |  |  | 0 | 0
10 | CLASS ROOM CHAIR WITH DESKLET | N.A. | - | 0 | 0.023576 | 0.023576 | 0 | 0 | 0 |  |  | 0 | 0
11 | PA System and Sport Material,Table Tannis for | N.A. | - | 0 | 0.01687 | 0.01687 | 0 | 0 | 0 |  |  | 0 | 0
12 | EXECUTIVE CHAIR WITH 5 SUPRT & S-TYPE CHAIR | N.A. | - | 0 | 0.01003 | 0.01003 | 0 | 0 | 0 |  |  | 0 | 0
13 | APPLN COOLER AIR SEMIEXH AIR COOLER ASSY | N.A. | - | 0 | 0.033896 | 0.033896 | 0 | 0 | 0 |  |  | 0 | 0
14 | FULL PAD CHAIRS WITH SIDE ARM | N.A. | - | 0 | 0.029637 | 0.029637 | 0 | 0 | 0 |  |  | 0 | 0
15 | Industrial Cabinet with 12 Lockers | N.A. | - | 0 | 0.0070163 | 0.0070163 | 0 | 0 | 0 |  |  | 0 | 0
16 | UV Water Purifier Filter | N.A. | - | 0 | 0.019116 | 0.019116 | 0 | 0 | 0 |  |  | 0 | 0
17 | FILTER RO+UV+UF+TDS WATER PURIFIER | N.A. | - | 0 | 0.032906 | 0.032906 | 0 | 0 | 0 |  |  | 0 | 0
18 | 2 Tone SPLIT AC INDOOR UNIT | N.A. | - | 0 | 0.008064 | 0.008064 | 0 | 0 | 0 |  |  | 0 | 0
19 | 1.5 TON CAPACITY SPLIT AC | N.A. | - | 0 | 0.006688 | 0.006688 | 0 | 0 | 0 |  |  | 0 | 0
20 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 1.698 | 1.698 | 0 | 0 | 0 |  |  | 0 | 0
21 | Logitech PTZ Group Camera 960-001054 | N.A. | - | 0 | 2.4375 | 2.4375 | 0 | 0 | 0 |  |  | 0 | 0
22 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011564 | 0.011564 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK BENCH WITHOUT DRAWER | 0 | - | 0 | 0.011647 | 0.011647 | 0 | 0 | 0 |  |  | 0 | 0
24 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.030075 | 0.030075 | 0 | 0 | 0 |  |  | 0 | 0
25 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011788 | 0.011788 | 0 | 0 | 0 |  |  | 0 | 0
26 | EXECUTIVE CHAIR, S-TYPE CH-7 CHAIR WITH ARM | 0 | - | 0 | 0.035229 | 0.035229 | 0 | 0 | 0 |  |  | 0 | 0
27 | SAMSUNG GALAXY TAB S3, 32GB 9.7 INCH | 0 | - | 0 | 0.003845 | 0.003845 | 0 | 0 | 0 |  |  | 0 | 0
28 | i5 Laptop - 2 Nos & i7 Laptop - 3 Nos | 0 | - | 0 | 0.037636 | 0.037636 | 0 | 0 | 0 |  |  | 0 | 0
29 | Godrej make 1.5 Ton High Wall Split AC | 0 | - | 0 | 0.020975 | 0.020975 | 0 | 0 | 0 |  |  | 0 | 0
30 | Complete Multimedia Projector with Std Accessories | 0 | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
31 | LED 40 INCH SMART TV | 0 | - | 0 | 0.0092016 | 0.0092016 | 0 | 0 | 0 |  |  | 0 | 0
32 | FULL PAD CHAIRS, EXECUTIVE CHAIR, | 0 | - | 0 | 0.068995 | 0.068995 | 0 | 0 | 0 |  |  | 0 | 0
33 | Cash Counting Machine | 0 | - | 0 | 0.001888 | 0.001888 | 0 | 0 | 0 |  |  | 0 | 0
34 | 230 V AC DIGITAL SINE WAVE INVERTER 1 No. | 0 | - | 0 | 0.010175 | 0.010175 | 0 | 0 | 0 |  |  | 0 | 0
35 | HPCV no.3 &4 Stem | 0 | - | 0 | 0.025694 | 0.025694 | 0 | 0 | 0 |  |  | 0 | 0
36 | HEAVY DUTY AIR PURIFIURE 230V,50HZ | 0 | - | 0 | 0.0105 | 0.0105 | 0 | 0 | 0 |  |  | 0 | 0
37 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.0048144 | 0.0048144 | 0 | 0 | 0 |  |  | 0 | 0
38 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.025939 | 0.025939 | 0 | 0 | 0 |  |  | 0 | 0
39 | APPLN COOLER WTR CAP CAP: 60 LITERS | 0 | - | 0 | 0.0053799 | 0.0053799 | 0 | 0 | 0 |  |  | 0 | 0
40 | LASER LASERJET PRINTER FOR A4 PAPER | 0 | - | 0 | 0.0057 | 0.0057 | 0 | 0 | 0 |  |  | 0 | 0
41 | 40 Inch Smart LED TV 3.00 | 0 | - | 0 | 0.010178 | 0.010178 | 0 | 0 | 0 |  |  | 0 | 0
42 | DESKTOP INTEL CORE I5 2300 PROCESSOR | 0 | - | 0 | 0.021459 | 0.021459 | 0 | 0 | 0 |  |  | 0 | 0
43 | ONLINE WATER HEATER, 3KW,3LTR. | 0 | - | 0 | 0.029683 | 0.029683 | 0 | 0 | 0 |  |  | 0 | 0
44 | CAMERA FOR VC, MICROPHONE WITH SPEAKER | 0 | - | 0 | 0.023889 | 0.023889 | 0 | 0 | 0 |  |  | 0 | 0
45 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
46 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 0.01873 | 0.01873 | 0 | 0 | 0 |  |  | 0 | 0
47 | Water Cooler | 0 | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
48 | PORTABLE HARD DISK USB 1TB | 0 | - | 0 | 0.0017388 | 0.0017388 | 0 | 0 | 0 |  |  | 0 | 0
49 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.00095 | 0.00095 | 0 | 0 | 0 |  |  | 0 | 0
50 | Garbox assembly for premium make type B-220 of | 0 | - | 0 | 0.44095 | 0.44095 | 0 | 0 | 0 |  |  | 0 | 0
51 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.006726 | 0.006726 | 0 | 0 | 0 |  |  | 0 | 0
52 | RO+UV+UF+TDS CAP 50 LITRE PER HOUR | 0 | - | 0 | 0.002731 | 0.002731 | 0 | 0 | 0 |  |  | 0 | 0
53 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.0025995 | 0.0025995 | 0 | 0 | 0 |  |  | 0 | 0
54 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.002183 | 0.002183 | 0 | 0 | 0 |  |  | 0 | 0
55 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0061808 | 0.0061808 | 0 | 0 | 0 |  |  | 0 | 0
56 | REGULAR CHAIR WITHOUT CUSHION | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
57 | BLDC Fans through GeM Portal and GA -2022-23 at | 0 | - | 0 | 0.0049556 | 0.0049556 | 0 | 0 | 0 |  |  | 0 | 0
58 | ALL IN ONE PC, CORE I5, 4 GB RAM, 500 GB | 0 | - | 0 | 0.02973 | 0.02973 | 0 | 0 | 0 |  |  | 0 | 0
59 | PRINTER LASER LASERJET NETWORK PRINTER | 0 | - | 0 | 0.0020024 | 0.0020024 | 0 | 0 | 0 |  |  | 0 | 0
60 | APPLN FAN AIR CEIL SIZE 1200 MM SWEEP | 0 | - | 0 | 0.033918 | 0.033918 | 0 | 0 | 0 |  |  | 0 | 0
61 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.014828 | 0.014828 | 0 | 0 | 0 |  |  | 0 | 0
62 | 400 MM, 230V, 3 BLADE DOMESTIC FAN | 0 | - | 0 | 0.0024532 | 0.0024532 | 0 | 0 | 0 |  |  | 0 | 0
63 | APPLN FAN AIR EXHAUST SIZE15"1400RPM-15 Nos | 0 | - | 0 | 0.01781 | 0.01781 | 0 | 0 | 0 |  |  | 0 | 0
64 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.013559 | 0.013559 | 0 | 0 | 0 |  |  | 0 | 0
65 | MICROWAVE OVEN CAPACITY 27 / 28 LITERS-1 Nos | 0 | - | 0 | 0.0048362 | 0.0048362 | 0 | 0 | 0 |  |  | 0 | 0
66 | REFRIGERATOR SINGLE DOOR CAPCITY 190 LTR | 0 | - | 0 | 0.0067225 | 0.0067225 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Thinclients on Buyback for NTPS | 0 | - | 0 | 0.23166 | 0.23166 | 0 | 0 | 0 |  |  | 0 | 0
68 | ABC Powder type DCP Composite Fire Extinguisher | 0 | - | 0 | 0.357 | 0.357 | 0 | 0 | 0 |  |  | 0 | 0
69 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024631 | 0.024631 | 0 | 0 | 0 |  |  | 0 | 0
70 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024213 | 0.024213 | 0 | 0 | 0 |  |  | 0 | 0
71 | Furniture Dining Table for Main Mess Hall and Cus | 0 | - | 0 | 0.019803 | 0.019803 | 0 | 0 | 0 |  |  | 0 | 0
72 | Servers for DSM at Nashik Thermal Power Station | 0 | - | 0 | 0.43559 | 0.43559 | 0 | 0 | 0 |  |  | 0 | 0
73 | DESKTOP INTEL CORE I5 2300 PROCESSOR - 5 Nos | 0 | - | 0 | 0.05632 | 0.05632 | 0 | 0 | 0 |  |  | 0 | 0
74 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.041064 | 0.041064 | 0 | 0 | 0 |  |  | 0 | 0
75 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.038246 | 0.038246 | 0 | 0 | 0 |  |  | 0 | 0
76 | APPLN TV STD ULSLIM 42" - 4 Nos | 0 | - | 0 | 0.037376 | 0.037376 | 0 | 0 | 0 |  |  | 0 | 0
77 | 1 T SPLIT AC COMPL UNIT WITH ACCESSORIES | 0 | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
78 | MULTIMEDIA PROJECTOR EPSON EB-U05-1 No | 0 | - | 0 | 0.0081606 | 0.0081606 | 0 | 0 | 0 |  |  | 0 | 0
79 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.0023246 | 0.0023246 | 0 | 0 | 0 |  |  | 0 | 0
80 | Procurement of Complete Vibrating Screen Assembly at CHP-II | 0 | - | 0 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Asset | 0 | - | 0 | 0.575 | 0.575 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 2044.4166 | 2066.1241 | -21.7075 | 89.2414 | 89.2414 | 0 | 0 | 89.2414 | -21.7075
FY 2028-29
a) DPR Schemes
0 | (i) Submitted to MERC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Measuring & Monitoring of Coal consumption | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 23.0165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Belt Weighers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3295 | 0.3295 | 0.3295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.793 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of inhaul outhaul betel chargers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 6 | 8.5943 | 8.5943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Dust Extraction System | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 1.65 | 1.713 | 1.713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Fogging system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 2.44 | 2.59 | 2.59 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Bunker level montoring system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.54 | 0.0694 | 0.0694 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.169 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Operating the CHP near to its full capacity | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 7.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Motor controller | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3732 | 0.3732 | 0.3732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 3.4218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Combustion optimization & Process improvement | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 58.7761 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Improvement in tooling techniques Power tools like cut off machines and surface grinders. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.52821 | 0.3388 | 0.3388 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Total replacement of boiler related skin insulation as well as skin cladding of furnace, Air pre heaters,air ducts and flue gas ducts Unit-4 &5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4.5892 | 4.7188 | 4.7188 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Painting of Boiler ,bunker structure and other structure.Unit-3,4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 7.775 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 8.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.5 | Retrofitting of Gas proportioning dampers, flue gas, primary and secondary air dampers. (SADC) for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.456 | 1.2566 | 1.2566 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.41356 | 0.41356 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Replacement of flue gas ducting zone prone to erosion with 6 to 8 mm high grade material & insulation of flue gas ducts. (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 4 and 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Replacement of boiler outlet valves and damaged valves of units 4 & 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.349 | 1.4313 | 1.4313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Replacement of coal pipe at direction changing sections & flow curvature zone by upgraded material. Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.3292 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.9 | Installation of Smart soot blower system for Unit- 4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 5.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.10 | Installation of Sonic soot blowers for second pass for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.83184 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.11 | Air pre heater upgradation of heat exchanger matrix &regenerative dynamic sealing for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.12 | Replacement Platen water wall for Unit-3. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.60762 | 0.6964 | 0.6964 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 13.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Turbine Auxiliary Consumption Improvement | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 39.2903 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Installation of Turbo vaned fly wheeling eco ventilators to all Units 3, 4, 5. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Replacement of selected old brass impellers of pumps with SS304 impellers. H.T. Auxiliary C.W. Pump and G.S. Water Pumps are selected. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.4 | 0.8251 | 0.8251 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Improving the BFP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.75 | 0.48804 | 0.48804 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Replacement of BFP (200 KHI) cartridge with energy efficient cartridge. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 14.4456 | 13.85 | 13.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Improving the CEP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.9 | 0.6018 | 0.6018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Replacement of CEP with energy efficient pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Replacement of Pumps - GS Pumps, H2Cooler booster pump, DM/DM pumps, DM Makeup pumps, Emergency lift pumps, Drip pumps, BFP Booster pumps with energy efficient pumps. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 4.2733 | 2.3608 | 2.3608 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.8 | Replacement of valves – MS - 3 to 8 , HD – 22,23,24 , MC- 36 , ES 3,4 and BFP Recirculation Valves. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.0852 | 1.3148 | 1.3148 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.9 | Replacement of tube nest of LP Heater no.3 of unit no.3, LP Heater no.4 of unit no.5, Main ejector 3B, GC2 of unit no.5, Seal oil coolers, H2 Coolers, BFP working and lub oil coolers, DM/GS plate type coolers. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 6.5962 | 1.9594 | 1.9594 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.11461 | 0.11461 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.10 | Steam path audit of Unit no,4,5 | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | EMS, Numeric relays, Microprocessor DVR & VFD | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 12.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.1 | Design, manufacture, supply, erection, commissioning & testing of Variable Frequency Drives (VFD) with latest design and technology super premium efficiency motors for 415 V LT Auxiliaries (Total 50 No) of 210 MW Unit 3, 4 & 5. | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 6.3 | 8.8183 | 6.2927 | 2.5255 | 0 | 0 |  |  | 0 | 2.5255
0 | IDC | 0 | - | 0.66 | 0.74645 | 0.74645 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Replacement of old EE make Generator Protection Relays with Numerical Generator Protection Relays for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 1.7 | 1.7029 | 1.7029 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Replacement of old AVR with Microprocessor based Digital Voltage Regulator for unit no. 3 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 2.44 | 1.7055 | 1.7055 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Installation and commissioning of Energy Management System for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.81 | 0.8313 | 0.8313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 14.5069 | 14.5069 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 57.9147 | 57.9147 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Faster unloading of coal wagons by upgrading existing system (Post Facto) | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 18.8481 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Re-design, Supply, Erection and commissioning of modified Apron Feeder. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.7219 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Design, manufacture, supply, erection and commissioning of modified bunker outlet cone of Unit 3, 4 and 5. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.3295 | 2.3196 | 2.3196 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Design, manufacture, Supply & Erection Of Components Suitable For Modification Of Wagon Tipplers to Handle BOXNHL , BOX-H,BOX-NR,BOX-NJLSR1 & 25 T AXLE WAGONS | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.1298 | 4.413 | 4.413 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Procurement of SAN Loco - 650-700 HP. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8627 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.5 | Revamping of CHP II Wagon Tippler by replacing the Split Wheel Assembly, Pawl Lever, Pinion Shaft Assembly, Toe, Spur Gear Shaft, W.T Drive Assembly, Rack Segment, Rail Table Assembly Of Wagon Tippler and Dismantling & Replacement of above parts | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8042 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement of 6.6 Kv HT motors as spare motors /for replacement | MERC/CAPEX/20152016/00422 | 2016-08-03 | 14.3563 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3125 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1025 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | FD FAN MOTOR 650 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | FD FAN MOTOR 750 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8505 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | PA FAN MOTOR 1250 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.029 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | BFP MOTOR 4000 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 4.5528 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | C/MILL MOTOR 320 kW (3 Nos) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3356 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.8 | SOP MOTOR 200 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.9 | CWP MOTOR 950 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8942 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.10 | CTLP MOTOR 710 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8081 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.11 | RWP MOTOR 335 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.4861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.12 | HP PUMP MOTOR 258 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3083 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.13 | CEP MOTOR 220 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2629 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.14 | GS PUMP MOTOR 260 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3107 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.15 | Testing charges | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.088 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Replacement of complete LTSH coils at Unit-3 Boiler & Economiser coils at Unit-5 Boiler | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 27.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Complete Supply & Erection of LTSH coils at Unit-3 210 MW Boiler (67 nos. upper and lower modules each. 01 module = 02 coils) | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 16.43 | 4.6378 | 4.6378 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Complete Supply & Erection of 270 nos. Economizer coils in second pass of Unit-5 210 MW Boiler at Nasik TPS. | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 9.57 | 3.0104 | 3.0104 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 1.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Enhancement of performance & life of Coal Handling plant | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 17.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Procurement of 02 nos of 320 hp bull dozers for Nasik TPS | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 3.2 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Procurement of gear box for Apron Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 1.59 | 1.6043 | 1.6043 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Procurement of gear box and 30 KW DC motor for Pedal Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.46 | 0.45847 | 0.45847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.4 | Procurement of Assembly of Impact Crusher Complete set, with Rotor Assembly and bearing Block. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 2.3 | 2.3366 | 2.3366 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.5 | Procurement of 10 KW Inline Magnetic Separator for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.4 | 0.54718 | 0.54718 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.6 | Restoration of RBCR by replacing feed end Spider (Drg. No. 400-1428-01/A) & Discharge end Spider (400-1428-02) suitable to rotary Bradford breaker machine No.CR/634 along with support wheels. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 8.14 | 10.2287 | 10.2287 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.7 | Procurement of 750 KW Impactor Motor for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.49 | 0.22635 | 0.22635 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.8 | Supply of Metal Detectors for CHP | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.14 | 0.09152 | 0.09152 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Retrofitting of 6.6 kV Breakers, Battery Replacement, System Improvement & MPCB Related schemes | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 14.7811 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Retrofitting of 6.6 kV HT MOCB/SF6 Breakers by VCB | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 3.57 | 5.0621 | 5.0621 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2a | A) Procurement & Replacement of 220V/ 1285 AH Battery set for U#3 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0493 | 1.0493 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2b | B) Procurement & Replacement of 220V/ 1285 AH Battery set for U#4 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0047 | 1.0047 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | O2 Measurement System in the furnace & flue gas ducting | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.17 | 1.2966 | 1.2966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Supply, erection, commissioning & testing of online CO, SO2, NOX Analyser for U#3/4/5 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.6511 | 1.6846 | 1.6846 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | A) Replacement of static Flame Monitoring System with Microprocessor based Flame Monitoring & Analyzing System | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.27 | 2.4267 | 2.4267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | CAAQMS monitoring of ambient air quality around the NTPS. | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1 | 0.81676 | 0.81676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | 3rd raising of Ash bund | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | 3rd raising of ash bund from TBL 581.50 to 586.50m in valley No. 4A at Nashik Thermal Power Station, Eklahare | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 12.3 | 10.2142 | 10.2142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | System Rehabilitation & Upgradation at Nasik TPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 13.3722 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.1 | Shifting, Transportation & Replacement of Existing Generator Stator of Unit no.3 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 7.98 | 0.8767 | 5.8767 | -5 | 0 | 0 |  |  | 0 | -5
0 | IDC | 0 | - | 0 | 0.26397 | 0.26397 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Turbine Supervisory Instrumentation System for Unit no.5 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.5542 | 0.45436 | 0.45436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Supply of Air Compressors for NTPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 3.398 | 3.8197 | 3.8197 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Replacement of Old Brass Impellers of CTLP with SS Impellers. | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 1.04 | 1.1331 | 1.1331 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up-gradation of DCS at U # 3 and New Rectiformers & ESP Refurbishment of U # 4 & 5 at Nasik TPS | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 33.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Decommissioning & Shifting of M/s ABB make DCS system at BTPS Unit # 2 & Re-commissioning with Up gradation to Symphony Plus at NTPS Unit #3, Nasik. | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 9.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Erection ,Testing & commissioning, Supply of rectiformer HVR 37/800 Hermatically sealed Rectiformer ( DC Peak voltage – 70 kV , Average voltage-45 KV ,DC Current – 800 milli amp , AC I/P – 1 Phase , 415 V ) | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 10.34 | 0 | 13 | -13 | 0 | 0 |  |  | 0 | -13 | 0 | 0
16.3 | Refurbishment of ESP for Unit No. 4 & 5 at Nashik TPS, Eklahare | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 12.5 | 12.8553 | 12.8553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 1.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Replacement of drum gate, augmentation of existing ash water recovery scheme and construction of concrete road for Nasik Thermal Power Station | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 14.5161 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Replacement of drum gate and restructuring of cofferdam, repairs to vertical sluice gate, Approach Bridge and allied civil works at Godavari barrage at Nashik TPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 6.273 | 3 | 6.27 | -3.27 | 0 | 0 |  |  | 0 | -3.27 | 0 | 0
17.2 | Augmentation of existing ash water recovery scheme and connecting overflow of waste weir to existing toe drain of ash bund valley no.4 to WWR at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 2.5999 | 3.1676 | 3.1676 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.2441 | 0.2441 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.3 | Up gradation of fly ash concrete road from Booster Pump house toward Hydrogen plant, Dirk India Company towards Hinganwedhe along ash bund valley No. 1 & 2, Ash bund approach road for ash transportation and abundant valley towards Kotamgaon road at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 5.3732 | 5.3752 | 5.3752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 0.27 | 0.38455 | 0.38455 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Various DPR Schemes for Renovation of colony at NTPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 10.8678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.1 | Renovation of staff quarters, playground, Jogging track & Gymnasium at NTPS colony, Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 4.071 | 3.5306 | 3.5306 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.92832 | 0.92832 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Road works in NTPS Colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 3.9766 | 3.8972 | 3.8972 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.3 | Water supply and sanitation works at NTPS colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 2.8202 | 1.4586 | 1.4586 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.19994 | 0.19994 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.4 | Renovation of Workers Recreation Club at Nashik TPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Life enhancement of stacker cum reclaimer machine in CHP & upgradation of SWAS laboratory at Nasik TPS | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 14.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Supply, Erection & installation of sole plates, Rail track & Hydraulic cylinder of the Stacker cum Reclaimer machine at Coal Handling Plant-II Nashik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 6.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.2 | Procurement and replacement of 220 V, 1285 AH battery set for Unit No. 4 at Nasik Thermal Power Station. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 1.39 | 1.4116 | 1.4116 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.2227 | 0.2227 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Supply of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers Ltd.) at Nasik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 3.11 | 3.0812 | 3.0812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Erection and commissioning of Steam and Water sampling system for SWAS Lab at WTP, NTPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 2.23 | 0 | 3 | -3 | 0 | 0 |  |  | 0 | -3 | 0 | 0
19.5 | Procurement of 3 nos. of Ash Slurry Disposal pump Type D - 85 for Ash Slurry Pump House of Unit no. 3, 4 & 5 at NTPSEklahare. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.55 | 0.55578 | 0.51878 | 0.037 | 0 | 0 |  |  | 0 | 0.037 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Flue Gas Desulphurization (FGD) System at Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Ash Augmentation System at Nasik & Koradi Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Ash Augmentation System at Nasik Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 5.71 | 5.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3.1 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 8.47 | 8.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6.2 | NASIK TPS (U-3 to 5) (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 2.8842 | 2.8842 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.76776 | 0.76776 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Nashik TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.2272 | 2.2272 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | TPS Nashik | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 2.3118 | 2.3118 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.1 | Procurement and Replacement of Complete sets of assembly of baskets for air preheater of type tri-sector APH 27 VI(T) 74” in NTPS unit no. 4 & 5 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 5.5929 | 5.5929 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.13531 | 0.13531 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | <DPR Name> | N.A. | N.A. | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Complete Replacement of HRH Coils, LTSH Coils, Economizer Coils at Unit No. 4 & Complete Replacement of Economizer coils at Unit No.3 Nashik TPS 210 MW Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Replacement HRH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 8.551 | 8.551 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete Replacement LTSH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 12.6608 | 12.6608 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete Replacement Economiser Coils at NTPS Unit No. 3 & 4 Boilers | 0 | - | 0 | 16.0672 | 16.0672 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 and Commissioning of AFGC system for Unit No. 3, 4 & 5 and Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5 at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of MSERW pipes for Replacement of various pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 at NTPS, Eklahare | 0 | - | 0 | 19.6769 | 19.6769 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, erection, commissioning & testing of Ammonia Flue gas Conditioning system for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 3.9046 | 3.9046 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5, 210 MW, NTPS, Eklahare, Nasik. | 0 | - | 0 | 2.9741 | 2.9741 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Complete replacement of Platen Superheater coils at Unit No.3,4 & 5 ; Complete replacement of HRH coils at Unit No.3,& 5; Complete replacement of LTSH coils at Unit No. 5;Replacement of thermal insulation at Boiler for Nashik TPS 210 MW boilers | 0 | - | 0 | 0 | 0 | 0 | 1.39 | 1.39 |  |  | 1.39 | 0
1 | Complete replacement of Platen Superheater coils at Unit No. 3,4 & 5 | 0 | - | 0 | 16.6 | 16.6 | 0 | 1.711 | 1.711 |  |  | 1.711 | 0
2 | Complete replacement of HRH coils at Unit No.3,& 5 | 0 | - | 0 | 15.391 | 15.391 | 0 | 1.911 | 1.911 |  |  | 1.911 | 0
3 | Complete replacement of LTSH coils at Unit No.5 | 0 | - | 0 | 10.7498 | 10.7498 | 0 | 2.64 | 2.64 |  |  | 2.64 | 0
4 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines at Unit No.3,4 & 5 | 0 | - | 0 | 6.897 | 6.897 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | Procurement of various pumps for TM & ODP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement and Erection Commissioning of Condenser vacuum pump for Unit No. 3 ,4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 29.24 | 29.24 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Three Pump assemblies of SAM TURBO makes Type 150/500 N for Booster Pump house at NTPS Eklahare. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 3 Nos Vertical Fly Ash Transfer Pump VO 150 /400 + ARS SAM make along with motor for ESP Hopper evacuation of Unit No.3,4 & 5 at NTPS Eklahare | 0 | - | 0 | 0.79 | 0.79 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection, installation, civil foundation, commissioning, testing & trial of Rotating &casing assembly of pumps for WTP at Nashik TPS, Eklahare | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement (10 nos.) of CWFW pumps (with motor) at Stage-II (Beacon make) | 0 | - | 0 | 0.94 | 0.94 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of RWP Pump assembly at NTPS. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Cooling Tower lift Pump Impeller for Jyoti make pump Type:-1200- VMI A 12 at NTPS Eklahare | 0 | - | 0 | 1.07 | 1.07 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Degasser Pump assembly with motor (06 Nos.) | 0 | - | 0 | 0.354 | 0.354 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 8 Nos. of Domestic water pumps (with motor) & Darna drinking water pump at Stage-I & II | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of 4 Nos. of DM backwash (2 Nos.) & CW backwash pump (2 Nos.)(with motor)at NTPS. | 0 | - | 0 | 0.36 | 0.36 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of HP Pumps at NTPS. | 0 | - | 0 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of ETP pump assembly (06 Nos.) | 0 | - | 0 | 1.42 | 1.42 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of RWP shaft with bearing, Impeller (02 Nos.) | 0 | - | 0 | 1.68 | 1.68 | 0 | 0 | 0 |  |  | 0 | 0
14 | Procurement of AWR pump (02 Nos.) | 0 | - | 0 | 0.47 | 0.47 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Submersible Slurry Pumps for handling Ash water / Clear water for dewatering at various locations at NTPS (10 Nos.) | 0 | - | 0 | 0.885 | 0.885 | 0 | 0 | 0 |  |  | 0 | 0
DPR 5 | Renovation of Compressed Air Refrigerated Dryer System, Refurbishment of Centralized Air Conditioning system, Supply, erection & commissioning of Condensate Extraction Pump, Procurement of CW Pump and GS pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Compressed Air Refrigerated Dryer System for Nashik TPS, 210 MW Unit No. 3, 4 & 5 | 0 | - | 0 | 11.3737 | 11.3737 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of Centralized Air Conditioning system of Unit No. 3, 4 & 5 at Nashik TPS, Eklahare. | 0 | - | 0 | 8.15 | 8.15 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers ltd. at Nasik TPS. Total Qty. 02 Nos. | 0 | - | 0 | 3.93 | 3.93 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of CW & CTLP Pump total 4 No.s | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of GS Pump assembly .Total qty- 3 No | 0 | - | 0 | 1.373 | 1.373 | 0 | 0 | 0 |  |  | 0 | 0
DPR 6 | Procurement of oil free Rotary Screw Compressors and BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of BFP cartridge | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of oil free rotary screw compressors | 0 | - | 0 | 21.6648 | 21.6648 | 0 | 0 | 0 |  |  | 0 | 0
DPR 7 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets, Refurbishment of HPT rotor along with supply, Procurement of HP & IP control valve with cam shaft assemblies, Procurement of complete governing system assembly, Supply, Errection & Commissioning of COP assembly, Procurement of Condenser tubes & ODP related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets at 3 x 210 MW, TM-II NTPS. | 0 | - | 0 | 0.63 | 0.63 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of HPT rotor along with supply. | 0 | - | 0 | 3.7908 | 3.7908 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of HP & IP control valve with cam shaft assemblies.qty-1set | 0 | - | 0 | 0.81 | 0.81 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of complete governing system assembly. qty-1 set | 0 | - | 0 | 0.27563 | 0.27563 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, Errection & Commissioning of COP assembly.Total Qty.- 3 Nos. | 0 | - | 0 | 0.9642 | 0.9642 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Condenser tubes for Unit No.3, 4 & 5.Total Qty:15700 tubes | 0 | - | 0 | 20.27 | 20.27 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of CT Fan Blade assembly & shaft- 36 nos for Unit No.3,4 & 5 at NTPS, Eklahare | 0 | - | 0 | 1.3 | 1.3 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Gearbox Assembly for Cooling Tower Fans type B-220 Premium make for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare (Qty-24) | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 5 nos. of Air Blowers for Degasser system | 0 | - | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Flocculator gearbox- 12 Nos. | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of Clinker grinder assembly at NTPS Eklahare | 0 | - | 0 | 0.65 | 0.65 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of 4 Nos. of Clinker grinder gearbox at NTPS Eklahare | 0 | - | 0 | 0.2 | 0.2 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of 5 Nos. of Air Blowers for Degasser system | 0 | - | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  |  | 0 | 0
14 | Augmentattion of existing Ash Water recovery Scheme(WWR,AWR, ETP-I,ETP-II & Phase-II pump assembly) | 0 | - | 0 | 2.97 | 2.97 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Feed Gate Housing (08 Nos.) | 0 | - | 0 | 0.57 | 0.57 | 0 | 0 | 0 |  |  | 0 | 0
DPR 8 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area & Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
DPR 9 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS , Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of LT energy efficient motor | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
DPR 10 | Upgradation of various electrical related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of 6.6KV HT motors and spares at Nashik TPS Unit No 3,4 & 5. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Boiler and turbine house lighting of Unit No.3,4 & 5 along with removal of old wiring. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacemet of IPH transformer 11KV/6.6 KV and lighting and welding transformer at NTPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
4 | Excitation Transformer at Unit No. 3, 4 & 5 | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
5 | GTR /UAT/ station transformer spares LV bushings replacement, HV bushings (spare)-3nos, LV busbar, palm joint both station transformers bushings at Unit No.3, 4 & 5 | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of overhead conductor HT/LT by underground HT/LT cable in Colony area. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
7 | LT transformer procurement/ rewinding work at NTPS | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
8 | LT MCC panel modification at ODP area NTPS | 0 | - | 0 | 10 | 10 | 0 | 1 | 1 |  |  | 1 | 0
9 | Battery Charger-220V,50V,380V UPS, 24V,DG set EMF panel with charger replacement, UPS battery replacement, Unit No. 5 station battery replacement,50 V battery set replacement at Unit No.3, 4 & 5 | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
10 | Replacement of HT motor Cables. (Old PILC Cable replacement with XLPE Cable) at Unit No.3, 4 & 5 & ODP area | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
11 | Unit No. 4 Field Breaker | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
DPR 11 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
DPR 12 | Replacement/Upgradation of C&I old systems at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement/Upgradation of Unit No.4 DVR System. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement/Upgradation of Unit No.4 UPS System. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotory Electronic Control Drive for Burner Tilt and Auxiliary Air Damper at Unit No. 3, 4 & 5 210 MW, NTPS, Eklahare Nashik. | 0 | - | 0 | 7.93 | 7.93 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification/Upgradation of Turbovisory system of Unit No. 3,4 & 5. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
5 | Auxiliary air dampers & BT, HAD, feed gate replacement/modification work. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Unit No.4 DCS-FCS 102 to FCS 106 (Total 5 Nos.) | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
7 | New sewage treatment plant required at NTPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
8 | Upgradation of Unit No.4 230 V UPS and new UPS, charger for Unit No. 3 & 5 DCS at NTPS. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
9 | ESP hopper high & low level indicator mounting in Unit No.3,4& 5. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
10 | OCEMS for Sox, Nox, opacity monitoring system upgradation work for Unit No.3, 4 & 5 at NTPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
11 | Supply, Erection, Commissioning & Testing of online H2 purity meter and Resistivity meter for Unit No. 5. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, Erection, commissioning of Hydra step system for Drum level control Unit No.3. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
13 | HPLP - Servo Spares | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
14 | Replacement of Relays and Energy meter at NTPS, Nashik. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
15 | ESP upgradation for Unit No. 3, 4 & 5. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
16 | Grounding Brush Monitoring System for Unit No. 3,4& 5. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
17 | Implementationof FGMO | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
DPR 13 | Modification & replacement of various CHP schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Modification of single stream conveyor belt Gearboxes with new design Helical Bevel type Gearboxes at CHP-II NTPS | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
2 | Modification of Primary Vibrating screen at CHP-II, NTPS | 0 | - | 0 | 0.7 | 0.7 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Rail table alongwith weighment frame for rotaside Wagon Tippler at CHP-II, NTPS | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification of Conveyor Drive system with Motorised Pulley drive system at CHP-II, NTPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
5 | Replacement of old damaged RBCR rail beam M/c No. CR/964 & screen to increase life of RBCR n reduced direct impact of raw coal on secondary impact crusher. | 0 | - | 0 | 5.09 | 5.09 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of copmlete crusher unit as per Drg. No. P00304/0 CO/1050 CR635-636(impact crusher body & rotor shaft assembly) 2 Nos | 0 | - | 0 | 6.4 | 6.4 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of appron feeder head shaft assembly-25/005 drg no.-M15076/2 & tail shaft assembly-25/006 Drg. No.- M15065/2 | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply & erection of wagon tippler rail table Drg. No.12578/45-01 , tippler support roller & bogei Drg. No-12616/45-2M | 0 | - | 0 | 1.9 | 1.9 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of seondary crusher motors 6.6KV, 750KW & 220KW motor for CHP | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
10 | Supply of LT motors for various conveyor belts of CHP | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
11 | Up-gradation of existing DC drive system of Wagon Tippler & Paddle feeder with new version DIGICON make system along with supply, installtion, commissioning & testing of DC drives at CHP-III. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply of Variable Frequency drives for Conv.16C2 at CHP-III. | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
13 | Up-gradation of existing relay panel of control room with microprocessor based PLC logic system along with supply, installtion, commissioning & testing of relay panel at CHP. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
14 | Supply of Magnetic seperators & Metal detectors at CHP | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Repair & renovation of NTPS colony ,Repairing work of ash bund side & Eklahare barrage | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of renovation of various residential quarters by providing and fixing kitchen sink, kitchen trolley & granite otta at NTPS Colony Eklahare. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing and applying external painting to various types residential buildings at NTPS colony Eklahare. | 0 | - | 0 | 1.81 | 1.81 | 0 | 0 | 0 |  |  | 0 | 0
3 | Providing and applying internal painting to various types of residential quarters at NTPS Colony Eklahare. | 0 | - | 0 | 1.61 | 1.61 | 0 | 0 | 0 |  |  | 0 | 0
4 | Providing and fixing vitrified tiles to various types of residnetial buildings at NTPS Colony Eklahare. | 0 | - | 0 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening works to various residential quarters at NTPS colony Eklahare. | 0 | - | 0 | 5.9 | 5.9 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing and fixing colour coated galvanised iron sheets for roofing at various residential buildings at NTPS Colony Eklahare. | 0 | - | 0 | 7.48 | 7.48 | 0 | 0.45 | 0.45 |  |  | 0.45 | 0
7 | Sewer line repair of various quarters at NTPS Eklahare | 0 | - | 0 | 3.8 | 3.8 | 0 | 0 | 0 |  |  | 0 | 0
8 | Stair case repairing of various building at NTPS Eklahare | 0 | - | 0 | 0.65 | 0.65 | 0 | 0 | 0 |  |  | 0 | 0
9 | Construction of WBM road over/at the top of ash bund at NTPS Eklahare. | 0 | - | 0 | 0.59 | 0.59 | 0 | 0 | 0 |  |  | 0 | 0
10 | Repairs to filters of drain well No.4 and other allied works at ash bund valley No.4A at NTPS Eklahare. | 0 | - | 0 | 0.57 | 0.57 | 0 | 0 | 0 |  |  | 0 | 0
11 | Repairs to Godavari river barrage gates and allied works at NTPS, Eklahare. | 0 | - | 0 | 0.59 | 0.59 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Structural repairs of Cooling Tower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repairs of cooling tower components at Unit No. 3A, 3B, 4A, 4B,5A & 5B, Stage-II NTPS Eklahare. | 0 | - | 0 | 38.54 | 38.54 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Structural repair & rehabilitation and Renovation and modification work at NTPS Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repair & rehabilitation of various machine foundations of ID, FD & PA fans for Unit No. 3, 4, 5 at Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0.36 | 0.36 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of removing and providing 24 B.W.G.for pent house side & roof at Unit No. 3,4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 2.48 | 2.48 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of removing and providing old damaged siporex wall and poly coated sheet for 28 mtr. height at Unit No. 3, 4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 1.8 | 1.8 | 0 | 0 | 0 |  |  | 0 | 0
4 | Structural repairs of chimney at Unit No. 3,4 & 5 Stage-II, NTPS, Eklahare. | 0 | - | 0 | 4.32 | 4.32 | 0 | 0 | 0 |  |  | 0 | 0
5 | Renovation of sump No. 2,3,4,5,6 and 7 at WTP Stage-II, NTPS Eklahare. | 0 | - | 0 | 2.36 | 2.36 | 0 | 0 | 0 |  |  | 0 | 0
6 | Work of structural repairing at CHP-I,II & III area at NTPS, Eklahare. | 0 | - | 0 | 1.09 | 1.09 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work of structural repairing at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 8.1 | 8.1 | 0 | 0 | 0 |  |  | 0 | 0
8 | Work of structural repair of GS pump Unit No. 3,4,& 5 and fire fighting pump house at Stage-II,NTPS, Eklahare. | 0 | - | 0 | 0.83 | 0.83 | 0 | 0 | 0 |  |  | 0 | 0
9 | Work of repairs to doors & windows of various building at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0.34 | 0.34 | 0 | 0 | 0 |  |  | 0 | 0
10 | Providing and fixing powder coated colored Zincalume profiled sheet for various building at CHP,AWR building, Time office & ODP EM at NTPS, Eklahare. | 0 | - | 0 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of external painting & internal painting at WTP, Stage-II NTPS, Eklahare. | 0 | - | 0 | 1.33 | 1.33 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of external painting & internal painting at CHP area NTPS, Eklahare. | 0 | - | 0 | 0.67 | 0.67 | 0 | 0 | 0 |  |  | 0 | 0
13 | Renovation and restructuring of shed No. 1, 2, 5, 6, 9 & 11 of major store custody of NTPS, Eklahare. | 0 | - | 0 | 3.39 | 3.39 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | As per I.B.Recommondation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of construction compound wall with concertina coil at various locations at Nashik TPS. | 0 | - | 0 | 58.87 | 58.87 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing & renovating security watch tower at NTPS Premises Eklahare. | 0 | - | 0 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | R&M/LE for Identified Thermal units of MSPGCL of (3 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL (3 x 210 MW) units of MSPGCL | 0 | - | 0 | 1180.14 | 1180.14 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | CHP Improvcement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 3 x 210 MW units | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | TATA Mini Truck SFC 709 EX No.MH-15-JV-3992 | N.A. | - | 0 | 0.32099 | 0.32099 | 0 | 0 | 0 |  |  | 0 | 0
2 | Executive chair(10),S Type Arm chai(20) | N.A. | - | 0 | 0.10784 | 0.10784 | 0 | 0 | 0 |  |  | 0 | 0
3 | Office Table and S-Type Chair with Arm | N.A. | - | 0 | 0.030968 | 0.030968 | 0 | 0 | 0 |  |  | 0 | 0
4 | Windows Slot in PC VPC 10-Intel Core 13 4th -NTC | N.A. | - | 0 | 0.010561 | 0.010561 | 0 | 0 | 0 |  |  | 0 | 0
5 | LG Screen wall mounted computer-LED display65"-NTC | N.A. | - | 0 | 5.0969 | 5.0969 | 0 | 0 | 0 |  |  | 0 | 0
6 | 20 Ton Split AC for Audtiorium -NTC | N.A. | - | 0 | 1.0873 | 1.0873 | 0 | 0 | 0 |  |  | 0 | 0
7 | Colour Laser Printer, All in one A3 LaserJet Print | N.A. | - | 0 | 1.0589 | 1.0589 | 0 | 0 | 0 |  |  | 0 | 0
8 | Digital DSLR Camera | N.A. | - | 0 | 1.0793 | 1.0793 | 0 | 0 | 0 |  |  | 0 | 0
9 | Indoor Gymnasium Equipments at NTC, Eklahare | N.A. | - | 0 | 0.02853 | 0.02853 | 0 | 0 | 0 |  |  | 0 | 0
10 | CLASS ROOM CHAIR WITH DESKLET | N.A. | - | 0 | 0.023576 | 0.023576 | 0 | 0 | 0 |  |  | 0 | 0
11 | PA System and Sport Material,Table Tannis for | N.A. | - | 0 | 0.01687 | 0.01687 | 0 | 0 | 0 |  |  | 0 | 0
12 | EXECUTIVE CHAIR WITH 5 SUPRT & S-TYPE CHAIR | N.A. | - | 0 | 0.01003 | 0.01003 | 0 | 0 | 0 |  |  | 0 | 0
13 | APPLN COOLER AIR SEMIEXH AIR COOLER ASSY | N.A. | - | 0 | 0.033896 | 0.033896 | 0 | 0 | 0 |  |  | 0 | 0
14 | FULL PAD CHAIRS WITH SIDE ARM | N.A. | - | 0 | 0.029637 | 0.029637 | 0 | 0 | 0 |  |  | 0 | 0
15 | Industrial Cabinet with 12 Lockers | N.A. | - | 0 | 0.0070163 | 0.0070163 | 0 | 0 | 0 |  |  | 0 | 0
16 | UV Water Purifier Filter | N.A. | - | 0 | 0.019116 | 0.019116 | 0 | 0 | 0 |  |  | 0 | 0
17 | FILTER RO+UV+UF+TDS WATER PURIFIER | N.A. | - | 0 | 0.032906 | 0.032906 | 0 | 0 | 0 |  |  | 0 | 0
18 | 2 Tone SPLIT AC INDOOR UNIT | N.A. | - | 0 | 0.008064 | 0.008064 | 0 | 0 | 0 |  |  | 0 | 0
19 | 1.5 TON CAPACITY SPLIT AC | N.A. | - | 0 | 0.006688 | 0.006688 | 0 | 0 | 0 |  |  | 0 | 0
20 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 1.698 | 1.698 | 0 | 0 | 0 |  |  | 0 | 0
21 | Logitech PTZ Group Camera 960-001054 | N.A. | - | 0 | 2.4375 | 2.4375 | 0 | 0 | 0 |  |  | 0 | 0
22 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011564 | 0.011564 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK BENCH WITHOUT DRAWER | 0 | - | 0 | 0.011647 | 0.011647 | 0 | 0 | 0 |  |  | 0 | 0
24 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.030075 | 0.030075 | 0 | 0 | 0 |  |  | 0 | 0
25 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011788 | 0.011788 | 0 | 0 | 0 |  |  | 0 | 0
26 | EXECUTIVE CHAIR, S-TYPE CH-7 CHAIR WITH ARM | 0 | - | 0 | 0.035229 | 0.035229 | 0 | 0 | 0 |  |  | 0 | 0
27 | SAMSUNG GALAXY TAB S3, 32GB 9.7 INCH | 0 | - | 0 | 0.003845 | 0.003845 | 0 | 0 | 0 |  |  | 0 | 0
28 | i5 Laptop - 2 Nos & i7 Laptop - 3 Nos | 0 | - | 0 | 0.037636 | 0.037636 | 0 | 0 | 0 |  |  | 0 | 0
29 | Godrej make 1.5 Ton High Wall Split AC | 0 | - | 0 | 0.020975 | 0.020975 | 0 | 0 | 0 |  |  | 0 | 0
30 | Complete Multimedia Projector with Std Accessories | 0 | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
31 | LED 40 INCH SMART TV | 0 | - | 0 | 0.0092016 | 0.0092016 | 0 | 0 | 0 |  |  | 0 | 0
32 | FULL PAD CHAIRS, EXECUTIVE CHAIR, | 0 | - | 0 | 0.068995 | 0.068995 | 0 | 0 | 0 |  |  | 0 | 0
33 | Cash Counting Machine | 0 | - | 0 | 0.001888 | 0.001888 | 0 | 0 | 0 |  |  | 0 | 0
34 | 230 V AC DIGITAL SINE WAVE INVERTER 1 No. | 0 | - | 0 | 0.010175 | 0.010175 | 0 | 0 | 0 |  |  | 0 | 0
35 | HPCV no.3 &4 Stem | 0 | - | 0 | 0.025694 | 0.025694 | 0 | 0 | 0 |  |  | 0 | 0
36 | HEAVY DUTY AIR PURIFIURE 230V,50HZ | 0 | - | 0 | 0.0105 | 0.0105 | 0 | 0 | 0 |  |  | 0 | 0
37 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.0048144 | 0.0048144 | 0 | 0 | 0 |  |  | 0 | 0
38 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.025939 | 0.025939 | 0 | 0 | 0 |  |  | 0 | 0
39 | APPLN COOLER WTR CAP CAP: 60 LITERS | 0 | - | 0 | 0.0053799 | 0.0053799 | 0 | 0 | 0 |  |  | 0 | 0
40 | LASER LASERJET PRINTER FOR A4 PAPER | 0 | - | 0 | 0.0057 | 0.0057 | 0 | 0 | 0 |  |  | 0 | 0
41 | 40 Inch Smart LED TV 3.00 | 0 | - | 0 | 0.010178 | 0.010178 | 0 | 0 | 0 |  |  | 0 | 0
42 | DESKTOP INTEL CORE I5 2300 PROCESSOR | 0 | - | 0 | 0.021459 | 0.021459 | 0 | 0 | 0 |  |  | 0 | 0
43 | ONLINE WATER HEATER, 3KW,3LTR. | 0 | - | 0 | 0.029683 | 0.029683 | 0 | 0 | 0 |  |  | 0 | 0
44 | CAMERA FOR VC, MICROPHONE WITH SPEAKER | 0 | - | 0 | 0.023889 | 0.023889 | 0 | 0 | 0 |  |  | 0 | 0
45 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
46 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 0.01873 | 0.01873 | 0 | 0 | 0 |  |  | 0 | 0
47 | Water Cooler | 0 | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
48 | PORTABLE HARD DISK USB 1TB | 0 | - | 0 | 0.0017388 | 0.0017388 | 0 | 0 | 0 |  |  | 0 | 0
49 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.00095 | 0.00095 | 0 | 0 | 0 |  |  | 0 | 0
50 | Garbox assembly for premium make type B-220 of | 0 | - | 0 | 0.44095 | 0.44095 | 0 | 0 | 0 |  |  | 0 | 0
51 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.006726 | 0.006726 | 0 | 0 | 0 |  |  | 0 | 0
52 | RO+UV+UF+TDS CAP 50 LITRE PER HOUR | 0 | - | 0 | 0.002731 | 0.002731 | 0 | 0 | 0 |  |  | 0 | 0
53 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.0025995 | 0.0025995 | 0 | 0 | 0 |  |  | 0 | 0
54 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.002183 | 0.002183 | 0 | 0 | 0 |  |  | 0 | 0
55 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0061808 | 0.0061808 | 0 | 0 | 0 |  |  | 0 | 0
56 | REGULAR CHAIR WITHOUT CUSHION | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
57 | BLDC Fans through GeM Portal and GA -2022-23 at | 0 | - | 0 | 0.0049556 | 0.0049556 | 0 | 0 | 0 |  |  | 0 | 0
58 | ALL IN ONE PC, CORE I5, 4 GB RAM, 500 GB | 0 | - | 0 | 0.02973 | 0.02973 | 0 | 0 | 0 |  |  | 0 | 0
59 | PRINTER LASER LASERJET NETWORK PRINTER | 0 | - | 0 | 0.0020024 | 0.0020024 | 0 | 0 | 0 |  |  | 0 | 0
60 | APPLN FAN AIR CEIL SIZE 1200 MM SWEEP | 0 | - | 0 | 0.033918 | 0.033918 | 0 | 0 | 0 |  |  | 0 | 0
61 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.014828 | 0.014828 | 0 | 0 | 0 |  |  | 0 | 0
62 | 400 MM, 230V, 3 BLADE DOMESTIC FAN | 0 | - | 0 | 0.0024532 | 0.0024532 | 0 | 0 | 0 |  |  | 0 | 0
63 | APPLN FAN AIR EXHAUST SIZE15"1400RPM-15 Nos | 0 | - | 0 | 0.01781 | 0.01781 | 0 | 0 | 0 |  |  | 0 | 0
64 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.013559 | 0.013559 | 0 | 0 | 0 |  |  | 0 | 0
65 | MICROWAVE OVEN CAPACITY 27 / 28 LITERS-1 Nos | 0 | - | 0 | 0.0048362 | 0.0048362 | 0 | 0 | 0 |  |  | 0 | 0
66 | REFRIGERATOR SINGLE DOOR CAPCITY 190 LTR | 0 | - | 0 | 0.0067225 | 0.0067225 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Thinclients on Buyback for NTPS | 0 | - | 0 | 0.23166 | 0.23166 | 0 | 0 | 0 |  |  | 0 | 0
68 | ABC Powder type DCP Composite Fire Extinguisher | 0 | - | 0 | 0.357 | 0.357 | 0 | 0 | 0 |  |  | 0 | 0
69 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024631 | 0.024631 | 0 | 0 | 0 |  |  | 0 | 0
70 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024213 | 0.024213 | 0 | 0 | 0 |  |  | 0 | 0
71 | Furniture Dining Table for Main Mess Hall and Cus | 0 | - | 0 | 0.019803 | 0.019803 | 0 | 0 | 0 |  |  | 0 | 0
72 | Servers for DSM at Nashik Thermal Power Station | 0 | - | 0 | 0.43559 | 0.43559 | 0 | 0 | 0 |  |  | 0 | 0
73 | DESKTOP INTEL CORE I5 2300 PROCESSOR - 5 Nos | 0 | - | 0 | 0.05632 | 0.05632 | 0 | 0 | 0 |  |  | 0 | 0
74 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.041064 | 0.041064 | 0 | 0 | 0 |  |  | 0 | 0
75 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.038246 | 0.038246 | 0 | 0 | 0 |  |  | 0 | 0
76 | APPLN TV STD ULSLIM 42" - 4 Nos | 0 | - | 0 | 0.037376 | 0.037376 | 0 | 0 | 0 |  |  | 0 | 0
77 | 1 T SPLIT AC COMPL UNIT WITH ACCESSORIES | 0 | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
78 | MULTIMEDIA PROJECTOR EPSON EB-U05-1 No | 0 | - | 0 | 0.0081606 | 0.0081606 | 0 | 0 | 0 |  |  | 0 | 0
79 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.0023246 | 0.0023246 | 0 | 0 | 0 |  |  | 0 | 0
80 | Procurement of Complete Vibrating Screen Assembly at CHP-II | 0 | - | 0 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | General Asset | 0 | - | 0 | 0.575 | 0.575 | 0 | 9.102 | 9.102 |  |  | 9.102 | 0
| Total |  |  |  | 2133.0831 | 2154.7905 | -21.7075 | 9.102 | 9.102 | 0 | 0 | 9.102 | -21.7075
FY 2029-30
0 | a) DPR Schemes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | (i) Submitted to MERC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
1.1 | Essential Works at Stage I | MERC/CAPEX /20112012/01181 | 2011-08-03 | 30.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2 | Measuring & Monitoring of Coal consumption | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 23.0165 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.1 | Belt Weighers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3295 | 0.3295 | 0.3295 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.2 | Fully automatic pit-less in motion weigh bridges | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.793 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.3 | Installation of inhaul outhaul betel chargers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 6 | 8.5943 | 8.5943 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.4 | Dust Extraction System | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 1.65 | 1.713 | 1.713 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.5 | Fogging system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 2.44 | 2.59 | 2.59 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.6 | Bunker level montoring system | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.54 | 0.0694 | 0.0694 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.7 | Rotary pneumatic or electrical hammers | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.169 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.8 | Operating the CHP near to its full capacity | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 7.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
2.9 | Motor controller | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 0.3732 | 0.3732 | 0.3732 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/01775 | 2010-12-24 | 3.4218 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
3.1 | Renovation & Modernization of Nasik U-3 | MERC/CAPEX/ 20112012/07 | 2011-04-01 | 481.46 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4 | Combustion optimization & Process improvement | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 58.7761 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.1 | Improvement in tooling techniques Power tools like cut off machines and surface grinders. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.52821 | 0.3388 | 0.3388 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.2 | Total replacement of boiler related skin insulation as well as skin cladding of furnace, Air pre heaters,air ducts and flue gas ducts Unit-4 &5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4.5892 | 4.7188 | 4.7188 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.3 | Painting of Boiler ,bunker structure and other structure.Unit-3,4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 7.775 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.4 | Dynamic coal flow measurement and control (balancing) system (one) | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 8.14 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4.5 | Retrofitting of Gas proportioning dampers, flue gas, primary and secondary air dampers. (SADC) for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.456 | 1.2566 | 1.2566 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.41356 | 0.41356 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.6 | Replacement of flue gas ducting zone prone to erosion with 6 to 8 mm high grade material & insulation of flue gas ducts. (need based depending on the deterioration) by new unbonded, felted, mineral/rock/slag wool mattresses for Unit 4 and 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.7 | Replacement of boiler outlet valves and damaged valves of units 4 & 5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.349 | 1.4313 | 1.4313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.8 | Replacement of coal pipe at direction changing sections & flow curvature zone by upgraded material. Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 2.3292 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.9 | Installation of Smart soot blower system for Unit- 4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 5.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.10 | Installation of Sonic soot blowers for second pass for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.83184 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.11 | Air pre heater upgradation of heat exchanger matrix &regenerative dynamic sealing for Unit-4,5 | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
4.12 | Replacement Platen water wall for Unit-3. | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 0.60762 | 0.6964 | 0.6964 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20102011/01756 | 2010-12-22 | 13.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5 | Turbine Auxiliary Consumption Improvement | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 39.2903 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.1 | Installation of Turbo vaned fly wheeling eco ventilators to all Units 3, 4, 5. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.09 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.2 | Replacement of selected old brass impellers of pumps with SS304 impellers. H.T. Auxiliary C.W. Pump and G.S. Water Pumps are selected. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.4 | 0.8251 | 0.8251 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.3 | Improving the BFP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.75 | 0.48804 | 0.48804 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.4 | Replacement of BFP (200 KHI) cartridge with energy efficient cartridge. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 14.4456 | 13.85 | 13.85 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.5 | Improving the CEP efficiency by replacing eroded internals of pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.9 | 0.6018 | 0.6018 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.6 | Replacement of CEP with energy efficient pump. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.7 | Replacement of Pumps - GS Pumps, H2Cooler booster pump, DM/DM pumps, DM Makeup pumps, Emergency lift pumps, Drip pumps, BFP Booster pumps with energy efficient pumps. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 4.2733 | 2.3608 | 2.3608 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.8 | Replacement of valves – MS - 3 to 8 , HD – 22,23,24 , MC- 36 , ES 3,4 and BFP Recirculation Valves. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.0852 | 1.3148 | 1.3148 | 0 | 0 | 0 |  |  | 0 | 0
5.9 | Replacement of tube nest of LP Heater no.3 of unit no.3, LP Heater no.4 of unit no.5, Main ejector 3B, GC2 of unit no.5, Seal oil coolers, H2 Coolers, BFP working and lub oil coolers, DM/GS plate type coolers. | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 6.5962 | 1.9594 | 1.9594 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.11461 | 0.11461 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
5.10 | Steam path audit of Unit no,4,5 | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 0.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20112012/00024 | 2011-04-05 | 3.55 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6 | EMS, Numeric relays, Microprocessor DVR & VFD | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 12.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
6.1 | Design, manufacture, supply, erection, commissioning & testing of Variable Frequency Drives (VFD) with latest design and technology super premium efficiency motors for 415 V LT Auxiliaries (Total 50 No) of 210 MW Unit 3, 4 & 5. | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 6.3 | 8.8183 | 6.2927 | 2.5255 | 0 | 0 |  |  | 0 | 2.5255 | 0 | 0
0 | IDC | 0 | - | 0.66 | 0.74645 | 0.74645 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.2 | Replacement of old EE make Generator Protection Relays with Numerical Generator Protection Relays for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 1.7 | 1.7029 | 1.7029 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.3 | Replacement of old AVR with Microprocessor based Digital Voltage Regulator for unit no. 3 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 2.44 | 1.7055 | 1.7055 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
6.4 | Installation and commissioning of Energy Management System for unit no. 3, 4 & 5 | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.81 | 0.8313 | 0.8313 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH-1/CAPEX/ 20132014/02001 | 2014-01-17 | 0.66 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
7.1 | Construction of Concrete road from Nashik-Pune Highway to Booster Pump House | MERC/CAPEX/ 20122013/00149 | 2012-05-30 | 11.95 | 14.5069 | 14.5069 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
8.1 | Renovation of Rail System | MERC/CAPEX/ 20112012/02118 | 2012-12-21 | 57.915 | 57.9147 | 57.9147 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9 | Faster unloading of coal wagons by upgrading existing system (Post Facto) | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 18.8481 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.1 | Re-design, Supply, Erection and commissioning of modified Apron Feeder. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.7219 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.2 | Design, manufacture, supply, erection and commissioning of modified bunker outlet cone of Unit 3, 4 and 5. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.3295 | 2.3196 | 2.3196 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.3 | Design, manufacture, Supply & Erection Of Components Suitable For Modification Of Wagon Tipplers to Handle BOXNHL , BOX-H,BOX-NR,BOX-NJLSR1 & 25 T AXLE WAGONS | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 5.1298 | 4.413 | 4.413 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.4 | Procurement of SAN Loco - 650-700 HP. | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8627 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
9.5 | Revamping of CHP II Wagon Tippler by replacing the Split Wheel Assembly, Pawl Lever, Pinion Shaft Assembly, Toe, Spur Gear Shaft, W.T Drive Assembly, Rack Segment, Rail Table Assembly Of Wagon Tippler and Dismantling & Replacement of above parts | MERC/TECH 1/ CAPEX/20122013/ 1367 | 2013-10-04 | 2.8042 | 2.81 | 2.81 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10 | Procurement of 6.6 Kv HT motors as spare motors /for replacement | MERC/CAPEX/20152016/00422 | 2016-08-03 | 14.3563 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.1 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3125 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.2 | ID FAN MOTOR (1700 kW) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.1025 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.3 | FD FAN MOTOR 650 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.7875 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.4 | FD FAN MOTOR 750 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8505 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.5 | PA FAN MOTOR 1250 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.029 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.6 | BFP MOTOR 4000 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 4.5528 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.7 | C/MILL MOTOR 320 kW (3 Nos) | MERC/CAPEX/20152016/00422 | 2016-08-03 | 1.3356 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.8 | SOP MOTOR 200 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2276 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.9 | CWP MOTOR 950 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8942 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.10 | CTLP MOTOR 710 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.8081 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.11 | RWP MOTOR 335 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.4861 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.12 | HP PUMP MOTOR 258 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3083 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.13 | CEP MOTOR 220 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.2629 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.14 | GS PUMP MOTOR 260 kW | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.3107 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
10.15 | Testing charges | MERC/CAPEX/20152016/00422 | 2016-08-03 | 0.088 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11 | Replacement of complete LTSH coils at Unit-3 Boiler & Economiser coils at Unit-5 Boiler | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 27.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.1 | Complete Supply & Erection of LTSH coils at Unit-3 210 MW Boiler (67 nos. upper and lower modules each. 01 module = 02 coils) | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 16.43 | 4.6378 | 4.6378 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
11.2 | Complete Supply & Erection of 270 nos. Economizer coils in second pass of Unit-5 210 MW Boiler at Nasik TPS. | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 9.57 | 3.0104 | 3.0104 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015 /007 | 2014-10-16 | 1.44 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12 | Enhancement of performance & life of Coal Handling plant | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 17.52 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.1 | Procurement of 02 nos of 320 hp bull dozers for Nasik TPS | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 3.2 | 4.2044 | 4.2044 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.2 | Procurement of gear box for Apron Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 1.59 | 1.6043 | 1.6043 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.3 | Procurement of gear box and 30 KW DC motor for Pedal Feeder in CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.46 | 0.45847 | 0.45847 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.4 | Procurement of Assembly of Impact Crusher Complete set, with Rotor Assembly and bearing Block. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 2.3 | 2.3366 | 2.3366 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.5 | Procurement of 10 KW Inline Magnetic Separator for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.4 | 0.54718 | 0.54718 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.6 | Restoration of RBCR by replacing feed end Spider (Drg. No. 400-1428-01/A) & Discharge end Spider (400-1428-02) suitable to rotary Bradford breaker machine No.CR/634 along with support wheels. | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 8.14 | 10.2287 | 10.2287 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.7 | Procurement of 750 KW Impactor Motor for CHP III | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.49 | 0.22635 | 0.22635 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
12.8 | Supply of Metal Detectors for CHP | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.14 | 0.09152 | 0.09152 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/TECH 1/ CAPEX/20142015/ 01639 | 2015-02-23 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13 | Retrofitting of 6.6 kV Breakers, Battery Replacement, System Improvement & MPCB Related schemes | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 14.7811 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.1 | Retrofitting of 6.6 kV HT MOCB/SF6 Breakers by VCB | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 3.57 | 5.0621 | 5.0621 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2a | A) Procurement & Replacement of 220V/ 1285 AH Battery set for U#3 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0493 | 1.0493 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.2b | B) Procurement & Replacement of 220V/ 1285 AH Battery set for U#4 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.11 | 1.0047 | 1.0047 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.3 | O2 Measurement System in the furnace & flue gas ducting | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.17 | 1.2966 | 1.2966 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.4 | Supply, erection, commissioning & testing of online CO, SO2, NOX Analyser for U#3/4/5 | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.6511 | 1.6846 | 1.6846 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.5 | A) Replacement of static Flame Monitoring System with Microprocessor based Flame Monitoring & Analyzing System | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 2.27 | 2.4267 | 2.4267 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
13.6 | CAAQMS monitoring of ambient air quality around the NTPS. | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1 | 0.81676 | 0.81676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01266 | 2014-12-03 | 1.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14 | 3rd raising of Ash bund | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 13.9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
14.1 | 3rd raising of ash bund from TBL 581.50 to 586.50m in valley No. 4A at Nashik Thermal Power Station, Eklahare | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 12.3 | 10.2142 | 10.2142 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/MSPGCL/ CAPEX/2014-15/01282 | 2014-12-08 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15 | System Rehabilitation & Upgradation at Nasik TPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 13.3722 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
15.1 | Shifting, Transportation & Replacement of Existing Generator Stator of Unit no.3 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 7.98 | 0.8767 | 5.8767 | -5 | 0 | 0 |  |  | 0 | -5 | 0 | 0
0 | IDC | 0 | - | 0 | 0.26397 | 0.26397 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.2 | Turbine Supervisory Instrumentation System for Unit no.5 | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.5542 | 0.45436 | 0.45436 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.3 | Supply of Air Compressors for NTPS | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 3.398 | 3.8197 | 3.8197 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
15.4 | Replacement of Old Brass Impellers of CTLP with SS Impellers. | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 1.04 | 1.1331 | 1.1331 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4153 | 2017-08-31 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16 | Up-gradation of DCS at U # 3 and New Rectiformers & ESP Refurbishment of U # 4 & 5 at Nasik TPS | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 33.8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.1 | Decommissioning & Shifting of M/s ABB make DCS system at BTPS Unit # 2 & Re-commissioning with Up gradation to Symphony Plus at NTPS Unit #3, Nasik. | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 9.27 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
16.2 | Erection ,Testing & commissioning, Supply of rectiformer HVR 37/800 Hermatically sealed Rectiformer ( DC Peak voltage – 70 kV , Average voltage-45 KV ,DC Current – 800 milli amp , AC I/P – 1 Phase , 415 V ) | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 10.34 | 0 | 13 | -13 | 0 | 0 |  |  | 0 | -13 | 0 | 0
16.3 | Refurbishment of ESP for Unit No. 4 & 5 at Nashik TPS, Eklahare | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 12.5 | 12.8553 | 12.8553 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4791 | 2017-11-28 | 1.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17 | Replacement of drum gate, augmentation of existing ash water recovery scheme and construction of concrete road for Nasik Thermal Power Station | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 14.5161 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.1 | Replacement of drum gate and restructuring of cofferdam, repairs to vertical sluice gate, Approach Bridge and allied civil works at Godavari barrage at Nashik TPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 6.273 | 3 | 6.27 | -3.27 | 0 | 0 |  |  | 0 | -3.27
17.2 | Augmentation of existing ash water recovery scheme and connecting overflow of waste weir to existing toe drain of ash bund valley no.4 to WWR at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 2.5999 | 3.1676 | 3.1676 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2441 | 0.2441 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
17.3 | Up gradation of fly ash concrete road from Booster Pump house toward Hydrogen plant, Dirk India Company towards Hinganwedhe along ash bund valley No. 1 & 2, Ash bund approach road for ash transportation and abundant valley towards Kotamgaon road at NTPS Eklahare. | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 5.3732 | 5.3752 | 5.3752 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/ 20172018/4753 | 2017-11-22 | 0.27 | 0.38455 | 0.38455 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18 | Various DPR Schemes for Renovation of colony at NTPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 10.8678 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
18.1 | Renovation of staff quarters, playground, Jogging track & Gymnasium at NTPS colony, Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 4.071 | 3.5306 | 3.5306 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.92832 | 0.92832 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.2 | Road works in NTPS Colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 3.9766 | 3.8972 | 3.8972 | 0 | 0 | 0 |  |  | 0 | 0
18.3 | Water supply and sanitation works at NTPS colony Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 2.8202 | 1.4586 | 1.4586 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.19994 | 0.19994 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
18.4 | Renovation of Workers Recreation Club at Nashik TPS Eklahare | MERC/CAPEX/ 20182019/0645 | 2018-05-18 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19 | Life enhancement of stacker cum reclaimer machine in CHP & upgradation of SWAS laboratory at Nasik TPS | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 14.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.1 | Supply, Erection & installation of sole plates, Rail track & Hydraulic cylinder of the Stacker cum Reclaimer machine at Coal Handling Plant-II Nashik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 6.58 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
19.2 | Procurement and replacement of 220 V, 1285 AH battery set for Unit No. 4 at Nasik Thermal Power Station. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 1.39 | 1.4116 | 1.4116 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.2227 | 0.2227 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.3 | Supply of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers Ltd.) at Nasik TPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 3.11 | 3.0812 | 3.0812 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
19.4 | Erection and commissioning of Steam and Water sampling system for SWAS Lab at WTP, NTPS. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 2.23 | 0 | 3 | -3 | 0 | 0 |  |  | 0 | -3 | 0 | 0
19.5 | Procurement of 3 nos. of Ash Slurry Disposal pump Type D - 85 for Ash Slurry Pump House of Unit no. 3, 4 & 5 at NTPSEklahare. | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.55 | 0.55578 | 0.51878 | 0.037 | 0 | 0 |  |  | 0 | 0.037 | 0 | 0
0 | IDC | MERC/CAPEX/2019-2020/0505 | 2019-08-06 | 0.34 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20 | Flue Gas Desulphurization (FGD) System at 10 Nos. of 210 MW Units at Chandrapur, Koradi, Khaperkheda & Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
20.1 | Flue Gas Desulphurization (FGD) System at Nasik TPS | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | Yet to be approved | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2 | Ash Augmentation System at Nasik & Koradi Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 2.1 | Ash Augmentation System at Nasik Thermal Power Station | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 18.03 | 5.71 | 5.71 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAP/DPR/10/08/537 | 2008-03-04 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 3.1 | Spare One set of fully bladed L.P. Turbine Rotor for 15 Nos. of 200/210 MW LMZ TG sets | MERC/CAPEX/20112012/00424 | 2011-05-19 | 11.4985 | 8.47 | 8.47 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 6 | Supply, Installation, Commissioning and Operation & Maintenance Services of Continuous Ambient Air Quality Monitoring Stations (CAAQMS) at various TPS | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 6.2 | NASIK TPS (U-3 to 5) (1 Nos.) | MERC/CAPEX/20162017/00423 | 2016-08-03 | 2.6515 | 2.8842 | 2.8842 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | 0 | - | 0 | 0.76776 | 0.76776 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7 | Installation of Real Time Online Coal-Ash Analyzer at various TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 7.2 | Nashik TPS | MERC/CAPEX/20162017/00774 | 2016-09-30 | 3.0414 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8 | Replacement of Fire Tenders at Various Power Stations of Mahagenco | MERC/CAPEX/20172018/4653 | 2017-11-13 | 2.7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.1 | Advance Multipurpose Fire Tender for Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.45 | 1.7765 | 1.7765 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 8.2 | Normal Multipurpose Fire Tender Nashik | MERC/CAPEX/20172018/4653 | 2017-11-13 | 1.25 | 2.2272 | 2.2272 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | IDC | MERC/CAPEX/20172018/4653 | 2017-11-13 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10 | Implementation of IB recommendations- Civil works at various TPS of Mahagenco | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 10.2a | TPS Nashik | MERC/CAPEX/20172018/0177 | 2018-02-06 | 2.478 | 2.3118 | 2.3118 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15 | Procurement & Replacement of Complete Sets of Air Pre-heater Baskets at Nashik, Parli & Chandrapur TPS of Mahagenco | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
HO DPR 15.1 | Procurement and Replacement of Complete sets of assembly of baskets for air preheater of type tri-sector APH 27 VI(T) 74” in NTPS unit no. 4 & 5 (210MW). (2 Sets Per Unit) | MERC/CAPEX/2019-2020/643 | 2019-08-26 | 4.22 | 5.5929 | 5.5929 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0.13531 | 0.13531 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 16.1 | Construction of new Administrative Building for Mahagenco at Vidyut Bhawan, Katol Road, Nagpur | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 54.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/2021-2022/MSPGCL/063 | 2022-02-12 | 2.76 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 69.309 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
HO DPR 17.1 | Centralized Monitoring Solution | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 66.009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | MERC/CAPEX/MSPGCL/2023-24/0576 | 2023-11-02 | 3.3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | (ii) Yet to be submitted to MERC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | <DPR Name> | N.A. | N.A. | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Complete Replacement of HRH Coils, LTSH Coils, Economizer Coils at Unit No. 4 & Complete Replacement of Economizer coils at Unit No.3 Nashik TPS 210 MW Boilers | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete Replacement HRH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 8.551 | 8.551 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete Replacement LTSH Coils at NTPS Unit No. 4 Boiler | 0 | - | 0 | 12.6608 | 12.6608 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete Replacement Economiser Coils at NTPS Unit No. 3 & 4 Boilers | 0 | - | 0 | 16.0672 | 16.0672 | 0 | 0 | 0 |  |  | 0 | 0
0 | IDC | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 and Commissioning of AFGC system for Unit No. 3, 4 & 5 and Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5 at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply of MSERW pipes for Replacement of various pipelines & structure strengthening at ODP & WTP area of Unit No. 3, 4 & 5 at NTPS, Eklahare | 0 | - | 0 | 19.6769 | 19.6769 | 0 | 0 | 0 |  |  | 0 | 0
2 | Supply, erection, commissioning & testing of Ammonia Flue gas Conditioning system for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 3.9046 | 3.9046 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotary Electronic Control Drive for ID, FD, PA IGV at Unit No.4 & 5, 210 MW, NTPS, Eklahare, Nasik. | 0 | - | 0 | 2.9741 | 2.9741 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Complete replacement of Platen Superheater coils at Unit No.3,4 & 5 ; Complete replacement of HRH coils at Unit No.3,& 5; Complete replacement of LTSH coils at Unit No. 5;Replacement of thermal insulation at Boiler for Nashik TPS 210 MW boilers | 0 | - | 0 | 1.39 | 1.39 | 0 | 0 | 0 |  |  | 0 | 0
1 | Complete replacement of Platen Superheater coils at Unit No. 3,4 & 5 | 0 | - | 0 | 18.311 | 18.311 | 0 | 0 | 0 |  |  | 0 | 0
2 | Complete replacement of HRH coils at Unit No.3,& 5 | 0 | - | 0 | 17.302 | 17.302 | 0 | 0 | 0 |  |  | 0 | 0
3 | Complete replacement of LTSH coils at Unit No.5 | 0 | - | 0 | 13.3898 | 13.3898 | 0 | 0 | 0 |  |  | 0 | 0
4 | Replacement of thermal insulation of Boiler, Ducts & Steam Pipelines at Unit No.3,4 & 5 | 0 | - | 0 | 6.897 | 6.897 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | Procurement of various pumps for TM & ODP | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement and Erection Commissioning of Condenser vacuum pump for Unit No. 3 ,4 & 5 at Nashik TPS, Eklahare | 0 | - | 0 | 29.24 | 29.24 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of Three Pump assemblies of SAM TURBO makes Type 150/500 N for Booster Pump house at NTPS Eklahare. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of 3 Nos Vertical Fly Ash Transfer Pump VO 150 /400 + ARS SAM make along with motor for ESP Hopper evacuation of Unit No.3,4 & 5 at NTPS Eklahare | 0 | - | 0 | 0.79 | 0.79 | 0 | 0 | 0 |  |  | 0 | 0
4 | Supply, erection, installation, civil foundation, commissioning, testing & trial of Rotating &casing assembly of pumps for WTP at Nashik TPS, Eklahare | 0 | - | 0 | 1.6 | 1.6 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement (10 nos.) of CWFW pumps (with motor) at Stage-II (Beacon make) | 0 | - | 0 | 0.94 | 0.94 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of RWP Pump assembly at NTPS. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of Cooling Tower lift Pump Impeller for Jyoti make pump Type:-1200- VMI A 12 at NTPS Eklahare | 0 | - | 0 | 1.07 | 1.07 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Degasser Pump assembly with motor (06 Nos.) | 0 | - | 0 | 0.354 | 0.354 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 8 Nos. of Domestic water pumps (with motor) & Darna drinking water pump at Stage-I & II | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of 4 Nos. of DM backwash (2 Nos.) & CW backwash pump (2 Nos.)(with motor)at NTPS. | 0 | - | 0 | 0.36 | 0.36 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of HP Pumps at NTPS. | 0 | - | 0 | 1.18 | 1.18 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of ETP pump assembly (06 Nos.) | 0 | - | 0 | 1.42 | 1.42 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of RWP shaft with bearing, Impeller (02 Nos.) | 0 | - | 0 | 1.68 | 1.68 | 0 | 0 | 0 |  |  | 0 | 0
14 | Procurement of AWR pump (02 Nos.) | 0 | - | 0 | 0.47 | 0.47 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Submersible Slurry Pumps for handling Ash water / Clear water for dewatering at various locations at NTPS (10 Nos.) | 0 | - | 0 | 0.885 | 0.885 | 0 | 0 | 0 |  |  | 0 | 0
DPR 5 | Renovation of Compressed Air Refrigerated Dryer System, Refurbishment of Centralized Air Conditioning system, Supply, erection & commissioning of Condensate Extraction Pump, Procurement of CW Pump and GS pump | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Renovation of Compressed Air Refrigerated Dryer System for Nashik TPS, 210 MW Unit No. 3, 4 & 5 | 0 | - | 0 | 11.3737 | 11.3737 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of Centralized Air Conditioning system of Unit No. 3, 4 & 5 at Nashik TPS, Eklahare. | 0 | - | 0 | 8.15 | 8.15 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Condensate Extraction Pump complete assembly at 3 X 210 MW, TM-II (Model- BHRC-28, make- Kirloskar Brothers ltd. at Nasik TPS. Total Qty. 02 Nos. | 0 | - | 0 | 3.93 | 3.93 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of CW & CTLP Pump total 4 No.s | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
5 | Procurement of GS Pump assembly .Total qty- 3 No | 0 | - | 0 | 1.373 | 1.373 | 0 | 0 | 0 |  |  | 0 | 0
DPR 6 | Procurement of oil free Rotary Screw Compressors and BFP cartridge | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of BFP cartridge | 0 | - | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 0 | 0
2 | Procurement of oil free rotary screw compressors | 0 | - | 0 | 21.6648 | 21.6648 | 0 | 0 | 0 |  |  | 0 | 0
DPR 7 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets, Refurbishment of HPT rotor along with supply, Procurement of HP & IP control valve with cam shaft assemblies, Procurement of complete governing system assembly, Supply, Errection & Commissioning of COP assembly, Procurement of Condenser tubes & ODP related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, erection & commissioning of Cummins make Diesel Engine powered Generator Sets at 3 x 210 MW, TM-II NTPS. | 0 | - | 0 | 0.63 | 0.63 | 0 | 0 | 0 |  |  | 0 | 0
2 | Refurbishment of HPT rotor along with supply. | 0 | - | 0 | 3.7908 | 3.7908 | 0 | 0 | 0 |  |  | 0 | 0
3 | Procurement of HP & IP control valve with cam shaft assemblies.qty-1set | 0 | - | 0 | 0.81 | 0.81 | 0 | 0 | 0 |  |  | 0 | 0
4 | Procurement of complete governing system assembly. qty-1 set | 0 | - | 0 | 0.27563 | 0.27563 | 0 | 0 | 0 |  |  | 0 | 0
5 | Supply, Errection & Commissioning of COP assembly.Total Qty.- 3 Nos. | 0 | - | 0 | 0.9642 | 0.9642 | 0 | 0 | 0 |  |  | 0 | 0
6 | Procurement of Condenser tubes for Unit No.3, 4 & 5.Total Qty:15700 tubes | 0 | - | 0 | 20.27 | 20.27 | 0 | 0 | 0 |  |  | 0 | 0
7 | Procurement of CT Fan Blade assembly & shaft- 36 nos for Unit No.3,4 & 5 at NTPS, Eklahare | 0 | - | 0 | 1.3 | 1.3 | 0 | 0 | 0 |  |  | 0 | 0
8 | Procurement of Gearbox Assembly for Cooling Tower Fans type B-220 Premium make for Unit No. 3, 4 & 5 at Nashik TPS, Eklahare (Qty-24) | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
9 | Procurement of 5 nos. of Air Blowers for Degasser system | 0 | - | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  |  | 0 | 0
10 | Procurement of Flocculator gearbox- 12 Nos. | 0 | - | 0 | 0.4 | 0.4 | 0 | 0 | 0 |  |  | 0 | 0
11 | Procurement of 4 Nos. of Clinker grinder assembly at NTPS Eklahare | 0 | - | 0 | 0.65 | 0.65 | 0 | 0 | 0 |  |  | 0 | 0
12 | Procurement of 4 Nos. of Clinker grinder gearbox at NTPS Eklahare | 0 | - | 0 | 0.2 | 0.2 | 0 | 0 | 0 |  |  | 0 | 0
13 | Procurement of 5 Nos. of Air Blowers for Degasser system | 0 | - | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  |  | 0 | 0
14 | Augmentattion of existing Ash Water recovery Scheme(WWR,AWR, ETP-I,ETP-II & Phase-II pump assembly) | 0 | - | 0 | 2.97 | 2.97 | 0 | 0 | 0 |  |  | 0 | 0
15 | Procurement of Feed Gate Housing (08 Nos.) | 0 | - | 0 | 0.57 | 0.57 | 0 | 0 | 0 |  |  | 0 | 0
DPR 8 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area & Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement of HT breaker of Unit No. 4 & 5 outdoor plant and CHP area. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
2 | Retrofitting of LT breakers at various LT boards at NTPS | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
DPR 9 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS , Replacement of LT energy efficient motor | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Supply, commissioning & testing of Variable Frequency drive (VFD) to 6.6KV, 220KW Condenser Extraction Pump (CEP) / GS Pump of Unit No.3,4 & 5 at NTPS. | 0 | - | 0 | 20 | 20 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of LT energy efficient motor | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
DPR 10 | Upgradation of various electrical related schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Procurement of 6.6KV HT motors and spares at Nashik TPS Unit No 3,4 & 5. | 0 | - | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement of Boiler and turbine house lighting of Unit No.3,4 & 5 along with removal of old wiring. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
3 | Replacemet of IPH transformer 11KV/6.6 KV and lighting and welding transformer at NTPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
4 | Excitation Transformer at Unit No. 3, 4 & 5 | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
5 | GTR /UAT/ station transformer spares LV bushings replacement, HV bushings (spare)-3nos, LV busbar, palm joint both station transformers bushings at Unit No.3, 4 & 5 | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of overhead conductor HT/LT by underground HT/LT cable in Colony area. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
7 | LT transformer procurement/ rewinding work at NTPS | 0 | - | 0 | 3 | 3 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
8 | LT MCC panel modification at ODP area NTPS | 0 | - | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 0 | 0
9 | Battery Charger-220V,50V,380V UPS, 24V,DG set EMF panel with charger replacement, UPS battery replacement, Unit No. 5 station battery replacement,50 V battery set replacement at Unit No.3, 4 & 5 | 0 | - | 0 | 4.5 | 4.5 | 0 | 0 | 0 |  |  | 0 | 0
10 | Replacement of HT motor Cables. (Old PILC Cable replacement with XLPE Cable) at Unit No.3, 4 & 5 & ODP area | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
11 | Unit No. 4 Field Breaker | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
DPR 11 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Retrofitting and upgradation of old C&I system of Unit No.3 & Unit No.5 into DCS at Nashik Thermal power plant,Nashik. | 0 | - | 0 | 40 | 40 | 0 | 0 | 0 |  |  | 0 | 0
DPR 12 | Replacement/Upgradation of C&I old systems at Nashik TPS | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Replacement/Upgradation of Unit No.4 DVR System. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
2 | Replacement/Upgradation of Unit No.4 UPS System. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply of Beck Rotory Electronic Control Drive for Burner Tilt and Auxiliary Air Damper at Unit No. 3, 4 & 5 210 MW, NTPS, Eklahare Nashik. | 0 | - | 0 | 7.93 | 7.93 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification/Upgradation of Turbovisory system of Unit No. 3,4 & 5. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
5 | Auxiliary air dampers & BT, HAD, feed gate replacement/modification work. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
6 | Upgradation of Unit No.4 DCS-FCS 102 to FCS 106 (Total 5 Nos.) | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
7 | New sewage treatment plant required at NTPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
8 | Upgradation of Unit No.4 230 V UPS and new UPS, charger for Unit No. 3 & 5 DCS at NTPS. | 0 | - | 0 | 4 | 4 | 0 | 0 | 0 |  |  | 0 | 0
9 | ESP hopper high & low level indicator mounting in Unit No.3,4& 5. | 0 | - | 0 | 6 | 6 | 0 | 0 | 0 |  |  | 0 | 0
10 | OCEMS for Sox, Nox, opacity monitoring system upgradation work for Unit No.3, 4 & 5 at NTPS. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
11 | Supply, Erection, Commissioning & Testing of online H2 purity meter and Resistivity meter for Unit No. 5. | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply, Erection, commissioning of Hydra step system for Drum level control Unit No.3. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
13 | HPLP - Servo Spares | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
14 | Replacement of Relays and Energy meter at NTPS, Nashik. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
15 | ESP upgradation for Unit No. 3, 4 & 5. | 0 | - | 0 | 5 | 5 | 0 | 0 | 0 |  |  | 0 | 0
16 | Grounding Brush Monitoring System for Unit No. 3,4& 5. | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
17 | Implementationof FGMO | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
DPR 13 | Modification & replacement of various CHP schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Modification of single stream conveyor belt Gearboxes with new design Helical Bevel type Gearboxes at CHP-II NTPS | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
2 | Modification of Primary Vibrating screen at CHP-II, NTPS | 0 | - | 0 | 0.7 | 0.7 | 0 | 0 | 0 |  |  | 0 | 0
3 | Supply, erection & commissioning of Rail table alongwith weighment frame for rotaside Wagon Tippler at CHP-II, NTPS | 0 | - | 0 | 1.2 | 1.2 | 0 | 0 | 0 |  |  | 0 | 0
4 | Modification of Conveyor Drive system with Motorised Pulley drive system at CHP-II, NTPS. | 0 | - | 0 | 2 | 2 | 0 | 0 | 0 |  |  | 0 | 0
5 | Replacement of old damaged RBCR rail beam M/c No. CR/964 & screen to increase life of RBCR n reduced direct impact of raw coal on secondary impact crusher. | 0 | - | 0 | 5.09 | 5.09 | 0 | 0 | 0 |  |  | 0 | 0
6 | Replacement of copmlete crusher unit as per Drg. No. P00304/0 CO/1050 CR635-636(impact crusher body & rotor shaft assembly) 2 Nos | 0 | - | 0 | 6.4 | 6.4 | 0 | 0 | 0 |  |  | 0 | 0
7 | Replacement of appron feeder head shaft assembly-25/005 drg no.-M15076/2 & tail shaft assembly-25/006 Drg. No.- M15065/2 | 0 | - | 0 | 1 | 1 | 0 | 0 | 0 |  |  | 0 | 0
8 | Supply & erection of wagon tippler rail table Drg. No.12578/45-01 , tippler support roller & bogei Drg. No-12616/45-2M | 0 | - | 0 | 1.9 | 1.9 | 0 | 0 | 0 |  |  | 0 | 0
9 | Supply of seondary crusher motors 6.6KV, 750KW & 220KW motor for CHP | 0 | - | 0 | 0.6 | 0.6 | 0 | 0 | 0 |  |  | 0 | 0
10 | Supply of LT motors for various conveyor belts of CHP | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
11 | Up-gradation of existing DC drive system of Wagon Tippler & Paddle feeder with new version DIGICON make system along with supply, installtion, commissioning & testing of DC drives at CHP-III. | 0 | - | 0 | 0.8 | 0.8 | 0 | 0 | 0 |  |  | 0 | 0
12 | Supply of Variable Frequency drives for Conv.16C2 at CHP-III. | 0 | - | 0 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 0 | 0
13 | Up-gradation of existing relay panel of control room with microprocessor based PLC logic system along with supply, installtion, commissioning & testing of relay panel at CHP. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
14 | Supply of Magnetic seperators & Metal detectors at CHP | 0 | - | 0 | 3 | 3 | 0 | 0 | 0 |  |  | 0 | 0
0 | Civil Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | Repair & renovation of NTPS colony ,Repairing work of ash bund side & Eklahare barrage | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of renovation of various residential quarters by providing and fixing kitchen sink, kitchen trolley & granite otta at NTPS Colony Eklahare. | 0 | - | 0 | 1.5 | 1.5 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing and applying external painting to various types residential buildings at NTPS colony Eklahare. | 0 | - | 0 | 1.81 | 1.81 | 0 | 0 | 0 |  |  | 0 | 0
3 | Providing and applying internal painting to various types of residential quarters at NTPS Colony Eklahare. | 0 | - | 0 | 1.61 | 1.61 | 0 | 0 | 0 |  |  | 0 | 0
4 | Providing and fixing vitrified tiles to various types of residnetial buildings at NTPS Colony Eklahare. | 0 | - | 0 | 5.4 | 5.4 | 0 | 0 | 0 |  |  | 0 | 0
5 | Structural strengthening works to various residential quarters at NTPS colony Eklahare. | 0 | - | 0 | 5.9 | 5.9 | 0 | 0 | 0 |  |  | 0 | 0
6 | Providing and fixing colour coated galvanised iron sheets for roofing at various residential buildings at NTPS Colony Eklahare. | 0 | - | 0 | 7.93 | 7.93 | 0 | 0 | 0 |  |  | 0 | 0
7 | Sewer line repair of various quarters at NTPS Eklahare | 0 | - | 0 | 3.8 | 3.8 | 0 | 0 | 0 |  |  | 0 | 0
8 | Stair case repairing of various building at NTPS Eklahare | 0 | - | 0 | 0.65 | 0.65 | 0 | 0 | 0 |  |  | 0 | 0
9 | Construction of WBM road over/at the top of ash bund at NTPS Eklahare. | 0 | - | 0 | 0.59 | 0.59 | 0 | 0 | 0 |  |  | 0 | 0
10 | Repairs to filters of drain well No.4 and other allied works at ash bund valley No.4A at NTPS Eklahare. | 0 | - | 0 | 0.57 | 0.57 | 0 | 0 | 0 |  |  | 0 | 0
11 | Repairs to Godavari river barrage gates and allied works at NTPS, Eklahare. | 0 | - | 0 | 0.59 | 0.59 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | Structural repairs of Cooling Tower | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repairs of cooling tower components at Unit No. 3A, 3B, 4A, 4B,5A & 5B, Stage-II NTPS Eklahare. | 0 | - | 0 | 38.54 | 38.54 | 0 | 0 | 0 |  |  | 0 | 0
DPR 3 | Structural repair & rehabilitation and Renovation and modification work at NTPS Plant | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Structural repair & rehabilitation of various machine foundations of ID, FD & PA fans for Unit No. 3, 4, 5 at Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0.36 | 0.36 | 0 | 0 | 0 |  |  | 0 | 0
2 | Work of removing and providing 24 B.W.G.for pent house side & roof at Unit No. 3,4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 2.48 | 2.48 | 0 | 0 | 0 |  |  | 0 | 0
3 | Work of removing and providing old damaged siporex wall and poly coated sheet for 28 mtr. height at Unit No. 3, 4 & 5 Stage-II NTPS, Eklahare. | 0 | - | 0 | 1.8 | 1.8 | 0 | 0 | 0 |  |  | 0 | 0
4 | Structural repairs of chimney at Unit No. 3,4 & 5 Stage-II, NTPS, Eklahare. | 0 | - | 0 | 4.32 | 4.32 | 0 | 0 | 0 |  |  | 0 | 0
5 | Renovation of sump No. 2,3,4,5,6 and 7 at WTP Stage-II, NTPS Eklahare. | 0 | - | 0 | 2.36 | 2.36 | 0 | 0 | 0 |  |  | 0 | 0
6 | Work of structural repairing at CHP-I,II & III area at NTPS, Eklahare. | 0 | - | 0 | 1.09 | 1.09 | 0 | 0 | 0 |  |  | 0 | 0
7 | Work of structural repairing at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 8.1 | 8.1 | 0 | 0 | 0 |  |  | 0 | 0
8 | Work of structural repair of GS pump Unit No. 3,4,& 5 and fire fighting pump house at Stage-II,NTPS, Eklahare. | 0 | - | 0 | 0.83 | 0.83 | 0 | 0 | 0 |  |  | 0 | 0
9 | Work of repairs to doors & windows of various building at WTP, Stage-II, NTPS, Eklahare. | 0 | - | 0 | 0.34 | 0.34 | 0 | 0 | 0 |  |  | 0 | 0
10 | Providing and fixing powder coated colored Zincalume profiled sheet for various building at CHP,AWR building, Time office & ODP EM at NTPS, Eklahare. | 0 | - | 0 | 3.89 | 3.89 | 0 | 0 | 0 |  |  | 0 | 0
11 | Work of external painting & internal painting at WTP, Stage-II NTPS, Eklahare. | 0 | - | 0 | 1.33 | 1.33 | 0 | 0 | 0 |  |  | 0 | 0
12 | Work of external painting & internal painting at CHP area NTPS, Eklahare. | 0 | - | 0 | 0.67 | 0.67 | 0 | 0 | 0 |  |  | 0 | 0
13 | Renovation and restructuring of shed No. 1, 2, 5, 6, 9 & 11 of major store custody of NTPS, Eklahare. | 0 | - | 0 | 3.39 | 3.39 | 0 | 0 | 0 |  |  | 0 | 0
DPR 4 | As per I.B.Recommondation | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | Work of construction compound wall with concertina coil at various locations at Nashik TPS. | 0 | - | 0 | 58.87 | 58.87 | 0 | 0 | 0 |  |  | 0 | 0
2 | Providing & renovating security watch tower at NTPS Premises Eklahare. | 0 | - | 0 | 0.61 | 0.61 | 0 | 0 | 0 |  |  | 0 | 0
0 | HO Yet to be submitted DPR | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
DPR 1 | R&M/LE for Identified Thermal units of MSPGCL of (3 x 210 MW) | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | R&M/LE for Identified Thermal units of MSPGCL (3 x 210 MW) units of MSPGCL | 0 | - | 0 | 1180.14 | 1180.14 | 0 | 0 | 0 |  |  | 0 | 0
DPR 2 | CHP Improvcement Schemes at 3 x 210 MW units | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | CHP Improvement Schemes at 3 x 210 MW units | 0 | - | 0 | 30 | 30 | 0 | 0 | 0 |  |  | 0 | 0
0 | B) Non-DPR Schemes | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
1 | TATA Mini Truck SFC 709 EX No.MH-15-JV-3992 | N.A. | - | 0 | 0.32099 | 0.32099 | 0 | 0 | 0 |  |  | 0 | 0
2 | Executive chair(10),S Type Arm chai(20) | N.A. | - | 0 | 0.10784 | 0.10784 | 0 | 0 | 0 |  |  | 0 | 0
3 | Office Table and S-Type Chair with Arm | N.A. | - | 0 | 0.030968 | 0.030968 | 0 | 0 | 0 |  |  | 0 | 0
4 | Windows Slot in PC VPC 10-Intel Core 13 4th -NTC | N.A. | - | 0 | 0.010561 | 0.010561 | 0 | 0 | 0 |  |  | 0 | 0
5 | LG Screen wall mounted computer-LED display65"-NTC | N.A. | - | 0 | 5.0969 | 5.0969 | 0 | 0 | 0 |  |  | 0 | 0
6 | 20 Ton Split AC for Audtiorium -NTC | N.A. | - | 0 | 1.0873 | 1.0873 | 0 | 0 | 0 |  |  | 0 | 0
7 | Colour Laser Printer, All in one A3 LaserJet Print | N.A. | - | 0 | 1.0589 | 1.0589 | 0 | 0 | 0 |  |  | 0 | 0
8 | Digital DSLR Camera | N.A. | - | 0 | 1.0793 | 1.0793 | 0 | 0 | 0 |  |  | 0 | 0
9 | Indoor Gymnasium Equipments at NTC, Eklahare | N.A. | - | 0 | 0.02853 | 0.02853 | 0 | 0 | 0 |  |  | 0 | 0
10 | CLASS ROOM CHAIR WITH DESKLET | N.A. | - | 0 | 0.023576 | 0.023576 | 0 | 0 | 0 |  |  | 0 | 0
11 | PA System and Sport Material,Table Tannis for | N.A. | - | 0 | 0.01687 | 0.01687 | 0 | 0 | 0 |  |  | 0 | 0
12 | EXECUTIVE CHAIR WITH 5 SUPRT & S-TYPE CHAIR | N.A. | - | 0 | 0.01003 | 0.01003 | 0 | 0 | 0 |  |  | 0 | 0
13 | APPLN COOLER AIR SEMIEXH AIR COOLER ASSY | N.A. | - | 0 | 0.033896 | 0.033896 | 0 | 0 | 0 |  |  | 0 | 0
14 | FULL PAD CHAIRS WITH SIDE ARM | N.A. | - | 0 | 0.029637 | 0.029637 | 0 | 0 | 0 |  |  | 0 | 0
15 | Industrial Cabinet with 12 Lockers | N.A. | - | 0 | 0.0070163 | 0.0070163 | 0 | 0 | 0 |  |  | 0 | 0
16 | UV Water Purifier Filter | N.A. | - | 0 | 0.019116 | 0.019116 | 0 | 0 | 0 |  |  | 0 | 0
17 | FILTER RO+UV+UF+TDS WATER PURIFIER | N.A. | - | 0 | 0.032906 | 0.032906 | 0 | 0 | 0 |  |  | 0 | 0
18 | 2 Tone SPLIT AC INDOOR UNIT | N.A. | - | 0 | 0.008064 | 0.008064 | 0 | 0 | 0 |  |  | 0 | 0
19 | 1.5 TON CAPACITY SPLIT AC | N.A. | - | 0 | 0.006688 | 0.006688 | 0 | 0 | 0 |  |  | 0 | 0
20 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 1.698 | 1.698 | 0 | 0 | 0 |  |  | 0 | 0
21 | Logitech PTZ Group Camera 960-001054 | N.A. | - | 0 | 2.4375 | 2.4375 | 0 | 0 | 0 |  |  | 0 | 0
22 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011564 | 0.011564 | 0 | 0 | 0 |  |  | 0 | 0
23 | WORK BENCH WITHOUT DRAWER | 0 | - | 0 | 0.011647 | 0.011647 | 0 | 0 | 0 |  |  | 0 | 0
24 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.030075 | 0.030075 | 0 | 0 | 0 |  |  | 0 | 0
25 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.011788 | 0.011788 | 0 | 0 | 0 |  |  | 0 | 0
26 | EXECUTIVE CHAIR, S-TYPE CH-7 CHAIR WITH ARM | 0 | - | 0 | 0.035229 | 0.035229 | 0 | 0 | 0 |  |  | 0 | 0
27 | SAMSUNG GALAXY TAB S3, 32GB 9.7 INCH | 0 | - | 0 | 0.003845 | 0.003845 | 0 | 0 | 0 |  |  | 0 | 0
28 | i5 Laptop - 2 Nos & i7 Laptop - 3 Nos | 0 | - | 0 | 0.037636 | 0.037636 | 0 | 0 | 0 |  |  | 0 | 0
29 | Godrej make 1.5 Ton High Wall Split AC | 0 | - | 0 | 0.020975 | 0.020975 | 0 | 0 | 0 |  |  | 0 | 0
30 | Complete Multimedia Projector with Std Accessories | 0 | - | 0 | 0.0109 | 0.0109 | 0 | 0 | 0 |  |  | 0 | 0
31 | LED 40 INCH SMART TV | 0 | - | 0 | 0.0092016 | 0.0092016 | 0 | 0 | 0 |  |  | 0 | 0
32 | FULL PAD CHAIRS, EXECUTIVE CHAIR, | 0 | - | 0 | 0.068995 | 0.068995 | 0 | 0 | 0 |  |  | 0 | 0
33 | Cash Counting Machine | 0 | - | 0 | 0.001888 | 0.001888 | 0 | 0 | 0 |  |  | 0 | 0
34 | 230 V AC DIGITAL SINE WAVE INVERTER 1 No. | 0 | - | 0 | 0.010175 | 0.010175 | 0 | 0 | 0 |  |  | 0 | 0
35 | HPCV no.3 &4 Stem | 0 | - | 0 | 0.025694 | 0.025694 | 0 | 0 | 0 |  |  | 0 | 0
36 | HEAVY DUTY AIR PURIFIURE 230V,50HZ | 0 | - | 0 | 0.0105 | 0.0105 | 0 | 0 | 0 |  |  | 0 | 0
37 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.0048144 | 0.0048144 | 0 | 0 | 0 |  |  | 0 | 0
38 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.025939 | 0.025939 | 0 | 0 | 0 |  |  | 0 | 0
39 | APPLN COOLER WTR CAP CAP: 60 LITERS | 0 | - | 0 | 0.0053799 | 0.0053799 | 0 | 0 | 0 |  |  | 0 | 0
40 | LASER LASERJET PRINTER FOR A4 PAPER | 0 | - | 0 | 0.0057 | 0.0057 | 0 | 0 | 0 |  |  | 0 | 0
41 | 40 Inch Smart LED TV 3.00 | 0 | - | 0 | 0.010178 | 0.010178 | 0 | 0 | 0 |  |  | 0 | 0
42 | DESKTOP INTEL CORE I5 2300 PROCESSOR | 0 | - | 0 | 0.021459 | 0.021459 | 0 | 0 | 0 |  |  | 0 | 0
43 | ONLINE WATER HEATER, 3KW,3LTR. | 0 | - | 0 | 0.029683 | 0.029683 | 0 | 0 | 0 |  |  | 0 | 0
44 | CAMERA FOR VC, MICROPHONE WITH SPEAKER | 0 | - | 0 | 0.023889 | 0.023889 | 0 | 0 | 0 |  |  | 0 | 0
45 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
46 | FILTER RO+UV+UF+TDS WATER PURIFIER | 0 | - | 0 | 0.01873 | 0.01873 | 0 | 0 | 0 |  |  | 0 | 0
47 | Water Cooler | 0 | - | 0 | 0.005 | 0.005 | 0 | 0 | 0 |  |  | 0 | 0
48 | PORTABLE HARD DISK USB 1TB | 0 | - | 0 | 0.0017388 | 0.0017388 | 0 | 0 | 0 |  |  | 0 | 0
49 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.00095 | 0.00095 | 0 | 0 | 0 |  |  | 0 | 0
50 | Garbox assembly for premium make type B-220 of | 0 | - | 0 | 0.44095 | 0.44095 | 0 | 0 | 0 |  |  | 0 | 0
51 | SINGLE SIDE DRAWER STEEL TABLE 4 X 2.5FT | 0 | - | 0 | 0.006726 | 0.006726 | 0 | 0 | 0 |  |  | 0 | 0
52 | RO+UV+UF+TDS CAP 50 LITRE PER HOUR | 0 | - | 0 | 0.002731 | 0.002731 | 0 | 0 | 0 |  |  | 0 | 0
53 | SAMSUNG MOBILE 2232 WITH ACCESSORIES | 0 | - | 0 | 0.0025995 | 0.0025995 | 0 | 0 | 0 |  |  | 0 | 0
54 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.002183 | 0.002183 | 0 | 0 | 0 |  |  | 0 | 0
55 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.0061808 | 0.0061808 | 0 | 0 | 0 |  |  | 0 | 0
56 | REGULAR CHAIR WITHOUT CUSHION | 0 | - | 0 | 0.0082836 | 0.0082836 | 0 | 0 | 0 |  |  | 0 | 0
57 | BLDC Fans through GeM Portal and GA -2022-23 at | 0 | - | 0 | 0.0049556 | 0.0049556 | 0 | 0 | 0 |  |  | 0 | 0
58 | ALL IN ONE PC, CORE I5, 4 GB RAM, 500 GB | 0 | - | 0 | 0.02973 | 0.02973 | 0 | 0 | 0 |  |  | 0 | 0
59 | PRINTER LASER LASERJET NETWORK PRINTER | 0 | - | 0 | 0.0020024 | 0.0020024 | 0 | 0 | 0 |  |  | 0 | 0
60 | APPLN FAN AIR CEIL SIZE 1200 MM SWEEP | 0 | - | 0 | 0.033918 | 0.033918 | 0 | 0 | 0 |  |  | 0 | 0
61 | WALL MOUNTED FAN 18" 230V 1440RPM | 0 | - | 0 | 0.014828 | 0.014828 | 0 | 0 | 0 |  |  | 0 | 0
62 | 400 MM, 230V, 3 BLADE DOMESTIC FAN | 0 | - | 0 | 0.0024532 | 0.0024532 | 0 | 0 | 0 |  |  | 0 | 0
63 | APPLN FAN AIR EXHAUST SIZE15"1400RPM-15 Nos | 0 | - | 0 | 0.01781 | 0.01781 | 0 | 0 | 0 |  |  | 0 | 0
64 | EXECUTIVE CHAIR WITH 5 SUPRT, ADJ HEIGHT | 0 | - | 0 | 0.013559 | 0.013559 | 0 | 0 | 0 |  |  | 0 | 0
65 | MICROWAVE OVEN CAPACITY 27 / 28 LITERS-1 Nos | 0 | - | 0 | 0.0048362 | 0.0048362 | 0 | 0 | 0 |  |  | 0 | 0
66 | REFRIGERATOR SINGLE DOOR CAPCITY 190 LTR | 0 | - | 0 | 0.0067225 | 0.0067225 | 0 | 0 | 0 |  |  | 0 | 0
67 | Supply of Thinclients on Buyback for NTPS | 0 | - | 0 | 0.23166 | 0.23166 | 0 | 0 | 0 |  |  | 0 | 0
68 | ABC Powder type DCP Composite Fire Extinguisher | 0 | - | 0 | 0.357 | 0.357 | 0 | 0 | 0 |  |  | 0 | 0
69 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024631 | 0.024631 | 0 | 0 | 0 |  |  | 0 | 0
70 | CLASS ROOM CHAIR WITH DESKLET | 0 | - | 0 | 0.024213 | 0.024213 | 0 | 0 | 0 |  |  | 0 | 0
71 | Furniture Dining Table for Main Mess Hall and Cus | 0 | - | 0 | 0.019803 | 0.019803 | 0 | 0 | 0 |  |  | 0 | 0
72 | Servers for DSM at Nashik Thermal Power Station | 0 | - | 0 | 0.43559 | 0.43559 | 0 | 0 | 0 |  |  | 0 | 0
73 | DESKTOP INTEL CORE I5 2300 PROCESSOR - 5 Nos | 0 | - | 0 | 0.05632 | 0.05632 | 0 | 0 | 0 |  |  | 0 | 0
74 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.041064 | 0.041064 | 0 | 0 | 0 |  |  | 0 | 0
75 | SPLIT AC 3 TON COMPLETE UNIT | 0 | - | 0 | 0.038246 | 0.038246 | 0 | 0 | 0 |  |  | 0 | 0
76 | APPLN TV STD ULSLIM 42" - 4 Nos | 0 | - | 0 | 0.037376 | 0.037376 | 0 | 0 | 0 |  |  | 0 | 0
77 | 1 T SPLIT AC COMPL UNIT WITH ACCESSORIES | 0 | - | 0 | 0.011682 | 0.011682 | 0 | 0 | 0 |  |  | 0 | 0
78 | MULTIMEDIA PROJECTOR EPSON EB-U05-1 No | 0 | - | 0 | 0.0081606 | 0.0081606 | 0 | 0 | 0 |  |  | 0 | 0
79 | WEIGHING SCALE 500KG CAPACITY | 0 | - | 0 | 0.0023246 | 0.0023246 | 0 | 0 | 0 |  |  | 0 | 0
80 | Procurement of Complete Vibrating Screen Assembly at CHP-II | 0 | - | 0 | 0.61 | 0.61 | 0 | 0.5 | 0.5 |  |  | 0.5 | 0
0 | General Asset | 0 | - | 0 | 9.677 | 9.677 | 0 | 0 | 0 |  |  | 0 | 0
| Total |  |  |  | 2141.5751 | 2163.2825 | -21.7075 | 0.5 | 0.5 | 0 | 0 | 0.5 | -21.7075